## Sheet1 (3)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 17/09/2025
CPC Name: |  |  |  |  | Axis Goregaon.
Date Of Property Visit |  |  |  |  | 2025-09-09
Name of the builder group |  |  |  |  | M/s. Ideal Group
Name of the builder company |  |  |  |  | M/s. Ideal Properties Builder & Developers.
Name of the Project |  |  |  |  | Ideal Avenue
Name / no of the Building |  |  |  |  | Building no.3 - Ideal Avenue Wing A - Type F1 Wing B - Type B1d Wing C - Type B1c Wing D - Type C1a
Docouments Provided |  |  |  |  | 1. Copy of Plans. 2. Copy of CC.
RERA No. |  |  |  |  | Wing A - Type F = P99000003409 Wing B - Type B1d = P99000009483 Wing C & D - Type Blc & Cla= P99000028528
Approved Layout Plan : |  | MHSL/K.1/MJ.1/NAP/SR/229/17 |  |  |  |  | Dated | 22/03/2019.
Project location details |  | Ideal City-Ideal Avenue, Building no.3, Gut No.179, 180 & 181, Sarpada, Umroli(E), Opp.Railway Station, Village. Umroli, Tal.Palghar, Dist.Palghar.
Gut No |  | 179, 180 & 181 |  |  | Locality |  | Umroli(E)
Road |  | Village Umroli(E) Road |  |  | District |  | Palghar
City |  | Palghar |  |  | Pin Code |  | 401404
Near by Landmark |  | Opp.Railway Station |  |  | Distance from city centre: |  | Near By Umroli Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open |  | Railway station |  | Open |  | Open
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.7556951,72.7584406
Location Link |  | https://goo.gl/maps/7WikqxUYgVzdYGVG7?coh=178572&entry=tt
Approval details:
Approved usage of the Property: Residential & Commercial. (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 12311.44
Permissible FSI |  |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.9
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 11080.296
Total number of Buildings |  |  |  |  | 01 Building (4 Wings )
Approval Detail : Plan approval
Layout Approval No |  | MHSL/K.1/MJ.1/NAP/SR/229/17 |  |  |  | Dated | 22/03/2019.
Building plan approval No (Type F1 & B1d) |  | MHSL/K.1/MJ.1/NAP/SR/229/17 Approval no. of floors = Gr.+3rd Floor |  |  |  | Dated | 22/03/2019.
Building plan approval No (Type B1c & C1a) |  | MHSL/U.1/M.1/NAP/SR/87/15 Approval no. of floors = Gr.+2nd Floor |  |  |  | Dated | 16/06/2016.
C.certificate No (Type F1, B1d, B1c & C1a) |  | MHSL/K.1/MJ.1/NAP/SR/229/17 Valid Upto : Type F1, B1d, B1c & C1a= Gr.+ 1st to 3rd Floor |  |  |  | Dated | 22/03/2019.
O. Certificate No.: NA |  | NA |  |  | Date of approval: NA | Dated | NA
Commencement date of construction |  |  | 22/03/2019. |  | Expected Completion |  | A Wing = 31/12/2029 B Wing = 31/12/2025 C & D Wing = 30/06/2025
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 11080.296 |  | Approved no of units |  | Shops = 23, Flats = 63
Approved no of Floors |  | Type F1 & B1d = Gr.+1st to 3rd Floor Type B1c & C1a = Gr.+1st to 2nd Floor
Proposed no of Floors |  |  | Gr.+4th Floor
Quality of construction: Good |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details:
Construction details: |  | Building No.3: Type-F1 (A Wing) = Gr + 1st to 4th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 3 Floor completed, Flooring upto 3 Floor completed, Painting upto 3 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 3 Floor completed, Flooring upto 3 Floor completed, Painting upto 3 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 72% |  | 84% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 4 | 80% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 3 | 75% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 3 | 75% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 75% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 75% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Building No.3: Type-B1d ( B Wing) = Gr + 1st to 4th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 3 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 3 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 72.5% |  | 88.75% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Building No.3: Type-B1c (C wing) = Gr + 1st to 4th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 2 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 68.12% |  | 86.25% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 3 | 75% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 50% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Building No.3: Type-C1a (D wing) = Gr + 1st to 4th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 2 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 68.12% |  | 86.25% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 3 | 75% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 50% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Rate of the flat Per Sq. Ft. (on Saleable area) = Building no.3 - Ideal Avenue | [6 empty] | 3300
Rate of the Shop Per Sq. Ft. (on Saleable area) = Building no.3 - Ideal Avenue | [6 empty] | 6000
Floor rise rate Per Sq. Ft. | [6 empty] | NA
Society formation charges | [6 empty] | 1,00,000/-
Recommended rate of Parking | [6 empty] | 50000/-
Distress valuation of the property Per Sq. Ft. = Building no.3 - Ideal Avenue | [6 empty] | 2640
Building details floor wise
Details of Flats in Building
Flat No. | Flat No. | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area | PLC Y/N
Building no.3 - Ideal Avenue
Type-F1 (A Wing)
Ground Floor For Parking & Commercial
1 |  | Shop | 156.9391 | 0 | 156.9391 | 0 | 235.4087 | NA
2 |  | Shop | 138.1021 | 0 | 138.1021 | 0 | 207.1532 | NA
3 |  | Shop | 179.113 | 0 | 179.113 | 0 | 268.6694 | NA
4 |  | Shop | 155.7551 | 0 | 155.7551 | 0 | 233.6326 | NA
5 |  | Shop | 112.5914 | 0 | 112.5914 | 0 | 168.8872 | NA
6 |  | Shop | 167.4878 | 0 | 167.4878 | 0 | 251.2318 | NA
7 |  | Shop | 171.6858 | 0 | 171.6858 | 0 | 257.5287 | NA
8 |  | Shop | 134.2271 | 0 | 134.2271 | 0 | 201.3406 | NA
9 |  | Shop | 123.1402 | 0 | 123.1402 | 0 | 184.7102 | NA
10 |  | Shop | 130.2444 | 0 | 130.2444 | 0 | 195.3666 | NA
1st to 3rd Floor
1 |  | 2BHK | 538.7382 | 0 | 538.7382 | 0 | 781.1704 | NA | 1.45
2 |  | 2BHK | 516.2414 | 0 | 516.2414 | 0 | 748.5501 | NA
3 |  | 1RK | 290.0898 | 0 | 290.0898 | 0 | 420.6302 | NA
4 |  | 1RK | 290.0898 | 0 | 290.0898 | 0 | 420.6302 | NA
5 |  | 1BHK | 376.5247 | 0 | 376.5247 | 0 | 545.9608 | NA
6 |  | 1BHK | 376.5247 | 0 | 376.5247 | 0 | 545.9608 | NA
7 |  | 1BHK | 374.5872 | 0 | 374.5872 | 0 | 543.1514 | NA
Type-B1d ( B Wing)
Ground Floor For Parking & Commercial
1 |  | Shop | 130.2444 | 0 | 130.2444 | 0 | 195.3666 | NA
2 |  | Shop | 123.1402 | 0 | 123.1402 | 0 | 184.7102 | NA
3 |  | Shop | 134.2271 | 0 | 134.2271 | 0 | 201.3406 | NA
4 |  | Shop | 171.6858 | 0 | 171.6858 | 0 | 257.5287 | NA
5 |  | Shop | 132.6125 | 0 | 132.6125 | 0 | 198.9187 | NA
6 |  | Shop | 94.7232 | 0 | 94.7232 | 0 | 142.0848 | NA
7 |  | Shop | 136.057 | 0 | 136.057 | 0 | 204.0854 | NA
8 |  | Shop | 159.1996 | 0 | 159.1996 | 0 | 238.7993 | NA
9 |  | Shop | 116.0359 | 0 | 116.0359 | 0 | 174.0539 | NA
10 |  | Shop | 165.7656 | 0 | 165.7656 | 0 | 248.6484 | NA
11 |  | Shop | 165.7656 | 0 | 165.7656 | 0 | 248.6484 | NA
12 |  | Shop | 127.1228 | 0 | 127.1228 | 0 | 190.6843 | NA
13 |  | Shop | 143.5918 | 0 | 143.5918 | 0 | 215.3876 | NA
1st to 3rd Floor
1 |  | 1BHK | 361.4551 | 0 | 361.4551 | 0 | 524.1099 | NA
2 |  | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287 | NA
3 |  | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287 | NA
4 |  | 2BHK | 516.2414 | 0 | 516.2414 | 0 | 748.5501 | NA
5 |  | 2BHK | 516.2414 | 0 | 516.2414 | 0 | 748.5501 | NA
6 |  | 1BHK | 339.4966 | 0 | 339.4966 | 0 | 492.27 | NA
Type-B1c (C wing)
Ground Floor For Parking, Residential & Commercial
1 | 1 | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287 | NA
2 | 2 | 1RK | 250.5859 | 0 | 250.5859 | 0 | 363.3496 | NA
1st & 2nd Floor
1 | 1 | 1BHK | 339.4966 | 0 | 339.4966 | 0 | 492.27 | NA
2 | 2 | 2BHK | 516.2414 | 0 | 516.2414 | 0 | 748.5501 | NA
3 | 3 | 2BHK | 516.2414 | 0 | 516.2414 | 0 | 748.5501 | NA
4 | 4 | 1BHK | 362.3162 | 0 | 362.3162 | 0 | 525.3585 | NA
5 | 5 | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287 | NA
6 | 6 | 1BHK | 361.4551 | 0 | 361.4551 | 0 | 524.1099 | NA
Type-C1a (D wing)
Ground Floor For Parking & Residential
1 | 1 | 1BHK | 365.976 | 0 | 365.976 | 0 | 530.6652 | NA
2 | 2 | 1BHK | 365.976 | 0 | 365.976 | 0 | 530.6652 | NA
1st & 2nd Floor
1 | 1 | 1BHK | 365.976 | 0 | 365.976 | 0 | 530.6652 | NA
2 | 2 | 1BHK | 304.083 | 0 | 304.083 | 0 | 440.9203 | NA
3 | 3 | 1BHK | 365.976 | 0 | 365.976 | 0 | 530.6652 | NA
4 | 4 | 1BHK | 365.976 | 0 | 365.976 | 0 | 530.6652 | NA
Remarks: 1. Wing B, C & D = Work is same as last visit (13/03/2025) but construction work is in procress at the time of visit (Very Slow Speed). Wing A = Construction work is same as last visit (dtd. 16/09/2024). 2. We considered saleable area as per our calculation. 3. Recommended rate considered as per market Inquire. 4. We update revised Approved plans of Type F1 & B1d, Layout & CC on 05/04/2019. 5. We have considered Other charges from cost sheet. 6. We have considered construction percent as per proposed no of floor( Gr.+ 4th Floor) because construction work goes beyond approved no. of floor(Gr.+ 3rd Floor). Please provide Revised approved plans & CC. 7. Since the project has received first CC on 22/03/2019., But construction work of Wing A, B, C & D is under construction. 8. As per RERA, completion period of project is expired on 30/06/2025 but still project is under construction. 9. As checked on RERA portal on dated 17/09/2025, we have observed that above project is kept under abeyance. 10. On site we met Mr. Anil 9892755827 On site we met Mr. Yadav : 9029664475. 7. A Wing - As per RERA, completion period of project Ideal Avenue is expired on 31/12/2022 but still project is under construction. | [9 empty] | Wing D - Construction work is same as last visit 22/02/2023.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  | Ideal Avenue
Google Map :
A
A Wing
A Wing
B Wing
C Wing
D Wing

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Commonfloor | Ideal Avenue | 1BHK | 420 | 609 | 2955.665 | 1800000
quikr. | Ideal Avenue | 1BHK | 420 | 609 | 2955.665 | 1800000
proptiger | Ideal Avenue | 1BHK | 323 | 468.35 | 3416.2485 | 1600000
proptiger | Ideal Avenue | 2BHK | 454 | 658.3 | 3190.0349 | 2100000
Average |  |  |  |  | 3129.4034
Valuation Adopted |  |  |  |  | 3200

## Note
19/08/2020.
11/11/2020. | Dhanashree | OLD APF
1. Rate has not Changed.

## Ground - C % 3A,B
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 80 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 4 | 80 | Progress |  |  | 10 | 32 | 12 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 24 | 12 | 0 | 0 | 0 | 0
| 5 | 4 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 0 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 32 | 24
Finishing | Total Floor | completed Floor |  | Bricks | 12 | 12
| 5 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 54 | 66

## Ground - C % 3A,B (2)
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 80 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 4 | 60 | Progress |  |  | 10 | 32 | 9 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 24 | 9 | 0 | 0 | 0 | 0
| 5 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 0 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 32 | 24
Finishing | Total Floor | completed Floor |  | Bricks | 9 | 9
| 5 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 51 | 63

## Ground - C % 3C
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 80 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 4 | 60 | Progress |  |  | 10 | 32 | 9 | 1 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 10 | Recommended |  |  | 30 | 24 | 9 | 1 | 0 | 0 | 0
| 5 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 0.5 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 32 | 24
Finishing | Total Floor | completed Floor |  | Bricks | 9 | 9
| 5 | 0 |  | Plaster | 1 | 1
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 52 | 64

## Ground - C % 3D
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 80 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 4 | 20 | Progress |  |  | 10 | 32 | 3 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 24 | 3 | 0 | 0 | 0 | 0
| 5 | 1 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 0 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 32 | 24
Finishing | Total Floor | completed Floor |  | Bricks | 3 | 3
| 5 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 45 | 57