## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com | [7 empty] | Construction work of Building No 8 (Block 8A & 8B) given combined in previous report Extra work given for Block 8A
Valuation Report | [7 empty] | Date 20/09/2024 Separate table given here after don’t change construction stage of Block 8B until it 8A construction matches with 8B also don’t put any remark
Date: |  |  |  | 17/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-08
Name of the builder group |  |  |  | M/s.Mahindra Happinest Developers Limited
Name of the builder company |  |  |  | M/s.Mahindra Happinest Developers Limited
Name of the Project |  |  |  | Mahindra Happinest Palghar Project 2 Phase I & II
Contact Details ( Name & Contact No.) |  |  |  | 022-67478600 /Stanley 8879541331
Name / No of the Building |  |  |  | Plot 2 - Phase I = Block 5A, 5B, 6A, 7A, 7B, 8A, 8B Phase II = Block 1, 2, 3, 4 & CFC
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | Phase I = P99000026225 Phase II = P99000053642
Project location details |  | Mahindra Happinest Palghar Project 2 Phase I & II, Gut No.158, 183P, 183P and Plot no 2, Baswat Pada, Nandore, Palghar, Palghar, Palghar.
Gut No |  | 158, 183P, 183P and Plot no 2
Road |  | Baswat Pada |  | Locality/Village |  | Nandore
City |  | Palghar |  | District |  | Palghar
Taluka |  | Palghar |  | Pin Code |  | 401404
Near by Landmark |  | Gundecha Woods |  | Distance from city centre: |  | 6.4km from Palghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | Bullet Train Marking/12 M W Road |  |  | Bullet Train Marking/ Road
West | NA | Other Plot |  |  | Building
North | NA | 12 M W Road |  |  | Road
South | NA | Other Plot |  |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.7335762,72.7899632
Location Link |  | https://goo.gl/maps/GAovZqtsKsbCKowZ8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 53878.3 |  |  |  | 19296.15
Permissible FSI |  |  |  | 1.288 |  |  |  | 1.288
Permissible TDR/Paid FSI |  |  |  | -0.00025447 |  |  |  | 24853.44
Total FSI availaible for the project |  |  |  | 1.2877 |  |  |  | 24854.728
Total Permisible Builtup area of the project (Sq.Mt) |  |  |  | 69381.54 |  |  |  | 29824.13
Total number of Buildings |  |  |  | 12 Wings |  |  |  | 07 Wings
Approval Detail : Plan approval
Layout Approval No |  | MAHSUL/KS.1/MJ.1/NAP/SR/110/19 |  |  | Dated | 2020-08-28
Approved Floor plan No. (Phase 1) |  | S.S.N.R./336 |  |  | Dated | 2020-02-20
Approved Floor plan No. (Phase 2) |  | MAHSUL/KS.1/MJ.1/NAP/SR/110/19 |  |  | Dated | 2020-08-28
Commencement Certificate No. Valid Up to: |  | MAHSUL/KS.1/T.1/NAP/SR-110/2019 |  |  | Dated | 2020-08-28
Block 5A, 5B, 6A, 7A, 7B, 8A, 8B = Gr + 4th Floor Block 1,2,3,4 & CFC = Gr + 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 27298.3 |  |  |  |  | 14805.52
Approved no of units |  |  | Flats = 745, Shops = 44, Units = 09 |  |  |  |  | Flats - 485
Approved no of Floors |  |  | Block 5 to 8 = Gr + 1st to 4th Floor Block 1 to 4 = Gr + 1st to 4th Floor CFC = Gr + 1st to 2nd Floor |  |  |  |  | Gr + 1st to 4th Floor
Proposed no of Floors |  |  | Block 5 to 8 = Gr + 1st to 4th Floor Block 1 to 4 = Gr + 1st to 4th Floor CFC = Gr + 1st to 2nd Floor |  |  |  |  | Gr + 1st to 4th Floor
Expected Completion |  |  | As per RERA - Phase 1 = 30/12/2024 Phase 2 = 28/02/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Block 5A, 5B = Gr + 1st to 4th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 92.5% |  | 95% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 75% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 75% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Block 6A = Gr + 1st to 4th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 91.25% |  | 95% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 75% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 50% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Block 7A, 7B = Gr + 1st to 4th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 91.25% |  | 95% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 75% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 50% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Block 8A = Gr + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 57.5% |  | 80% |  | Excavation in process | 2 | Construction work of Building No 8 (Block 8A & 8B) given combined in previous report Extra work given for Block 8A
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4 | Date 20/09/2024 Separate table given here after don’t change construction stage of Block 8B until it 8A construction matches with 8B
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Block 8B = Gr + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 3 Floor, Flooring upto 3 Floor, Painting upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 3 Floor, Flooring upto 3 Floor, Painting upto 2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 82.5% |  | 92.5% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 75% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 2 | 50% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Block 1 = G + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 26% |  | 57% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 2 | 40% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Block 2 = Gr + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 18% |  | 51% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 1 | 20% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Block 3 = G + 1st to 4th Floor | [5 empty] | Piling work in process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Piling work in process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 1 | 25% | 0% |  | 5% |  | Excavation in process | 2
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Block 4 = Gr + 1st to 4th Floor | [5 empty] | Piling work in process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Piling work in process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 1 | 25% | 0% |  | 5% |  | Excavation in process | 2
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | CFC Building = Gr + 2nd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 2
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.5
Excavation |  | 2 | 100% | 36.67% |  | 65% |  | Excavation in process | 1
Plinth |  | 2 | 100% |  |  |  |  | Excavation Completed | 2
RCC (Including podiums) |  | 2 | 66.67% |  |  |  |  | Footing in Process | 0.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 1
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 1.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 2
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Entrance etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 4000
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Distressed valuation of the Property |  |  |  |  | 3200
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Shops |  | 44 | 4462.3023 |  | 6916.5686
Units |  | 9 | 7139.449 |  | 11066.146
Total |  | 53 | 11601.7514 |  | 17982.7146
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Block 5A & 5B |  | 95 | 38067.1013 |  | 57100.6519
Block 6A |  | 59 | 17070.8429 |  | 25606.2643
Block7A & 7B |  | 158 | 30587.6282 |  | 45881.4424
Block 8A & 8B |  | 173 | 33645.6806 |  | 50468.521
Block 1 |  | 60 | 25715.196 |  | 38572.794 |  |  | OK
Block 2 |  | 40 | 16698.839 |  | 25048.2586 |  |  | OK
Block 3 |  | 60 | 25715.196 |  | 38572.794 |  |  | OK
Block 4 |  | 100 | 41720.8334 |  | 62581.2502 |  |  | OK
Total |  | 745 | 229221.3175 |  | 343831.9763
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading : | 10.764
55%
Phase II
CFC
Ground Floor For Commercial
1 |  | Shop | 100.3851 | 0 | 100.3851 | 0 | 155.5968
2 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
3 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
4 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
5 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
6 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
7 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
8 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
9 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
10 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
11 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
12 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
13 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
14 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
15 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
16 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
17 |  | Shop | 34.574 | 0 | 34.574 | 0 | 53.5897
18 |  | Shop | 89.6318 | 0 | 89.6318 | 0 | 138.9293
19 |  | Shop | 89.6318 | 0 | 89.6318 | 0 | 138.9293
20 |  | Shop | 89.6318 | 0 | 89.6318 | 0 | 138.9293
21 |  | Shop | 89.6318 | 0 | 89.6318 | 0 | 138.9293
22 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
23 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
24 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
25 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
26 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
27 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
28 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
29 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
30 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
31 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
32 |  | Shop | 99.567 | 0 | 99.567 | 0 | 154.3288
33 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
34 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
35 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
36 |  | Shop | 100.3851 | 0 | 100.3851 | 0 | 155.5968
37 |  | Shop | 83.6578 | 0 | 83.6578 | 0 | 129.6696
38 |  | Shop | 89.6318 | 0 | 89.6318 | 0 | 138.9293
39 |  | Shop | 89.6318 | 0 | 89.6318 | 0 | 138.9293
40 |  | Shop | 89.6318 | 0 | 89.6318 | 0 | 138.9293
41 |  | Shop | 89.6318 | 0 | 89.6318 | 0 | 138.9293
42 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
43 |  | Shop | 107.5431 | 0 | 107.5431 | 0 | 166.6918
44 |  | Shop | 100.3851 | 0 | 100.3851 | 0 | 155.5968
1st Floor For Commercial
1 |  | Unit | 780.39 | 0 | 780.39 | 0 | 1209.6045
2 |  | Unit | 446.7921 | 0 | 446.7921 | 0 | 692.5278
3 |  | Unit | 446.706 | 0 | 446.706 | 0 | 692.3943
4 |  | Unit | 371.4549 | 0 | 371.4549 | 0 | 575.7551
5 |  | Unit | 838.6448 | 0 | 838.6448 | 0 | 1299.8994
6 |  | Unit | 446.706 | 0 | 446.706 | 0 | 692.3943
7 |  | Unit | 325.6863 | 0 | 325.6863 | 0 | 504.8138
8 |  | Unit | 1344.1545 | 0 | 1344.1545 | 0 | 2083.4395
2nd Floor For Commercial
1 |  | Unit | 2138.9144 | 0 | 2138.9144 | 0 | 3315.3174
Flat/Shop No. |  | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor |  | 10.764
Phase I
Block 5A & 5B
Ground Floor for Residential
1 |  | 1BHK | 308.8192 | 0 | 463.2287 | Ground Floor for Residential
2 |  | 1BHK | 317.2151 | 0 | 475.8226 |  |  | 4077.1496
3 |  | 1BHK | 317.2151 | 0 | 475.8226
4 |  | 1BHK | 317.2151 | 0 | 475.8226
5 |  | 1BHK | 319.5832 | 0 | 479.3747
6 |  | 1BHK | 317.2151 | 0 | 475.8226
7 |  | 1BHK | 317.2151 | 0 | 475.8226
8 |  | 1BHK | 317.2151 | 0 | 475.8226
9 |  | 2BHK | 502.2482 | 0 | 753.3724
10 |  | 1BHK | 317.2151 | 0 | 475.8226
11 |  | 1BHK | 317.2151 | 0 | 475.8226
12 |  | 1BHK | 317.2151 | 0 | 475.8226
13 |  | 1BHK | 317.2151 | 0 | 475.8226
14 |  | 1BHK | 317.2151 | 0 | 475.8226
15 |  | 1BHK | 317.2151 | 0 | 475.8226
16 |  | 1BHK | 317.2151 | 0 | 475.8226
17 |  | 1BHK | 317.2151 | 0 | 475.8226
18 |  | 1BHK | 317.2151 | 0 | 475.8226
19 |  | 2BHK | 461.4527 | 0 | 692.179
1st to 4th Floor
1 |  | 2BHK | 543.0438 | 0 | 814.5657 | 1st to 4th Floor
2 |  | 1BHK | 384.3824 | 0 | 576.5737
3 |  | 1BHK | 384.3824 | 0 | 576.5737
4 |  | 1BHK | 384.3824 | 0 | 576.5737
5 |  | 2BHK | 543.0438 | 0 | 814.5657
6 |  | 1BHK | 384.3824 | 0 | 576.5737
7 |  | 1BHK | 384.3824 | 0 | 576.5737
8 |  | 1BHK | 384.3824 | 0 | 576.5737
9 |  | 2BHK | 534.325 | 0 | 801.4874
10 |  | 1BHK | 384.3824 | 0 | 576.5737
11 |  | 1BHK | 384.3824 | 0 | 576.5737
12 |  | 1BHK | 384.3824 | 0 | 576.5737
13 |  | 1BHK | 384.3824 | 0 | 576.5737
14 |  | 1BHK | 384.3824 | 0 | 576.5737
15 |  | 1BHK | 384.3824 | 0 | 576.5737
16 |  | 1BHK | 384.3824 | 0 | 576.5737
17 |  | 1BHK | 384.3824 | 0 | 576.5737
18 |  | 1BHK | 384.3824 | 0 | 576.5737
19 |  | 2BHK | 543.0438 | 0 | 814.5657
Block 6
Ground Floor for Residential
1 |  | 1BHK | 289.3363 | 0 | 434.0045 | Ground Floor for Residential
2 |  | 1BHK | 289.3363 | 0 | 434.0045
3 |  | 1BHK | 289.3363 | 0 | 434.0045
4 |  | 1BHK | 289.3363 | 0 | 434.0045
5 |  | 1BHK | 289.3363 | 0 | 434.0045
6 |  | 1BHK | 289.3363 | 0 | 434.0045
7 |  | 1BHK | 289.3363 | 0 | 434.0045
8 |  | 1BHK | 289.3363 | 0 | 434.0045
9 |  | 1BHK | 289.3363 | 0 | 434.0045
10 |  | 1BHK | 289.3363 | 0 | 434.0045
11 |  | 1BHK | 289.3363 | 0 | 434.0045
1st to 4th Floor
1 |  | 1BHK | 289.3363 | 0 | 434.0045 | 1st to 4th Floor
2 |  | 1BHK | 289.3363 | 0 | 434.0045
3 |  | 1BHK | 289.3363 | 0 | 434.0045
4 |  | 1BHK | 289.3363 | 0 | 434.0045
5 |  | 1BHK | 289.3363 | 0 | 434.0045
6 |  | 1BHK | 289.3363 | 0 | 434.0045
7 |  | 1BHK | 289.3363 | 0 | 434.0045
8 |  | 1BHK | 289.3363 | 0 | 434.0045
9 |  | 1BHK | 289.3363 | 0 | 434.0045
10 |  | 1BHK | 289.3363 | 0 | 434.0045
11 |  | 1BHK | 289.3363 | 0 | 434.0045
12 |  | 1BHK | 289.3363 | 0 | 434.0045
Block 7A &7B
Ground Floor for Residential
1 |  | 1BHK | 289.3363 | 0 | 434.0045 | Ground Floor for Residential
2 |  | 1BHK | 289.3363 | 0 | 434.0045
3 |  | 1BHK | 289.3363 | 0 | 434.0045
4 |  | 1BHK | 289.3363 | 0 | 434.0045
5 |  | 1BHK | 289.3363 | 0 | 434.0045
6 |  | 1RK | 161.1371 | 0 | 241.7056
7 |  | 1RK | 161.1371 | 0 | 241.7056
8 |  | 1RK | 161.1371 | 0 | 241.7056
9 |  | 1RK | 161.1371 | 0 | 241.7056
10 |  | 1RK | 161.1371 | 0 | 241.7056
11 |  | 1RK | 161.1371 | 0 | 241.7056
12 |  | 1RK | 161.1371 | 0 | 241.7056
13 |  | 1RK | 161.1371 | 0 | 241.7056
14 |  | 1RK | 161.1371 | 0 | 241.7056
15 |  | 1RK | 161.1371 | 0 | 241.7056
16 |  | 1RK | 161.1371 | 0 | 241.7056
17 |  | 1RK | 161.1371 | 0 | 241.7056
18 |  | 1RK | 161.1371 | 0 | 241.7056
19 |  | 1RK | 161.1371 | 0 | 241.7056
20 |  | 1RK | 161.1371 | 0 | 241.7056
21 |  | 1RK | 161.1371 | 0 | 241.7056
22 |  | 1RK | 161.1371 | 0 | 241.7056
23 |  | 1RK | 161.1371 | 0 | 241.7056
24 |  | 1RK | 161.1371 | 0 | 241.7056
25 |  | 1RK | 161.1371 | 0 | 241.7056
26 |  | 1RK | 161.1371 | 0 | 241.7056
27 |  | 1RK | 161.1371 | 0 | 241.7056
28 |  | 1BHK | 289.3363 | 0 | 434.0045
29 |  | 1BHK | 289.3363 | 0 | 434.0045
30 |  | 1BHK | 289.3363 | 0 | 434.0045
1st to 4th Floor
1 |  | 1BHK | 289.3363 | 0 | 434.0045 | 1st to 4th Floor
2 |  | 1BHK | 289.3363 | 0 | 434.0045
3 |  | 1BHK | 289.3363 | 0 | 434.0045
4 |  | 1BHK | 289.3363 | 0 | 434.0045
5 |  | 1BHK | 289.3363 | 0 | 434.0045
6 |  | 1RK | 161.1371 | 0 | 241.7056
7 |  | 1RK | 161.1371 | 0 | 241.7056
8 |  | 1RK | 161.1371 | 0 | 241.7056
9 |  | 1RK | 161.1371 | 0 | 241.7056
10 |  | 1RK | 161.1371 | 0 | 241.7056
11 |  | 1RK | 161.1371 | 0 | 241.7056
12 |  | 1RK | 161.1371 | 0 | 241.7056
13 |  | 1RK | 161.1371 | 0 | 241.7056
14 |  | 1RK | 161.1371 | 0 | 241.7056
15 |  | 1RK | 161.1371 | 0 | 241.7056
16 |  | 1RK | 161.1371 | 0 | 241.7056
17 |  | 1RK | 161.1371 | 0 | 241.7056
18 |  | 1RK | 161.1371 | 0 | 241.7056
19 |  | 1RK | 161.1371 | 0 | 241.7056
20 |  | 1RK | 161.1371 | 0 | 241.7056
21 |  | 1RK | 161.1371 | 0 | 241.7056
22 |  | 1RK | 161.1371 | 0 | 241.7056
23 |  | 1RK | 161.1371 | 0 | 241.7056
24 |  | 1RK | 161.1371 | 0 | 241.7056
25 |  | 1RK | 161.1371 | 0 | 241.7056
26 |  | 1RK | 161.1371 | 0 | 241.7056
27 |  | 1RK | 161.1371 | 0 | 241.7056
28 |  | 1RK | 161.1371 | 0 | 241.7056
29 |  | 1RK | 161.1371 | 1 | 241.7056
30 |  | 1BHK | 289.3363 | 2 | 434.0045
31 |  | 1BHK | 289.3363 | 0 | 434.0045
32 |  | 1BHK | 289.3363 | 0 | 434.0045
Block 8A & 8B
Ground Floor for Residential
1 |  | 1BHK | 289.3363 | 0 | 434.0045 | Ground Floor for Residential
2 |  | 1BHK | 289.3363 | 0 | 434.0045
3 |  | 1BHK | 289.3363 | 0 | 434.0045
4 |  | 1RK | 161.1371 | 0 | 241.7056 |  |  | 3909.7146
5 |  | 1RK | 161.1371 | 0 | 241.7056
6 |  | 1RK | 161.1371 | 0 | 241.7056
7 |  | 1RK | 161.1371 | 0 | 241.7056
8 |  | 1RK | 161.1371 | 0 | 241.7056
9 |  | 1RK | 161.1371 | 0 | 241.7056
10 |  | 1RK | 161.1371 | 0 | 241.7056
11 |  | 1RK | 161.1371 | 0 | 241.7056
12 |  | 1RK | 161.1371 | 0 | 241.7056
13 |  | 1RK | 161.1371 | 0 | 241.7056
14 |  | 1RK | 161.1371 | 0 | 241.7056
15 |  | 1RK | 161.1371 | 0 | 241.7056
16 |  | 1RK | 161.1371 | 0 | 241.7056
17 |  | 1RK | 161.1371 | 0 | 241.7056
18 |  | 1RK | 161.1371 | 0 | 241.7056
19 |  | 1RK | 161.1371 | 0 | 241.7056
20 |  | 1RK | 161.1371 | 0 | 241.7056
21 |  | 1RK | 161.1371 | 0 | 241.7056
22 |  | 1RK | 161.1371 | 0 | 241.7056
23 |  | 1RK | 161.1371 | 0 | 241.7056
24 |  | 1RK | 161.1371 | 0 | 241.7056
25 |  | 1RK | 161.1371 | 0 | 241.7056
26 |  | 1RK | 161.1371 | 0 | 241.7056
27 |  | 1RK | 161.1371 | 0 | 241.7056
28 |  | 1BHK | 289.3363 | 0 | 434.0045
29 |  | 1BHK | 289.3363 | 0 | 434.0045
30 |  | 1BHK | 289.3363 | 0 | 434.0045
31 |  | 1BHK | 289.3363 | 0 | 434.0045
32 |  | 1BHK | 289.3363 | 0 | 434.0045
33 |  | 1BHK | 289.3363 | 0 | 434.0045
1st to 4th Floor
1 |  | 1BHK | 289.3363 | 0 | 434.0045 | 1st to 4th Floor
2 |  | 1BHK | 289.3363 | 0 | 434.0045
3 |  | 1BHK | 289.3363 | 0 | 434.0045
4 |  | 1RK | 161.1371 | 0 | 241.7056
5 |  | 1RK | 161.1371 | 0 | 241.7056
6 |  | 1RK | 161.1371 | 0 | 241.7056
7 |  | 1RK | 161.1371 | 0 | 241.7056
8 |  | 1RK | 161.1371 | 0 | 241.7056
9 |  | 1RK | 161.1371 | 0 | 241.7056
10 |  | 1RK | 161.1371 | 0 | 241.7056
11 |  | 1RK | 161.1371 | 0 | 241.7056
12 |  | 1RK | 161.1371 | 0 | 241.7056
13 |  | 1RK | 161.1371 | 0 | 241.7056
14 |  | 1RK | 161.1371 | 0 | 241.7056
15 |  | 1RK | 161.1371 | 0 | 241.7056
16 |  | 1RK | 161.1371 | 0 | 241.7056
17 |  | 1RK | 161.1371 | 0 | 241.7056
18 |  | 1RK | 161.1371 | 0 | 241.7056
19 |  | 1RK | 161.1371 | 0 | 241.7056
20 |  | 1RK | 161.1371 | 0 | 241.7056
21 |  | 1RK | 161.1371 | 0 | 241.7056
22 |  | 1RK | 161.1371 | 0 | 241.7056
23 |  | 1RK | 161.1371 | 0 | 241.7056
24 |  | 1RK | 161.1371 | 0 | 241.7056
25 |  | 1RK | 161.1371 | 0 | 241.7056
26 |  | 1RK | 161.1371 | 0 | 241.7056
27 |  | 1RK | 161.1371 | 0 | 241.7056
28 |  | 1RK | 161.1371 | 0 | 241.7056
29 |  | 1RK | 161.1371 | 0 | 241.7056
30 |  | 1BHK | 289.3363 | 0 | 434.0045
31 |  | 1BHK | 289.3363 | 0 | 434.0045
32 |  | 1BHK | 289.3363 | 0 | 434.0045
33 |  | 1BHK | 289.3363 | 0 | 434.0045
34 |  | 1BHK | 289.3363 | 0 | 434.0045
35 |  | 1BHK | 289.3363 | 0 | 434.0045
Phase II | [7 empty] | Added From Here
Block 1
Ground Floor for Residential & Meter Room
1 |  | 1BHK | 390.2381 | 0 | 585.3571 | Ground Floor for Residential & Meter Room
2 |  | 1BHK | 390.2381 | 0 | 585.3571
3 |  | 1BHK | 390.2381 | 0 | 585.3571 |  |  |  |  | 29.0451
4 |  | 1BHK | 370.7122 | 0 | 556.0682
5 |  | 2BHK | 512.5817 | 0 | 768.8725 |  |  | 42.6631
6 |  | 1BHK | 390.2381 | 0 | 585.3571
7 |  | 1BHK | 390.2381 | 0 | 585.3571
8 |  | 1BHK | 390.2381 | 0 | 585.3571
9 |  | 2BHK | 512.5817 | 0 | 768.8725
10 |  | 1BHK | 390.2381 | 0 | 585.3571
11 |  | 1BHK | 390.2381 | 0 | 585.3571
12 |  | 1BHK | 370.7122 | 0 | 556.0682
1st to 4th Floor
1 |  | 1BHK | 382.5956 | 0 | 573.8934 | 1st to 4th Floor
2 |  | 1BHK | 382.5956 | 0 | 573.8934
3 |  | 1BHK | 382.5956 | 0 | 573.8934
4 |  | 2BHK | 536.4778 | 0 | 804.7166
5 |  | 2BHK | 536.4778 | 0 | 804.7166
6 |  | 1BHK | 382.5956 | 0 | 573.8934
7 |  | 1BHK | 382.5956 | 0 | 573.8934
8 |  | 1BHK | 382.5956 | 0 | 573.8934
9 |  | 2BHK | 536.4778 | 0 | 804.7166
10 |  | 1BHK | 382.5956 | 0 | 573.8934
11 |  | 1BHK | 382.5956 | 0 | 573.8934
12 |  | 2BHK | 536.4778 | 0 | 804.7166
Block 2
Ground Floor for Residential & Meter Room
1 |  | 1BHK | 390.2381 | 0 | 585.3571 | Ground Floor for Residential & Meter Room
2 |  | 1BHK | 390.2381 | 0 | 585.3571
3 |  | 1BHK | 390.2381 | 0 | 585.3571
4 |  | 1BHK | 390.2381 | 0 | 585.3571
5 |  | 2BHK | 512.5817 | 0 | 768.8725
6 |  | 1BHK | 390.2381 | 0 | 585.3571
7 |  | 1BHK | 390.2381 | 0 | 585.3571
8 |  | 1BHK | 370.7122 | 0 | 556.0682
1st to 4th Floor
1 |  | 1BHK | 382.5956 | 0 | 573.8934 | 1st to 4th Floor
2 |  | 1BHK | 382.5956 | 0 | 573.8934
3 |  | 1BHK | 382.5956 | 0 | 573.8934
4 |  | 1BHK | 382.5956 | 0 | 573.8934
5 |  | 2BHK | 536.4778 | 0 | 804.7166
6 |  | 1BHK | 382.5956 | 0 | 573.8934
7 |  | 1BHK | 382.5956 | 0 | 573.8934
8 |  | 2BHK | 536.4778 | 0 | 804.7166
Block 3
Ground Floor for Residential & Meter Room
1 |  | 1BHK | 390.2381 | 0 | 585.3571 | Ground Floor for Residential & Meter Room
2 |  | 1BHK | 390.2381 | 0 | 585.3571
3 |  | 1BHK | 390.2381 | 0 | 585.3571
4 |  | 1BHK | 370.7122 | 0 | 556.0682
5 |  | 2BHK | 512.5817 | 0 | 768.8725
6 |  | 1BHK | 390.2381 | 0 | 585.3571
7 |  | 1BHK | 390.2381 | 0 | 585.3571
8 |  | 1BHK | 390.2381 | 0 | 585.3571
9 |  | 2BHK | 512.5817 | 0 | 768.8725
10 |  | 1BHK | 390.2381 | 0 | 585.3571
11 |  | 1BHK | 390.2381 | 0 | 585.3571
12 |  | 1BHK | 370.7122 | 0 | 556.0682
1st to 4th Floor
1 |  | 1BHK | 382.5956 | 0 | 573.8934 | 1st to 4th Floor
2 |  | 1BHK | 382.5956 | 0 | 573.8934
3 |  | 1BHK | 382.5956 | 0 | 573.8934
4 |  | 2BHK | 536.4778 | 0 | 804.7166
5 |  | 2BHK | 536.4778 | 0 | 804.7166
6 |  | 1BHK | 382.5956 | 0 | 573.8934
7 |  | 1BHK | 382.5956 | 0 | 573.8934
8 |  | 1BHK | 382.5956 | 0 | 573.8934
9 |  | 2BHK | 536.4778 | 0 | 804.7166
10 |  | 1BHK | 382.5956 | 0 | 573.8934
11 |  | 1BHK | 382.5956 | 0 | 573.8934
12 |  | 2BHK | 536.4778 | 0 | 804.7166
Block 4
Ground Floor for Residential & Meter Room
1 |  | 2BHK | 517.6408 | 0 | 776.4611 | Ground Floor for Residential & Meter Room
2 |  | 1BHK | 390.2381 | 0 | 585.3571
3 |  | 1BHK | 390.2381 | 0 | 585.3571
4 |  | 1BHK | 390.2381 | 0 | 585.3571
5 |  | 1BHK | 390.2381 | 0 | 585.3571
6 |  | 1BHK | 390.2381 | 0 | 585.3571
7 |  | 1BHK | 390.2381 | 0 | 585.3571
8 |  | 1BHK | 390.2381 | 0 | 585.3571
9 |  | 1BHK | 390.2381 | 0 | 585.3571
10 |  | 1BHK | 390.2381 | 0 | 585.3571
11 |  | 1BHK | 390.2381 | 0 | 585.3571
12 |  | 1BHK | 370.7122 | 0 | 556.0682
13 |  | 2BHK | 512.5817 | 0 | 768.8725
14 |  | 1BHK | 390.2381 | 0 | 585.3571
15 |  | 1BHK | 390.2381 | 0 | 585.3571
16 |  | 1BHK | 370.7122 | 0 | 556.0682
17 |  | 1BHK | 390.2381 | 0 | 585.3571
18 |  | 1BHK | 390.2381 | 0 | 585.3571
19 |  | 1BHK | 390.2381 | 0 | 585.3571
20 |  | 1BHK | 370.7122 | 0 | 556.0682
1st to 4th Floor
1 |  | 2BHK | 546.5959 | 0 | 819.8939 | 1st to 4th Floor
2 |  | 1BHK | 382.5956 | 0 | 573.8934
3 |  | 1BHK | 382.5956 | 0 | 573.8934
4 |  | 1BHK | 382.5956 | 0 | 573.8934
5 |  | 1BHK | 382.5956 | 0 | 573.8934
6 |  | 1BHK | 382.5956 | 0 | 573.8934
7 |  | 1BHK | 382.5956 | 0 | 573.8934
8 |  | 1BHK | 382.5956 | 0 | 573.8934
9 |  | 1BHK | 382.5956 | 0 | 573.8934
10 |  | 1BHK | 382.5956 | 0 | 573.8934
11 |  | 1BHK | 382.5956 | 0 | 573.8934
12 |  | 2BHK | 536.4778 | 0 | 804.7166
13 |  | 2BHK | 536.4778 | 0 | 804.7166
14 |  | 1BHK | 382.5956 | 0 | 573.8934
15 |  | 1BHK | 382.5956 | 0 | 573.8934
16 |  | 2BHK | 536.4778 | 0 | 804.7166
17 |  | 1BHK | 382.5956 | 0 | 573.8934
18 |  | 1BHK | 382.5956 | 0 | 573.8934
19 |  | 1BHK | 382.5956 | 0 | 573.8934
20 |  | 2BHK | 536.2625 | 0 | 804.3937
Remarks: | [10 empty] | 1. Building No. 5 to 8, Block 1 & 2 = Construction work is in process at the time of Visit.(Internal Visit Not Allowed). Block 3, 4 & CFC Building = Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area. 5. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 6. We have considered rate by verifying it from market inquire. 7. Car parking is subjected to authentic documentation. 8. We have considered only RERA registered Buildings. 9.The project has received first CC on 28/08/2020, But construction work of project is not yet completed. 10. As per RERA, completion period of project Happinest Palghar Project 2 Phase I is expired on 30/12/2024 but still project is under construction. 11. We have added Phase 2 on 23/07/2025. 12. Please provide unit nomenclature term for 1st & 2nd floor of CFC Building . 13. Bullet train marking passing nearby the project Mahindra Happinest Palghar. Please provide the NHSRCL NOC. 14. As per the layout, few building lies in Bullet train projection area. please check before any disbursment. 15. Please provide the Environmental clearance certificate.
1. Building No. 5 to 8, Block 1 & 3 = Construction work is in process at the time of Visit. (Internal Visit Not Allowed). Block 3, 4 & CFC Building = Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area. 5. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 6. We have considered rate by verifying it from market inquire. 7. Car parking is subjected to authentic documentation. 8. We have considered only RERA registered Buildings. 9.The project has received first CC on 28/08/2020, But construction work of project is not yet completed. 10. As per RERA, completion period of project Happinest Palghar Project 2 Phase I is expired on 30/12/2024 but still project is under construction. 11. We have added Phase 2 on 23/07/2025. 12. Please provide unit nomenclature term for 1st & 2nd floor of CFC Building . 13. Bullet train marking passing nearby the project Mahindra Happinest Palghar. Please provide the NHSRCL NOC. 14. As per the layout, few building lies in Bullet train projection area. please check before any disbursment. 15. Please provide the Environmental clearance certificate. | [7 empty] | Building No.6 & 7 = Work is same as last visit (08/12/2023).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Yadnesh Patil |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Mahindra Happinest Palghar Project 2 Phase I & II
Layout :
Google Map :
8B
B7
Bldg 8
B8
Block 5
Block 6
Block 7
Block 8
Block 4
Block 3
Block 2
Block 1
Bullet Train Marking
Bullet Train Projection
Building No. 6
Building No. 7
Building No. 2
Happinest Palghar Project 2 Phase I & 2
Bullet Train Marking

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.5 | 2.9 | 13.05 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.88 | 2.13 | 4.0044 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.9 | 1.07 | 2.033 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 205.4568 | 19.0874 |  |  | 0 | 0 |  | 0 | 0
|  |  | 205.4568 | 19.0874