## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 17/09/2025
CPC Name: |  |  |  |  | Axis Goregaon.
Date Of Property Visit |  |  |  |  | 2025-09-09
Name of the builder group (Building No. 1 Wing A, B & C) |  |  |  |  | Gajanan Builders & Developers
Name of the builder group (Building No. 1 Wing D) |  |  |  |  | Shree Shiv Kripa Builders & Developer |  |  |  |  | Pramoter has been change for this project
Name of the Project |  |  |  |  | Ideal Garden
Name / no of the Building |  |  |  |  | Building no.1 - Ideal Garden = Wing A - Type B1a Wing B - Type B1b Wing C - Type C2 Wing D - Type D1
Docouments Provided |  |  |  |  | 1. Copy of Plans. 2. Copy of CC.
RERA No |  |  |  |  | Building No.1 : Type -B1a (A & C Wing) = P99000013416 Building no.1 (D Wing) - P99000016177
Approved Layout Plan : |  | MHSL/K.1/MJ.1/NAP/SR/229/17 |  |  |  |  | Dated | 22/03/2019.
Project location details |  | Ideal City- Ideal Garden, Building no.1, Gut No.179, 180 & 181, Sarpada, Umroli(E), Opp.Railway Station, Village. Umroli, Tal.Palghar, Dist.Palghar.
Gut No | 179, 180 & 181 |  |  | Plot No | NA | Locality | Umroli(E)
Road | Village Umroli(E) Road |  |  |  | District | Palghar
City | Palghar |  |  |  | Pin Code | 401 404.
Near by Landmark |  | Opp.Railway Station |  |  | Distance from city centre: |  | Near By Umroli Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open |  | Railway station |  | Open |  | Open
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | Latitude |  | 19.7557 |  | Longitude |  | 72.7584
Location Link |  | https://goo.gl/maps/XnKtBiZjsWqtuA739?coh=178572&entry=tt
Approval details:
Approved usage of the Property: Residential & Commercial. (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 12302.82
Permissible FSI |  |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  |  | 0.28342
Total FSI availaible for the project |  |  |  |  | 1.3834
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 17019.93
Total number of Buildings |  |  |  |  | 4 Wings
Approval Detail : Plan approval
Layout Approval No |  | MHSL/K.1/MJ/B.S.P/S.R/C.R/74/2021 |  |  |  | Dated | 2023-03-01
Building plan approval No |  | MHSL/K.1/MJ/B.S.P/S.R/C.R/74/2021 Bldg No. 1(Type B1a) = 2nd to 4th Floor Bldg No.2(Type C2) =Gr + 2nd to 4th Floor |  |  |  | Dated | 2023-03-01
Building plan approval No |  | MHSL/K.1/MJ.1/NAP/SR/229/17 Approval no. of Floors = Gr.+ 3rd Floor |  |  |  | Dated | 22/03/2019.
C.certificate No Valid Up to: |  | MHSL/K.1/T.1/NAP/SR-74/2021 Type-B1a, B1b, C2 & D1 = Gr + 1st to 4th Floor |  |  |  | Dated | 29/03/2023.
O. Certificate No.: NA |  | NA |  |  | Date of approval: NA | Dated | NA | Expiry date: NA
Commencement date of construction |  |  | 29/03/2023. |  | Expected Completion |  | Building No.1B1a (A & C Wing) = 31/03/2028 Building No 1 D Wing = 31/12/2025
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 17019.93 |  | Approved no of units residential |  |  | Flats = 80 Shops = 20
No of floors at site : |  | See Construction details
Approved no of Floors |  | Type-B1a & C2 = Gr.+1st to 4th Floor Type-B1b & D1 = Gr + 1st to 3rd Floor
Proposed no of Floors |  | Type-B1a, B1b, C2 & D1 = Gr + 1st to 4th Floor
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Building No.1 : Type -B1a (A Wing) |  |  |  | Gr.+1st to 4th Floor |  |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 3 Floor, Flooring upto 3 Floor, Painting upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 3 Floor, Flooring upto 3 Floor, Painting upto 2 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 82.5% |  | 92.5% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 75% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 2 | 50% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Building No.1 : Type -B1b (B Wing) = Gr.+1st to 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 3 Floor, External Plaster upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 3 Floor, External Plaster upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 65.62% |  | 85% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 3 | 75% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 1 | 25% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Building No.1 :Type -C2 (C Wing) |  |  |  | Gr.+1st to 4th Floor |  |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 3 Floor, Flooring upto 3 Floor, Painting upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 3 Floor, Flooring upto 3 Floor, Painting upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 81.25% |  | 92.5% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 75% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 1 | 25% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Building No.1 : Type -D1 (D Wing) = Gr.+1st to 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 3 Floor, External Plaster upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 3 Floor, External Plaster upto 3 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 70.62% |  | 87.5% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 3 | 75% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Rate of the flat Per Sq. Ft. (on Saleable area) = Building no.1 - Ideal Garden | [6 empty] | 3700
Rate of the shop Per Sq. Ft. (on Saleable area) = Building no.1 - Ideal Garden | [6 empty] | 6000
Floor rise rate Per Sq. Ft. | [6 empty] | NA
Society formation charges | [6 empty] | 1,00,000/-
Recommended rate of Parking | [6 empty] | 100000/-
Development charges Per Sq. Ft. | [6 empty] | NA
Valuation as per Government reckoners rates | [6 empty] | NA
Distress valuation of the property Per Sq. Ft. = Building no.1 - Ideal Garden | [6 empty] | 2960
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  |  |  | Total Saleable Area
Type -B1a (A Wing) |  | 13 |  | 1824.7133 |  |  |  | 2737.0699
Type -B1b (B Wing) |  | 7 |  | 985.2289 |  |  |  | 1477.8434
Total |  | 20 |  | 2809.9422 |  |  |  | 4214.9133
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  |  |  | Total Saleable Area
Type -B1a (A Wing) |  | 24 |  | 10805.0108 |  |  |  | 15667.2657
Type -B1b (B Wing) |  | 20 |  | 7094.3371 |  |  |  | 10286.7888
Type -C2 (C Wing) |  | 18 |  | 7118.5561 |  |  |  | 10321.9064
Type- D1 (D Wing) |  | 18 |  | 7359.5621 |  |  |  | 10671.365
Total |  | 80 |  | 32377.4662 |  |  |  | 46947.3259
Grand Total |  | 100 |  | 35187.4084 |  |  |  | 51162.2392
Building details floor wise
Details of Flats in Building
Flat No. |  | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area | Floor
Building no.1 - Ideal Garden
Type -B1a (A Wing)
Ground Floor For Parking & Commercial
1 |  | Shop | 161.3524 | 0 | 161.3524 | 0 | 242.0285 | Ground Floor For Parking & Commercial
2 |  | Shop | 133.9042 | 0 | 133.9042 | 0 | 200.8562
3 |  | Shop | 165.7656 | 0 | 165.7656 | 0 | 248.6484
4 |  | Shop | 165.7656 | 0 | 165.7656 | 0 | 248.6484
5 |  | Shop | 116.0359 | 0 | 116.0359 | 0 | 174.0539
6 |  | Shop | 159.1996 | 0 | 159.1996 | 0 | 238.7993
7 |  | Shop | 136.057 | 0 | 136.057 | 0 | 204.0854
8 |  | Shop | 94.7232 | 0 | 94.7232 | 0 | 142.0848
9 |  | Shop | 132.6125 | 0 | 132.6125 | 0 | 198.9187
10 |  | Shop | 171.6858 | 0 | 171.6858 | 0 | 257.5287
11 |  | Shop | 134.2271 | 0 | 134.2271 | 0 | 201.3406
12 |  | Shop | 123.1402 | 0 | 123.1402 | 0 | 184.7102
13 |  | Shop | 130.2444 | 0 | 130.2444 | 0 | 195.3666
1st Floor
1 |  | 1BHK | 339.4966 | 0 | 339.4966 | 0 | 492.27 | 1st Floor
2 |  | 2BHK | 516.2414 | 0 | 516.2414 | 0 | 748.5501
3 |  | 2BHK | 516.2414 | 0 | 516.2414 | 0 | 748.5501
4 |  | 1BHK | 362.3162 | 0 | 362.3162 | 0 | 525.3585
5 |  | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287
6 |  | 1BHK | 361.4551 | 0 | 361.4551 | 0 | 524.1099
2nd to 4th Floor
1 |  | 1BHK | 326.795 | 60.9511 | 387.7462 | 0 | 562.232 | 2nd to 4th Floor | 30.8875 | 10.764
2 |  | 2BHK | 505.2622 | 82.7482 | 588.0104 | 0 | 852.6151
3 |  | 2BHK | 514.1963 | 60.5475 | 574.7438 | 0 | 833.3785
4 |  | 1BHK | 361.0246 | 40.365 | 401.3896 | 0 | 582.0149
5 |  | 1BHK | 354.3509 | 62.5657 | 416.9166 | 0 | 604.5291
6 |  | 1BHK | 348.323 | 64.1804 | 412.5034 | 0 | 598.1299
Type -B1b (B Wing)
Ground Floor For Residential & Commercial
1 |  | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287 | Ground Floor For Residential & Commercial
2 |  | 1RK | 251.2318 | 0 | 251.2318 | 0 | 364.2861
1 |  | Shop | 86.112 | 0 | 86.112 | 0 | 129.168
2 |  | Shop | 156.2933 | 0 | 156.2933 | 0 | 234.4399
3 |  | Shop | 116.0359 | 0 | 116.0359 | 0 | 174.0539
4 |  | Shop | 165.7656 | 0 | 165.7656 | 0 | 248.6484
5 |  | Shop | 165.7656 | 0 | 165.7656 | 0 | 248.6484
6 |  | Shop | 133.9042 | 0 | 133.9042 | 0 | 200.8562
7 |  | Shop | 161.3524 | 0 | 161.3524 | 0 | 242.0285
1st to 3rd Floor
1 |  | 1BHK | 361.4551 | 0 | 361.4551 | 0 | 524.1099 | 1st to 3rd Floor
2 |  | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287 | NA
3 |  | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287 | NA
4 |  | 1BHK | 362.3162 | 0 | 362.3162 | 0 | 525.3585 | NA
5 |  | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287 | NA
6 |  | 1BHK | 339.4966 | 0 | 339.4966 | 0 | 492.27 | NA
Type -C2 (C Wing)
Ground Floor For Residential & Parking
1 |  | 1BHK | 374.6948 | 0 | 374.6948 | 0 | 543.3075 | Ground Floor For Residential & Parking
2 |  | 1BHK | 374.6948 | 0 | 374.6948 | 0 | 543.3075
1st Floor
1 |  | 1BHK | 359.3023 | 0 | 359.3023 | 0 | 520.9884 | 1st Floor
2 |  | 1BHK | 359.3023 | 0 | 359.3023 | 0 | 520.9884
3 |  | 1BHK | 359.3023 | 0 | 359.3023 | 0 | 520.9884
4 |  | 1BHK | 359.3023 | 0 | 359.3023 | 0 | 520.9884
2nd to 4th Floor
1 |  | 1BHK | 348.4307 | 62.5657 | 410.9964 | 0 | 595.9448 | 2nd to 4th Floor
2 |  | 1BHK | 348.4307 | 62.5657 | 410.9964 | 0 | 595.9448
3 |  | 1BHK | 348.4307 | 62.5657 | 410.9964 | 0 | 595.9448
4 |  | 1BHK | 348.4307 | 62.5657 | 410.9964 | 0 | 595.9448
Type- D1 (D Wing)
Ground Floor For Residential & Parking
1 |  | 1BHK | 375.7712 | 0 | 375.7712 | 0 | 544.8683 | Ground Floor For Residential & Parking
2 |  | 1BHK | 359.5176 | 0 | 359.5176 | 0 | 521.3005 | NA
3 |  | 1BHK | 375.7712 | 0 | 375.7712 | 0 | 544.8683 | NA
1st to 3rd Floor
1 |  | 2BHK | 485.887 | 0 | 485.887 | 0 | 704.5361 | 1st to 3rd Floor
2 |  | 1BHK | 375.7712 | 0 | 375.7712 | 0 | 544.8683
3 |  | 1BHK | 359.5176 | 0 | 359.5176 | 0 | 521.3005
4 |  | 1BHK | 375.7712 | 0 | 375.7712 | 0 | 544.8683
5 |  | 2BHK | 485.887 | 0 | 485.887 | 0 | 704.5361
Remarks: 1. Wing A & C = Construction work is in process at the time of visit (Very slow speed). Wing B & D = Construction work same as last visit 19/06/2025 but work is in process at the time of visit (Very slow speed). 2. We considered saleable area as per our calculation. 3. We have considered rate by verifying it from market inquire. 4. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 5. We have considered Other charges from cost sheet. 5. Car parking is subjected to authentic documentation. 6. We updated revised Approved plans of Type B1a, B1b, C2 & D1, layout & CC on 05/04/2019. 8. Building No.1 : Type -B1a (B Wing) = Not Registered on RERA. 9. We hvae updated revised approved CC for building no. 1 Type B1a, B1b, C2 & D1 on 27/12/2023. 10. We have updated approved layout plan & floor plan of Building No. 1 (Type B1a) = 2nd to 4th Floor & Building No. 1 (Type C2) = Gr + 2nd to 4th Floor on 29/08/2024. 11. The approved Layout Plan & Floor plan does not consist the complete date. 12. As discussed with the Builder & Bank Officials, the clarification letter for the date which is not mentioned in the plans is attached below, which is provided by the bank officials on mail. 13. As per the builder, the corrected plans will get soon. Send the revised approved plans as soon as they are available. 14. As checked on RERA portal on dated 17/09/2025, we have observed that above project is kept under abeyance. 15. As per RERA, completion period of project name Ideal Garden Building No.1(A & C Wing) is expired on Date 31/03/2025 but still project is under construction.
Undertaking:
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  | Ideal Garden
Remark No. 11
Remark No. 12
Google Map :
Wing B
Wing C
Wing A
Wing B
Wing C
Wing A
Wing B
Wing C
Wing B
Wing C
Wing D
Wing C
Wing D
Wing A

## Note
20/03/2020. | Pratiksha | Recommended rate considered as per Builder cost sheet & Shop's rate as per market inquire.
03/02/2021. | Pratiksha

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Housing |  |  |  |  | #DIV/0!
Proptiger |  |  |  |  | #DIV/0!
Magic Brick |  |  |  |  | #DIV/0!
Magic Brick |  |  |  |  | #DIV/0!
Magic Brick |  |  |  |  | #DIV/0!
99 Acres |  |  |  |  | #DIV/0!
99 Acres |  |  |  |  | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted |  |  |  |  | 32000

## C % 1A,C
Particulars | totaL floor | 3 | total no of floor considered 5 because shops are 100% completed so I want to give them %
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 4 | 100 | Progress |  |  | 10 | 40 | 15 | 5 | 2.5 | 1.25 | 1.25
Bricks | Total Floor | completed Floor | 50 | Recommended |  |  | 30 | 30 | 15 | 5 | 1.25 | 1.25 | 1.25
| 4 | 4 | 25
plaster | Total Floor | completed Floor | 25
| 4 | 2 | 25
Flooring | Total Floor | completed Floor
| 4 | 1 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 1 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 4 | 1 |  | Plaster | 5 | 5
|  |  |  | Flooring | 2.5 | 1.25
|  |  |  | Wood & painting | 1.25 | 1.25
|  |  |  | Finishing | 1.25 | 1.25
|  |  |  | total | 75 | 83.75

## B
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 4 | 75 | Progress |  |  | 10 | 40 | 11.25 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 11.25 | 0 | 0 | 0 | 0
| 4 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 11.25 | 11.25
| 4 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 61.25 | 71.25

## D
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 75 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 3 | 75 | Progress |  |  | 10 | 30 | 11.25 | 5 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 50 | Recommended |  |  | 30 | 22.5 | 11.25 | 5 | 0 | 0 | 0
| 4 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 2 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 30 | 22.5
Finishing | Total Floor | completed Floor |  | Bricks | 11.25 | 11.25
| 4 | 0 |  | Plaster | 5 | 5
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 56.25 | 68.75