## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-11
Name of the builder group |  |  |  | Rare Livspace
Name of the builder company |  |  |  | Rare Livspace
Name of the Project |  |  |  | Hrishikesh 3
Provided Contact Details (Name & Contact No.) |  |  |  | 9022703322
Site Person - Contact Details (Name & Contact No.) |  |  |  | NA
Name / No of the Building |  |  |  | Wing A, B, C & D
Name / No of the Existing Building |  |  |  | NA | [8 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet & Airport Noc. | [8 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000052666 |  |  |  | #N/A |  |  |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Hrishikesh 3, Survey No.3/3/B, near Kartik residency co op hsg soc, Panvel Waterfall Road, Vasan Nagar, Nevali, Kalamboli East, Panvel, Raigad - 413511. | [10 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 3/3/B | [10 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Vasan Nagar | [10 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Panvel Waterfall Road |  | Locality/Village |  | Nevali | [6 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Kalamboli East |  | District |  | Raigad | [6 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Panvel |  | Pin Code |  | 413511 | [9 empty] | Mahad | Daund
Nearby Landmark |  | Kartik residency co op hsg soc |  | Distance from city centre: |  | 2.60KM from Kalamboli Railway Station | [9 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [11 empty] | Mangaon | Ambegaon
[16 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [11 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [11 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [11 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Existing Newali Village Road |  |  | Internal Road
West | NA | Survey No. 3/Part |  |  | Kartik residency co op hsg soc
North | NA | Existing Newali Village Road |  |  | Panvel Waterfall Road
South | NA | Other Plot |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.023043,73.126583
Location Link |  | https://maps.app.goo.gl/dQzsAb5cKRbeSNqJ7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2127.08
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | -0.0090909
Total FSI availaible for the project |  |  |  | 0.99091
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 2107.743 |  |  |  | 22687.7457 | 44108.7098 | 21420.9641
Total number of Buildings |  |  |  | 04 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Navi Mumbai Airport Influence Notified Area (NAINA)
Layout Approval No |  | CIDCO/NAINA/Panvel/Nevali/ BP-00665/CC/2023/0421 |  |  | Dated | 2023-08-21
Approved Floor plan No. |  | CIDCO/NAINA/Panvel/Nevali/ BP-00665/CC/2023/0421 |  |  | Dated | 2023-08-21
Commencement-CC No |  | CIDCO/NAINA/Panvel/Nevali/ BP-00665/CC/2023/0421 |  |  | Dated | 2023-08-21
Valid Up to: |  | Building 1 (A to D Wing) = Stilt/Ground + 1st to 4th Floor Net Builtup Area = 2107.75sq.m
Airport NOC Valid Up to: |  | NAVI/WEST/B/030923/746042 67.19M (AMSL) |  |  | Dated Valid Upto | 12/04/2023 11/04/2031
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 2107.743
Approved no of units |  |  | Flats - 65, Shops - 05
Approved no of Floors |  |  | Wing (A) = G + 1st to 6th Floor
Wing (B to D) = G + 1st to 5th Floor
Proposed no of Floors |  |  | Wing A = G + 1st to 6th Floor
Wing B & C = G + 1st to 5th Floor
Wing D = G + 1st to 5th Floor
Expected Completion |  |  | As per RERA - 31/10/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Club House, Gymnasium, Kids Swimming Pool, Tennis Court, Kids Playing Area, etc,
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = G + 1st to 6th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 5 Floor, Flooring upto 4 Floor, Painting upto 4 Floor, Finishing upto 2 Floor Completed | , External Plaster upto 5 Floor, Flooring upto 4 Floor, Painting upto 4 Floor, Finishing upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 6 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 5 Floor, Flooring upto 4 Floor, Painting upto 4 Floor, Finishing upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.5
Excavation |  | 6 | 100% | 85% |  | 92.5% |  | Excavation in process | 3
Plinth |  | 6 | 100% |  |  |  |  | Excavation Completed | 6
RCC (Including podiums) |  | 7 | 100% |  |  |  |  | Footing in Process | 1.5
Brickwork | Brickwork & Internal Plaster | 6 | 100% |  |  |  |  | Footing Completed | 3
Internal Plaster | Brickwork & Internal Plaster | 6 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 83.33% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 66.67% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 66.67% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 33.33% |  |  |  |  | Plinth in process | 4.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 6
Construction details: |  | Wing B & C = G + 1st to 5th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 4 Floor, Painting upto 4 Floor, Finishing upto 2 Floor Completed | , Flooring upto 4 Floor, Painting upto 4 Floor, Finishing upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 5 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 4 Floor, Painting upto 4 Floor, Finishing upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% | 89% |  | 94% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% |  |  |  |  | Excavation Completed | 5
RCC (Including podiums) |  | 6 | 100% |  |  |  |  | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% |  |  |  |  | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 80% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 80% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 40% |  |  |  |  | Plinth in process | 3.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 5
Construction details: |  | Wing D = G + 1st to 5th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 4 Floor, Finishing upto 1 Floor Completed | , Painting upto 4 Floor, Finishing upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 5 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 4 Floor, Finishing upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% | 90% |  | 95% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% |  |  |  |  | Excavation Completed | 5
RCC (Including podiums) |  | 6 | 100% |  |  |  |  | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% |  |  |  |  | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 80% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 1 | 20% |  |  |  |  | Plinth in process | 3.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 5
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4400 |  |  |  | 4200 to 4400 | 2023-11-29 | sanket | verbal
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 8000 |  |  | SA changed to 696 from 650 by smith for over valued index 2 26/12/2024
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges |  |  |  |  | 200000
Club Charges |  |  |  |  | 75000
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 200000
Distressed valuation of the Property |  |  |  |  | 3520
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A | Shops | 5 |  | 429.8065 |  | 644.7098
Total |  | 5 |  | 429.8065 |  | 644.7098
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 16 |  | 6629.9782 |  | 10960
Wing B |  | 16 |  | 6294.7872 |  | 10584
Wing C |  | 16 |  | 6294.7872 |  | 10400
Wing D |  | 17 |  | 6970.0883 |  | 11520
Total |  | 65 |  | 26189.6408 |  | 43464
Grand Total |  | 70 |  | 26619.4473 |  | 44108.7098
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
50%
Building No. 1
A Wing
Ground Floor For Commercial & Parking
1 |  | Shop | 100.9125 | 0 | 151.3687 | Ground Floor For Commercial & Parking |  | 9.375
2 |  | Shop | 99.8899 | 0 | 149.8349 |  |  | 9.2812
3 |  | Shop | 53.2818 | 0 | 79.9227 |  |  | 4.945
4 |  | Shop | 74.8098 | 0 | 112.2147
5 |  | Shop | 100.9125 | 0 | 151.3687
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building No. 1
A Wing
1st to 4th Floor For Residential | [9 empty] | 4.8
101 to 401 |  | 1BHK | 393.4242 | 0 | 650 | 1st to 4th Floor For Residential |  | 36.55 | 34.535 | 25.055 | 650 | 1.6522
102 to 402 |  | 1BHK | 458.8263 | 0 | 760 |  |  | 42.626 | 40.1625 |  | 760 | 1.6564
103 to 403 |  | 1BHK | 411.8199 | 0 | 680 |  |  | 38.259 | 36.33 |  | 680 | 1.6512
104 to 404 |  | 1BHK | 393.4242 | 0 | 650 | [5 empty] | 650 | 1.6522
B Wing
Ground Floor For Parking
1st Floor For Residential
101 |  | 1BHK | 393.4242 | 0 | 696 | 1st Floor For Residential |  | SA changed to 696 from 650 by smith for over valued index 2 26/12/2024
102 |  | 1BHK | 393.4242 | 0 | 650
103 |  | 1BHK | 393.4242 | 0 | 650
104 |  | 1BHK | 393.4242 | 0 | 650
2nd to 4th Floor For Residential
201 to 401 |  | 1BHK | 393.4242 | 0 | 650 | 2nd to 4th Floor For Residential |  | 36.55 | 34.775 |  | 650 | 1.6522
202 to 402 |  | 1BHK | 393.4242 | 0 | 650 | [5 empty] | 650 | 1.6522
203 to 403 |  | 1BHK | 393.4242 | 0 | 650 | [5 empty] | 650 | 1.6522
204 to 404 |  | 1BHK | 393.4242 | 0 | 650 | [5 empty] | 650 | 1.6522
C Wing
Ground Floor For Meter Room, Society Office, Drivers Room & Parking
1st to 4th Floor For Residential
101 to 401 |  | 1BHK | 393.4242 | 0 | 650 | 1st to 4th Floor For Residential
102 to 402 |  | 1BHK | 393.4242 | 0 | 650
103 to 403 |  | 1BHK | 393.4242 | 0 | 650
104 to 404 |  | 1BHK | 393.4242 | 0 | 650
D Wing
Ground Floor For Residential & Parking
001 |  | 1BHK | 340.1101 | 0 | 560 | Ground Floor For Residential & Parking |  |  | 1.6465 |  | 720
- |  | Parking
-
-
1st to 4th Floor For Residential
101 to 401 |  | 1BHK | 393.4242 | 0 | 650 | 1st to 4th Floor For Residential
102 to 402 |  | 1BHK | 458.8263 | 0 | 760
103 to 403 |  | 1BHK | 411.8199 | 0 | 680
104 to 404 |  | 1BHK | 393.4242 | 0 | 650
Remarks:
* | Wing A, B, C & D = Construction work is in process at the time of Visit. Wing B = Work is same as last visit.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Chajja Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates of the Property have been revised on 29/11/2023 & 26/12/2024.
* | Construction work goes beyond CC permission . Please provide Revised Approved plans & CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ravindra Vishwakarma |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Hrishikesh 3
Layout :
Google Map :
Formulas:
Nevali = [Nevali, row above]
Wing A
Wing B
Wing C
Wing D
Wing A
Wing B
Wing C
Wing D
Wing D
Wing C
Wing B
Wing D
Wing A
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D56: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC