## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-11
Name of the builder group |  |  |  | M/s.Shree Sai Home Makers
Name of the builder company |  |  |  | M/s.Shree Sai Home Makers
Name of the Project |  |  |  | K K Residency
Contact Details ( Name & Contact No.) |  |  |  | 9029756271/9702474661
Name / No of the Building |  |  |  | Building No.1(A, B & C Wing) Building No.2(D & E Wing)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | P52000027162
Project location details |  | K K Residency, CTS No.377, 378/A, 382/A, 382/B, 389, 390/A, 390/B, 391/A, 391/B, 92/A, 393, 394, 395/A, 395/B, 397/A, 397/B, 398/A, 398/B, 399, 586/A & 586/B, near Commanders Renaissance, Panvel Matheran Road, Koproli, Panvel, Panvel, Raigad.
CTS No |  | 377, 378/A, 382/A, 382/B, 389, 390/A, 390/B, 391/A, 391/B, 92/A, 393, 394, 395/A, 395/B, 397/A, 397/B, 398/A, 398/B, 399, 586/A & 586/B
Road |  | Panvel Matheran Road |  | Village |  | Koproli
City |  | Panvel |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410208
Nearby Landmark |  | Commanders Renaissance |  | Distance from city centre: |  | 5.5Km from Panvel Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Road
West | NA | NA |  |  | Building
North | NA | NA |  |  | Panvel Matheran Road
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude |  | 19.011921,73.1578487
Location Link |  | https://goo.gl/maps/Fx8mkSBKLem1WqyW6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 4208.27
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 1
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 4208.27
Total number of Buildings |  |  |  | 05 Building
Approval Detail : Plan approval
Layout Approval No |  | CIDCO/NAINA/Panvel/Koproli/BP-00511/CC/2020/0025 |  |  | Dated | 07/02/2020.
Approved Floor plan No. |  | CIDCO/NAINA/Panvel/Koproli/BP-00511/CC/2020/0025 |  |  | Dated | 07/02/2020.
Commencement Certificate No. |  | CIDCO/NAINA/Panvel/Koproli/BP-00511/CC/2020/0025 |  |  | Dated | 07/02/2020.
Valid Up to: Building No.1 (Wing A to C) = Gr/St + 4th Floor Building No.2 (Wing D & E) = Gr/St + 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 4208.27
Approved no of units |  |  | Flats - 124, Shops - 26
Approved no of Floors |  |  | Building No.1 - Wing A to C = Gr/St + 4th Floor Building No.2 - Wing D & E(EWS) = Gr/St + 4th Floor
Proposed no of Floors |  |  | Building No. 1 A & B Wing = Gr/St + 4th Floor
B Wing = Gr/St + 4th Floor
Building No. 1 C Wing = Gr/St + 4th Floor
Building No. 2 D & E Wing = Gr/St + 4th Floor
E Wing (EWS) = Gr/St + 4th Floor
Expected Completion |  |  | As per RERA - 31/03/2026.
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Building No. 1 A Wing = Gr/St + 4th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 3 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 3 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 1
Excavation |  | 4 | 100% | 72.5% |  | 88.75% |  | Excavation in process |  | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed |  | 4
RCC |  | 5 | 100% |  |  |  |  | Footing in Process |  | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed |  | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 4
Construction details: |  | B Wing = Gr/St + 4th Floor | [5 empty] | Excavation work completed, Plinth work completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 1
Excavation |  | 4 | 100% | 10% |  | 45% |  | Excavation in process |  | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed |  | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process |  | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed |  | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 4
Construction details: |  | Building No. 1 B Wing = Gr/St + 4th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 3 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 3 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 1
Excavation |  | 4 | 100% | 72.5% |  | 88.75% |  | Excavation in process |  | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed |  | 4
RCC |  | 5 | 100% |  |  |  |  | Footing in Process |  | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed |  | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 4
Construction details: |  | Building No. 1 C Wing = Gr/St + 4th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 3 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 3 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 1
Excavation |  | 4 | 100% | 70.62% |  | 87.5% |  | Excavation in process |  | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed |  | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process |  | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed |  | 2
Internal Plaster | Brickwork & Internal Plaster | 3 | 75% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 4
Construction details: |  | Building No. 2 D & E Wing = Gr/St + 4th Floor | [5 empty] | Excavation work completed, 0
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | All work Completed. Provide OC. |  |  | Please check before changing construction table
Stage of construction: |  | Excavation work completed, Plinth work is process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 1
Excavation |  | 4 | 100% | 8.75% |  | 41.88% |  | Excavation in process |  | 2
Plinth |  | 3.5 | 87.5% |  |  |  |  | Excavation Completed |  | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process |  | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed |  | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 4
Construction details: |  | E Wing (EWS) = Gr/St + 4th Floor | [5 empty] | Work not yet Started.
Basement | 4 | Ground | 1 | Podium | 0 | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Work not yet Started. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 1
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process |  | 2
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed |  | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process |  | 0.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed |  | 1
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 |  | 1.5
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 |  | 2
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 |  | 2.5
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 3
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 3.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 4
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property : | [8 empty] | 4000 to 4700 | 2023-03-31 | smith pal | Cost sheet
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5000 |  |  | 4700 to 5000 by smith on 31/01/2025.Index II on mail
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 7500
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | 150000
Gym Charges |  |  |  |  | 25000
Legal Charges |  |  |  |  | 10,000/-
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Charges |  |  |  |  | 50000
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 4000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing |  | 16 |  | 1600.6821 |  | 2881.2279
D Wing |  | 4 |  | 389.011 |  | 700.2197
E Wing |  | 6 |  | 599.1996 |  | 1078.5593
Total |  | 26 |  | 2588.8927 |  | 4660.0069
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing |  | 28 |  | 9603.8346 |  | 18775
B Wing |  | 28 |  | 8836.695 |  | 16635
C Wing |  | 30 |  | 9858.0695 |  | 18735
D Wing |  | 22 |  | 7718.8859 |  | 14620
E Wing |  | 16 |  | 6832.3414 |  | 12298.2144
Total |  | 124 |  | 42849.8263 |  | 81063.2144
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
80%
Building No.1
A Wing
Ground Floor for Commercial & Parking
1 |  | Shop | 87.1884 | 0 | 156.9391 | Ground Floor for Commercial & Parking
2 |  | Shop | 106.5636 | 0 | 191.8145
3 |  | Shop | 106.5636 | 0 | 191.8145
4 |  | Shop | 87.1884 | 0 | 156.9391
5 |  | Shop | 106.5636 | 0 | 191.8145
6 |  | Shop | 104.6261 | 0 | 188.3269
7 |  | Shop | 107.2094 | 0 | 192.977
8 |  | Shop | 98.2753 | 0 | 176.8956
9 |  | Shop | 106.5636 | 0 | 191.8145
10 |  | Shop | 76.2845 | 0 | 137.312
11 |  | Shop | 93.2485 | 0 | 167.8474
12 |  | Shop | 107.2094 | 0 | 192.977
13 |  | Shop | 100.5035 | 0 | 180.9062
14 |  | Shop | 103.6035 | 0 | 186.4863
15 |  | Shop | 103.6035 | 0 | 186.4863
16 |  | Shop | 105.4872 | 0 | 189.877
Building No.2
D Wing
Ground Floor for Residential & Parking
17 |  | Shop | 106.5636 | 0 | 191.8145 | Ground Floor for Residential & Parking | [6 empty] | 1 & 1 | 1 | 1
18 |  | Shop | 69.7507 | 0 | 125.5513 | [7 empty] | 2 & 2 | 2 | 2
19 |  | Shop | 106.5636 | 0 | 191.8145 | [7 empty] | 3 & 3 | 3 | 3
20 |  | Shop | 106.133 | 0 | 191.0395 | [7 empty] | 4 & 4 | 4 | 4
E Wing
Ground Floor for Residential & Parking
21 |  | Shop | 106.5636 | 0 | 191.8145 | Ground Floor for Residential & Parking | [6 empty] | 1 & 1 | 1 | 1
22 |  | Shop | 87.1884 | 0 | 156.9391 | [7 empty] | 2 & 2 | 2 | 2
23 |  | Shop | 106.5636 | 0 | 191.8145 | [7 empty] | 3 & 3 | 3 | 3
24 |  | Shop | 106.5636 | 0 | 191.8145 | [7 empty] | 4 & 4 | 4 | 4
25 |  | Shop | 87.1884 | 0 | 156.9391 | [7 empty] | #REF! | #REF! | #NUM!
26 |  | Shop | 105.132 | 0 | 189.2376 | [7 empty] | #REF! | #REF! | #NUM!
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building No.1
A Wing
1st Floor
101 |  | 1BHK | 346.5039 | 58.47 | 685 | 1st Floor | [6 empty] | 101 & 101 | 101 | 101
102 |  | 1BHK | 350.3467 | 84.5082 | 730 | [7 empty] | 102 & 102 | 102 | 102
103 |  | 1BHK | 326.0954 | 54.6381 | 640 | [7 empty] | 103 & 103 | 103 | 103
104 |  | 1BHK | 364.2753 | 111.8918 | 820 | [7 empty] | 104 & 104 | 104 | 104
105 |  | 1BHK | 326.0954 | 56.3926 | 645 | [7 empty] | 105 & 105 | 105 | 105
106 |  | 1BHK | 351.6599 | 71.2792 | 710 | [7 empty] | 106 & 106 | 106 | 106
107 |  | 1BHK | 322.5648 | 34.8754 | 605 | [7 empty] | 107 & 107 | 107 | 107
3rd Floor
301 |  | 1BHK | 346.5039 | 58.47 | 685 | 3rd Floor | [6 empty] | #REF! | #REF! | 301
302 |  | 1BHK | 350.3467 | 84.5082 | 730 | [7 empty] | #REF! | #REF! | 302
303 |  | 1BHK | 326.0954 | 54.6381 | 640 | [7 empty] | #REF! | #REF! | 303
304 |  | 1BHK | 364.2753 | 66.7583 | 775 | [7 empty] | #REF! | #REF! | 304
305 |  | 1BHK | 326.0954 | 56.3926 | 645 | [7 empty] | #REF! | #REF! | 305
306 |  | 1BHK | 351.6599 | 71.2792 | 710 | [7 empty] | #REF! | #REF! | 306
307 |  | 1BHK | 322.5648 | 34.8754 | 605 | [7 empty] | #REF! | #REF! | 307
2nd & 4th Floor
201 & 401 |  | 1BHK | 345.1261 | 48.438 | 660 | 2nd & 4th Floor |  |  | 1.772 |  |  |  | 201 & 401 | 201 | 401
202 & 402 |  | 1BHK | 350.1314 | 0 | 590 |  |  | 4000 | 1.6851 |  |  |  | 202 & 402 | 202 | 402
203 & 403 |  | 1BHK | 326.0954 | 44.4768 | 625 |  |  |  | 1.7802 |  |  |  | 203 & 403 | 203 | 403
204 & 404 |  | 1BHK | 393.3381 | 30.9465 | 715 |  |  |  | 1.7391 |  |  |  | 204 & 404 | 204 | 404
205 & 405 |  | 1BHK | 326.0954 | 54.1644 | 640 |  |  |  | 1.7965 |  |  |  | 205 & 405 | 205 | 405
206 & 406 |  | 1BHK | 351.0248 | 64.218 | 695 |  |  |  | 1.797 |  |  |  | 206 & 406 | 206 | 406
207 & 407 |  | 1BHK | 322.5648 | 64.218 | 650 |  |  |  | 1.816 |  |  |  | 207 & 407 | 207 | 407
B Wing
Ground Floor for Residential & Parking
1 |  | 1BHK | 347.1713 | 0 | 585 | Ground Floor for Residential & Parking |  |  | 1.685 | 363.3711 | 1.685
2 |  | 1BHK | 345.5029 | 0 | 580 |  |  |  | 1.6787
3 |  | 1RK | 238.5841 | 0 | 400 |  |  | 4092.5 | 1.6766
4 |  | 1RK | 262.9968 | 0 | 440 |  |  | 3720.4545 | 1.673
1st & 3rd Floor
101 & 301 |  | 1BHK | 346.5255 | 46.1022 | 660 | 1st & 3rd Floor |  | 1.681 | 1.7716 | 362.7253 | 3102000 | 3327000 | 101 & 301 | 101 | 301 | 5000 | 3240000
102 & 302 |  | 1BHK | 345.5029 | 73.066 | 700 |  |  |  | 1.8146 |  | 3525000 | 5000 | 102 & 302 | 102 | 302 |  | 4000000
103 & 303 |  | 1RK | 238.5948 | 69.7507 | 515 |  |  |  | 1.8661 |  |  |  | 103 & 303 | 103 | 303
104 & 304 |  | 1RK | 262.9968 | 0 | 440 |  |  |  | 1.673 |  |  |  | 104 & 304 | 104 | 304
105 & 305 |  | 1BHK | 366.3527 | 71.8282 | 720 |  |  |  | 1.7693 |  |  |  | 105 & 305 | 105 | 305
106 & 306 |  | 1BHK | 359.7652 | 41.6567 | 680 |  |  |  | 1.7743 |  |  |  | 106 & 306 | 106 | 306
2nd & 4th Floor
201 & 401 |  | 1BHK | 345.2338 | 64.8316 | 690 | 2nd & 4th Floor |  |  | 1.8109 |  |  |  | 201 & 401 | 201 | 401
202 & 402 |  | 1BHK | 345.2876 | 55.9513 | 675 |  |  |  | 1.7928 |  |  |  | 202 & 402 | 202 | 402
203 & 403 |  | 1RK | 238.5841 | 0 | 400 |  |  |  | 1.6766 |  |  |  | 203 & 403 | 203 | 403
204 & 404 |  | 1RK | 262.9968 | 0 | 440 |  |  |  | 1.673 |  |  |  | 204 & 404 | 204 | 404
205 & 405 |  | 1BHK | 349.6147 | 45.1335 | 690 |  |  |  | 1.8445 |  |  |  | 205 & 405 | 205 | 405
206 & 406 |  | 1BHK | 359.7652 | 58.2871 | 705 |  |  |  | 1.7976 |  |  |  | 206 & 406 | 206 | 406
C Wing
Ground Floor for Residential & Parking
1 |  | 1BHK | 348.9904 | 0 | 585 | Ground Floor for Residential & Parking |  |  | 1.6763
2 |  | 1BHK | 346.0088 | 0 | 580 |  |  |  | 1.6763
1st & 3rd Floor
101 & 301 |  | 2BHK | 498.8038 | 70.5365 | 950 | 1st & 3rd Floor |  |  | 1.7631 |  |  |  | 101 & 301 | 101 | 301
102 & 302 |  | 1BHK | 340.7667 | 90.0947 | 730 |  |  |  | 1.8778 |  |  |  | 102 & 302 | 102 | 302
103 & 303 |  | 1RK | 246.9046 | 63.6152 | 520 |  |  |  | 1.8484 |  |  |  | 103 & 303 | 103 | 303
104 & 304 |  | 1RK | 246.3987 | 60.3753 | 515 |  |  |  | 1.8451 |  |  |  | 104 & 304 | 104 | 304
105 & 305 |  | 1RK | 265.7955 | 0 | 445 |  |  |  | 1.6742 |  |  |  | 105 & 305 | 105 | 305
106 & 306 |  | 1BHK | 345.1154 | 73.7011 | 710 |  |  |  | 1.8437 |  |  |  | 106 & 306 | 106 | 306
107 & 307 |  | 1BHK | 345.5029 | 45.3703 | 660 |  |  |  | 1.7789 |  |  |  | 107 & 307 | 107 | 307
2nd & 4th Floor
201 & 401 |  | 2BHK | 498.8038 | 49.945 | 920 | 2nd & 4th Floor |  |  | 1.7443 |  |  |  | 201 & 401 | 201 | 401
202 & 402 |  | 1BHK | 340.9282 | 25.2954 | 615 |  |  |  | 1.7297 |  |  |  | 202 & 402 | 202 | 402
203 & 403 |  | 1RK | 246.797 | 0 | 415 |  |  |  | 1.6815 |  |  |  | 203 & 403 | 203 | 403
204 & 404 |  | 1RK | 246.3987 | 34.6601 | 475 |  |  |  | 1.7871 |  |  |  | 204 & 404 | 204 | 404
205 & 405 |  | 1RK | 265.7955 | 0 | 445 |  |  |  | 1.6742 |  |  |  | 205 & 405 | 205 | 405
206 & 406 |  | 1BHK | 348.0216 | 67.2535 | 695 |  |  |  | 1.8038 |  |  |  | 206 & 406 | 206 | 406
207 & 407 |  | 1BHK | 345.5029 | 64.8316 | 690 |  |  |  | 1.8094 |  |  |  | 207 & 407 | 207 | 407
Building No.2
D Wing
Ground Floor for Residential & Parking
1 |  | 1BHK | 362.8006 | 0 | 610 | Ground Floor for Residential & Parking |  |  | 1.6814 |  |  |  | #REF! | #REF! | #NUM!
2 |  | 1BHK | 331.585 | 0 | 550 |  |  |  | 1.6587 |  |  |  | #REF! | #REF! | #NUM!
1st & 3rd Floor
101 & 301 |  | 1BHK | 345.9011 | 61.118 | 685 | 1st & 3rd Floor |  |  | 1.8036 |  |  |  | 101 & 301 | 101 | 301
102 & 302 |  | 1BHK | 362.8006 | 54.6381 | 700 |  |  |  | 1.7788 |  |  |  | 102 & 302 | 102 | 302
103 & 303 |  | 1BHK | 326.203 | 54.6381 | 635 |  |  |  | 1.7791 |  |  |  | 103 & 303 | 103 | 303
104 & 304 |  | 1BHK | 354.1356 | 100.1913 | 735 |  |  |  | 1.7926 |  |  |  | 104 & 304 | 104 | 304
105 & 305 |  | 1BHK | 367.0309 | 62.8941 | 725 |  |  |  | 1.804 |  |  |  | 105 & 305 | 105 | 305
2nd & 4th Floor
201 & 401 |  | 1BHK | 345.9011 | 47.1463 | 660 | 2nd & 4th Floor |  |  | 1.7718 |  |  |  | 201 & 401 | 201 | 401
202 & 402 |  | 1BHK | 362.8006 | 44.4768 | 685 |  |  |  | 1.7655 |  |  |  | 202 & 402 | 202 | 402
203 & 403 |  | 1BHK | 326.203 | 44.4768 | 625 |  |  |  | 1.7796 |  |  |  | 203 & 403 | 203 | 403
204 & 404 |  | 1BHK | 354.2432 | 39.7192 | 660 |  |  | 3672 | 1.751 |  |  |  | 204 & 404 | 204 | 404
205 & 405 |  | 1BHK | 367.0309 | 0 | 620 |  |  |  | 1.6892 |  |  |  | 205 & 405 | 205 | 405
E Wing (EWS)
1st to 4th Floor
101 to 401 |  | 1BHK | 408.9028 | 0 | 736.0251 | 1st to 4th Floor | [6 empty] | 101 & 401 | 101 | 401
102 to 402 |  | 1BHK | 410.7004 | 0 | 739.2608 | [7 empty] | 102 & 402 | 102 | 402
103 to 401 |  | 1BHK | 435.533 | 0 | 783.9593 | [7 empty] | 103 & 403 | 103 | 403
104 to 401 |  | 1BHK | 452.9491 | 0 | 815.3084 | [7 empty] | 104 & 404 | 104 | 404
Remarks:
1 | Building No.1 - Wing A & B = Construction work same as last visit dtd 06/06/2025 but work is in process at the time of Visit. (Very Slow Speed) Building No.1 - Wing C = Construction work is in process at the time of Visit. (Slow speed) Building No.2 - Wing D & E = Construction work is same as last visit dtd. 31/11/2024.
2 | We considered Saleable area Shop as per our calculation & Flat area as per builder area sheet.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Enclose balcony.
5 | We have considered rate by verifying it from market inquire.
6 | Car parking is subjected to authentic documentation.
7 | Recommended Rates/Other Charges of the Property have been revised on 31/01/2025.
8 | The project has received first CC on 07/02/2020, But construction work is not yet completed.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ravindra |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | K K Residency
Google Map :
Wing E
Wing C
Wing D
Wing B
Wing A

## AXIS
Actual Stage Provided by AXIS Bank
Stage calculator as per Revised Valuation Manual
| Completed | Net completed | Recommended | Net recommended | No of floors in building | No of constructed floors | Completed (%) | Recommended (%)
Excavation | 0 | 0 | 20 | 20 | 20 | 20 | 0 | 20
Plinth | 10 | 10 | 45 | 25 | 20 | 20 | 10 | 25
RCC (Including podiums) | 50 | 40 | 75 | 30 | 25 | 25 | 40 | 30
Brickwork & Internal Plaster | 65 | 15 | 85 | 10 | 20 | 20 | 15 | 10
Flooring & Fitting | 75 | 10 | 90 | 5 | 20 | 20 | 10 | 5
External Plaster & Plumbing | 85 | 10 | 95 | 5 | 20 | 20 | 10 | 5
Building Common Amenities & Painting | 95 | 10 | 95 | 0 | 20 | 0 | 0 | 0
Possession | 100 | 5 | 100 | 5 | 20 | 0 | 0 | 0
|  | 100 |  | 100 |  | Final Stage (%) | 85 | 95
Split % by Asmita ---OK By Ajinkya
Stage calculator as per Revised Valuation Manual
| Completed | Net completed | Recommended | Net recommended | No of floors in building | No of constructed floors | Completed (%) | Recommended (%)
Excavation | 0 | 0 | 20 | 20 | 30 | 30 | 0 | 20
Plinth | 10 | 10 | 45 | 25 | 30 | 30 | 10 | 25
RCC (Including podiums) | 50 | 40 | 75 | 30 | 35 | 35 | 40 | 30
Brickwork | 57.5 | 7.5 | 80 | 5 | 30 | 30 | 7.5 | 5
Internal Plaster | 65 | 7.5 | 85 | 5 | 30 | 30 | 7.5 | 5
External Plaster & Plumbing | 75 | 10 | 90 | 5 | 30 | 30 | 10 | 5
Flooring & Fitting | 85 | 10 | 95 | 5 | 30 | 30 | 10 | 5
Painting & Wooden | 90 | 5 | 95 | 0 | 30 | 30 | 5 | 0
Building Common Amenities | 95 | 5 | 95 | 0 | 30 | 30 | 5 | 0
Possession | 100 | 5 | 100 | 5 | 30 | 30 | 5 | 5
|  | 100 |  | 100 |  | Final Stage (%) | 100 | 100
ASMITA recommendation
Stage calculator as per Revised Valuation Manual
| Completed | Net completed | Recommended | Net recommended | No of floors in building | No of constructed floors | Completed (%) | Recommended (%)
Excavation | 0 | 0 | 20 | 20 | 30 | 30 | 0 | 20
Plinth | 10 | 10 | 45 | 25 | 30 | 30 | 10 | 25
RCC (Including podiums) | 50 | 40 | 75 | 30 | 35 | 35 | 40 | 30
Brickwork | 57.5 | 10 | 82.5 | 7.5 | 30 | 30 | 7.5 | 7.5
External Plaster & Plumbing | 62.5 | 5 | 85 | 2.5 | 30 | 30 | 5 | 2.5
Internal Plaster | 67.5 | 5 | 87.5 | 2.5 | 30 | 30 | 5 | 2.5
Flooring & Fitting | 77.5 | 10 | 90 | 2.5 | 30 | 30 | 10 | 2.5
Painting & Wooden | 87.5 | 10 | 95 | 5 | 30 | 30 | 10 | 5
Building Common Amenities | 92.5 | 5 | 97.5 | 2.5 | 30 | 30 | 5 | 2.5
Possession | 100 | 5 | 100 | 2.5 | 30 | 30 | 5 | 2.5
|  | 100 |  | 100 |  | Final Stage (%) | 97.5 | 100
Note on F4: No of habitable floors
Note on F6: No of RCC slabs including podiums
Note on G6: No of constructed RCC slabs including podium
Note on F17: No of habitable floors
Note on F19: No of RCC slabs including podiums
Note on G19: No of constructed RCC slabs including podium
Note on F34: No of habitable floors
Note on F36: No of RCC slabs including podiums
Note on G36: No of constructed RCC slabs including podium

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 3.95 | 10.8625 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.25 | 2.05 | 4.6125 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.75 | 2.4 | 6.6 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.2 | 0.9 | 1.08 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.5 | 1.2 | 1.8 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.05 | 0.95 | 0.9975 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 279.3527 | 25.9525 |  |  | 0 | 0 |  | 0 | 0
|  |  | 279.3527 | 25.9525

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing. | K K Residency | 1RK | 206 | 298.7 | 4921.3257 | 1470000
housing. | K K Residency | 1RK | 229 | 332.05 | 4929.9804 | 1637000
housing. | K K Residency | 1BHK | 295 | 427.75 | 4932.7878 | 2110000
housing. | K K Residency | 1BHK | 321 | 465.45 | 4930.7122 | 2295000
housing. | K K Residency | 2BHK | 428 | 620.6 | 4922.6555 | 3055000
Average |  |  |  |  | 4927.4923
Valuation Adopted |  |  |  |  | 5000