## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-08
Name of the builder group |  |  |  | Micron Infra
Name of the builder company |  |  |  | Micron Infra
Name of the Project |  |  |  | Micron Residency
Provided Contact Details ( Name & Contact No.) |  |  |  | 9820584787
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Sachin 93217519354 |  |  |  | Miss. Srushti : 9820305880
Name / No of the Building |  |  |  | 1 Building
Docouments Provided |  |  |  | Approved Plans, CC, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P51700047065
Project location details |  | Micron Residency, Plot No.323, Sector - 17, near Krishna Paradise, Internal Road, Sector 17, Ulwe, Kharkopar East, Panvel, Raigad - 410206.
Plot No |  | 323, Sector - 17
Locality |  | Sector 17
Road |  | Internal Road |  | Locality/Village |  | Ulwe
City |  | Kharkopar East |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410206
Nearby Landmark |  | Krishna Paradise |  | Distance from city centre: |  | 1.1KM from Kharkopar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Plot No. 318 & 317 |  |  | Building
West | NA | Internal Rd |  |  | Internal Road
North | NA | Plot No. 321 & 322 |  |  | Krisha Corner
South | NA | Plot No. 324 |  |  | Krishna Paradise
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 18.9602 |  | Longitude |  | 73.0216
Location Link |  | https://goo.gl/maps/fPbw95pEZiNKYUVbA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1098.06 |  |  |  | 1.1
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 2.5108
Total FSI availaible for the project |  |  |  | 3.6108
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 3964.92
Total number of Buildings |  |  |  | 1 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | City and Industrial Development Corporation (CIDCO)
Layout Approval No |  | CIDCO/BP-18047/TPO(NM&K)/2022/12666 |  |  | Dated | 2024-06-27
Approved Floor plan No. |  | CIDCO/BP-18047/TPO(NM&K)/2022/12666 |  |  | Dated | 2024-06-27
Commencement-CC No Valid Up to: |  | CIDCO/BP-18047/TPO(NM&K)/2022/12666 |  |  | Dated | 2024-06-27
Gr/St + 1st to 7th Floor Total Built Up Area = 3964.92 Sq.M. Residential Units = 55 Nos, & Commercial Units = 06 Nos.
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 3964.92
Approved no of units |  |  | Flats - 55, Shops - 6
Approved no of Floors |  |  | Gr/St + 1st to 7th Floor
Proposed no of Floors |  |  | Gr/St + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/07/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Gr/St + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 6 Floor, Painting upto 6 Floor, Finishing upto 3 Floor Completed | , Flooring upto 6 Floor, Painting upto 6 Floor, Finishing upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 6 Floor, Painting upto 6 Floor, Finishing upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 90% |  | 94.29% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 6 | 85.71% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 6 | 85.71% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 42.86% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 7000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 8000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges & Development Charges |  |  |  |  | 400000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 5600
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | rate sheet
Shops |  | 6 |  | 2443.428 |  | 3787.3134 |  |  | cost sheet
Residential Area Details : | [8 empty] | 7000
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 55 |  | 31176.1795 |  | 54113
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : 55% | Floor
Ground Floor For Commercial & Parking
1 |  | Shop | 370.3892 | 0 | 574.1033 | Ground Floor For Commercial & Parking |  | 29.605 | 810 | 2.1869
2 |  | Shop | 483.9494 | 0 | 750.1216 |  |  | 45.5625 | 1060 | 2.1903
3 |  | Shop | 367.3753 | 0 | 569.4317 |  |  | 34.5938 | 810 | 2.2048
4 |  | Shop | 367.3753 | 0 | 569.4317 |  |  | 10536.8203 | 810 | 2.2048
5 |  | Shop | 483.9494 | 0 | 750.1216 |  |  |  | 1060 | 2.1903
6 |  | Shop | 370.3892 | 0 | 574.1033 |  |  |  | 810 | 2.1869
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
1st Floor For Residential, Drivers Room & Fitness Center | [8 empty] | 10.764
1 |  | 2 | 719.5196 | 41.8181 | 1340 | 1st Floor For Residential, Drivers Room & Fitness Center |  | 54.275 | 1213.1819 | 1.6861 | 1.8624
2 |  | 2 | 719.5196 | 41.8181 | 1340 |  |  | 584.2161 | 1162.0529 | 1.615
3 |  | 1 | 443.9612 | 92.9471 | 877 |  |  |  | 784.0529 | 1.766
4 |  | 1 | 461.9128 | 0 | 860 |  |  |  | 860 | 1.8618
5 |  | 2 | 652.3522 | 0 | 1122 |  |  |  | 1122 | 1.7199
6 |  | 2 | 616.3197 | 0 | 1175 |  |  |  | 1175 | 1.9065
7 |  | 1 | 450.1101 | 92.9471 | 845 |  |  |  | 752.0529 | 1.6708
2nd to 5th Floor for Residential
1 |  | 2 | 719.5196 | 0 | 1255 | 2nd to 5th Floor for Residential |  |  | 1255 | 1.7442
2 |  | 2 | 719.5196 | 0 | 1255 |  |  | 6230.2789 | 1255 | 1.7442
3 |  | 1 | 443.9612 | 0 | 782 |  |  | 6393.8619 | 782 | 1.7614
4 |  | 1 | 461.7756 | 0 | 765 |  |  | 6535.9477 | 765 | 1.6566
5 |  | 2 | 652.3522 | 0 | 1122 |  |  | 4456.328 | 1122 | 1.7199
6 |  | 2 | 616.3197 | 0 | 1058 |  |  |  | 1058 | 1.7166
7 |  | 1 | 451.0654 | 0 | 772 |  |  |  | 772 | 1.7115
8 |  | 1 | 450.1101 | 0 | 750 |  |  |  | 750 | 1.6663
6th Floor | [9 empty] | #DIV/0!
1 |  | 2 | 719.5196 | 0 | 1255 | 6th Floor |  |  | 1255 | 1.7442
2 |  | 2 | 719.5196 | 0 | 1255 |  |  |  | 1255 | 1.7442
3 |  | 1 | 443.9612 | 0 | 782 |  |  |  | 782 | 1.7614
4 |  | 1 | 461.7756 | 0 | 765 |  |  |  | 765 | 1.6566
5 |  | 2 | 657.196 | 0 | 1122 |  |  |  | 1122 | 1.7073
6 |  | 2 | 616.3197 | 0 | 1058 |  |  |  | 1058 | 1.7166
7 |  | 1 | 451.0654 | 0 | 772 |  |  |  | 772 | 1.7115
8 |  | 1 | 451.8324 | 0 | 750 |  |  |  | 750 | 1.6599
7th Floor | [9 empty] | #DIV/0!
1 |  | 2 | 719.5196 | 0 | 1255 | 7th Floor |  |  | 1255 | 1.7442
2 |  | 2 | 719.5196 | 0 | 1255 |  |  |  | 1255 | 1.7442
3 |  | 1 | 443.9612 | 0 | 782 |  |  |  | 782 | 1.7614
4 |  | 1 | 461.7756 | 0 | 765 |  |  |  | 765 | 1.6566
5 |  | 2 | 661.3402 | 0 | 1122 |  |  |  | 1122 | 1.6966
6 |  | 2 | 625.7382 | 0 | 1058 |  |  |  | 1058 | 1.6908
7 |  | 1 | 451.0654 | 0 | 772 |  |  |  | 772 | 1.7115
8 |  | 1 | 449.8814 | 0 | 750 |  |  |  | 750 | 1.6671
Ground Floor
1 |  |  |  | 0 | #REF! | Ground Floor
2 |  |  |  | 0 | #REF! | Ground Floor
3 |  |  |  | 0 | #REF! | Ground Floor
4 |  |  |  | 0 | #REF! | Ground Floor
2nd Floor
201 |  |  |  | 0 | #REF! | 2nd Floor
202 |  |  |  | 0 | #REF! | 2nd Floor
203 |  |  |  | 0 | #REF! | 2nd Floor
204 |  |  |  | 0 | #REF! | 2nd Floor
205 |  |  |  | 0 | #REF! | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | #REF! | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | #REF! | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | #REF! | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | #REF! | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | #REF! | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | #REF! | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | #REF! | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | #REF! | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | #REF! | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | #REF! | 2nd & 5th Floor
Remarks:
1 | Construction work is in process at the time of Visit.
2 | We considered Saleable area of Flat as per Builder area Sheet.
3 | We have considered Saleable area of Commercial as per our Calculation. | [6 empty] | We considered Saleable area of Commercial as per Builder area Sheet.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Enclose Balcony + Balcony.
6 | We have considered proposed No. of Floor for Stage Calculation.
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | We have updated latest approved floor plans & CC (On 03/12/2024).
11 | As per the site visit dtd. 03/12/2024, we have observed that the construction work of the 1st floor terrace area is not done as per the approved 1st floor plan. (Extra terrace area are constructed for flats No. 101 & 102). Photographs are attached below.
12 | Please check for the approved subject to the conditions mentioned in letter to the No.CIDCO/BP-18047/TPO(NM & K)/2022/12666 dtd.27/06/2024. As mentioned in the approved plans, which are attached below.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Anish Vishwakarma |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Micron Residency
Layout Plan :
Remark No. 11 :
Remark No. 11 :
Google Map :
Formulas:
Ulwe = [Ulwe, row above]
1st Floor

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted