## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-09
Name of the builder group |  |  |  | M/s.Puranik Builders Limited
Name of the builder company |  |  |  | M/s.Puranik Builders Limited
Name of the Project |  |  |  | Puraniks Unicorn Phase I & II
Contact Details ( Name & Contact No.) |  |  |  | Mr. Prathamesh Gawane - 9152034971
Name / No of the Building |  |  |  | Phase I = Building Type - T6A (Celestia) Phase II = Building Type - T6B (Asta)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | Phase I = Building Type - T6A = P51700032292 Phase II = Building Type - T6B = P51700047561
Project location details |  | Puraniks Unicorn Phase I & II, Survey No.55/1/C, near Puranik City Reserva, Ghodbunder Road, Mogharpada, Thane West, Thane, Thane - 400615.
Survey No |  | 55/1/C
Road |  | Ghodbunder Road |  | Locality/Village |  | Mogharpada
City |  | Thane West |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400615
Nearby Landmark |  | Puranik City Reserva |  | Distance from city centre: |  | 13.7KM from Thane Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.27953,72.965725
Location Link |  | https://goo.gl/maps/jxzCuyv2murpxj2w7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 7054.51
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.77665
Total FSI availaible for the project |  |  |  | 1.8767
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 13238.86
Total number of Buildings |  |  |  | 1 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Thane Municipal Corporation (TMC)
Layout Approval No |  | V.P.S06/0367/21/TMC/TD-DP/TPS/4085/22 |  |  | Dated | 2022-06-17
Approved Floor plan No. |  | V.P.S06/0367/21/TMC/TD-DP/TPS/4085/22 |  |  | Dated | 2022-06-17
Commencement-CC No Valid Up to: |  | V.P.No.S06/0367/21/TMC/TDD/4195/22 |  |  | Dated | 2022-09-16
Building Type T6A = LG + G + Stilt(pt)/ Podium(pt) + 1st to 32nd Floors Building Type T6B = LG + G + Stilt(pt)/Podium(pt) + 1st to 32nd Floors
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 13238.86
Approved no of units |  |  | Flats - 508, Shops - 10
Approved no of Floors |  |  | Phase I = Building Type T6A = LG + G + Stilt(pt)/ Podium(pt) + 1st to 32nd Floor Phase II = Building Type T6B = LG + G + Stilt(pt)/Podium(pt) + 1st to 33rd Floor
Proposed no of Floors |  |  | Phase I = Building Type T6A = LG + G + Stilt(pt)/ Podium(pt) + 1st to 32nd Floor
Phase II = Building Type T6B = LG + G + Stilt(pt)/ Podium(pt) + 1st to 33rd Floor
Expected Completion |  |  | As per RERA - Building Type T6A = 31/12/2028 Building Type T6B = 31/12/2029
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Phase I = Building Type T6A = LG + G + Stilt(pt)/ Podium(pt) + 1st to 32nd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 21 Slab Completed, Brickwork upto 19 Floor Completed, Internal Plaster upto 14.25 Floor Completed, External Plaster upto 12.35 Floor Completed.
Basement | 1 | Ground | 1 | Podium | 1 | Floors | 32
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 21 Slab Completed, Brickwork upto 19 Floor Completed, Internal Plaster upto 14.25 Floor Completed, External Plaster upto 12.35 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8
Excavation |  | 32 | 100% | 46.36% |  | 70.65% |  | Excavation in process | 16
Plinth |  | 32 | 100% |  |  |  |  | Excavation Completed | 32
RCC (Including podiums) |  | 21 | 61.76% |  |  |  |  | Footing in Process | 8
Brickwork | Brickwork & Internal Plaster | 19 | 59.38% |  |  |  |  | Footing Completed | 16
Internal Plaster | Brickwork & Internal Plaster | 14.25 | 44.53% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12.35 | 38.59% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 24
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 32
Construction details: |  | Phase II = Building Type T6B = LG + G + Stilt(pt)/ Podium(pt) + 1st to 33rd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 14 Slab Completed, Brickwork upto 12 Floor Completed, Internal Plaster upto 9 Floor Completed, External Plaster upto 7.8 Floor Completed.
Basement | 1 | Ground | 1 | Podium | 1 | Floors | 33
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 14 Slab Completed, Brickwork upto 12 Floor Completed, Internal Plaster upto 9 Floor Completed, External Plaster upto 7.8 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8.25
Excavation |  | 33 | 100% | 33.14% |  | 61.36% |  | Excavation in process | 16.5
Plinth |  | 33 | 100% |  |  |  |  | Excavation Completed | 33
RCC (Including podiums) |  | 14 | 40% |  |  |  |  | Footing in Process | 8.25
Brickwork | Brickwork & Internal Plaster | 12 | 36.36% |  |  |  |  | Footing Completed | 16.5
Internal Plaster | Brickwork & Internal Plaster | 9 | 27.27% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7.8 | 23.64% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 24.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 33
Recommended Rates of the Property :
Recommended rate of the Flat Per Sq. Ft. (on Saleable area) |  |  |  |  | 10000
Recommended rate of the Shop Per Sq. Ft. (on Saleable area) |  |  |  |  | 20000
MSEB Deposit Charges |  |  |  |  | 50000
Water Connection Charges |  |  |  |  | 50000
Society Reg Charges |  |  |  |  | 48000
Club Charges
Legal Services Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 8000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building Type - T6B (Asta) | Shop | 10 |  | 3890.2172 |  | 9129.633
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building Type - T6A (Celestia) | Flats | 250 |  | 93713.1062 |  | 149940.97
Building Type - T6B (Asta) |  | 258 |  | 96713.8942 |  | 154742.2307
Total |  | 508 |  | 190427.0004 |  | 304683.2006
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Phase II
Building Type - T6B (Asta)
Ground Floor for Commercial & Parking
1 |  | Shop | 509.6754 | 249.3211 | 1214.3945 | Ground Floor for Commercial & Parking |  | 47.401
2 |  | Shop | 521.3005 | 256.1832 | 1243.974
3 |  | Shop | 441.4316 | 215.0109 | 1050.3081
4 |  | Shop | 280.6175 | 116.6871 | 635.6874
5 |  | Shop | 300.1003 | 137.241 | 699.7461
6 |  | Shop | 259.9506 | 75.1112 | 536.0989
7 |  | Shop | 280.4022 | 116.8836 | 635.6573
8 |  | Shop | 281.9092 | 163.1284 | 712.0601
9 |  | Shop | 561.5579 | 264.3638 | 1321.4748
10 |  | Shop | 453.272 | 221.8729 | 1080.232
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Phase I
Building Type - T6A (Celestia)
Lower Ground Floor For Parking
Ground Floor For Parking
Stilt / Podium Floor For Society Office, Drivers Room & Parking
1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th & 32nd Floor for Residential
1 |  | 1BHK | 290.0898 | 0 | 464.1437 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th & 32nd Floor for Residential |  | 25.685 | 11203.4274 | 9695.2737
2 |  | 1BHK | 289.5516 | 0 | 463.2826
3 |  | 2BHK | 487.2863 | 0 | 779.658 |  |  | 42.735 |  | 9363.0791
4 |  | 2BHK | 487.2863 | 0 | 779.658
5 |  | 1BHK | 287.1835 | 0 | 459.4936
6 |  | 1BHK | 287.7217 | 0 | 460.3548
7 |  | 1BHK | 385.3512 | 0 | 616.5619 |  |  |  |  | 9244.8136
8 |  | 2BHK | 486.3175 | 0 | 778.108
6th, 11th, 16th, 21st, 26th & 31st Floor (Part Refuge Area)
1 |  | 1BHK | 290.0898 | 0 | 464.1437 | 6th, 11th, 16th, 21st, 26th & 31st Floor (Part Refuge Area)
2 |  | 1BHK | 289.5516 | 0 | 463.2826
3 |  | 2BHK | 487.2863 | 0 | 779.658
4 |  | 2BHK | 487.2863 | 0 | 779.658
5 |  | 1BHK | 287.1835 | 0 | 459.4936 |  |  | 11303.7475
6 |  | 1BHK | 287.7217 | 0 | 460.3548
7 |  | Refuge Area
8 |  | 2BHK | 486.3175 | 0 | 778.108
Phase II
Building Type - T6B (Asta)
Lower Ground Floor For Parking
Stilt / Podium Floor For Meter Room & Parking
Ground Floor For Commercial & Parking
1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th, 32nd & 33rd Floor for Residential
1 |  | 1BHK | 290.0898 | 0 | 464.1437 | 1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th, 32nd & 33rd Floor for Residential |  | 25.685
2 |  | 1BHK | 289.5516 | 0 | 463.2826
3 |  | 2BHK | 487.2863 | 0 | 779.658
4 |  | 2BHK | 487.2863 | 0 | 779.658
5 |  | 1BHK | 287.1835 | 0 | 459.4936
6 |  | 1BHK | 287.7217 | 0 | 460.3548
7 |  | 1BHK | 385.3512 | 0 | 616.5619
8 |  | 2BHK | 486.3175 | 0 | 778.108
6th, 11th, 16th, 21st, 26th & 31st Floor (Part Refuge Area)
1 |  | 1BHK | 290.0898 | 0 | 464.1437 | 6th, 11th, 16th, 21st, 26th & 31st Floor (Part Refuge Area)
2 |  | 1BHK | 289.5516 | 0 | 463.2826
3 |  | 2BHK | 487.2863 | 0 | 779.658
4 |  | 2BHK | 487.2863 | 0 | 779.658
5 |  | 1BHK | 287.1835 | 0 | 459.4936
6 |  | 1BHK | 287.7217 | 0 | 460.3548
7 |  | Refuge Area
8 |  | 2BHK | 486.3175 | 0 | 778.108
Remarks:
* | Building Type - T6A & T6B = Construction work is in process at the time of visit. (Internal photographs not allowed)
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have update latest approved floor plan & CC of Building Type - T6A & T6B (On 23/01/2023).
* | On Site, we meet Mr.Nikhil (Sales) - 8108660034.
* | We refer latest CC from Rera site.
* | As per Rera, Building Type - T6A is named as Celestia & Building Type - T6B is Asta.
* | Also, building type T6A belongs to phase I, and building type T6B belongs to phase II.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ajay Songare |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Puraniks Unicorn Phase I & II
Google Map :
Formulas:
Mogharpada = [Mogharpada, row above]
T6B
T6A

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
99 Acres |  | 1bhk | 290 | 464 | 9698.2759 | 4500000
100 Acres |  | 2bhk | 487 | 779.2 | 9368.5832 | 7300000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted