## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-09
Name of the builder group |  |  |  | Aayushi Corporation
Name of the builder company |  |  |  | Aayushi Corporation
Name of the Project |  |  |  | Raghunath
Provided Contact Details (Name & Contact No.) |  |  |  | 9892955677
Site Person - Contact Details (Name & Contact No.) |  |  |  | NA
Name / No of the Building |  |  |  | 1 building
Name / No of the Existing Building
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P52000051331
Project location details |  | Raghunath, Plot No..222, Sector No. 21, near Siddheshwar Heights, Internal Road, Kamothe, Panvel, Khandeshwar East, Panvel, Raigad - 410206.
Plot No. |  | 222, Sector No. 21
Locality |  | Kamothe
Road |  | Internal Road |  | Locality/Village |  | Panvel
City |  | Khandeshwar East |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410206
Nearby Landmark |  | Siddheshwar Heights |  | Distance from city centre: |  | 1.3KM from Khandeshwar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Plot No. 222A |  |  | Ganga Tower
West | NA | Pathway |  |  | Siddheshwar Heights
North | NA | Wide Road |  |  | Internal Road
South | NA | Buillding. 228, 203 |  |  | Shreeji Residency
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.015215, 73.098234
Location Link |  | https://goo.gl/maps/fXn3yBA8JgGf6bDX9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1000
Permissible FSI |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  | 1.6659
Total FSI availaible for the project |  |  |  | 3.1659
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 3165.859
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation (PMC)
Layout Approval No |  | PMP/NRV/16364/J.K-826/2023 |  |  | Dated | 2023-03-31
Approved Floor plan No. |  | PMP/NRV/16364/J.K-826/2023 |  |  | Dated | 2023-03-31
Commencement-CC No Valid Up to: |  | PMC/TP/Kamothe/21/222/21-23/16364/829/2023 |  |  | Dated | 2023-03-31
Stilt + 11 Upper Floors
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 3165.859
Approved no of units |  |  | Flats - 55
Approved no of Floors |  |  | Gr/St + 1st to 11th Floor
Proposed no of Floors |  |  | Gr/St + 1st to 14th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Gymnasium, Rooftop Amenities, Fire fighting system, Yoga & Meditation zone.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Gr/St + 1st to 14th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 12 Slab, Brickwork upto 9 Floor, Internal Plaster upto 8 Floor, External Plaster upto 6 Floor, Flooring upto 4 Floor Completed | , RCC upto 12 Slab, Brickwork upto 9 Floor, Internal Plaster upto 8 Floor, External Plaster upto 6 Floor, Flooring upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 12 Slab, Brickwork upto 9 Floor, Internal Plaster upto 8 Floor, External Plaster upto 6 Floor, Flooring upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 58.25% |  | 78.64% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 12 | 80% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 9 | 64.29% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 8 | 57.14% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 42.86% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 28.57% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 9000
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges
Club Charges |  |  |  |  | 100000
Legal Charges |  |  |  |  | 15000
Gas Connection Charges
Water, MSEB & Development Charges |  |  |  |  | 300000
Society Formation + Infrastructure + Maintenance Charges |  |  |  |  | 100000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 400000
Distressed valuation of the Property |  |  |  |  | 7200
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 55 |  | 23150.1133 |  | 34725.1699
Total
Grand Total |  | 0 |  | 0 |  | 0
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
45%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Ground Floor For Parking, Clubhouse, Drivers Room & Meter Room
1st to 7th, 9th & 10th Floor For Residential | [8 empty] | 10.764
1 |  | 2 | 574.5716 | 0 | 861.8573 | 1st to 7th, 9th & 10th Floor For Residential |  |  | 50.1072 | 7.539 | 11095.2238 | Builder
2 |  | 1 | 395.0173 | 0 | 592.5259 | [5 empty] | 8500 | visitor
3 |  | 1 | 379.3234 | 0 | 568.985 |  |  |  | 33.4457 | 5.3625
4 |  | 1 | 379.3234 | 0 | 568.985
5 |  | 1 | 377.4181 | 0 | 566.1272 | [5 empty] | 7325787.339
8th Floor (Part Refuge Area at Mid landing)
1 |  | 2 | 574.5716 | 0 | 861.8573 | 8th Floor (Part Refuge Area at Mid landing)
2 |  | 1 | 395.0173 | 0 | 592.5259
3 |  | 1 | 379.3234 | 0 | 568.985
4 |  | 1 | 379.3234 | 0 | 568.985
5 |  | 1 | 377.4181 | 0 | 566.1272
11th Floor
1 |  | 2 | 562.4943 | 0 | 843.7415 | 11th Floor
2 |  | 1 | 395.0173 | 0 | 592.5259
3 |  | 1 | 379.3234 | 0 | 568.985
4 |  | 1 | 379.3234 | 0 | 568.985
5 |  | 1 | 377.4181 | 0 | 566.1272
Ground Floor
1 |  | 2 |  | 0 | 0 | Ground Floor
2 |  | 2 |  | 0 | 0 | Ground Floor
3 |  | 2 |  | 0 | 0 | Ground Floor
4 |  | 2 |  | 0 | 0 | Ground Floor
5 |  | 2 |  | 0 | 0 | Ground Floor
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
* | Construction work same as last visit dtd 06/06/2025.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mayur Ranvare |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Raghunath
Layout :
Google Map :
Formulas:
Panvel = [Panvel, row above]
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted