## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 17/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-08
Name of the builder group |  |  |  | Level Up Realtors
Name of the builder company |  |  |  | Level Up Realtors
Name of the Project |  |  |  | Rameshwar Arcade
Provided Contact Details ( Name & Contact No.) |  |  |  | 8554058171
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Vartak 9373538506
Name / No of the Building |  |  |  | 1 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area
RERA No. |  |  |  | P99000032414
Project location details |  | Rameshwar Arcade, Gut No.70/1/1, near Decent Lifespace, Old Palghar Manor Road, Vevoor, Palghar, Palghar East, Palghar, Palghar - 401404.
Gut No |  | 70/1/1
Locality |  | Vevoor
Road |  | Old Palghar Manor Road |  | Locality/Village |  | Palghar
City |  | Palghar East |  | District |  | Palghar
Taluka |  | Palghar |  | Pin Code |  | 401404
Nearby Landmark |  | Decent Lifespace |  | Distance from city centre: |  | 1.6 KM from Palghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Kamla Park
West | NA | NA |  |  | Internal Road
North | NA | NA |  |  | Decent Lifespace
South | NA | NA |  |  | Old Palghar Manor Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.7041 |  | Longitude |  | 72.7713
Location Link |  | https://goo.gl/maps/Hgu8sib6dDTqP1fu6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1354.37
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 2.0224
Total FSI availaible for the project |  |  |  | 3.1224
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 4228.86
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Palghar Municipal Council
Layout Approval No |  | NRV-4483 |  |  | Dated | 2021-09-29
Approved Floor plan No. |  | NRV-4483 |  |  | Dated | 2021-09-29
Commencement-CC No Valid Up to: |  | PNP/NRV-4483/2021-2022 |  |  | Dated | 2021-09-29
G + 1st to 9th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 4228.86
Approved no of units |  |  | Flats - 53, Shops - 15
Approved no of Floors |  |  | G + 1st to 9th Floor
Proposed no of Floors |  |  | G + 1st to 9th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | G + 1st to 9th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 5 Floor Completed | , Finishing upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 9 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.25
Excavation |  | 9 | 100% | 92.78% |  | 95% |  | Excavation in process | 4.5
Plinth |  | 9 | 100% |  |  |  |  | Excavation Completed | 9
RCC (Including podiums) |  | 10 | 100% |  |  |  |  | Footing in Process | 2.25
Brickwork | Brickwork & Internal Plaster | 9 | 100% |  |  |  |  | Footing Completed | 4.5
Internal Plaster | Brickwork & Internal Plaster | 9 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 9 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 9 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 5 | 55.56% |  |  |  |  | Plinth in process | 6.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 9
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4000 |  |  |  | mis | mb | visitor
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 8000 |  |  |  | 3500 avg | 3600 | 4100
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 150000
Distressed valuation of the Property |  |  |  |  | 3200
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 15 |  | 2397.1428 |  | 3835.4285
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 53 |  | 30366.1051 |  | 48321.8231
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor For Commercial & Part Parking | [8 empty] | 10.764
1 |  | Shop | 196.0124 | 0 | 313.6199 | Ground Floor For Commercial & Part Parking
2 |  | Shop | 128.7374 | 0 | 205.9799 | Ground Floor For Commercial & Part Parking
3 |  | Shop | 131.1055 | 0 | 209.7688 | Ground Floor For Commercial & Part Parking
4 |  | Shop | 153.387 | 0 | 245.4192 | Ground Floor For Commercial & Part Parking
5 |  | Shop | 165.4427 | 0 | 264.7083 | Ground Floor For Commercial & Part Parking
6 |  | Shop | 128.7374 | 0 | 205.9799 | Ground Floor For Commercial & Part Parking
7 |  | Shop | 206.7764 | 0 | 330.8423 | Ground Floor For Commercial & Part Parking
8 |  | Shop | 125.9388 | 0 | 201.5021 | Ground Floor For Commercial & Part Parking
9 |  | Shop | 156.5086 | 0 | 250.4137 | Ground Floor For Commercial & Part Parking
10 |  | Shop | 168.1337 | 0 | 269.0139 | Ground Floor For Commercial & Part Parking
11 |  | Shop | 205.8077 | 0 | 329.2923 | Ground Floor For Commercial & Part Parking
12 |  | Shop | 117.3276 | 0 | 187.7242 | Ground Floor For Commercial & Part Parking
13 |  | Shop | 156.5086 | 0 | 250.4137 | Ground Floor For Commercial & Part Parking
14 |  | Shop | 128.7374 | 0 | 205.9799 | Ground Floor For Commercial & Part Parking
15 |  | Shop | 227.9815 | 0 | 364.7704 | Ground Floor For Commercial & Part Parking
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
1st Floor For Residential
101 |  | 1 | 387.7193 | 0 | 621 | 1st Floor For Residential |  | 4413.8486 | 621 | 1.6017 | 35.288
102 |  | 2 | 490.1926 | 0 | 784 | 1st Floor For Residential |  | 4376.2755 | 784 | 1.5994
103 |  | 2 | 490.1926 | 0 | 784 | 1st Floor For Residential |  |  | 784 | 1.5994
104 |  | 2 | 548.1029 | 0 | 877 | 1st Floor For Residential |  |  | 877 | 1.6001
105 |  | 2 | 490.1926 | 0 | 784 | 1st Floor For Residential |  |  | 784 | 1.5994
106 |  | 2 | 490.1926 | 0 | 784 | 1st Floor For Residential |  |  | 784 | 1.5994
2nd to 7th & 9th Floor | [9 empty] | #DIV/0!
201 ,.., 901 |  | 1 | 444.9838 | 0 | 704 | 2nd to 7th & 9th Floor |  |  | 704 | 1.5821
202 ,.., 902 |  | 2 | 610.9646 | 0 | 972 | 2nd to 7th & 9th Floor |  |  | 972 | 1.5909 | 50.3048
203 ,.., 903 |  | 2 | 610.9646 | 0 | 972 | 2nd to 7th & 9th Floor |  |  | 972 | 1.5909
204 ,.., 904 |  | 2 | 606.2285 | 0 | 966 | 2nd to 7th & 9th Floor |  |  | 966 | 1.5935
205 ,.., 905 |  | 2 | 610.9646 | 0 | 972 | 2nd to 7th & 9th Floor |  |  | 972 | 1.5909
206 ,.., 906 |  | 2 | 610.9646 | 0 | 972 | 2nd to 7th & 9th Floor |  |  | 972 | 1.5909
8th Floor (Part Refuge Area) | [9 empty] | #DIV/0!
801 |  | 1 | 444.9838 | 0 | 704 | 8th Floor (Part Refuge Area) |  |  | 704 | 1.5821
802 |  | 2 | 610.9646 | 0 | 972 | 8th Floor (Part Refuge Area) |  |  | 972 | 1.5909
803 |  | 3 | 726.1394 | 0 | 1161.8231 | 8th Floor (Part Refuge Area) |  |  |  | 0
804 |  | Refuge Area |  |  |  | 8th Floor (Part Refuge Area) |  |  |  | #DIV/0!
805 |  | 2 | 610.9646 | 0 | 972 | 8th Floor (Part Refuge Area) |  |  | 972 | 1.5909
806 |  | 2 | 610.9646 | 0 | 972 | 8th Floor (Part Refuge Area) |  |  | 972 | 1.5909
Ground Floor
1 |  |  |  | 0 | #REF! | Ground Floor
2 |  |  |  | 0 | #REF! | Ground Floor
3 |  |  |  | 0 | #REF! | Ground Floor
4 |  |  |  | 0 | #REF! | Ground Floor
2nd Floor
201 |  |  |  | 0 | #REF! | 2nd Floor
202 |  |  |  | 0 | #REF! | 2nd Floor
203 |  |  |  | 0 | #REF! | 2nd Floor
204 |  |  |  | 0 | #REF! | 2nd Floor
205 |  |  |  | 0 | #REF! | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | #REF! | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | #REF! | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | #REF! | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | #REF! | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | #REF! | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | #REF! | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | #REF! | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | #REF! | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | #REF! | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | #REF! | 2nd & 5th Floor
Remarks:
* | Some flats are occupied by tenants but Lift work is in process.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On site we met Sales person - 8554058171.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnyesh Patil |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Rameshwar Arcade
Layout :
Google Map :
Formulas:
Palghar = [Palghar, row above]

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted