## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 17/09/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-09-08
Name of the builder group |  |  |  |  | M/s.Sai Krishna Signature Homes LLP
Name of the builder company |  |  |  |  | M/s.Sai Krishna Signature Homes LLP
Name of the Project |  |  |  |  | Sai Krishna Vatika
Contact Details ( Name & Contact No.) |  |  |  |  | 9819048949/7977811324
Name / No of the Building |  |  |  |  | 01 Building
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | P99000017408
Project location details |  | Sai Krishna Vatika, Gut No. 27/2/A, Plot No.7, Station Road, Navali, Palghar.
Gut No |  | 27/2/A |  |  | Plot No |  | 7
Road |  | Station Road |  |  | Locality/Village |  | Navali
City |  | Palghar |  |  | District |  | Palghar
Taluka |  | Palghar |  |  | Pin Code |  | 401404
Near by Landmark |  | Suraj Dairy Farm |  |  | Distance from city centre: |  | About 2.6Km from Palghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Bungalow |  | Road |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.68556, 72.7827258
Location |  | https://goo.gl/maps/AJx11TiENSxfGobx6
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 331.84
Permissible FSI |  |  |  |  | 1.2
Permissible TDR/Paid FSI |  |  |  |  | 0.60002
Total FSI availaible for the project |  |  |  |  | 1.8
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 597.32
Total number of Buildings |  |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | K.B.V.198 |  |  |  | Dated | 01/01/2019.
Approved Floor plan No. |  | K.B.V.198 |  |  |  | Dated | 01/01/2019.
Commencement Certificate No. |  | P.N.P./BD/KY-198/2018-2019 Valid Up to: G + 4th Floors |  |  |  | Dated | 01/01/2019.
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 01/01/2019. |  | Expected Completion |  | 31/12/2025
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 597.32 |  | Approved no of units |  | Flats = 16, shop = 08 & Office = 02
Approved no of Floors |  | G + 4th Floors |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details:
Construction details: |  | G + 1st to 4th Floor | [6 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 3 Floor Completed | , External Plaster upto 3 Floor
Basement | 0 | Ground | 1 |  | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 3 Floor Completed | [6 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 72.5% |  | 88.75% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3700 |  |  |  |  | 3500 to 3700 & Charges | Nikhil P. Dani, | 2023-02-07 | IGR & Cost Sheet
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 6500/-
Development Charges | [5 empty] | 150000
Society Formation Charges | [5 empty] | 100000
Maintenance Charges | [5 empty] | 50000
Recommended rate of Parking | [5 empty] | 50000/-
Distressed valuation of the Property | [5 empty] | 2960
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Shop |  | 8 | 699.9829 |  |  | 1264
Office |  | 2 | 155.2169 |  |  | 297
Total |  | 10 | 855.1998 |  |  | 1561
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
1 |  | 16 | 4356.729 |  |  | 4356.729
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Ground Floor is For Parking & Commercial
1 |  | Shop | 101.7198 |  | 0 | 189 | N | Ground Floor
2 |  | Shop | 69.7507 |  | 0 | 126 | N
3 |  | Shop | 74.7022 |  | 0 | 126 | N
4 |  | Shop | 108.824 |  | 0 | 194 | N
5 |  | Shop | 70.9348 |  | 0 | 126 | N
6 |  | Shop | 55.4346 |  | 0 | 105 | N
7 |  | Shop | 118.9422 |  | 0 | 226 | N
8 |  | Shop | 99.6746 |  | 0 | 172 | N
1 |  | Office | 48.438 |  | 0 | 103 | N
2 |  | Office | 106.7789 |  | 0 | 194 | N
1st To 4th Floor
1 |  | 1RK | 266.7319 |  | 0 | 450 | N | 1st To 4th Floor
2 |  | 1RK | 251.7161 |  | 0 | 565 | N |  |  |  | 2.2446
3 |  | 1BHK | 279.0567 |  | 0 | 575 | N
4 |  | 1BHK | 291.6775 |  | 0 | 610 | N
Remarks:
1. Construction work is same as last visit dtd. 08/03/2025. 2. We considered Saleable area as per Builder area sheet. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + W.S Area. 5. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 6. We have considered rate by verifying from market inquire. 7. Car parking is subjected to authentic documentation. 8. The project has received first CC on 01/01/2019, But construction work is not yet completed. 9. On site we met Mr. Yadav : 9082106423. 9. As per RERA, completion period of project Sai Krishna Vatika is expired on 31/03/2024 but still project is under construction. | [9 empty] | Construction work was not active at the time of visit.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnyesh Patil |  | Report Prepared By : |  |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sai Krishna Vatika
Google Map :

## C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 0 | 0% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 10% | 30% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0