## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 15/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-11
Name of the builder |  |  |  |  | Mr. Walmik Raghunath Khairnar
Name of the builder company |  |  |  |  | M/s. Om Sai Associate
Name of the Project |  |  |  |  | Sai Angan (Wing A to F)
Contact Details ( Name & Contact No.) |  |  |  |  | 86554 44445 & 94992 64445
RERA No. |  |  |  |  | P52000004010
Docouments Provided |  |  |  |  | Refer Data
Project location details |  | Sai Angan (A to E Wing), Survey No. 48, Hissa No. 1 at Village Newali, Panvel, Navi Mumbai - 410 206.
S No | 48 |  |  | Hissa No. | 1 | Locality | Newali
Road | Takka Road |  |  |  | District | Raigad
City | Panvel |  |  |  | Pin Code | 410 206
Near by Landmark |  | Channel Paradise |  |  | Distance from city centre: |  | About 1.6Km Distance From Panvel Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Open Plot |  | Building |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.022239,73.123498
Location Link |  | https://goo.gl/maps/GisifJkq8p6t9pxS7
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 7030
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | -
Total FSI availaible for the project |  |  |  |  | -
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 3900
Total number of Buildings |  |  |  |  | 06 Wings
Approval Detail : Plan approval
Layout Approval No |  | ADTPO/RA/48/1/2058 |  |  |  | Dated | 28/08/2015.
Building plan approval No |  | ADTPO/RA/48/1/2058 |  |  |  | Dated | 28/08/2015.
C.certificate No |  | K.Masha/L.N.A1(B)/S.R.91/2015 Valid Up to: A to F Wing = G + 1st to 3rd Floor |  |  |  | Dated | 2015-11-04 | Expiry date: One year from date of issue
O. Certificate No.: |  | NA |  |  | Date of approval: | Dated | NA | Expiry date: NA
Commencement date of construction |  |  | 2015-11-04 |  | Expected Completion |  | 2021-12-30
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 3900 |  | Approved no of units residential |  |  | NA
Approved no of Floors |  | G + 1st to 3rd Floor |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: | [8 empty] | As per visit (11/03/2025) Lift work is pending A to E
Construction details: |  | Wing A, B, C & E = G + 1st to 3rd Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% |  | 100% |  | 100% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed | 3
RCC (Including podiums) |  | 4 | 100% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 100% | [5 empty] | Plinth in process | 2.25
Possession |  | 3 | 100% | [5 empty] | Plinth completed | 3
Construction details: |  | Wing D = G + 1st to 3rd Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% |  | 93.33% |  | 96.67% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed | 3
RCC (Including podiums) |  | 4 | 100% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 1 | 33.33% | [5 empty] | Plinth in process | 2.25
Possession |  | 1 | 33.33% | [5 empty] | Plinth completed | 3
Construction details: |  | Wing F = G + 1st to 3rd Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 2 Floor, Painting upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 2 Floor, Painting upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% |  | 83.33% |  | 93.33% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed | 3
RCC (Including podiums) |  | 4 | 100% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 66.67% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 1 | 33.33% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 3
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleble area) | [5 empty] | 4700
Recommended Car Parking | [5 empty] | 100000/-
Distress valuation of the property Per Sq. Ft. | [5 empty] | 3760
Remarks: 1. Wing A to C & E = All work completed. Please provide OC. Few tenants have occupied flats in building. Wing D = Work stopped. Lift work is pending. Few tenants have occupied flats in building. Wing F = Work stopped. Lift installation & finishing work is pending. 2. We have given rate verify by Market Inquire. 3. Car parking is subjected to authentic documentation. 4. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 5. The few flats in the A, B, C, D & E wings are occupied by the tenants. 6. As per RERA, completion period of project Sai Angan is expired on 30/12/2021 but project is still under construction. 7. Since the project has received first CC on 04/11/2015, But construction work of Wing F is not yet completed. 5. On site, we meet Mr.Rajesh (Supervisor) - 9820641822.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sai Angan (Wing A to F)
Google Map :
C
D
Wing A
Wing B
Wing C
Wing D
Wing E
Wing F
Wing F
Wing E
Wing D
Wing C
Wing B
Wing A

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
99Acers | Sai Aangan | 1BHK | 0 | 625 | 4400 | 2750000
99Acers | Sai Aangan | 1RK | 0 | 400 | 4500 | 1800000
nobroker | Channel Paradise | 2BHK | 0 | 1000 | 7500 | 7500000
nobroker | Pamruchi-Takka Chs | 2BHK | 0 | 930 | 7204.3011 | 6700000
housing | Shree Siddhivinayak Complex | 1BHK | 0 | 485 | 3501.0309 | 1698000
housing | Shree Siddhivinayak Complex | 2BHK | 0 | 680 | 3500 | 2380000
Average |  |  | 0 | 0 | 5100.8887
Valuation Adopted |  |  |  |  | 5000

## Note
26/08/2020. | Pratiksha
28/10/2020. | Dhanashree | OLD APF
Rate has not Changed.

## A
Basement | Podium | Ground | Upper Floor
0 | 0 | 0 | 3
Particulars | total floor | 3
plinth | 10 | 10 | 100%
slab | 3 | 3 | 100% |  | Parking |  | Rate
Bricks | 3 | 3 | 100% |  | Palghar |  | 100000/-
plaster | 3 | 3 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 3 | 1 | 33.33% |  | Panvel |  | 300000/-
Wood & painting | 3 | 1 | 33.33% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 3 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 3.3333 | 1.6667 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 1.6667 | 1.6667 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 3.3333 | 1.6667
Wood & painting | 1.6667 | 1.6667
Finishing | 0 | 0
total | 80% | 88.33% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 3
Particulars | total floor | 3
plinth | 10 | 10 | 100%
slab | 4 | 4 | 100% |  | Parking |  | Rate
Bricks | 3 | 3 | 100% |  | Palghar |  | 100000/-
plaster | 3 | 1.5 | 50% |  | Ulwe, karanjade |  | 200000/-
Flooring | 3 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 3 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 3 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 5 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 5 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 5 | 5
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 70% | 80% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## C
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 3
Particulars | total floor | 3
plinth | 10 | 10 | 100%
slab | 4 | 4 | 100% |  | Parking |  | Rate
Bricks | 3 | 3 | 100% |  | Palghar |  | 100000/-
plaster | 3 | 1.5 | 50% |  | Ulwe, karanjade |  | 200000/-
Flooring | 3 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 3 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 3 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 5 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 5 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 5 | 5
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 70% | 80% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## D
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 3
Particulars | total floor | 3
plinth | 10 | 10 | 100%
slab | 4 | 4 | 100% |  | Parking |  | Rate
Bricks | 3 | 3 | 100% |  | Palghar |  | 100000/-
plaster | 3 | 3 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 3 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 3 | 0.7 | 23.33% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 3 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 0 | 1.1667 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 0 | 1.1667 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 0 | 0
Wood & painting | 1.1667 | 1.1667
Finishing | 0 | 0
total | 76.17% | 86.17% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## E
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 3
Particulars | total floor | 3
plinth | 10 | 10 | 100%
slab | 4 | 4 | 100% |  | Parking |  | Rate
Bricks | 3 | 3 | 100% |  | Palghar |  | 100000/-
plaster | 3 | 2 | 66.67% |  | Ulwe, karanjade |  | 200000/-
Flooring | 3 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 3 | 0.5 | 16.67% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 3 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 6.6667 | 0 | 0.83333 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 6.6667 | 0 | 0.83333 | 0
Bricks | 15 | 15
Plaster | 6.6667 | 6.6667
Flooring | 0 | 0
Wood & painting | 0.83333 | 0.83333
Finishing | 0 | 0
total | 72.5% | 82.5% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## F
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 3
Particulars | total floor | 3
plinth | 10 | 10 | 100%
slab | 4 | 1.3 | 32.5% |  | Parking |  | Rate
Bricks | 3 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 3 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 3 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 3 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 3 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 13 | 0 | 0 | 0 | 0 | 0
RCC | 13 | 9.75 |  | Recommended |  | 30 | 9.75 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 23% | 39.75% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0