## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-08
Name of the builder |  |  |  | M/s.Sameer Haribhau Mhatre
Name of the builder company |  |  |  | M/s.Sameer Haribhau Mhatre
Name of the Project |  |  |  | Seth Hari Niwas
Contact Details ( Name & Contact No.) |  |  |  | 7700926600
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  | NA
Name / No of the Building |  |  |  | 01 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | P52000020598
Project location details |  | Seth Hari Niwas, Plot No.127, Sector No.25, near Grampanchayat Targhar, Aamar Marg, Targhar, Kharkopar West, Panvel, Raigad.
Plot No |  | 127, Sector No.25
Road |  | Aamar Marg |  | Locality/Village |  | Targhar
City |  | Kharkopar West |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410206
Nearby Landmark |  | Grampanchayat Targhar |  | Distance from city centre: |  | 2.9 KM from Kharkopar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Krushna Plaza
West | NA | NA |  |  | Road
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 18.961772,73.033972
Location Link |  | https://goo.gl/maps/6gfsQny4mKrJXFkTA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 259.87
Permissible FSI |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  | 1.924e-05
Total FSI availaible for the project |  |  |  | 1.5
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 389.81
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | CIDCO/BP-16380/TPO(NM & K)/2019 /5066 |  |  | Dated | 2019-07-29
Approved Floor plan No. |  | CIDCO/BP-16380/TPO(NM & K)/2019 /5066 |  |  | Dated | 2019-07-29
Commencement Certificate No. |  | CIDCO/BP-16380/TPO(NM & K)/2019 /5066 |  |  | Dated | 2019-07-29
Valid Up to: G + 1st to 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 389.81
Approved no of units |  |  | Flats - 15, Shops - 2
Approved no of Floors |  |  | G + 1st to 4th Floor
Proposed no of Floors |  |  | G + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 30/06/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | G + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 3 Floor, Painting upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 3 Floor, Painting upto 1 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 73.75% |  | 88.75% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 1 | 25% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 6000
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 12000
Development Charges |  |  |  |  | 3,00,000/-
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | 50,000/-
Society Maintenance Charges (One Year) |  |  |  |  | 1,60,000/-
Recommended rate of Parking |  |  |  |  | 2,00,000/-
Distressed valuation of the Property |  |  |  |  | 4800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 2 |  | 345.955 |  | 536.2302
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 15 |  | 4519.2116 |  | 6817.5436
Grand Total |  | 17 |  | 4865.1665 |  | 7353.7737
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Ground Floor For Commercial
1 |  | Shop | 172.9775 | 0 | 268.1151 | Ground Floor For Commercial |  | 12681.1212
2 |  | Shop | 172.9775 | 0 | 268.1151 |  |  | 12681.1212
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
1st Floor For Residential
101 |  | 1RK | 243.6162 | 0 | 353.2435 | 1st Floor For Residential |  | 7360.3612
102 |  | 1BHK | 332.9305 | 14.2623 | 497.0116 |  |  | 7444.4949
103 |  | 1BHK | 332.9305 | 14.2623 | 497.0116
104 |  | 1RK | 243.6162 | 0 | 353.2435
2nd Floor
201 |  | 1RK | 243.6162 | 0 | 353.2435 | 2nd Floor
202 |  | 2.5BHK | 702.6739 | 8.7188 | 1027.596 | 2nd Floor |  | 6033.4994
203 |  | 1RK | 243.6162 | 0 | 353.2435 | 2nd Floor
3rd Floor
301 |  | 1RK | 243.6162 | 0 | 353.2435 | 3rd Floor
302 |  | 1BHK | 354.7276 | 14.2623 | 528.6173
303 |  | 1BHK | 354.7276 | 14.2623 | 528.6173
304 |  | 1RK | 243.6162 | 0 | 353.2435
4th Floor
401 |  | 1RK | 243.6162 | 0 | 353.2435 | 4th Floor
402 |  | 1BHK | 246.1458 | 99.4594 | 456.3707 | 4th Floor
403 |  | 1BHK | 246.1458 | 99.4594 | 456.3707 | 4th Floor
404 |  | 1RK | 243.6162 | 0 | 353.2435 | 4th Floor
Remarks:
1 | Construction work was not active at the time of visit. (Slow Speed). Internal visit not possible due to the building entry gate being locked. We are unable to determine the internal construction stage. | [6 empty] | Construction work is same since visit (dtd. 30/08/2023). but work is in process at the time of visit. (Very Slow Speed)
2 | We considered Saleable area as per our calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Enclose balcony + Chajja Area.
5 | We have considered rate by verifying it from market inquire.
6 | Car parking is subjected to authentic documentation.
7 | On Site, we meet Mr........(........).
7 | The project has received first CC on 29/07/2019, But construction work is not yet completed. | [6 empty] | Please provide revised approved CC.
8 | As per RERA, completion period of project Seth Hari Niwas is expired on 09/10/2024 but still project work is pending.
7 | As per RERA, completion period of project is expired on 30/06/2025 but still project is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mayur Ranvare |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Seth Hari Niwas
Google Map :
Formulas:
Targhar = [Targhar, row above]
Gate Lock

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  | 1BHK | 355 | 514.75 | 8021.3696 | 4129000
Average |  |  |  |  | #DIV/0!
Valuation Adopted