## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 18/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-09
Name of the builder group |  |  |  | Uniquepoonam Homes LLP
Name of the builder company |  |  |  | Uniquepoonam Homes LLP
Name of the Project |  |  |  | Sky City Phase I & II
Contact Details ( Name & Contact No.) |  |  |  | 8446718881/ 8446175757
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Sanjay : 8446718881
Name / No of the Building |  |  |  | Phase 1 = Building No. 2 (Wing F to I) Phase 2 = (Building No.2 Wing A) & (Building No.1 Wing B to E)
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet, Sale Plan
RERA No. |  |  |  | Phase 1 = P99000045278 Phase 2 = P99000051766
Project location details |  | Sky City Phase I & II, Survey No.220 H.No. 6 (Pt), S.No.224 H.No. 2(Old), S.No. 224/B/1, 224/B/2, 224/B/3 (New), near Riddhi Vinayak Multispeciality Hospital, Yashavant Nagar Road, Yashavant Nagar, Nilemore, Virar West, Vasai, Palghar - 401303.
Survey No |  | 220 H.No. 6 (Pt), S.No.224 H.No. 2(Old), S.No. 224/B/1, 224/B/2, 224/B/3 (New)
Locality |  | Yashavant Nagar
Road |  | Yashavant Nagar Road |  | Village |  | Nilemore
City |  | Virar West |  | District |  | Palghar
Taluka |  | Vasai |  | Pin Code |  | 401303
Nearby Landmark |  | Riddhi Vinayak Multispeciality Hospital |  | Distance from city centre: |  | 2.4KM from Virar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | 30.00M Wide D.P Road |  |  | Yashwant Gaurav Road
West | NA | Other Plot |  |  | Open Plot
North | NA | 30.00M Wide D.P Road |  |  | Internal Road/Open Plot
South | NA | PS Area, Hospital Area |  |  | Riddhi Vinayak Multispeciality Hospital
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.437178,72.811791
Location Link |  | https://maps.app.goo.gl/z3aKmD14X8TbDXt7A
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 12125.88
Permissible FSI |  |  |  | 1.1 |  |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 5.0711 |  |  |  |  | 12071.28
Total FSI availaible for the project |  |  |  | 6.1711 |  |  |  |  | 13278.41 | 1.1 | 4.4266
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 74829.56 |  |  |  |  | 66713.64 | 5.5266
Total number of Buildings |  |  |  | 9 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Vasai-virar City Municipal Corporation
Layout Approval No |  | VVCMC/TP/AMEND/VP/6157 & 5894/540/2022-23 |  |  | Dated | 2023-03-14
Approved Floor plan No. |  | VVCMC/TP/AMEND/VP/6157 & 5894/540/2022-23 |  |  | Dated | 2023-03-14
Commencement-CC No Valid Up to: |  | VVCMC/TP/RDPVP-6157 & 5894/540/2022-23 |  |  | Dated | 2023-03-14
Building No. 2 (Wing F to I) = Gr/St (Pt) + 1st to 22nd Floor Building No.2 (Wing A) = Gr/St (Pt) + 1st to 23rd Floor Building No.1 (Wing B to E) = Gr/St (Pt) + 1st to 23rd Floor
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 74829.56
Approved no of units |  |  | Flats -1505, Shops - 40
Approved no of Floors |  |  | Phase I = Building No. 2 (Wing F to I) = Gr + 1st to 22nd Floor Phase II = Builing No. 2 (Wing A) = Gr/St (Pt) + 1st to 23rd Floor Phase II = Building No.1 (Wing B) = Gr/St (Pt) + 1st to 23rd Floor Phase II = Building No.1 (Wing C) = Gr/St (Pt) + 1st to 23rd Floor Phase II = Building No.1 (Wing D) = Gr/St (Pt) + 1st to 23rd Floor Phase II = Building No.1 (Wing E) = Gr/St (Pt) + 1st to 23rd Floor
Proposed no of Floors |  |  | Phase 1 = Building No. 2 (Wing F to I) = Gr + 1st to 22nd Floor
Phase I = Building No.2 (Wing G) = Gr + 1st to 22nd Floor
Phase I = Building No.2 (Wing H) = Gr + 1st to 22nd Floor
Phase I = Building No.2 (Wing I) = Gr + 1st to 22nd Floor
Phase II = Building No.2 (Wing A) = Gr/St + 1st to 23rd Floor
Phase II = Building No.1 (Wing B) = Gr/St (Pt) + 1st to 23rd Floor
Phase II = Building No.1 (Wing C) = Gr/St (Pt) + 1st to 23rd Floor
Phase II = Building No.1 (Wing D) = Gr/St (Pt) + 1st to 23rd Floor
Phase II = Building No.1 (Wing E) = Gr/St (Pt) + 1st to 23rd Floor
Expected Completion |  |  | Phase I & II = As per RERA - 31/12/2028
Projected life of the structure |  |  | 60 Years After Completion |  |  |  |  | All work Completed, Waiting for OC
Quality of construction: |  |  | Good |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Proposed Amenities : |  |  | Grand Entrance Lobby, Branded Elevators, 24X7 Power Backup in Common Areas, Fire Fighting System, Stack Parking Space, CCTV With 24x7 Security, Security Services, Rainwater Harvesting, Common Sewage Treatment Plant, Sky Garden & Landscape Podium Garden |  |  |  |  | Completed |  | SkyCity 4 pager_R3_CC pdf
Violations Observed if any : |  |  | NA |  |  |  |  | Piling Work in process | 5.5
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc |  |  |  |  | Excavation in process | 11 |  | 2025-09-18
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction |  |  | Excavation Completed | 22
Construction details: |  | Phase 1 = Building No. 2 (Wing F & G) = Gr + 1st to 22nd Floor | [5 empty] | Footing in Process | 5.5
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Footing Completed | 11
Stage of construction: |  | All work Completed, Waiting for OC | [5 empty] | Basement 1 | 0
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Basement 2 | 0
Excavation |  | 22 | 100% | 95% |  | 95% |  | Basement 3 | 0
Plinth |  | 22 | 100% |  |  |  |  | Basement 4 | 0
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Plinth in process | 16.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Plinth completed | 22
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | All work Completed, Waiting for OC
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Flooring & Fitting | Flooring & Fitting | 22 | 100% |  |  |  |  | Completed
Painting & Wooden |  | 22 | 100% |  |  |  |  | Piling Work in process | 5.5
Building Common Amenities | Building Common Amenities | 22 | 100% |  |  |  |  | Excavation in process | 11
Possession |  | 0 | 0% |  |  |  |  | Excavation Completed | 22
Construction details: |  | Phase 1 = Building No. 2 (Wing H & I) = Gr + 1st to 22nd Floor | [5 empty] | Footing in Process | 5.5
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Footing Completed | 11
Stage of construction: |  | All work Completed, Waiting for OC | [5 empty] | Basement 1 | 0
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Basement 2 | 0
Excavation |  | 22 | 100% | 95% |  | 95% |  | Basement 3 | 0
Plinth |  | 22 | 100% |  |  |  |  | Basement 4 | 0
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Plinth in process | 16.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Plinth completed | 22
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 20 Floor, External Plaster upto 18 Floor, Flooring upto 10 Floor Completed | , Internal Plaster upto 20 Floor, External Plaster upto 18 Floor, Flooring upto 10 Floor
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork
Flooring & Fitting | Flooring & Fitting | 22 | 100% |  |  |  |  | Completed | Completed
Painting & Wooden |  | 22 | 100% |  |  |  |  | Piling Work in process | 5.5
Building Common Amenities | Building Common Amenities | 22 | 100% |  |  |  |  | Excavation in process | 11
Possession |  | 0 | 0% |  |  |  |  | Excavation Completed | 22
Construction details: |  | Phase I = Building No.2 (Wing H) = Gr + 1st to 22nd Floor | [5 empty] | Footing in Process | 5.5
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Footing Completed | 11
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 20 Floor, External Plaster upto 18 Floor, Flooring upto 10 Floor Completed | [5 empty] | Basement 1 | 0
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Basement 2 | 0
Excavation |  | 22 | 100% | 77.05% |  | 90.91% |  | Basement 3 | 0
Plinth |  | 22 | 100% |  |  |  |  | Basement 4 | 0
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Plinth in process | 16.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Plinth completed | 22
Internal Plaster | Brickwork & Internal Plaster | 20 | 90.91% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 20 Floor, External Plaster upto 18 Floor, Flooring upto 10 Floor Completed | , Internal Plaster upto 20 Floor, External Plaster upto 18 Floor, Flooring upto 10 Floor
Ext. Plaster & Plumbing | External Plaster & Plumbing | 18 | 81.82% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork
Flooring & Fitting | Flooring & Fitting | 10 | 45.45% |  |  |  |  | Completed | Completed
Painting & Wooden |  | 0 | 0% |  |  |  |  | Piling Work in process | 5.5
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Excavation in process | 11
Possession |  | 0 | 0% |  |  |  |  | Excavation Completed | 22
Construction details: |  | Phase I = Building No.2 (Wing I) = Gr + 1st to 22nd Floor | [5 empty] | Footing in Process | 5.5
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Footing Completed | 11
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 20 Floor, External Plaster upto 18 Floor, Flooring upto 10 Floor Completed | [5 empty] | Basement 1 | 0
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Basement 2 | 0
Excavation |  | 22 | 100% | 77.05% |  | 90.91% |  | Basement 3 | 0
Plinth |  | 22 | 100% |  |  |  |  | Basement 4 | 0
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Plinth in process | 16.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Plinth completed | 22
Internal Plaster | Brickwork & Internal Plaster | 20 | 90.91%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 18 | 81.82%
Flooring & Fitting | Flooring & Fitting | 10 | 45.45%
Painting & Wooden |  | 0 | 0%
Building Common Amenities | Building Common Amenities | 0 | 0%
Possession |  | 0 | 0%
Construction details: |  | Phase II = Building No.2 (Wing A) = Gr/St + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 22 Floor, Flooring upto 18 Floor, Painting upto 18 Floor Completed | , External Plaster upto 22 Floor, Flooring upto 18 Floor, Painting upto 18 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 22 Floor, Flooring upto 18 Floor, Painting upto 18 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 86.3% |  | 93.7% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 95.65% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 18 | 78.26% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 18 | 78.26% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Phase II = Building No.1 (Wing B) = Gr/St (Pt) + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 21 Floor, Flooring upto 15 Floor, Painting upto 4 Floor Completed | , External Plaster upto 21 Floor, Flooring upto 15 Floor, Painting upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 21 Floor, Flooring upto 15 Floor, Painting upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 81.52% |  | 92.83% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 21 | 91.3% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 15 | 65.22% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 17.39% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Phase II = Building No.1 (Wing C) = Gr/St (Pt) + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 20 Floor, Flooring upto 10 Floor, Painting upto 5 Floor Completed | , External Plaster upto 20 Floor, Flooring upto 10 Floor, Painting upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 20 Floor, Flooring upto 10 Floor, Painting upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 79.13% |  | 91.52% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20 | 86.96% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 10 | 43.48% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 21.74% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Phase II = Building No.1 (Wing D) = Gr/St (Pt) + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 18 Floor Completed | , External Plaster upto 18 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 18 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 72.83% |  | 88.91% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 18 | 78.26% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Phase II = Building No.1 (Wing E) = Gr/St (Pt) + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 15 Floor, External Plaster upto 15 Floor Completed | , Internal Plaster upto 15 Floor, External Plaster upto 15 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 15 Floor, External Plaster upto 15 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 68.91% |  | 86.52% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 15 | 65.22% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 65.22% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  |  |  | rate 6200 | by trupti | 2024-01-15
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6600 |  |  |  |  | Rate & Charges added by Nikhil 11/09/2023
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 11000 |  |  |  |  | 6200 to 6600 | 2024-03-21 | By trupti
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges |  |  |  |  | 150000 |  |  |  |  | Visitor rate 10000 |  | 6300 to 6600 | 2023-03-24 | nikhil
Club Charges | [8 empty] | online 28 lac to 32 lac
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges |  |  |  |  | 100000 |  |  |  |  | rate sheet
Advance Maintenance Charges |  |  |  |  | 50000 |  |  |  |  | cost sheet | visitor
Recommended rate of Parking |  |  |  |  | 200000 |  |  |  |  | 6300 | 6400
Distressed valuation of the Property |  |  |  |  | 5280
Commercial Area Details :Phase II
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 | Wing B | 8 |  | 1088.5633 |  | 1741.7013
| Wing C | 12 |  | 1504.1614 |  | 2406.6582
| Wing D | 12 |  | 1504.1614 |  | 2406.6582
| Wing E | 8 |  | 1091.2543 |  | 1746.0069
Total |  | 40 |  | 5188.1404 |  | 8301.0246
Residential Area Details : Phase I
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.2 | Wing F | 173 |  | 49347.558 |  | 76488.7149
| Wing G | 173 |  | 49347.558 |  | 76488.7149
| Wing H | 173 |  | 49347.558 |  | 76488.7149
| Wing I | 173 |  | 56049.2244 |  | 86876.2978
Total |  | 692 |  | 204091.8984 |  | 316342.4425
Residential Area Details :Phase II
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 | Wing B | 135 |  | 57091.2872 |  | 88518.1361
| Wing C | 181 |  | 74564.8114 |  | 115628.7394
| Wing D | 181 |  | 74564.8114 |  | 115628.7394
| Wing E | 135 |  | 57362.1095 |  | 88937.9106
Building No.2 | Wing A | 181 |  | 66120.561 |  | 102486.8696 |  | 1505
Total |  | 813 |  | 329703.5804 |  | 511200.3951
Grand Total |  | 1505 |  | 533795.4788 |  | 827542.8376
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Phase 2
Building No.1 | [7 empty] | 10.764
Wing B
Ground Floor For Commercial, Entrance Lobby, Meter Room, Driver Room & Parking
1 |  | Shop | 177.2831 | 0 | 283.6529 | Ground Floor For Commercial, Entrance Lobby, Meter Room, Driver Room & Parking |  | 15.66 | 106.2
2 |  | Shop | 159.1996 | 0 | 254.7193
3 |  | Shop | 122.8172 | 0 | 196.5076
4 |  | Shop | 96.0149 | 0 | 153.6238
5 |  | Shop | 122.8172 | 0 | 196.5076 |  |  | 10.6475
6 |  | Shop | 158.3384 | 0 | 253.3415
7 |  | Shop | 115.9283 | 0 | 185.4852
8 |  | Shop | 136.1646 | 0 | 217.8634 |  |  | 11.885
Wing C
Ground Floor For Commercial, Entrance Lobby, Society Office, Creche, Fitness Center, Meter Room, Driver Room, Fire Panel Room & Parking
9 |  | Shop | 136.1646 | 0 | 217.8634 | Ground Floor For Commercial, Entrance Lobby, Society Office, Creche, Fitness Center, Meter Room, Driver Room, Fire Panel Room & Parking |  | 11.885
10 |  | Shop | 115.9283 | 0 | 185.4852
11 |  | Shop | 158.3384 | 0 | 253.3415
12 |  | Shop | 122.8172 | 0 | 196.5076
13 |  | Shop | 96.0149 | 0 | 153.6238
14 |  | Shop | 122.8172 | 0 | 196.5076
15 |  | Shop | 122.8172 | 0 | 196.5076
16 |  | Shop | 96.0149 | 0 | 153.6238
17 |  | Shop | 122.8172 | 0 | 196.5076
18 |  | Shop | 158.3384 | 0 | 253.3415
19 |  | Shop | 115.9283 | 0 | 185.4852
20 |  | Shop | 136.1646 | 0 | 217.8634
Wing D
Ground Floor For Commercial, Entrance Lobby, Meter Room, Fire Panel Room & Parking
21 |  | Shop | 136.1646 | 0 | 217.8634 | Ground Floor For Commercial, Entrance Lobby, Meter Room, Fire Panel Room & Parking
22 |  | Shop | 115.9283 | 0 | 185.4852
23 |  | Shop | 158.3384 | 0 | 253.3415
24 |  | Shop | 122.8172 | 0 | 196.5076
25 |  | Shop | 96.0149 | 0 | 153.6238 |  |  |  | `
26 |  | Shop | 122.8172 | 0 | 196.5076
27 |  | Shop | 122.8172 | 0 | 196.5076
28 |  | Shop | 96.0149 | 0 | 153.6238 |  |  |  | 2.176
29 |  | Shop | 122.8172 | 0 | 196.5076
30 |  | Shop | 158.3384 | 0 | 253.3415
31 |  | Shop | 115.9283 | 0 | 185.4852
32 |  | Shop | 136.1646 | 0 | 217.8634
Wing E
Ground Floor For Commercial, Entrance Lobby, Meter Room, Driver Room & Parking
33 |  | Shop | 136.1646 | 0 | 217.8634 | Ground Floor For Commercial, Entrance Lobby, Meter Room, Driver Room & Parking
34 |  | Shop | 106.456 | 0 | 170.3295
35 |  | Shop | 158.3384 | 0 | 253.3415
36 |  | Shop | 122.8172 | 0 | 196.5076
37 |  | Shop | 96.0149 | 0 | 153.6238
38 |  | Shop | 122.8172 | 0 | 196.5076
39 |  | Shop | 171.3629 | 0 | 274.1806
40 |  | Shop | 177.2831 | 0 | 283.6529
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
[5 empty] | 55% |  |  | 6330.6986 | 24.788 | 2608574.67 | 101 | 2201 |  |  | 101,...,2201
Phase 1 | [7 empty] | 6446.0489 |  | 2608574.67 | 102 | 2202 |  |  | 102,...,2202
Building No.2 | [9 empty] | 2608574.67 | 103 | 2203 |  |  | 103,...,2203
Wing F | [9 empty] | 2608574.67 | 104 | 2204 |  |  | 104,...,2204
Ground Floor For Parking | [9 empty] | 2608574.67 | 105 | 2205 |  |  | 105,...,2205
1st to 7th & 9th to 12th & 14th to 17th & 19th to 22nd Floor For Residential | [9 empty] | 2608574.67 | 106 | 2206 |  |  | 106,...,2206
1 |  | 1 | 285.246 | 0 | 442.1313 | 1st to 7th & 9th to 12th & 14th to 17th & 19th to 22nd Floor For Residential |  |  |  | 2608574.67 | 107 | 2207 |  |  | 107,...,2207
2 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67 | 108 | 2208 |  |  | 108,...,2208
3 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 0
4 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
5 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
6 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 0
7 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
8 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
8th, 13th & 18th Floor (Part Refuge Area) | [9 empty] | 2608574.67
1 |  | 1 | 285.246 | 0 | 442.1313 | 8th, 13th & 18th Floor (Part Refuge Area) |  |  |  | 2608574.67
2 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
3 |  | Refuge Area | [7 empty] | 0
4 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 0
5 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 0
6 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67 |  |  | 101 | 2201 | 101,...,2201
7 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67 |  |  | 102 | 2202 | 102,...,2202
8 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67 |  |  | 103 | 2203 | 103,...,2203
Wing G | [9 empty] | 2608574.67 |  |  | 104 | 2204 | 104,...,2204
Ground Floor For Parking | [9 empty] | 2608574.67 |  |  | 105 | 2205 | 105,...,2205
1st to 7th & 9th to 12th & 14th to 17th & 19th to 22nd Floor For Residential | [9 empty] | 2608574.67 |  |  | 106 | 2206 | 106,...,2206
1 |  | 1 | 285.246 | 0 | 442.1313 | 1st to 7th & 9th to 12th & 14th to 17th & 19th to 22nd Floor For Residential |  |  |  | 2608574.67 |  |  | 107 | 2207 | 107,...,2207
2 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67 |  |  | 108 | 2208 | 108,...,2208
3 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 0
4 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
5 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
6 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 0
7 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
8 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
8th, 13th & 18th Floor (Part Refuge Area) | [9 empty] | 2608574.67
1 |  | 1 | 285.246 | 0 | 442.1313 | 8th, 13th & 18th Floor (Part Refuge Area) |  |  |  | 2608574.67
2 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
3 |  | Refuge Area | [7 empty] | 0
4 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 0
5 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 0
6 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67 |  |  | 101 | 2201 | 101,...,2201
7 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67 |  |  | 102 | 2202 | 102,...,2202
8 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67 |  |  | 103 | 2203 | 103,...,2203
Wing H | [9 empty] | 2608574.67 |  |  | 104 | 2204 | 104,...,2204
Ground Floor For Parking | [9 empty] | 2608574.67 |  |  | 105 | 2205 | 105,...,2205
1st to 7th & 9th to 12th & 14th to 17th & 19th to 22nd Floor For Residential | [9 empty] | 2608574.67 |  |  | 106 | 2206 | 106,...,2206
1 |  | 1 | 285.246 | 0 | 442.1313 | 1st to 7th & 9th to 12th & 14th to 17th & 19th to 22nd Floor For Residential |  |  |  | 2608574.67 |  |  | 107 | 2207 | 107,...,2207
2 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67 |  |  | 108 | 2208 | 108,...,2208
3 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 0
4 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
5 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
6 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 0
7 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
8 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
8th, 13th & 18th Floor (Part Refuge Area) | [9 empty] | 2608574.67
1 |  | 1 | 285.246 | 0 | 442.1313 | 8th, 13th & 18th Floor (Part Refuge Area) |  |  |  | 2608574.67
2 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67
3 |  | Refuge Area | [7 empty] | 0
4 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 0
5 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 0
6 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 3322241.325 |  |  | 101 | 2201 | 101,...,2201
7 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 3322241.325 |  |  | 102 | 2202 | 102,...,2202
8 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2608574.67 |  |  | 103 | 2203 | 103,...,2203
Wing I | [9 empty] | 2608574.67 |  |  | 104 | 2204 | 104,...,2204
Ground Floor For Parking | [9 empty] | 3322241.325 |  |  | 105 | 2205 | 105,...,2205
1st to 7th & 9th to 12th & 14th to 17th & 19th to 22nd Floor For Residential | [9 empty] | 3322241.325 |  |  | 106 | 2206 | 106,...,2206
1 |  | 1 | 363.285 | 0 | 563.0917 | 1st to 7th & 9th to 12th & 14th to 17th & 19th to 22nd Floor For Residential |  |  |  | 2574121.797 |  |  | 107 | 2207 | 107,...,2207
2 |  | 1 | 363.285 | 0 | 563.0917 |  |  |  | 33.75 | 2574121.797 |  |  | 108 | 2208 | 108,...,2208
3 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 0
4 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 3322241.325
5 |  | 1 | 363.285 | 0 | 563.0917 |  |  |  |  | 3322241.325
6 |  | 1 | 363.285 | 0 | 563.0917 |  |  |  |  | 0
7 |  | 1 | 281.4786 | 0 | 436.2918 |  |  |  |  | 2608574.67
8 |  | 1 | 281.4786 | 0 | 436.2918 |  |  |  |  | 3322241.325
8th, 13th & 18th Floor (Part Refuge Area) | [9 empty] | 3322241.325
1 |  | 1 | 363.285 | 0 | 563.0917 | 8th, 13th & 18th Floor (Part Refuge Area) |  |  |  | 2574121.797
2 |  | 1 | 363.285 | 0 | 563.0917 |  |  |  |  | 2574121.797
3 |  | Refuge Area | [7 empty] | 0
4 |  | 1 | 285.246 | 0 | 442.1313 |  |  |  |  | 2604737.304
5 |  | 1 | 363.285 | 0 | 563.0917
6 |  | 1 | 363.285 | 0 | 563.0917
7 |  | 1 | 281.4786 | 0 | 436.2918
8 |  | 1 | 281.4786 | 0 | 436.2918
Phase 2
Building No.2
Wing A | [7 empty] | 10.764
Ground Floor For Entrance Lobby, Meter Room, Fire Panel Room & Parking
1st to 7th, 9th to 12th & 14th to 17th & 19th to 23rd Floor For Residential
1 |  | 1 | 280.0793 | 0 | 434.1229 | 1st to 7th, 9th to 12th & 14th to 17th & 19th to 23rd Floor For Residential |  | 24.83
2 |  | 1 | 280.0793 | 0 | 434.1229
3 |  | 1 | 368.3441 | 0 | 570.9333 |  |  | 26.0685 | 5.5
4 |  | 1 | 368.3441 | 0 | 570.9333
5 |  | 1 | 368.3441 | 0 | 570.9333
6 |  | 1 | 368.3441 | 0 | 570.9333
7 |  | 2 | 527.0054 | 0 | 816.8584 |  |  | 46.8882
8 |  | 1 | 365.3302 | 0 | 566.2617
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 1 | 280.0793 | 0 | 434.1229 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 1 | 280.0793 | 0 | 434.1229
3 |  | 1 | 368.3441 | 0 | 570.9333
4 |  | 1 | 368.3441 | 0 | 570.9333
5 |  | 1 | 368.3441 | 0 | 570.9333
6 |  | Refuge Area
7 |  | 2 | 503.8628 | 0 | 780.9874 |  |  |  |  | 0
8 |  | 1 | 365.3302 | 0 | 566.2617 |  |  |  |  | 0
0
#REF! |  |  |  | 0 | 0 | 0
#REF! |  |  |  | 0 | 0 | 0
#REF! |  |  |  | 0 | 0 | 0
#REF! |  |  |  | 0 | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Building No.1
Wing B | [7 empty] | 10.764
1st Floor For Residential
1 |  | 1.5BHK | 438.5254 | 0 | 679.7143 | 1st Floor For Residential |  | 35.629
2 |  | 1BHK | 295.0412 | 0 | 457.3139
3 |  | 1BHK | 367.2677 | 26.6409 | 595.9058
4 |  | 1BHK | 367.2677 | 0 | 569.2649 |  |  | 23.9825
5 |  | 2BHK | 544.1202 | 0 | 843.3863 |  |  | 38.6995 | 8.39
6 |  | 1BHK | 373.1879 | 0 | 578.4412
2nd to 7th, 9th to 12th, 14th to 17th & 19th to 23rd Floor
1 |  | 2BHK | 516.4567 | 0 | 800.5079 | 2nd to 7th, 9th to 12th, 14th to 17th & 19th to 23rd Floor |  |  | 8.64
2 |  | 1BHK | 368.3441 | 0 | 570.9333 |  |  | 26.8525
3 |  | 1BHK | 367.3753 | 0 | 569.4317
4 |  | 1BHK | 367.3753 | 0 | 569.4317
5 |  | 2BHK | 544.1202 | 0 | 843.3863
6 |  | 1BHK | 373.1879 | 0 | 578.4412
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2BHK | 516.4567 | 0 | 800.5079 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | Refuge Area
3 |  | 1BHK | 367.3753 | 0 | 569.4317
4 |  | 1BHK | 367.3753 | 0 | 569.4317
5 |  | 2BHK | 544.1202 | 0 | 843.3863
6 |  | 1BHK | 373.1879 | 0 | 578.4412
Wing C
1st Floor For Residential
1 |  | 1BHK | 367.3753 | 0 | 569.4317 | 1st Floor For Residential |  | 26.1325
2 |  | 1BHK | 367.3753 | 26.6409 | 596.0726
3 |  | 1BHK | 295.0412 | 0 | 457.3139
4 |  | 1BHK | 295.0412 | 0 | 457.3139
5 |  | 1BHK | 367.3753 | 26.6409 | 596.0726
6 |  | 1BHK | 367.3753 | 0 | 569.4317
7 |  | 2BHK | 545.089 | 0 | 844.8879
8 |  | 2BHK | 545.089 | 0 | 844.8879
2nd to 7th, 9th to 12th, 14th to 17th & 19th to 23rd Floor
1 |  | 1BHK | 367.3753 | 0 | 569.4317 | 2nd to 7th, 9th to 12th, 14th to 17th & 19th to 23rd Floor
2 |  | 1BHK | 367.3753 | 0 | 569.4317
3 |  | 1BHK | 368.3441 | 0 | 570.9333
4 |  | 1BHK | 368.3441 | 0 | 570.9333
5 |  | 1BHK | 367.3753 | 0 | 569.4317
6 |  | 1BHK | 367.3753 | 0 | 569.4317
7 |  | 2BHK | 545.089 | 0 | 844.8879
8 |  | 2BHK | 545.089 | 0 | 844.8879
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 1BHK | 367.3753 | 0 | 569.4317 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 1BHK | 367.3753 | 0 | 569.4317
3 |  | 1BHK | 368.3441 | 0 | 570.9333
4 |  | Refuge Area
5 |  | 1BHK | 367.3753 | 0 | 569.4317
6 |  | 1BHK | 367.3753 | 0 | 569.4317
7 |  | 2BHK | 545.089 | 0 | 844.8879
8 |  | 2BHK | 545.089 | 0 | 844.8879
Wing D
1st Floor For Residential
1 |  | 1BHK | 367.3753 | 0 | 569.4317 | 1st Floor For Residential
2 |  | 1BHK | 367.3753 | 26.6409 | 596.0726
3 |  | 1BHK | 295.0412 | 0 | 457.3139
4 |  | 1BHK | 295.0412 | 0 | 457.3139
5 |  | 1BHK | 367.3753 | 26.6409 | 596.0726
6 |  | 1BHK | 367.3753 | 0 | 569.4317
7 |  | 2BHK | 545.089 | 0 | 844.8879
8 |  | 2BHK | 545.089 | 0 | 844.8879
2nd to 7th, 9th to 12th, 14th to 17th & 19th to 23rd Floor
1 |  | 1BHK | 367.3753 | 0 | 569.4317 | 2nd to 7th, 9th to 12th, 14th to 17th & 19th to 23rd Floor
2 |  | 1BHK | 367.3753 | 0 | 569.4317
3 |  | 1BHK | 368.3441 | 0 | 570.9333
4 |  | 1BHK | 368.3441 | 0 | 570.9333
5 |  | 1BHK | 367.3753 | 0 | 569.4317
6 |  | 1BHK | 367.3753 | 0 | 569.4317
7 |  | 2BHK | 545.089 | 0 | 844.8879
8 |  | 2BHK | 545.089 | 0 | 844.8879
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 1BHK | 367.3753 | 0 | 569.4317 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 1BHK | 367.3753 | 0 | 569.4317
3 |  | 1BHK | 368.3441 | 0 | 570.9333
4 |  | Refuge Area
5 |  | 1BHK | 367.3753 | 0 | 569.4317
6 |  | 1BHK | 367.3753 | 0 | 569.4317
7 |  | 2BHK | 545.089 | 0 | 844.8879
8 |  | 2BHK | 545.089 | 0 | 844.8879
Wing E
1st Floor For Residential
1 |  | 1BHK | 367.3753 | 0 | 569.4317 | 1st Floor For Residential
2 |  | 1BHK | 367.3753 | 26.6409 | 596.0726
3 |  | 1BHK | 295.0412 | 0 | 457.3139
4 |  | 1.5BHK | 456.6089 | 0 | 707.7438
5 |  | 1BHK | 371.5733 | 0 | 575.9386
6 |  | 2BHK | 544.1202 | 0 | 843.3863
2nd to 7th, 9th to 12th, 14th to 17th & 19th to 23rd Floor
1 |  | 1BHK | 367.3753 | 0 | 569.4317 | 2nd to 7th, 9th to 12th, 14th to 17th & 19th to 23rd Floor
2 |  | 1BHK | 367.3753 | 0 | 569.4317
3 |  | 1BHK | 359.41 | 0 | 557.0854
4 |  | 2BHK | 537.3389 | 0 | 832.8753 |  |  |  | 11
5 |  | 1BHK | 371.5733 | 0 | 575.9386
6 |  | 2BHK | 544.1202 | 0 | 843.3863
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 1BHK | 367.3753 | 0 | 569.4317 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 1BHK | 367.3753 | 0 | 569.4317
3 |  | Refuge Area
4 |  | 2BHK | 537.3389 | 0 | 832.8753
5 |  | 1BHK | 371.5733 | 0 | 575.9386
6 |  | 2BHK | 544.1202 | 0 | 843.3863
Remarks:
* | Wing F, G, H & I = All work completed. Waiting for OC. Wing A to E = Construction work is in process at the time of Visit. Internal photographs was not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated revised approved floor plan wing B to E (on 09/11/2023).
* | Since Project's Builtup Area is above 20000 Sq.M. Please check for Environment Clearance Certificate.
* | As per RERA site Sky City Phase II conisit of Building No.2 (Wing A) & Building No.1 (Wing B to E)
* | Recommended Rates of the Property have been revised on 21/03/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Navnath Bhatkar |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sky City Phase I & II
Layout Plan:
Google Map :
Building No.2
Wing A
Building No.2
Wing F
Building No.2
Wing G
Building No.2
Wing H
Building No.2
Wing I
Building No.1
Wing B
Building No.1
Wing C
Building No.1
Wing D
Building No.1 Wing E
Railway Track
A Wing
A
B
C
D
E
F
G & H
I

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted