## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 19/09/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-09-16
Name of the builder group |  |  |  | M/s. Buidtech Homes
Name of the builder company |  |  |  | M/s. Buidtech Homes
Name of the Project |  |  |  | Sky Annex
Contact Details ( Name & Contact No.) |  |  |  | Mr. Hardik Sejpal 7498066255
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Tripathi 8108755761
Name / No of the Building |  |  |  | Sale Building No.1
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans.
RERA No. |  |  |  | P51800015214
Project location details |  | Proposed slum rehabilitation scheme on plot bearing C.T.S. No.128, of village Maravali, Chembur, Mumbai : 400071, for Uttkarsha CHS
CTS No |  | 128
Locality |  | Maravali
Road |  | Internal Road |  | Locality/Village |  | Maravali
City |  | Chembur West |  | District |  | Mumbai
Taluka |  | Mumbai |  | Pin Code |  | 400071
Nearby Landmark |  | Bharat Petroleum |  | Distance from city centre: |  | 3.7KM from Chembur Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Lok Vihar Hospital
West | NA | NA |  |  | Buildtech Heights
North | NA | NA |  |  | Ghausiya Masjid
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.0350211,72.8945351
Location Link |  | https://goo.gl/maps/4YrgDR8LYZBv8iYi9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 4719.16
Permissible FSI |  |  |  | 4
Permissible TDR/Paid FSI |  |  |  | 0.082082
Total FSI availaible for the project |  |  |  | 4.0821
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 19264
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | SRA
Layout Approval No |  | SRA/ENG/3870/ME/STGL/AP |  |  | Dated | 2021-09-27
Approved Floor plan No. |  | SRA/ENG/3870/ME/STGL/AP |  |  | Dated | 2021-09-27
Commencement-CC No Valid Up to: |  | SRA/ENG/3870/ME/STGL/AP |  |  | Dated | 2021-12-23
This plinth C.C. is re-endorosed as per amended plan dated 27/09/2021
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 19264
Approved no of units |  |  | Flats -288
Approved no of Floors |  |  | Sale Building No.1 = G + 1st to 25th Floor
Proposed no of Floors |  |  | Sale Building No.1 = G + 1st to 35th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Sale Building No.1 = G + 1st to 35th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 3 Slab Completed | , RCC upto 3 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 35 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 3 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8.75
Excavation |  | 35 | 100% | 13.33% |  | 47.5% |  | Excavation in process | 17.5
Plinth |  | 35 | 100% |  |  |  |  | Excavation Completed | 35
RCC (Including podiums) |  | 3 | 8.333% |  |  |  |  | Footing in Process | 8.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 17.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 26.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 35
Construction details: |  | Part II = Sale Building No.1 = G + 1st to 35th Floor | [5 empty] | Excavation Completed, Plinth work is process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 35 | Excavation | , Plinth work is process
Stage of construction: |  | Excavation Completed, Plinth work is process | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8.75
Excavation |  | 35 | 100% | 7.5% |  | 38.75% |  | Excavation in process | 17.5
Plinth |  | 26.25 | 75% |  |  |  |  | Excavation Completed | 35
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 8.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 17.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 26.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 35
Average Progress % |  | 10.42% |  | Average Disbursement % |  | 43.12%
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 14000 |  |  |  | 13800 to 14000 & 3.5L OC | 2023-12-30 | Rushikesh
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges |  |  |  |  | 350000
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 800000
Distressed valuation of the Property |  |  |  |  | 11200
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Sale Building No.1 |  | 288 |  | 127320.79 |  | 203713.2639
Building details Floor Wise
Details of Flats in Building
Basement For Parking
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Sale Building No.1
Ground Floor For Parking
1st Floor For Residential & Amenities
1 |  | 1BHK | 368.7746 | 0 | 590.0394 | 1st Floor For Residential & Amenities
2 |  | 1BHK | 367.0524 | 0 | 587.2838 | 1st Floor For Residential & Amenities
3 |  | 1BHK | 367.2677 | 0 | 587.6283 | 1st Floor For Residential & Amenities |  |  | Sale Building No.1
4 |  | 1BHK | 367.2677 | 0 | 587.6283 | 1st Floor For Residential & Amenities
5 |  | 1BHK | 367.2677 | 0 | 587.6283 | 1st Floor For Residential & Amenities
6 |  | 1BHK | 367.2677 | 0 | 587.6283 | 1st Floor For Residential & Amenities
7 |  | Amenities |  |  |  | 1st Floor For Residential & Amenities
8 | [5 empty] | 1st Floor For Residential & Amenities
9 | [5 empty] | 1st Floor For Residential & Amenities
10 |  | 2BHK | 552.0856 | 0 | 883.3369 | 1st Floor For Residential & Amenities
11 |  | 2BHK | 552.0856 | 0 | 883.3369 | 1st Floor For Residential & Amenities
12 |  | 3BHK | 605.2597 | 0 | 968.4156 | 1st Floor For Residential & Amenities
2nd to 5th & 7th to 12th & 14th to 19th &21st to 25th Floor
1 |  | 1BHK | 368.7746 | 0 | 590.0394 | 2nd to 5th & 7th to 12th & 14th to 19th &21st to 25th Floor
2 |  | 1BHK | 367.0524 | 0 | 587.2838 | 2nd to 5th & 7th to 12th & 14th to 19th &21st to 25th Floor |  | 13792.3087
3 |  | 1BHK | 367.2677 | 0 | 587.6283 | 2nd to 5th & 7th to 12th & 14th to 19th &21st to 25th Floor
4 |  | 1BHK | 367.2677 | 0 | 587.6283 | 2nd to 5th & 7th to 12th & 14th to 19th &21st to 25th Floor
5 |  | 1BHK | 367.2677 | 0 | 587.6283 | 2nd to 5th & 7th to 12th & 14th to 19th &21st to 25th Floor
6 |  | 1BHK | 367.2677 | 0 | 587.6283 | 2nd to 5th & 7th to 12th & 14th to 19th &21st to 25th Floor
7 |  | 1BHK | 365.2225 | 0 | 584.356 | 2nd to 5th & 7th to 12th & 14th to 19th &21st to 25th Floor
8 |  | 1BHK | 368.7746 | 0 | 590.0394 | 2nd to 5th & 7th to 12th & 14th to 19th &21st to 25th Floor
9 |  | 3BHK | 668.9826 | 0 | 1070.3722 | 2nd to 5th & 7th to 12th & 14th to 19th &21st to 25th Floor
10 |  | 2BHK | 552.0856 | 0 | 883.3369 | 2nd to 5th & 7th to 12th & 14th to 19th &21st to 25th Floor
11 |  | 2BHK | 552.0856 | 0 | 883.3369 | 2nd to 5th & 7th to 12th & 14th to 19th &21st to 25th Floor
12 |  | 3BHK | 605.2597 | 0 | 968.4156 | 2nd to 5th & 7th to 12th & 14th to 19th &21st to 25th Floor
6th, 13th & 20th Floor (Part Refuge Area)
1 |  | 1BHK | 368.7746 | 0 | 590.0394 | 6th, 13th & 20th Floor (Part Refuge Area)
2 |  | 1BHK | 367.0524 | 0 | 587.2838 | 6th, 13th & 20th Floor (Part Refuge Area)
3 |  | 1BHK | 367.2677 | 0 | 587.6283 | 6th, 13th & 20th Floor (Part Refuge Area)
4 |  | 1BHK | 367.2677 | 0 | 587.6283 | 6th, 13th & 20th Floor (Part Refuge Area)
5 |  | 1BHK | 367.2677 | 0 | 587.6283 | 6th, 13th & 20th Floor (Part Refuge Area)
6 |  | 1BHK | 367.2677 | 0 | 587.6283 | 6th, 13th & 20th Floor (Part Refuge Area)
7 |  | Refuge Area |  |  |  | 6th, 13th & 20th Floor (Part Refuge Area)
8 | [5 empty] | 6th, 13th & 20th Floor (Part Refuge Area)
9 | [5 empty] | 6th, 13th & 20th Floor (Part Refuge Area)
10 |  | 2BHK | 552.0856 | 0 | 883.3369 | 6th & 13th &20th Floor
11 |  | 2BHK | 552.0856 | 0 | 883.3369 | 6th & 13th &20th Floor
12 |  | 3BHK | 605.2597 | 0 | 968.4156 | 6th & 13th &20th Floor
Remarks:
* | Construction work is in process at the time of visit (Slow Speed).
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Mr. Khan : 8080829777.
* | Reference taken from approved Plan, As per Approved Site layout & Elevation Sale Building No. 1 is Gr. + 35th Floor structure As per Approved Floor plan Sale Building No. 1 is Gr. + 25th Floor structure So please provide an approved floor plan of 26th to 35th floor of Sale building No. 1.
* | Recommended Rates/Other Charges of the Property have been revised on 30/12/2023.
* | Construction work goes beyond approved CC. Provide revised CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Akash Kadam |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sky Annex
Google Map :

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted