## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 08/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Badlapur | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-09-07 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Shree Budhdev Infra | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Shree Budhdev Infra | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Usha Residency | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Brijesh Pandey : 8668630805 & Vivek Pandey : 9226122208
Site Person - Contact Details (Name & Contact No.) |  |  |  | Vivek Pandey : 9821234569
Name / No of the Building |  |  |  | Building No.1, 2 & 3
Name / No of the Existing Building | [16 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51700053334 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Usha Residency, Survey No.18, H.No.10, near The Polymath School, Chinchoti Anjurphata Marg, Anjurphata, Narpoli, Bhiwandi, Bhiwandi, Thane - 421302. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 18, H.No.10 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Anjurphata | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Chinchoti Anjurphata Marg |  | Locality/Village |  | Narpoli | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Bhiwandi |  | District |  | Thane | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Bhiwandi |  | Pin Code |  | 421302 | [13 empty] | Mahad | Daund
Nearby Landmark |  | The Polymath School |  | Distance from city centre: |  | 13.7 KM from Kalwa Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Other Plot |  |  | Open Plot
West | NA | Other Plot |  |  | Open Plot
North | NA | Other Plot |  |  | Open Plot
South | NA | 18.0 M.Wide D.P. Road |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.2807548,73.0341008
Location Link |  | https://maps.app.goo.gl/xTeUgh9fj5RhZJmE8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 9850
Permissible FSI |  |  |  | 2.5
Permissible TDR/Paid FSI |  |  |  | 1.7577
Total FSI availaible for the project |  |  |  | 4.2577
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 41938.59
Total number of Buildings |  |  |  | 03 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority (MHADA) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | EE/BP/PMAY/A/MHADA/755/2023 |  |  | Dated | 2023-09-18 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | EE/BP/PMAY/A/MHADA/755/2023 |  |  | Dated | 2023-09-18 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | EE/BP/PMAY/A/MHADA/431/2024 |  |  | Dated | 2024-06-24 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | This Further CC is Granted under sanction 45 of MRTP Act 1966 for the building no.1 & 3 of Stilt + 14th having height 43.80 m, Bldg No.2 Gr + 14th Floor having 44.55 m. Comprising total 997 EWS T/s. & 23 Conv. Shops as per approved plans issued by this office vide letter No. EE/BP/PMAY/A/MHADA/755/2021 plans dtd 18/09/2023. | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  |  |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | SIA/MH/INFRA2/442881/2023 |  |  | Dated | 2024-02-02 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
|  | Plot Area = 9850 Sqm Proposed Builtup Area = 45551.01 Sqm | [15 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | Plot Area = 9850 Sqm Proposed Builtup Area = 45551.01 Sqm |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
[5 empty] | Valid Upto Date | [12 empty] | Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 41938.59
Approved no of units |  |  | Sale Flats - 936, B.N.C.M.C Flats - 61, Shops - 23
Approved no of Floors |  |  | Building No.1 to 3 = Gr/Stilt + 1st to 14th Floor
Proposed no of Floors |  |  | Building No.1 = Gr/Stilt + 1st to 14th Floor
Building No.2 = Gr/Stilt + 1st to 14th Floor
Building No.3 = Gr/Stilt + 1st to 14th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 24x7 CCTV Security, Branded Elevator, Ample Car Parking Space, Gym, Cricket Practice Pitch, Landscape Garden, Power Backup Common, Jogging Track, Yoga Deck, Temple, Senior Citizen Area, Seating Lounch, Common Toilet Area, Indoor Games, Fitness & Recreation Area, Children Play Zone, ATM, Solar Energy connection, Gated Community
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Part 1 Building No.1 = Gr/Stilt + 1st to 14th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 8 Floor, External Plaster upto 8 Floor Completed | , Internal Plaster upto 8 Floor, External Plaster upto 8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 8 Floor, External Plaster upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 67.5% |  | 85.71% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 8 | 57.14% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8 | 57.14% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Part 2 Building No.1 = Gr/Stilt + 1st to 14th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed, Brickwork upto 13 Floor Completed | , Brickwork upto 13 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed, Brickwork upto 13 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 56.96% |  | 79.64% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 13 | 92.86% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Building No. 1 Average Progress % |  | 62.23% |  | Building No. 1 Average Disburstment % |  | 82.68%
Construction details: |  | Building No.2 = Gr/Stilt + 1st to 14th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 13 Floor, External Plaster upto 12 Floor, Flooring upto 5 Floor Completed | , Internal Plaster upto 13 Floor, External Plaster upto 12 Floor, Flooring upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 13 Floor, External Plaster upto 12 Floor, Flooring upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 76.61% |  | 90.71% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 13 | 92.86% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 85.71% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 35.71% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Building No.3 = Gr/Stilt + 1st to 14th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed, Brickwork upto 13 Floor, Internal Plaster upto 10 Floor Completed | , Brickwork upto 13 Floor, Internal Plaster upto 10 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed, Brickwork upto 13 Floor, Internal Plaster upto 10 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 62.32% |  | 83.21% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 13 | 92.86% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 10 | 71.43% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Part 2 Building No.3 = Gr/Stilt + 1st to 14th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 5 Slab Completed | , RCC upto 5 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 5 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 23.33% |  | 55% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 5 | 33.33% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Building No. 3 Average Progress % |  | 42.83% |  | Building No. 3 Average Disbursement % |  | 69.11%
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  |  | Online | Visitor | MIS |  |  |  |  | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3500 |  |  | 3455.7573 | 3084.495 | 3282.7769 | 4000 | [5 empty] | 800000 | 100000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 5000 | [11 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 100000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 2800 | [12 empty] | 1000000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 23 |  | 4572.2243 |  | 7086.9476
Total |  | 23 |  | 4572.2243 |  | 7086.9476
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 |  | 360 |  | 131766.8602 |  | 199547.1223
Building No.2 |  | 360 |  | 129429.5652 |  | 196685.1586
Building No.3 | B.N.C.M.C Flats | 61 |  | 21961.5739 |  | 32942.3609
| Sale | 216 |  | 77899.9291 |  | 116849.8937
Total |  | 997 |  | 361057.9284 |  | 546024.5355
Grand Total |  | 1020 |  | 365630.1527 |  | 553111.4831
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
55%
Building No.2 | [8 empty] | 10.764
Ground Floor for Commercial, Electric Meter Room, Society Office & Parking
1 |  | Shop | 256.5061 | 0 | 256.5061 | 0 | 397.5845 | 23.615
2 |  | Shop | 235.301 | 0 | 235.301 | 0 | 364.7166
3 |  | Shop | 231.1031 | 0 | 231.1031 | 0 | 358.2098
4 |  | Shop | 66.1986 | 0 | 66.1986 | 0 | 102.6078
5 |  | Shop | 256.5061 | 0 | 256.5061 | 0 | 397.5845
6 |  | Shop | 235.301 | 0 | 235.301 | 0 | 364.7166
7 |  | Shop | 231.1031 | 0 | 231.1031 | 0 | 358.2098
8 |  | Shop | 126.1541 | 0 | 126.1541 | 0 | 195.5388
9 |  | Shop | 126.1541 | 0 | 126.1541 | 0 | 195.5388
10 |  | Shop | 231.1031 | 0 | 231.1031 | 0 | 358.2098
11 |  | Shop | 235.301 | 0 | 235.301 | 0 | 364.7166
12 |  | Shop | 231.1031 | 0 | 231.1031 | 0 | 358.2098
13 |  | Shop | 66.1986 | 0 | 66.1986 | 0 | 102.6078
14 |  | Shop | 256.5061 | 0 | 256.5061 | 0 | 397.5845
15 |  | Shop | 235.301 | 0 | 235.301 | 0 | 364.7166
16 |  | Shop | 231.1031 | 0 | 231.1031 | 0 | 358.2098
17 |  | Shop | 66.1986 | 0 | 66.1986 | 0 | 102.6078
18 |  | Shop | 256.5061 | 0 | 256.5061 | 0 | 397.5845
19 |  | Shop | 231.1031 | 0 | 231.1031 | 0 | 358.2098
20 |  | Shop | 231.1031 | 0 | 231.1031 | 0 | 358.2098
21 |  | Shop | 151.1266 | 0 | 151.1266 | 0 | 234.2462
22 |  | Shop | 167.2726 | 0 | 167.2726 | 0 | 259.2725
23 |  | Shop | 217.971 | 0 | 217.971 | 0 | 337.855
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | AP Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Building No.1
Ground Floor for Parking
1st Floor for Residential
1 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409 | 29.0275
2 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
3 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
4 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 198.3267 | 618.338
5 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
6 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
7 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
8 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 66.6022 | 585.7769
9 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 57.8296 | 577.0042
10 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
11 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
12 |  | 1BHK | 322.7047 | 46.6619 | 369.3667 | 28.5246 | 582.5746
13 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
14 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 66.6022 | 585.7769
15 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 57.8296 | 577.0042
16 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
17 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
18 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
19 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
20 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 198.3267 | 618.338
21 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
22 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
23 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
24 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
25 |  | 1BHK | 322.7047 | 46.6619 | 369.3667 | 28.5246 | 582.5746
26 |  | 1BHK | 322.7047 | 23.4117 | 346.1164 | 77.3662 | 596.5409
2nd to 7th, 9th to 12th & 14th Floor
1 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437 |  | 3084.495 | 3265.9358
2 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
3 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
4 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
5 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
6 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
7 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
8 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
9 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
10 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
11 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
12 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
13 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
14 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
15 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
16 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
17 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
18 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
19 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
20 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
21 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
22 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
23 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
24 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
25 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
26 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
8th & 13th Floor (Part Refuge Area)
1 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
2 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
3 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
4 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
5 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
6 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
7 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
8 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
9 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
10 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
11 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
12 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
13 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
14 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
15 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
16 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
17 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
18 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
19 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
20 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
21 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
22 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
23 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
24 |  | 1BHK | 322.7047 | 44.7244 | 367.4291 | 0 | 551.1437
25 |  | Refuge Area
26
Building No.2
1st Floor for Residential | [8 empty] | 10.764
1 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
2 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
3 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
4 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 206.8033 | 585.6872
5 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 206.8033 | 585.6872
6 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
7 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
8 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
9 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
10 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
11 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
12 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 70.6388 | 587.3915
13 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 81.4027 | 598.1555
14 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
15 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
16 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
17 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 100.2398 | 641.2115
18 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
19 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
20 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
21 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
22 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
23 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
24 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 583.4626 | 662.6184
25 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
26 |  | 1BHK | 322.7047 | 21.7971 | 344.5018 | 100.2398 | 616.9925
2nd to 7th, 9th to 12th & 14th Floor
1 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717 |  |  | 3299.6179
2 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
3 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
4 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
5 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
6 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
7 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
8 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
9 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
10 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
11 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
12 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
13 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
14 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
15 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
16 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
17 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
18 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
19 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
20 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
21 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
22 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
23 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
24 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
25 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
26 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
8th & 13th Floor (Part Refuge Area)
1 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
2 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
3 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
4 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
5 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
6 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
7 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
8 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
9 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
10 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
11 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
12 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
13 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
14 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
15 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
16 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
17 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
18 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
19 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
20 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
21 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
22 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
23 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
24 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
25 |  | Refuge Area
26
Building No.3
Ground Floor for Residential & Parking
1 | B.N.C.M.C | 1BHK | 322.7047 | 0 | 322.7047 | 0 | 484.0571
1st to 3rd Floor for Residential (Total EWS to be handed over to B.N.C.M.C)
1 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
2 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
3 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
4 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
5 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
6 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
7 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
8 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
9 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
10 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
11 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
12 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
13 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
14 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
15 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
16 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
17 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
18 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
19 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
20 | B.N.C.M.C | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
4th Floor
1 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
2 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
3 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
4 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
5 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
6 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
7 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
8 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
9 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
10 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
11 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
12 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
13 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
14 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
15 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
16 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
17 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
18 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
19 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
20 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
5th to 7th, 9th to 12th & 14th Floor
1 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
2 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
3 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
4 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
5 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
6 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
7 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
8 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
9 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
10 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
11 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
12 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
13 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
14 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
15 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
16 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
17 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
18 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
19 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
20 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
8th & 13th Floor (Part Refuge Area)
1 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
2 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
3 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
4 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
5 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
6 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
7 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
8 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
9 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
10 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
11 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
12 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
13 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
14 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
15 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
16 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
17 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
18 |  | 1BHK | 322.7047 | 37.9431 | 360.6478 | 0 | 540.9717
19 |  | Refuge Area
20
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + A.P. Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation. | [6 empty] | EC Updated on 27/04/2024
* | We have updated revised C.C (on 26/06/2024).
* | Please check for Environment Clearance Certificate.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Mangesh Bapardekar |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Usha Residency
Layout :
Google Map :
Formulas:
Narpoli = [Narpoli, row above]
Bldg No.1
Bldg No.2
Bldg No.3
Bldg No.3
Bldg No.1
Bldg No.2
Part 1 Bldg 1
Part 2 Bldg 1
Bldg 2
Bldg 3
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F153: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H204: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14
15
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate