## Table 1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  | 10/09/2025
CPC Name: |  |  | Axis Sanpada
Date Of Property Visit |  |  | 2025-09-08
Name of the builder group |  |  | M/s.Samarth Erectors And Developers
Name of the builder company |  |  | M/s.Samarth Erectors And Developers
Name of the Project |  |  | Samarth Tanish
Contect Details ( Name & Contact No.) |  |  | 9324653017
Site Meet Person Contect Details ( Name & Contact No.) |  |  | NA
Name / no of the Building |  |  | Samarth Tanish/1 Building (A & B Wings)
Docouments Provided |  |  | Approved Plans, CC & Cost Sheet.
RERA No. |  |  | P51800003379
Project location details |  | Samarth Tanish, CTS No - 313,314,318,319,320,321,322, 323,324,325,326,327, Village- Pahadi Goregaon (E), Mumbai.
CTS No. | 313, 314, 318, 319, 320, 321, 322, 323, 324, 325, 326, 327 |  |  |  | Locality | Gorgaon East
Road | JP Road No. 5 |  | District | Mumbai
City | Borivali |  | Pin Code | 400063
Near by Landmark |  | Hanuman Temple, Pahadi, Goregaon East | Distance from city centre: |  | About 0.75 Km from Goregaon Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  | Yes
Class of locality |  |  | Upper Class
Nature of land with topographical condtion |  |  | Plane
Nature of the locality |  |  | Developed
Quality of infrastructure in vicinity |  |  | Good
Boundaries |  | East | West | South |  | North
As per deed |  | NA | NA | NA |  | NA
At site |  | Aarey Colony | Marathi Mandir | Road |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.165578,72.854746
Location Link |  | https://goo.gl/maps/64XBp7RDjG3UwdXRA
Approval details:
Approved usage of the Property: Residential (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  | Slum |  | Vacant Plot
|  |  | 1152.5 |  | 374.9
Permissible FSI |  |  | 4 |  | 1
Permissible TDR/Paid FSI |  |  | 0 |  | 0
Total FSI availaible for the project |  |  | 4 |  | 1
Total Approved Builtup area of the project in Sq. Mt. |  |  | 4610 |  | 374.9
Total number of Buildings |  |  | 02 Wings
Approval Detail : Plan approval
Layout Approval No |  | SRA/ENG/3035/PS/PL/AP |  | Dated | 2021-02-02
Building plan approval No |  | SRA/ENG/3035/PS/PL/AP |  | Dated | 2021-02-02
Date of Commencement of Construction |  | SRA/ENG/3035/PS/PL/AP |  | Dated | 07/11/2019. | Expiry date: One year from date of issue
Valid Up to: A Wing = Gr.(pt) + Stilt(pt) + 1st to 23rd Floor. B Wing = Gr.(pt) + Stilt(pt) + 1st to 21st Floor.
Date of Commencement of Construction |  | SRA/ENG/3035/PS/PL/AP |  | Dated | 2021-11-24 | Expiry date: One year from date of issue
Valid Up to: This C.C is re-endorse for Rehab Wing A and Sale Wing B as per approved amended plans dated 02/02/2021 & further extended upto 22nd upper floor for RCC frame structure only for sale wing B. Plinth CC is granted for rehab wing A-1 for the portion marked A-B-C-D-E-F-G-H-I-J-A on plan at at page no 1001 as per approved amended plans dated 02/02/2021.
O. Certificate No.: NA |  |  | Date of approval: NA
Commencement date of construction |  | 07/11/2019. | Expected Completion |  | 2025-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  | 4610 | No of units | A Wing: Rehab Flats = 74 & Sale Flats = 47 B Wing: Sale Flats = 64
Approved no of Floors |  | A & B Wing = Gr. + 1st to 23rd Floor
Proposed no of Floors |  | Gr. + 1st to 23rd Floor
Quality of construction: Good |  |  | Projected life : 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Rehab A Wing = Gr. + 1st to 23rd Floor |  |  |  |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 21 Floor, Painting upto 21 Floor, Finishing upto 4 Floor Completed
Ground |  | 1 | Podium | 0 | Floors | 23
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 21 Floor, Painting upto 21 Floor, Finishing upto 4 Floor Completed |  |  |  |  | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 89.57% |  | 94.57% | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 21 | 91.3% |  |  |  | Basement 3 | 0
Painting & Wooden |  | 21 | 91.3% |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 17.39% |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  | Plinth completed | 23
Construction details: |  | Sale B Wing = Gr. + 1st to 23rd Floor |  |  |  |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 17 Floor, Painting upto 10 Floor Completed
Ground |  | 1 | Podium | 0 | Floors | 23
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 17 Floor, Painting upto 10 Floor Completed |  |  |  |  | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 84.57% |  | 93.7% | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 17 | 73.91% |  |  |  | Basement 3 | 0
Painting & Wooden |  | 10 | 43.48% |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  | Plinth completed | 23
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 16500 |  | 15000 to 16500 by viraj 23/12/2023.
Gym facility Charges |  |  |  |  | 25000/-
Electric Substation Charges |  |  |  |  | 30000/-
Water Meter Charges |  |  |  |  | 30000/-
Maintenance charges |  |  |  |  | 18000/-
Society formation charges |  |  |  |  | 2,75,000/-
Recommended rate of Parking |  |  |  |  | 12,00,000/-
Development charges |  |  |  |  | 45000/-
Distressed valuation of the Property |  |  |  |  | 15520
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Carpet area | Attached Terrace area | Saleable area | Floor
A & B Wing
Ground floor for parking
1st Floor for Amenities
A Wing
2nd Floor for Amenities
3rd & 5th Floor
1 | Rehab | 1BHK | 301.0691 | 0 | 452 | 3rd & 5th Floor | 1.5013
2 | Rehab | 1BHK | 299.9927 | 0 | 450 |  | 1.5
3 | Sale | 1BHK | 299.9927 | 0 | 450 |  | 1.5 |  | 45000
4 | Sale | 1BHK | 299.9927 | 0 | 450 |  | 1.5 |  | 45000
5 | Sale | 1BHK | 300.208 | 0 | 450
6 | Rehab | 1BHK | 300.3156 | 0 | 450
4th, 6th, 7th, 9th & 10th Floor
1 | Rehab | 1BHK | 301.0691 | 0 | 452 | 4th, 6th, 7th, 9th & 10th Floor | 1.5013
2 | Rehab | 1BHK | 299.9927 | 0 | 450 |  | 1.5
3 | Sale | 1BHK | 299.9927 | 0 | 450 |  | 1.5
4 | Sale | 1BHK | 299.9927 | 0 | 450 |  | 1.5 |  | 45000
5 | Rehab | 1BHK | 300.208 | 0 | 450 |  | 1.499 |  | 45000
6 | Rehab | 1BHK | 300.3156 | 0 | 450
8th Floor (Part Refuge Area)
1 | Rehab | 1BHK | 301.0691 | 0 | 452 | 8th Floor (Part Refuge Area)
2 | Rehab | 1BHK | 299.9927 | 0 | 450
3 | Sale | 1BHK | 299.9927 | 0 | 450
4 | Rehab | 1BHK | 299.9927 | 0 | 450
5 | Refuge Area
6 | Refuge Area
11th & 12th Floor
1 | Rehab | 1BHK | 301.0691 | 0 | 452 | 11th & 12th Floor | 1.5013
2 | Rehab | 1BHK | 299.9927 | 0 | 450 |  | 1.5
3 | Sale | 1BHK | 299.9927 | 0 | 450 |  | 1.5 |  | 45000
4 | Sale | 1BHK | 299.9927 | 0 | 450 |  | 1.5 |  | 45000
5 | Rehab | 1BHK | 300.208 | 0 | 450 |  | 1.499
6 | Rehab | 1BHK | 300.3156 | 0 | 450
13th, 14th & 17th Floor
1 | Rehab | 1BHK | 301.0691 | 0 | 452 | 13th, 14th & 17th Floor
2 | Rehab | 1BHK | 299.9927 | 0 | 450
3 | Sale | 1BHK | 299.9927 | 0 | 450
4 | Sale | 1BHK | 299.9927 | 0 | 450 |  |  |  | 18000
5 | Rehab | 1BHK | 300.208 | 0 | 450 |  |  |  | 0
6 | Rehab | 1BHK | 300.3156 | 0 | 450 |  |  |  | 0
15th Floor (Part Refuge Area)
1 | Rehab | 1BHK | 301.0691 | 0 | 452 | 15th Floor (Part Refuge Area)
2 | Rehab | 1BHK | 299.9927 | 0 | 450
3 | Sale | 1BHK | 299.9927 | 0 | 450
4 | Rehab | 1BHK | 299.9927 | 0 | 450
5 | Refuge Area
6 | Refuge Area
16th Floor
1 | Rehab | 1BHK | 301.0691 | 0 | 452 | 16th Floor | 1.5013
2 | Rehab | 1BHK | 299.9927 | 0 | 450 |  | 1.5
3 | Sale | 1BHK | 299.9927 | 0 | 450 |  | 1.5 |  | 274500
4 | Sale | 1BHK | 299.9927 | 0 | 450 |  | 1.5 |  | 274500
5 | Rehab | 1BHK | 300.208 | 0 | 450 |  | 1.499
6 | Rehab | 1BHK | 300.3156 | 0 | 450
18th Floor
1 | Rehab | 1BHK | 301.0691 | 0 | 452 | 18th Floor | 1.5013
2 | Rehab | 1BHK | 299.9927 | 0 | 450 |  | 1.5
3 | Sale | 1BHK | 299.9927 | 0 | 450 |  | 1.5
4 | Sale | 1BHK | 299.9927 | 0 | 450 |  | 1.5
5 | Rehab | 1BHK | 300.208 | 0 | 450 |  | 1.499
6 | Rehab | 1BHK | 300.3156 | 0 | 450
19th to 21st & 23rd Floor
1 | Rehab | 1BHK | 301.0691 | 0 | 452 | 19th to 21st & 23rd Floor
2 | Rehab | 1BHK | 299.9927 | 0 | 450
3 | Sale | 1BHK | 299.9927 | 0 | 450
4 | Sale | 1BHK | 299.9927 | 0 | 450
5 | Sale | 1BHK | 300.208 | 0 | 450
6 | Rehab | 1BHK | 300.3156 | 0 | 450
22nd Floor (Part Refuge Area)
1 | Rehab | 1BHK | 301.0691 | 0 | 452 | 22nd Floor (Part Refuge Area) | 121
2 | Rehab | 1BHK | 299.9927 | 0 | 450
3 | Sale | 1BHK | 299.9927 | 0 | 450
4 | Sale | 1BHK | 299.9927 | 0 | 450
5 | Sale | 1BHK | 300.208 | 0 | 450
6 | Refuge Area
B Wing
2nd Floor
1 | Sale | 1BHK | 421.9757 | 0 | 633 | 2nd Floor | 16137.4408
2 | Sale | 1BHK | 402.8319 | 0 | 604
4 | Sale | 1BHK | 384.1672 | 0 | 576
3rd & 5th Floor
1 | Sale | 1BHK | 421.9757 | 0 | 633 | 3rd & 5th Floor
2 | Sale | 1BHK | 402.8319 | 0 | 604
4 | Sale | 1BHK | 384.1672 | 0 | 576
4th, 6th, 7th, 9th & 10th Floor
1 | Sale | 1BHK | 421.9757 | 0 | 633 | 4th, 6th, 7th, 9th & 10th Floor
2 | Sale | 1BHK | 402.8319 | 0 | 604
4 | Sale | 1BHK | 384.1672 | 0 | 576
8th Floor (Part Refuge Area)
1 | Sale | 1BHK | 421.9757 | 0 | 633 | 8th Floor (Part Refuge Area)
2 | Sale | 1BHK | 402.8319 | 0 | 604
4 | - | Refuge Area
11th & 12th Floor
1 | Sale | 1BHK | 421.9757 | 0 | 633 | 11th & 12th Floor
2 | Sale | 1BHK | 402.8319 | 0 | 604
4 | Sale | 1BHK | 384.1672 | 0 | 576
13th, 14th & 17th Floor
1 | Sale | 1BHK | 422 | 0 | 633 | 13th, 14th & 17th Floor | 1.5
2 | Sale | 1BHK | 403 | 0 | 604 |  | 1.4988
4 | Sale | 1BHK | 384 | 0 | 576 |  | 1.5
15th Floor
1 | Sale | 1BHK | 422 | 0 | 633 | 15th Floor | 1.5
2 | Sale | 1BHK | 403 | 0 | 604 |  | 1.4988
4 | Sale | 1BHK | 384 | 0 | 576 |  | 1.5
16th Floor (Part Refuge Area) | [6 empty] | #DIV/0!
1 | Sale | 1BHK | 422 | 0 | 633 | 16th Floor (Part Refuge Area)
2 | Sale | 1BHK | 403 | 0 | 604
4 | - | Refuge Area
18th Floor
1 | Sale | 1BHK | 422 | 0 | 633 | 18th Floor | 1.5
2 | Sale | 1BHK | 403 | 0 | 604 |  | 1.4988
4 | Sale | 1BHK | 384 | 0 | 576 |  | 1.5
19th to 21st & 23rd Floor
1 | Sale | 1BHK | 422 | 0 | 633 | 19th to 21st & 23rd Floor
2 | Sale | 1BHK | 403 | 0 | 604
4 | Sale | 1BHK | 384 | 0 | 576
22nd Floor | [8 empty] | 64
1 | Sale | 1BHK | 422 | 0 | 633 | 22nd Floor | 1.5
2 | Sale | 1BHK | 403 | 0 | 604 |  | 1.4988
4 | Sale | 1BHK | 384 | 0 | 576 |  | 1.5
Remarks: 1. Sale B Wing = Construction work is in process at the time of Visit. Internal photographs was not allowed. Rehab A Wing = Construction work is in process at the time of visit. Internal photos was not allowed. 2. We considered Saleable area as per our Calculation. 3. We considered Carpet area as per Approved Plan. 4. We have considered rate by verifying it from market inquire. 5. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 6. We have considered Other charges from cost sheet. 7. Car parking is subjected to authentic documentation. 8. We update revised approved plans (on 15/05/2021) 9. Construction percentage are given by considering revised approved no. of floors. 10.Please provide latest approved CC. 11. Recommended Rates/Other Charges of the Property have been revised on 23/12/2023. 12. We have updated CC from MCGM site on 10/09/2025. 12. As per RERA, completion period of project Samarth Tanish is expired on 29/12/2024 but still project is under construction. 10. On site, we meet Mr. Akshay Rane (7401028028)
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  | Samarth Tanish
Google Map :
Formulas:
Locality = [Locality, row above]
Rehab A Wing
Rehab A Wing
Sale B Wing

## NOTE
16/03/2021. | Dhanashree | 1. Rate has changed from 19400/- to 16000/- as per market inquiry.
2.Index II has been matched, According to that rate is 14500/-(on16/03/2021)
15/05/2021. | Sachin | 1. Rate has changed from 16000/- to 15000/- as per market inquiry.
2.Index II has been matched, According to that rate is 14500/-(on15/05/2021)

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
99 Acres | Samarth Tanish | 1BHK | 406 | 604 | 13576.1589 | 8200000 | 609 | 13464.6962
Magic Brick | Samarth Tanish | 1BHK | 317 | 458 | 15720.524 | 7200000 | 475.5 | 15141.9558
Magic Brick | Samarth Tanish | 1BHK | 317 | 458 | 14192.1397 | 6500000 | 475.5 | 13669.8212
Magic Brick | Samarth Tanish | 1BHK | 406 | 604 | 14072.8477 | 8500000 | 609 | 13957.3071
Average |  |  |  |  | 14390.4176
Valuation Adopted |  |  |  |  | 14400

## A %
Particulars | totaL floor | 23
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 83.3333 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 24 | 20 | 56.5217 | Progress |  |  | 10 | 33.3333 | 8.4783 | 2.1739 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 21.7391 | Recommended |  |  | 30 | 25 | 8.4783 | 2.1739 | 0 | 0 | 0
| 23 | 13 | 0
plaster | Total Floor | completed Floor | 0
| 23 | 5 | 0
Flooring | Total Floor | completed Floor
| 23 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 23 | 0 |  | RCC | 33.3333 | 25
Finishing | Total Floor | completed Floor |  | Bricks | 8.4783 | 8.4783
| 23 | 0 |  | Plaster | 2.1739 | 2.1739
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 53.9855 | 65.6522

## B %
Particulars | totaL floor | 23
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 83.3333 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 24 | 20 | 56.5217 | Progress |  |  | 10 | 33.3333 | 8.4783 | 5.2174 | 0.86957 | 0 | 0
Bricks | Total Floor | completed Floor | 52.1739 | Recommended |  |  | 30 | 25 | 8.4783 | 5.2174 | 0.43478 | 0 | 0
| 23 | 13 | 8.6957
plaster | Total Floor | completed Floor | 0
| 23 | 12 | 0
Flooring | Total Floor | completed Floor
| 23 | 2 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 23 | 0 |  | RCC | 33.3333 | 25
Finishing | Total Floor | completed Floor |  | Bricks | 8.4783 | 8.4783
| 23 | 0 |  | Plaster | 5.2174 | 5.2174
|  |  |  | Flooring | 0.86957 | 0.43478
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 57.8986 | 69.1304