## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 11/09/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-09-08
Name of the builder group |  |  |  |  | Avani Group
Name of the builder company |  |  |  |  | M/s. Dharati Developers
Name of the Project |  |  |  |  | Avani Residency
Contact Details ( Name & Contact No.) |  |  |  |  | 9920977460/9960704607/7875888891
Docouments Provided |  |  |  |  | 1. Layout Plan 2. Building Plan 3. CC
RERA No. |  |  |  |  | P99000006263
Approved Layout Plan : |  | MHSL/Unit.1/M.1/NAP/SR/67/16 |  |  |  |  | Dated | 21/12/2016.
Project location details |  | Avani Residency, Gut No.101/1 & 142/1, Village-Wrangde, Taluka-Wada, Tal-Palghar, Palghar.
Gut No |  | 101/1 & 142/1 |  |  | Locality |  | Wrangde
Road |  | Boisar Road |  |  | District |  | Palghar.
City |  | Palghar |  |  | Pin Code |  | 401 501.
Near by Landmark |  | D-Mart |  |  | Distance from city centre: |  | About 6.7 Km from Boisar Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 2 to 3 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open |  | Open |  | Internal Road |  | School
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.78637037,72.80323175
Location Link |  | https://goo.gl/maps/NqeSx3ZBvtDMyx7v7
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 14170
Permissible FSI |  |  |  |  | 0.75
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.75
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 10627.5
Total number of Buildings |  |  |  |  | 02 Wings
Approval Detail : Plan approval
Layout Approval No |  | MHSL/Unit.1/M.1/NAP/SR/67/16 |  |  |  | Dated | 21/12/2016.
Building plan approval No |  | MHSL/Unit.1/M.1/NAP/SR/67/16 |  |  |  | Dated | 21/12/2016.
C.certificate No |  | MHSL/Unit.1/M.1/NAP/SR/67/16 Valid Up to: Stilt + 1st to 2nd Floor |  |  |  | Dated | 21/12/2016.
O. Certificate No.: |  |  |  |  | Date of approval: |  |  | Expiry date: NA
Commencement date of construction |  |  | 21/12/2016. |  | Expected Completion |  | As Per RERA = 31/12/2026
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 10627.5 |  | Approved no of units residential |  |  | 27
Approved no of Floors |  | Gr.+1st to 2nd Floor |  |  | No of floors at site : See Construction details
Proposed no of Floors |  |  | Gr.+ 1st to 3rd Floor
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | (Wing B & C) = Gr + 1st to 3rd Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed, Brickwork upto 2 Floor completed, Internal Plaster upto 1 Floor completed, External Plaster upto 1 Floor completed , Painting upto 1 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 3 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed, Brickwork upto 2 Floor completed, Internal Plaster upto 1 Floor completed, External Plaster upto 1 Floor completed , Painting upto 1 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 0.75
Excavation |  | 3 | 100% |  | 52.5% |  | 74.17% |  | Excavation in process |  | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed |  | 3
RCC(Including podiums) |  | 3 | 75% | [5 empty] | Footing in Process |  | 0.75
Brickwork | Brickwork & Internal Plaster | 2 | 66.67% | [5 empty] | Footing Completed |  | 1.5
Internal Plaster | Brickwork & Internal Plaster | 1 | 33.33% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 1 | 33.33% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 1 | 33.33% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 3
Construction details: |  | (Wing B) = Gr + 1st to 3rd Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed, Brickwork upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 3 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed, Brickwork upto 2 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 0.75
Excavation |  | 3 | 100% |  | 45% |  | 70.83% |  | Excavation in process |  | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed |  | 3
RCC (Including podiums) |  | 3 | 75% | [5 empty] | Footing in Process |  | 0.75
Brickwork | Brickwork & Internal Plaster | 2 | 66.67% | [5 empty] | Footing Completed |  | 1.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 3
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleble area) | [5 empty] | 3000
Floor rise rate Per Sq. Ft. | [5 empty] | NA
Society formation charges | [5 empty] | 60,000/-
Society Maintenance Charges | [5 empty] | 38,000/-
Club House Charges | [5 empty] | 2,30,000/-
Water & Electric Meter Charges | [5 empty] | 55,000/-
Development charges | [5 empty] | 120000/- |  |  |  |  | 119700
Valuation as per Government reckoners rates | [5 empty] | NA
Distress valuation of the property Per Sq. Ft. | [5 empty] | 2400
Building details floor wise
Details of Flats in Building
Flat No. |  | Description | Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
TYPE 2 -Building No 3 & Wings are B & C
Ground Floor
1 |  | 1BHK | 274.9126 |  | 0 | 398.6232 | NA | Ground Floor
2 |  | 1BHK | 274.9126 |  | 0 | 398.6232 | NA | Ground Floor |  |  | 1.45
3 |  | 1RK | 175.6685 |  | 0 | 254.7193 | NA | Ground Floor
4 |  | 1RK | 175.6685 |  | 0 | 254.7193 | NA | Ground Floor
5 |  | 1RK | 175.6685 |  | 0 | 254.7193 | NA | Ground Floor
6 |  | 1RK | 175.6685 |  | 0 | 254.7193 | NA | Ground Floor
7 |  | 1RK | 175.6685 |  | 0 | 254.7193 | NA | Ground Floor
8 |  | 1RK | 175.6685 |  | 0 | 254.7193 | NA | Ground Floor
9 |  | 1RK | 175.6685 |  | 0 | 254.7193 | NA | Ground Floor
1st & 2nd Floor
1 |  | 1BHK | 281.2633 |  | 0 | 407.8318 | NA | 1st & 2nd |  | 122400 | 76500
2 |  | 1BHK | 281.2633 |  | 0 | 407.8318 | NA | 1st & 2nd
3 |  | 1RK | 214.2843 |  | 0 | 310.7123 | NA | 1st & 2nd
4 |  | 1RK | 214.2843 |  | 0 | 310.7123 | NA | 1st & 2nd
5 |  | 1RK | 214.2843 |  | 0 | 310.7123 | NA | 1st & 2nd
6 |  | 1RK | 214.2843 |  | 0 | 310.7123 | NA | 1st & 2nd
7 |  | 1RK | 214.2843 |  | 0 | 310.7123 | NA | 1st & 2nd
8 |  | 1RK | 214.2843 |  | 0 | 310.7123 | NA | 1st & 2nd
9 |  | 1RK | 214.2843 |  | 0 | 310.7123 | NA | 1st & 2nd
Remarks: 1. Wing B & C = Construction stage is same as last visit dtd.05/06/2025 but work is in process (Slow Speed). 2. We have considered rate by verifying it from market inquire. 3. We have considered Other charges from cost sheet. 4. As per Builder Details by mail TYPE 2 -Building No 3 & Wings are B & C, Same is mentioned development agreement as well. 5. We have given construction percentage as per proposed no of Floors (G+3) because work goes beyond approved no of Floors(G+2). 6. The project has received first CC on 21/12/2016, But construction work of project is not yet completed. 6. Please proved Revised latest Plans & CC. 7. As per RERA, completion period of project Avani Residency is expired on 30/12/2021 but still project is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHY OF PROPERTY: |  |  |  | Avani Residency
GOOGLE MAP :

## C% -Wing B
Particulars | totaL floor | 2
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 3 | 3 | 66.6667 | Progress |  |  | 10 | 40 | 10 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 10 | 0 | 0 | 0 | 0
| 3 | 2 | 0
plaster | Total Floor | completed Floor | 0
| 3 | 0 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 3 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 10 | 10
| 3 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 60 | 70

## C%- Wing C
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 75 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 3 | 50 | Progress |  |  | 10 | 30 | 7.5 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 22.5 | 7.5 | 0 | 0 | 0 | 0
| 4 | 2 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 30 | 22.5
Finishing | Total Floor | completed Floor |  | Bricks | 7.5 | 7.5
| 4 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 47.5 | 60

## Note
2020-10-16 | Pratiksha
2021-02-03 | Pratiksha

## Valuation
2020-10-15 | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A | 1 | 1 | 1BHK | 274.9126 | 0 | 274.9126 | 0 | 398.6232 | NA
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0 | 2 | 2 | 1BHK | 274.9126 | 0 | 274.9126 | 0 | 398.6232 | NA
|  |  |  | 0 | FB |  |  | 0 |  |  | 0 | 3 | 3 | 1RK | 175.6685 | 0 | 175.6685 | 0 | 254.7193 | NA
|  |  |  | 0 |  |  |  | 0 |  |  | 0 | 4 | 4 | 1RK | 175.6685 | 0 | 175.6685 | 0 | 254.7193 | NA
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0 | 5 | 5 | 1RK | 175.6685 | 0 | 175.6685 | 0 | 254.7193 | NA
|  |  |  | 0 | FB |  |  | 0 |  |  | 0 | 6 | 6 | 1RK | 175.6685 | 0 | 175.6685 | 0 | 254.7193 | NA
|  |  |  | 0 |  |  |  | 0 |  |  | 0 | 7 | 7 | 1RK | 175.6685 | 0 | 175.6685 | 0 | 254.7193 | NA
|  |  |  | 0 |  |  |  | 0 |  |  | 0 | 8 | 8 | 1RK | 175.6685 | 0 | 175.6685 | 0 | 254.7193 | NA
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0 | 9 | 9 | 1RK | 175.6685 | 0 | 175.6685 | 0 | 254.7193 | NA
|  |  |  | 0 | FB |  |  | 0 |  |  | 0 | 1st & 2nd Floor
|  |  |  | 0 |  |  |  | 0 |  |  | 0 | 10 | 1 | 1BHK | 250.0477 | 0 | 250.0477 | 0 | 362.5692 | NA
|  |  |  | 0 |  |  |  | 0 |  |  | 0 | 11 | 2 | 1BHK | 250.0477 | 0 | 250.0477 | 0 | 362.5692 | NA
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0 | 12 | 3 | 1RK | 177.2831 | 0 | 177.2831 | 0 | 257.0605 | NA
|  |  |  | 0 | FB |  |  | 0 |  |  | 0 | 13 | 4 | 1RK | 177.2831 | 0 | 177.2831 | 0 | 257.0605 | NA
|  |  |  | 0 |  |  |  | 0 |  |  | 0 | 14 | 5 | 1RK | 177.2831 | 0 | 177.2831 | 0 | 257.0605 | NA
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0 | 15 | 6 | 1RK | 177.2831 | 0 | 177.2831 | 0 | 257.0605 | NA
|  |  |  | 0 | FB |  |  | 0 |  |  | 0 | 16 | 7 | 1RK | 177.2831 | 0 | 177.2831 | 0 | 257.0605 | NA
|  |  |  | 0 |  |  |  | 0 |  |  | 0 | 17 | 8 | 1RK | 177.2831 | 0 | 177.2831 | 0 | 257.0605 | NA
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0 | 18 | 9 | 1RK | 177.2831 | 0 | 177.2831 | 0 | 257.0605 | NA
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0