## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 06/10/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-09
Name of the builder group |  |  |  |  | M/s. Sahajanand Developers
Name of the builder |  |  |  |  | Mr. Jitendra Shankerlal Brahmbhatt
Contact Number |  |  |  |  | Mr. Viranchi Brahmbhatt - 9819509466
Name of the Project |  |  |  |  | Arista
Name & No of Buildings |  |  |  |  | Wings A, B & C
Documents Provided |  |  |  |  | CC
RERA No. |  |  |  |  | P51800003375
Project location details |  | Arista, Proposed Redevelopment For Existing Building No. 1, 2, 3, 4 & 5 Bearing C.T.S No. 26(pt), Teachers Colony, MHADA Layout, Siddharth Nagar, Opp.Spectra Motors, Goregaon (West), Mumbai - 400062.
CTS No |  | 26(pt) |  |  | Locality |  | Goregaon
Road |  | Swami Vivekananda Road |  |  | District |  | Mumbai
City |  | Goregoan |  |  | Pin Code |  | 400062
Near by Landmark |  | Suyog Building |  |  | Distance from city centre: |  | About 800m from Ram Mandir Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | S. V. Road |  | Prabhodhan Thakare Road |  | Siddha Society |  | Siddhartha Nagar Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.1539317,72.842748
Location Link |  | https://goo.gl/maps/QtLZE5YqtSHC8nzQ9
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 8659.44
Permissible FSI |  |  |  |  | 2.5
Permissible TDR/Paid FSI |  |  |  |  | 18541.7
Total Fungible Area |  |  |  |  | 1327.2
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 30120.76
Total number of Buildings |  |  |  |  | 03 Wing
Approval Detail : Plan approval
Layout Approval No |  | Letter No. 51/377/Not legible/GM/MHADA |  |  |  | Dated | 26/09/2019.
Building plan approval No |  | Letter No. 51/377/Not legible/GM/MHADA |  |  |  | Dated | 26/09/2019. | Expiry date:NA
Commencement-CC No Valid Up to: |  | MH/EE/(B.P.)/GM/MHADA-51/377/2019 |  |  |  | Dated | 2019-11-06 | Expiry date: One year from date of issue
This CC is now issued for Wing A & B - Stilt floor at Ground Level + 1st to 3rd podium floor + 4th podium(upper stilt) + 1st to 17th upper floors and Wing C - 1st Basement + 2nd Basement + Stilt floor at Ground Level + 1st to 3rd podium floor + 4th podium(upper stilt) + 1st to 20th upper floors for residential use for the building under reference as per approved plans u/no. MH/EE/(B.P.)/GM/MHADA51/377/2019 dtd. 26/09/2019
Commencement-CC No Valid Up to: |  | MH/EE/BP Cell/GM/MHADA-51/377/2024 |  |  |  | Dated | 2024-07-25 | Expiry date: One year from date of issue
This CC is now extended from 21st Floor to 29th upper floor for residential user for Wing -"C" as per approved amended plan dtd.25.05.2022
O. Certificate No.: |  | NA |  |  | Date of approval: NA | Dated | NA | Expiry date: NA
Commencement date of construction |  |  | 2019-11-06 |  | Expected Completion |  | 2025-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 30120.76 |  | Approved no of units |  |  | NA
Approved no of Floors |  | Wing A & B - Stilt + 4 Podium + 1st to 17th Floor Wing C - 2 Basement + Stilt + 1st to 3rd Podium Parking + 4th Amenities Floor + 1st to 29th + 30th Pt. Floor.
Proposed no of Floors |  | Wing A & B - Stilt + 4Podium + 1st to 17th Floor Wing C - 2 Basement + 3Podium + Amenities Floor + 1st to 48th Floor.
Quality of construction: Good |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: | [8 empty] | All work completed. Please provide OC.
Construction details: |  | Wing A & B - Stilt + 4 Podium + 1st to 17th Floor
Basement | 0 | Ground | 1 | Podium |  | 4 | Floors | 17 | All work Completed. OC Received.
Stage of construction: |  | All work completed. Please provide OC.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
[9 empty] | Piling Work in process | 4.25
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Excavation in process | 8.5
Excavation |  | 17 | 100% |  | 100% |  | 100% |  | Excavation Completed | 17
Plinth |  | 17 | 100% | [5 empty] | Footing in Process | 4.25
RCC(Including podiums) |  | 22 | 100% | [5 empty] | Footing Completed | 8.5
Brickwork | Brickwork & Internal Plaster | 17 | 100% | [5 empty] | Basement 1 | 0
Internal Plaster | Brickwork & Internal Plaster | 17 | 100% | [5 empty] | Basement 2 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 17 | 100% | [5 empty] | Basement 3 | 0
Flooring & Fitting | Flooring & Fitting | 17 | 100% | [5 empty] | Basement 4 | 0
Painting & Wooden |  | 17 | 100% | [5 empty] | Plinth in process | 12.75
Building Common Amenities | Building Common Amenities | 17 | 100% | [5 empty] | Plinth completed | 17
Possession |  | 17 | 100% | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 30 Slab, Brickwork upto 29 Floor, Internal Plaster upto 24 Floor, External Plaster upto 24 Floor, Flooring upto 24 Floor, Painting upto 15 Floor Completed
Construction details: |  | Wing C - 2 Basement + 3Podium + Amenities Floor + 1st to 48th Floor.
Basement | 2 | Ground | 1 | Podium |  | 4 | Floors | 48 | All work Completed. OC Received.
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 30 Slab, Brickwork upto 29 Floor, Internal Plaster upto 24 Floor, External Plaster upto 24 Floor, Flooring upto 24 Floor, Painting upto 15 Floor Completed | [6 empty] | Piling Work in process | 12
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Excavation in process | 24
Excavation |  | 48 | 100% |  | 52.49% |  | 72.5% |  | Excavation Completed | 48
Plinth |  | 48 | 100% | [5 empty] | Footing in Process | 12 |  | SSS
RCC (Including podiums) |  | 30 | 56.6% | [5 empty] | Footing Completed | 24 | 26
Brickwork | Brickwork & Internal Plaster | 29 | 60.42% | [5 empty] | Basement 1 | 36
Internal Plaster | Brickwork & Internal Plaster | 24 | 50% | [5 empty] | Basement 2 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 24 | 50% | [5 empty] | Basement 3 | 0
Flooring & Fitting | Flooring & Fitting | 24 | 50% | [5 empty] | Basement 4 | 0
Painting & Wooden |  | 15 | 31.25% | [5 empty] | Plinth in process | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed | 48
Possession |  | 0 | 0%
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Super builtup area) | [5 empty] | 14000
Floor rise rate Per Sq. Ft. (from 1st Floor) | [5 empty] | 81/-
Society formation charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | 400000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Distress valuation of the property Per Sq. Ft. | [5 empty] | 11200
Remarks: 1. We have release report on the basis of other vendor report. 2. Wing A & B - All work completed. Please provide OC. Wing C - Construction work was stopped. Work is same as visit 08/12/2023. 3. Car parking is subjected to authentic documentation. 4. We have considered rate by verifying it from market inquire. 5. Construction percentages are reduced because we have given stage by considering proposed No of Floors. 6. We have updated revised approved CC for Wing C on 06/10/2025. 7. As per RERA, completion period of project Arista is expired on 30/12/2022 but still project is under construction.
Authorized Signatory Name & Seal of the agency
Photographs of Property : |  |  | Arista
Google Map :

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
99 Acres | Arista | 3BHK | 1072 | 1715.2 | 14284.0485 | 24500000
99 Acres | Arista | 3BHK | 1128 | 1804.8 | 15237.1454 | 27500000
Magic Brick | Arista | 3BHK | 1142 | 1768 | 14705.8824 | 26000000
Magic Brick | Arista | 2BHK | 862 | 1379.2 | 17256.3805 | 23800000
Average |  |  |  |  | 15370.8642
Valuation Adopted |  |  |  |  | 15400

## A&B
Particulars | totaL floor | 21
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 22 | 22 | 100 | Progress |  |  | 10 | 40 | 15 | 10 | 10 | 5 | 5
Bricks | Total Floor | completed Floor | 100 | Recommended |  |  | 30 | 30 | 15 | 10 | 5 | 5 | 5
| 21 | 21 | 100
plaster | Total Floor | completed Floor | 100
| 21 | 21 | 100
Flooring | Total Floor | completed Floor
| 21 | 21 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 21 | 21 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 21 | 21 |  | Plaster | 10 | 10
|  |  |  | Flooring | 10 | 5
|  |  |  | Wood & painting | 5 | 5
|  |  |  | Finishing | 5 | 5
|  |  |  | total | 95 | 100

## C%
Construction details: Building No. = | [7 empty] | Plinth work completed, RCC upto 23 Slab completed, Brickwork upto 22 Floor completed, Plaster upto 22 Floor completed
Basement + Ground |  | 1 |  | Podium | 4 | Floors | 48 | All work Completed. Wait For OC.
Stage of construction: |  | Plinth work completed, RCC upto 23 Slab completed, Brickwork upto 22 Floor completed, Plaster upto 22 Floor completed | [5 empty] | All work Completed. Provide OC.
Type of Work |  | Completed Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Plinth |  | 10 | 100% | 38.82% |  | 54.48%
RCC Slab |  | 23 | 43.4% |  |  |  |  | Excavation in process | 1% | 2%
Brick |  | 22 | 42.31% |  |  |  |  | Excavation Completed | 2% | 4%
Plaster |  | 22 | 42.31% |  |  |  |  | Footing in Process | 4% | 8%
Flooring |  | 0 | 0% |  |  |  |  | Footing Completed | 5% | 15%
Painting & Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 7% | 20%
Finishing |  | 0 | 0% |  |  |  |  | Plinth completed | 10% | 30%
38.82%
54.48%
over % diya he feb ki report me esliye match kiya he
Next time ASMITA se hi puchke karna

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0