## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 24/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-08
Name of the builder group |  |  |  |  | Mr. Mohansingh Tararam Choudhary
Name of the builder company |  |  |  |  | M/s.Varsha Enterprises
Name of the Project |  |  |  |  | Balaji Park
Contact Details ( Name & Contact No.) |  |  |  |  | 022-27565742/27565743
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  |  | Mr. Dinesh 022-27565742 |  |  |  | Ms. Namrata 8850110848
Name / No of the Building |  |  |  |  | A Wing & B Wing |  |  |  | Mr. Dinesh 022-27565742
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | P52000024410
Project location details |  | Balaji Park, Sector No.17, Plot No.6, 6A, 6B & 6C, Rani Laxmi Bai Marg, Kharghar, Panvel, Raigad.
Sector No |  | 17 |  |  | Plot No |  | 6, 6A, 6B & 6C
Road |  | Rani Laxmi Bai Marg |  |  | Locality/Village |  | Kharghar
City |  | Kharghar |  |  | District |  | Raigad
Taluka |  | Panvel |  |  | Pin Code |  | 410210
Near by Landmark |  | Celebration CHS |  |  | Distance from city centre: |  | 3.5Km from Kharghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Celebration CHS |  | Vastu Vihar Road |  | Road |  | Celebration Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.046565,73.082143
Location Link |  | https://goo.gl/maps/N87CE4YmEQZzQM1t8
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 5192.62
Permissible FSI |  |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1.5
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 7788.93
Total number of Buildings |  |  |  |  | 2 Wings
Approval Detail : Plan approval
Layout Approval No |  | CIDCO/BP-17323/TPO(NM & K)/2019/6465 |  |  |  | Dated | 2020-01-27
Approved Floor plan No. |  | CIDCO/BP-17323/TPO(NM & K)/2019/6465 |  |  |  | Dated | 2020-01-27
Commencement Certificate No. |  | CIDCO/BP-17323/TPO(NM & K)/2019/6465 Valid Up to: A & B Wing - G + P1 + P2 + 3rd to 26th Floor |  |  |  | Dated | 2020-01-27
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 2020-01-27 |  | Expected Completion |  | As per RERA-18/10/2026
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 7788.93 |  | Approved no of units |  | Flats = 96 & Shop = 34
Approved no of Floors |  | A Wing - G + P1 + P2 + 3rd to 26th Floor B Wing - G + P1 + P2 + 3rd to 26th Floor |  |  |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details:
Construction details: |  | B Wing - G + P1 + P2 + 3rd to 26th Floor | [6 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 25 Floor, Finishing upto 22 Floor Completed | , Painting upto 25 Floor, Finishing upto 22 Floor
Basement | 0 | Ground | 1 |  | Podium | 0 | Floors | 26 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 25 Floor, Finishing upto 22 Floor Completed | [6 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 6.5
Excavation |  | 26 | 100% |  | 94.04% |  | 95% |  | Excavation in process | 13
Plinth |  | 26 | 100% | [5 empty] | Excavation Completed | 26
RCC (Including podiums) |  | 27 | 100% | [5 empty] | Footing in Process | 6.5
Brickwork | Brickwork & Internal Plaster | 26 | 100% | [5 empty] | Footing Completed | 13
Internal Plaster | Brickwork & Internal Plaster | 26 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 26 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 26 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 25 | 96.15% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 22 | 84.62% | [5 empty] | Plinth in process | 19.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 26
Construction details: |  | A Wing - G + P1 + P2 + 3rd to 26th Floor | [6 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 25 Floor, Flooring upto 20 Floor, Painting upto 16 Floor, Finishing upto 4 Floor Completed | , External Plaster upto 25 Floor, Flooring upto 20 Floor, Painting upto 16 Floor, Finishing upto 4 Floor
Basement | 0 | Ground | 1 |  | Podium | 0 | Floors | 26 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 25 Floor, Flooring upto 20 Floor, Painting upto 16 Floor, Finishing upto 4 Floor Completed | [6 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 6.5
Excavation |  | 26 | 100% |  | 86.15% |  | 93.65% |  | Excavation in process | 13
Plinth |  | 26 | 100% | [5 empty] | Excavation Completed | 26
RCC (Including podiums) |  | 27 | 100% | [5 empty] | Footing in Process | 6.5
Brickwork | Brickwork & Internal Plaster | 26 | 100% | [5 empty] | Footing Completed | 13
Internal Plaster | Brickwork & Internal Plaster | 26 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 25 | 96.15% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 20 | 76.92% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 16 | 61.54% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 15.38% | [5 empty] | Plinth in process | 19.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 26
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property : | [8 empty] | rate 12300 to16500 Smith sir on 23/09/2025
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 16500 |  |  | 10000 to 12300 +Park 8L + 6L OC Smith Verbal & Cost sheet on 23/12/2024
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 22000
Development charges | [5 empty] | 360000
Club charges | [5 empty] | 325000
Society Formation + Grill charges | [5 empty] | 175000
Recommended rate of Parking | [5 empty] | 800000
Distressed valuation of the Property | [5 empty] | 13200
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
A & B Wing |  | 34 | 13635.0817 |  |  | 22497.8848
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
A Wing |  | 48 | 43027.1525 |  |  | 66828.0303
B Wing |  | 48 | 30512.7108 |  |  | 30512.7108
Total |  | 96 | 73539.8633 |  |  | 97340.7411
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
A & B Wing
Ground Floor for Commercial & Parking
1 |  | Shop | 409.1396 |  | 0 | 675.0804 | N | Ground Floor
2 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
3 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
4 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
5 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
6 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
7 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
8 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
9 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
10 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
11 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
12 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
13 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
14 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
15 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
16 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
17 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
18 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
19 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
20 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
21 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
22 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
23 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
24 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
25 |  | Shop | 441.6469 |  | 0 | 728.7174 | N
26 |  | Shop | 437.449 |  | 0 | 721.7908 | N
27 |  | Shop | 484.8106 |  | 0 | 799.9374 | N
28 |  | Shop | 249.6172 |  | 0 | 411.8683 | N
29 |  | Shop | 249.6172 |  | 0 | 411.8683 | N
30 |  | Shop | 250.0477 |  | 0 | 412.5787 | N
31 |  | Shop | 238.7455 |  | 0 | 393.9301 | N
32 |  | Shop | 238.7455 |  | 0 | 393.9301 | N | Ground Floor
33 |  | Shop | 238.7455 |  | 0 | 393.9301 | N
34 |  | Shop | 238.6379 |  | 0 | 393.7525 | N
A Wing
1st Floor for Parking
2nd Floor for Amenities
3rd, 5th, 7th & 9th Floor
1 |  | 3BHK | 860.6894 |  | 0 | 1334.0686 | N | 3rd, 5th, 7th & 9th Floor
2 |  | 3BHK | 860.6894 |  | 0 | 1334.0686 | N
4th, 6th, 8th & 10th Floor
1 |  | 3BHK | 860.6894 |  | 0 | 1334.0686 | N | 4th, 6th, 8th & 10th Floor
2 |  | 3BHK | 860.6894 |  | 0 | 1334.0686 | N
11th, 13th, 15th, 17th, 19th, 21th, 23rd & 25th Floor
1 |  | 3BHK | 921.7213 |  | 0 | 1428.668 | N | 11th, 13th, 15th, 17th, 19th, 21th, 23rd & 25th Floor
2 |  | 3BHK | 921.7213 |  | 0 | 1428.668 | N
12th, 14th, 16th, 18th, 20th, 22nd & 24th Floor
1 |  | 3BHK | 921.7213 |  | 0 | 1428.668 | N | 12th, 14th, 16th, 18th, 20th, 22nd & 24th Floor
2 |  | 3BHK | 921.7213 |  | 0 | 1428.668 | N
26th Floor
1 |  | 2BHK | 802.2409 |  | 135.9439 | 1311.4454 | N | 26th Floor
2 |  | 2BHK | 802.2409 |  | 135.9439 | 1311.4454 | N
B Wing
1st Floor Podium
2nd Floor Podium
3rd, 5th, 7th & 9th Floor
1 |  | 2BHK | 610.2112 |  | 0 | 945.8273 | N | 3rd, 5th, 7th & 9th Floor
2 |  | 2BHK | 610.2112 |  | 0 | 945.8273 | N
4th, 6th, 8th & 10th Floor
1 |  | 2BHK | 610.2112 |  | 0 | 945.8273 | N | 4th, 6th, 8th & 10th Floor
2 |  | 2BHK | 610.2112 |  | 0 | 945.8273 | N
11th, 13th, 15th, 17th, 19th, 21th, 23rd & 25th Floor
1 |  | 2BHK | 656.4964 |  | 0 | 1017.5694 | N | 11th, 13th, 15th, 17th, 19th, 21th, 23rd & 25th Floor
2 |  | 2BHK | 656.4964 |  | 0 | 1017.5694 | N
12th, 14th, 16th, 18th, 20th, 22nd & 24th Floor
1 |  | 2BHK | 656.4964 |  | 0 | 1017.5694 | N | 12th, 14th, 16th, 18th, 20th, 22nd & 24th Floor
2 |  | 2BHK | 656.4964 |  | 0 | 1017.5694 | N
26th Floor
1 |  | 1BHK | 527.2207 |  | 144.5605 | 889.4724 | N | 26th Floor
2 |  | 1BHK | 527.2207 |  | 144.5605 | 889.4724 | N
Remarks:
1. Wing A = Construction work was in process at the time of visit. (Internal Photo was not allowed) Wing B = Finishing work was in process at the time of visit. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. Recommended Rates/Other Charges of the Property have been revised on 23/10/2023 & 23/09/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mayur Ranvare |  | Report Prepared By : |  |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Balaji Park
Google Map :
Formulas:
Kharghar = [Kharghar, row above]
Wing A
Wing B
Wing A
Wing B

## Note
20/06/2020. | Pratiksha | 8. On Site, we meet Mr. Nagaram Choudhary (9167330234).
Rate As per site inspection - 10000/-
18/02/2021. | Pratiksha

## A&B%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 26
Particulars | total floor | 26
plinth | 10 | 10 | 100%
slab | 27 | 2 | 7.407% |  | Parking |  | Rate
Bricks | 26 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 26 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 26 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 26 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 26 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 2.963 | 0 | 0 | 0 | 0 | 0
RCC | 2.963 | 2.2222 |  | Recommended |  | 30 | 2.2222 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 12.96% | 32.22% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0