## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Goregaon | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-09-08 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Shree Krishna Sai Development Corporation | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Shree Krishna Sai Development Corporation | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Khandelwal Luxor Wing B | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Sadik Jafari 9987000099
Site Person - Contact Details (Name & Contact No.) |  |  |  | 8655993118
Name / No of the Building |  |  |  | Wing B
Name / No of the Existing Building |  |  |  | Gorai Shri Shiv Parvati C.H.S.L. | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Commencement Certificate. | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800045675 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Khandelwal Luxor Wing B, Plot No.8, R.S.C. 3, Redevlopement of "Gorai Shri Shiv Parvati C.H.S.L.", near Gorai Bus Depot, Gorai Road, , Gorai III, Borivali West, Borivali, Mumbai - 400091. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Plot No |  | 8, R.S.C. 3, Redevlopement of "Gorai Shri Shiv Parvati C.H.S.L." | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | NA | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Gorai Road |  | Locality/Village |  | Gorai III | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Borivali West |  | District |  | Mumbai | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Borivali |  | Pin Code |  | 400091 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Gorai Bus Depot |  | Distance from city centre: |  | 3.40KM from Borivali Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | 12.20 M. Wide Road |  |  | Internal Road
West | NA | College |  |  | Open Plot
North | NA | Plot No. 7 |  |  | Khandelwal Reserve Wing B
South | NA | Plot No. 9 |  |  | Casa bellsimo Gorai Laxmi
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.234339,72.831092
Location Link |  | https://maps.app.goo.gl/28VagwtoXzgPpfTb9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2866.14
Permissible FSI |  |  |  | 2.5
Permissible TDR/Paid FSI |  |  |  | 0.13774
Total FSI availaible for the project |  |  |  | 2.6377
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 7560.13
Total number of Buildings |  |  |  | 01 Wing
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority(MHADA) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | Mhada-72/1104/2022 |  |  | Dated | 20/04/2022. | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | Mhada-72/1104/2022 |  |  | Dated | 20/04/2022. | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | MH/EE/(BP)/GM/MHADA-72/1104/2024/FCC/1/Amend |  |  | Dated | 01/02/2024. | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | This C.C. is further extended for work upto top of 22nd upper floor (i.e. ht. upto 69.60 m AGL) as per approved IOA dtd. 20.04.2022 |  |  | Valid Upto Date | 26/05/2026. | [10 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | This C.C. is further extended for work upto top of 22nd upper floor (i.e. ht. upto 69.60 m AGL) as per approved IOA dtd. 20.04.2022 |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 7560.13
Approved no of units |  |  | Flats - 160
Approved no of Floors |  |  | Wing B = G + 1st to 22nd Floor
Proposed no of Floors |  |  | Wing B = G + 1st to 22nd Floor
B Wing = 1B + G + 1st to 20th Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Terrace Garden, Kids Play Area, Banquet Mall, Sitout Area, Yoga, Gymnasium, etc. | [5 empty] | https://khandelwalluxor.in
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing B = G + 1st to 22nd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 20 Floor, Painting upto 18 Floor, Finishing upto 8 Floor Completed | , Flooring upto 20 Floor, Painting upto 18 Floor, Finishing upto 8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 20 Floor, Painting upto 18 Floor, Finishing upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 90% |  | 94.55% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 20 | 90.91% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 18 | 81.82% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 8 | 36.36% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | B Wing = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 10% |  | 45% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | C Wing = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 15000 |  |  |  | the rate is kept same as Khandelwal Reserve Wing B | [7 empty] | 700000 | 300000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. | [16 empty] | 900000 | 350000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 400000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 500000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 600000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 700000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 800000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 900000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 1000000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000
Recommended rate of Parking |  |  |  |  | 700000 | [11 empty] | 1800000
Distressed valuation of the Property |  |  |  |  | 12000 | [5 empty] | 14000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing B |  | 160 |  | 72712.1117 |  | 109068.1675
Total
Grand Total |  | 0 |  | 0 |  | 0
Building details Floor Wise
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Ground Floor
1 |  |  |  | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
[7 empty] | 50% | 10.764
Wing B
Ground Floor For Entrance Lobby, Meter Room & Puzzle Parking
1st Floor For Residential (Part Puzzle Parking) | [7 empty] | 1
1 |  | 1BHK | 408.7091 | 0 | 408.7091 | 0 | 613.0636 | 37.0189 | 1 | 1-22 |  | 37.97
2 |  | 2BHK | 595.3568 | 0 | 595.3568 | 0 | 893.0353 | 53.4277 | 2 | 1-6, 8-13, 15-20, 22 |  | 55.31 | 21 | 26.07
3 |  | Puzzle Parking | [6 empty] | 3 | 4-6, 8-13, 15-22 |  | 37.84
4 | [8 empty] | 4 | 4-22 |  | 37.59
5 | [8 empty] | 5 | 4-22 |  | 37.59
6 | [8 empty] | 6 | 4-22 |  | 37.84
7 |  | 2BHK | 595.3568 | 0 | 595.3568 | 0 | 893.0353 |  | 7 | 1-22 |  | 55.31
8 |  | 1BHK | 408.7091 | 0 | 408.7091 | 0 | 613.0636 |  | 8 | 1-22 |  | 37.97
2nd Floor (Part Puzzle Parking) | [7 empty] | 1
1 |  | 1BHK | 408.7091 | 0 | 408.7091 | 0 | 613.0636
2 |  | 2BHK | 595.3568 | 0 | 595.3568 | 0 | 893.0353
3 |  | Puzzle Parking
4
5
6
7 |  | 2BHK | 595.3568 | 0 | 595.3568 | 0 | 893.0353
8 |  | 1BHK | 408.7091 | 0 | 408.7091 | 0 | 613.0636
3rd Floor (E- Deck For Parking & Fitness Centre) | [7 empty] | 1
1 |  | 1BHK | 408.7091 | 0 | 408.7091 | 0 | 613.0636
2 |  | 2BHK | 595.3568 | 0 | 595.3568 | 0 | 893.0353
3 |  | Parking & Fitness Centre
4
5
6
7 |  | 2BHK | 595.3568 | 0 | 595.3568 | 0 | 893.0353
8 |  | 1BHK | 408.7091 | 0 | 408.7091 | 0 | 613.0636
4th to 6th, 8th to 13th, 15th to 20th & 22nd Floor | [7 empty] | 16
1 |  | 1BHK | 408.7091 | 0 | 408.7091 | 0 | 613.0636
2 |  | 2BHK | 595.3568 | 0 | 595.3568 | 0 | 893.0353
3 |  | 1BHK | 407.3098 | 0 | 407.3098 | 0 | 610.9646
4 |  | 1BHK | 404.6188 | 0 | 404.6188 | 0 | 606.9281 |  | 23726.0378
5 |  | 1BHK | 404.6188 | 0 | 404.6188 | 0 | 606.9281
6 |  | 1BHK | 407.3098 | 0 | 407.3098 | 0 | 610.9646
7 |  | 2BHK | 595.3568 | 0 | 595.3568 | 0 | 893.0353
8 |  | 1BHK | 408.7091 | 0 | 408.7091 | 0 | 613.0636
7th & 14th Floor (Part Refuge Area) | [7 empty] | 2
1 |  | 1BHK | 408.7091 | 0 | 408.7091 | 0 | 613.0636
2 |  | Refuge Area
3
4 |  | 1BHK | 404.6188 | 0 | 404.6188 | 0 | 606.9281
5 |  | 1BHK | 404.6188 | 0 | 404.6188 | 0 | 606.9281
6 |  | 1BHK | 407.3098 | 0 | 407.3098 | 0 | 610.9646
7 |  | 2BHK | 595.3568 | 0 | 595.3568 | 0 | 893.0353
8 |  | 1BHK | 408.7091 | 0 | 408.7091 | 0 | 613.0636
21st Floor (Part Refuge Area) | [7 empty] | 1
1 |  | 1BHK | 408.7091 | 0 | 408.7091 | 0 | 613.0636
2 |  | 1RK | 280.6175 | 0 | 280.6175 | 0 | 420.9262
- |  | Refuge Area
3 |  | 1BHK | 407.3098 | 0 | 407.3098 | 0 | 610.9646
4 |  | 1BHK | 404.6188 | 0 | 404.6188 | 0 | 606.9281
5 |  | 1BHK | 404.6188 | 0 | 404.6188 | 0 | 606.9281
6 |  | 1BHK | 407.3098 | 0 | 407.3098 | 0 | 610.9646
7 |  | 2BHK | 595.3568 | 0 | 595.3568 | 0 | 893.0353
8 |  | 1BHK | 408.7091 | 0 | 408.7091 | 0 | 613.0636
Remarks:
* | Construction work is in process at the time of Visit.(Internal photos was not allowed).
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Environment Clearance Certificate.
* | Provided C.C validity expired on 26/05/2023. Provide revised approved C.C.
* | We have refered approved plans from MHADA site.
* | The Gorai Dump Yard is near the project @230m approx on west side & On east side Water Body is present.
* | We have updated revised approved CC from Mhada site on 19/04/2024.
* | Validity of CC is expired on 26/05/2024. Please provide revised CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Suraj Mali |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Khandelwal Luxor Wing B
Layout :
Google Map :
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F122: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H152: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | There are inadequate transportation options to get to the project and the area is not developed.
15 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sales plan.
16 | River located on west side of the project.
15
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate