## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 17/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-11
Name of the builder group |  |  |  | M/s. Cemcon Developers
Name of the builder company |  |  |  | M/s. Cemcon Developers
Name of the Project |  |  |  | Innovative Icon
Contact Details ( Name & Contact No.) |  |  |  | 8566968566
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Rohidas 8108809181
Name / No of the Building |  |  |  | 01 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P52000022661
Project location details |  | Innovative Icon, Plot No.21 & 22-A, Sector No.18, near Kalpavruksha Valley, Internal Road, Taloja, Taloja, Panvel, Raigad - 410208.
Plot No |  | 21 & 22-A, Sector No.18
Road |  | Internal Road |  | Locality/Village |  | Taloja
City |  | Taloja |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410208
Nearby Landmark |  | Kalpavruksha Valley |  | Distance from city centre: |  | 5M from Pendhar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | 15.00 M. Wide Road |  |  | Internal Road
West | NA | Other Plot |  |  | Open Plot
North | NA | 20.00 m. Wide Road |  |  | Pendhar Metro Station/Taloja Metro Road
South | NA | Other Plot |  |  | Prism Heights
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.071927,73.097586
Location Link |  | https://maps.app.goo.gl/wQB44aZPA5QiE7kG8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2858.59
Permissible FSI |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  | 1.2993
Total FSI availaible for the project |  |  |  | 2.7993
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 8002.104 |  |  |  | 8002.104
Total number of Buildings |  |  |  | 1 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | City and Industrial Development Corporation of Maharashtra (CIDCO)
Layout Approval No |  | CIDCO/BP-16823/TPO(NM & K)/2019/12120 |  |  | Dated | 2024-03-01
Approved Floor plan No. |  | CIDCO/BP-16823/TPO(NM & K)/2019/12120 |  |  | Dated | 2024-03-01
Commencement Certificate No. Valid Up to: |  | CIDCO/BP-16823/TPO(NM & K)/2019/12120 |  |  | Dated | 2024-03-01
|  | Gr/St + 1st to 21st Floor (Amended BUA = 4558.85) | [5 empty] | 4558.85
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 8002.104
Approved no of units |  |  | Flats - 144, Shops - 19
Approved no of Floors |  |  | Gr/St + 1st to 21st Floor
Proposed no of Floors |  |  | Gr/St + 1st to 21st Floor
Expected Completion |  |  | As per RERA - 30/12/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | FitnessCentre, Jogging Track, Basket Ball, Childrens Play Area, Senior Citizen Area & Party Lawn |  |  |  |  | Approved plan
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Gr/St + 1st to 21st Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 18 Floor Completed, Painting upto 16 Floor Completed, Finishing upto 2 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 21
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster Completed, Flooring upto 18 Floor Completed, Painting upto 16 Floor Completed, Finishing upto 2 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 87.86% |  | 94.29% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 22 | 100% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 21 | 100% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 21 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 21 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 18 | 85.71% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 16 | 76.19% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 9.524% |  |  |  |  | Plinth in process | 15.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. (on Saleable area) |  |  |  |  | 5800
Recommended rate of the shop Per Sq. Ft. (on Saleable area) |  |  |  |  | 12000
Floor Rise Rate Per Sq.ft |  |  |  |  | 30/- from 4th Floor
Development Charges |  |  |  |  | 300000
Club Charges |  |  |  |  | 150000
Legal Services Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges |  |  |  |  | 150000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 4640
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop |  | 19 |  | 10411.4252 |  | 17923.4539 |  |  | 147785.0287 | 80009.6785
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 144 |  | 69598.2533 |  | 129861.5748
Toal |  | 163 |  | 80009.6785 |  | 147785.0287
Building details Floor Wise | [11 empty] | 152
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor for Commercial, Entrance Lobby, Meter Room, Pump Room, Driver Room & Parking | [10 empty] | 10.764
1 |  | Shop | 439.8709 | 90.1485 | 793.9419 | Ground Floor for Commercial, Entrance Lobby, Meter Room, Pump Room, Driver Room & Parking |  | 41.1045 | 32.495 | 4.62
2 |  | Shop | 431.9701 | 88.803 | 779.9551
3 |  | Shop | 432.6159 | 88.803 | 780.9885
4 |  | Shop | 432.293 | 88.803 | 780.4718
5 |  | Shop | 522.9689 | 135.8955 | 904.6981
6 |  | Shop | 507.3611 | 90.1485 | 901.9263
7 |  | Shop | 390.7009 | 98.2215 | 723.343
8 |  | Shop | 910.0424 | 269.6382 | 1545.9472
9 |  | Shop | 488.0936 | 102.258 | 832.0787 |  |  | 45.98
10 |  | Shop | 585.8307 | 102.258 | 988.4581
11 |  | Shop | 585.8307 | 102.258 | 988.4581
12 |  | Shop | 585.8307 | 102.258 | 988.4581
13 |  | Shop | 585.8307 | 102.258 | 988.4581
14 |  | Shop | 585.8307 | 102.258 | 988.4581
15 |  | Shop | 585.8307 | 102.258 | 988.4581
16 |  | Shop | 585.8307 | 102.258 | 988.4581
17 |  | Shop | 585.8307 | 102.258 | 988.4581
18 |  | Shop | 585.8307 | 102.258 | 988.4581
19 |  | Shop | 583.0321 | 102.258 | 983.9803 |  |  | 54.53
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area + Balcony + Varandah + Chajja | Attached Terrace area | Builder Saleable area | Floor
1st & 2nd Floor for Parking
3rd Floor for FitnessCentre, Jogging Track, Basket Ball, Childrens Play Area, Society Office, Senior Citizen Area & Party Lawn
4th, 6th, 8th, 10th & 14th Floor for Residential | [7 empty] | 7
1 |  | 1BHK | 364.2268 | 0 | 665 | 4th, 6th, 8th, 10th & 14th Floor for Residential |  | 28 | 1.8258 |  | 18
2 |  | 2BHK | 544.6853 | 0 | 1020 |  |  | 42.1125 | 1.8726 |  |  | 144
3 |  | 2BHK | 559.5396 | 0 | 1040 |  |  |  | 1.8587
4 |  | 1BHK | 376.4978 | 0 | 705 |  |  |  | 1.8725
5 |  | 1BHK | 376.4978 | 0 | 705 |  |  |  | 1.8725
6 |  | 2BHK | 559.6473 | 0 | 1040 |  |  |  | 1.8583
7 |  | 2BHK | 544.6853 | 0 | 1020 |  |  |  | 1.8726
8 |  | 1BHK | 341.6225 | 0 | 660 |  |  |  | 1.932
5th Floor
1 |  | 1BHK | 364.6305 | 0 | 665 | 5th Floor
2 |  | 2BHK | 544.6853 | 0 | 1020 | 5th Floor
3 |  | 2BHK | 559.5396 | 0 | 1040 | 5th Floor
4 |  | 1BHK | 376.4978 | 0 | 705 | 5th Floor
5 |  | 1BHK | 376.4978 | 0 | 705 | 5th Floor
6 |  | 2BHK | 559.6473 | 0 | 1040 | 5th Floor
7 |  | 2BHK | 544.6853 | 0 | 1020 | 5th Floor
8 |  | 1BHK | 342.1068 | 0 | 660 | 5th Floor
12th Floor | [7 empty] | 7
1 |  | 1BHK | 364.2268 | 0 | 665 | 12th Floor |  | 28 | 1.8258 |  | 18
2 |  | 2BHK | 544.6853 | 0 | 1020 |  |  | 42.1125 | 1.8726 |  |  | 144
3 |  | 2BHK | 559.5396 | 0 | 1040 |  |  |  | 1.8587
4 |  | 1BHK | 376.4978 | 0 | 705 |  |  |  | 1.8725
5 |  | 1BHK | 376.4978 | 0 | 714 |  |  |  | 1.8964
6 |  | 2BHK | 559.6473 | 0 | 1040 |  |  |  | 1.8583
7 |  | 2BHK | 544.6853 | 0 | 1020 |  |  |  | 1.8726
8 |  | 1BHK | 341.6225 | 0 | 660 |  |  |  | 1.932
5th Floor | [7 empty] | 7
1 |  | 1BHK | 364.2268 | 0 | 665 | 5th Floor |  | 28 | 1.8258
2 |  | 2BHK | 544.6853 | 0 | 1020 |  |  | 42.1125 | 1.8726
3 |  | 2BHK | 559.5396 | 0 | 1040 |  |  |  | 1.8587
4 |  | 1BHK | 376.4978 | 0 | 705 |  |  |  | 1.8725
5 |  | 1BHK | 376.4978 | 0 | 705 |  |  |  | 1.8725
6 |  | 2BHK | 559.6473 | 0 | 1040 |  |  |  | 1.8583
7 |  | 2BHK | 544.6853 | 0 | 1020 |  |  |  | 1.8726
8 |  | 1BHK | 341.6225 | 0 | 660 |  |  |  | 1.932
7th, 9th, 11th, 13th, 15th Floor (Refuge Balcony at Mid landing of Stairecase) | [7 empty] | 5 | #DIV/0!
1 |  | 1BHK | 364.2268 | 0 | 665 | 7th, 9th, 11th, 13th, 15th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.8258
2 |  | 2BHK | 544.6853 | 0 | 1020 | 7th, 9th, 11th, 13th, 15th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.8726
3 |  | 2BHK | 559.5396 | 0 | 1040 | 7th, 9th, 11th, 13th, 15th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.8587
4 |  | 1BHK | 376.4978 | 0 | 705 | 7th, 9th, 11th, 13th, 15th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.8725
5 |  | 1BHK | 376.4978 | 0 | 705 | 7th, 9th, 11th, 13th, 15th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.8725
6 |  | 2BHK | 559.6473 | 0 | 1040 | 7th, 9th, 11th, 13th, 15th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.8583
7 |  | 2BHK | 544.6853 | 0 | 1020 | 7th, 9th, 11th, 13th, 15th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.8726
8 |  | 1BHK | 342.0261 | 0 | 660 | 7th, 9th, 11th, 13th, 15th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.9297
16th, 18th & 20th Floor (Refuge Balcony at Mid landing of Stairecase) | [7 empty] | 3 | #DIV/0!
1 |  | 1BHK | 418.1114 | 0 | 777.6873 | 16th, 18th & 20th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.86 |  |  | 10.764
2 |  | 2BHK | 658.0894 | 0 | 1224.0463 | 16th, 18th & 20th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.86 | 48
3 |  | 2BHK | 624.2689 | 0 | 1161.1402 | 16th, 18th & 20th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.86
4 |  | 1BHK | 421.0554 | 0 | 783.163 | 16th, 18th & 20th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.86
5 |  | 1BHK | 421.0554 | 0 | 783.163 | 16th, 18th & 20th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.86
6 |  | 2BHK | 645.7969 | 0 | 1201.1823 | 16th, 18th & 20th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.86
7 |  | 2BHK | 658.0787 | 0 | 1224.0263 | 16th, 18th & 20th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.86
8 |  | 1BHK | 418.1114 | 0 | 777.6873 | 16th, 18th & 20th Floor (Refuge Balcony at Mid landing of Stairecase) |  |  | 1.86
17th, 19th & 21st Floor | [7 empty] | 3 | #DIV/0!
1 |  | 1BHK | 418.1114 | 0 | 777.6873 | 17th, 19th & 21st Floor |  |  | 1.86 |  |  | 10.764
2 |  | 2BHK | 658.0894 | 0 | 1224.0463 | 17th, 19th & 21st Floor |  |  | 1.86
3 |  | 2BHK | 624.2689 | 0 | 1161.1402 | 17th, 19th & 21st Floor |  |  | 1.86
4 |  | 1BHK | 421.0554 | 0 | 783.163 | 17th, 19th & 21st Floor |  |  | 1.86
5 |  | 1BHK | 421.0554 | 0 | 783.163 | 17th, 19th & 21st Floor |  |  | 1.86
6 |  | 2BHK | 645.7969 | 0 | 1201.1823 | 17th, 19th & 21st Floor |  |  | 1.86
7 |  | 2BHK | 658.0787 | 0 | 1224.0263 | 17th, 19th & 21st Floor |  |  | 1.86
8 |  | 1BHK | 418.1114 | 0 | 777.6873 | 17th, 19th & 21st Floor |  |  | 1.86
Remarks:
* | Construction work is in process at the time of Visit. (Internal visit was not allowed.)
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + Varandah + Chajja Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated approved plan & C.C (On 09/03/2024).
* | On Site, we meet Mr. Tanvir : 8566968566. | [6 empty] | we have asked for Metro NOC, but as per akash sir request we have removed remark
* | Project Lay Near Metro Railway Track. Please provide RAILWAY NOC.
* | Recommended Other charges of the Property have been revised on 24/03/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mayur Ranvare |  | Report By : |  | Pranita Mhatre
PHOTOGRAPHS OF PROPERTY : |  |  | Innovative Icon
Layout :
Google Map :
Formulas:
Taloja = [Taloja, row above]
N

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted