## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 10/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-10
Name of the builder group |  |  |  | Saroj Landmark Realty LLP |  |  |  | Surya Builders and Developers
Name of the builder company |  |  |  | Saroj Landmark Realty LLP
Name of the Project |  |  |  | Greenairy
Contact Details ( Name & Contact No.) |  |  |  | 9152010697
Site Meet Contact Details ( Name & Contact No.) |  |  |  | Mr. Dhawani 8976967474 Mr. Hari 9136776847 |  |  |  | Mr. Dhawani - 8976967474
Name / No of the Building |  |  |  | Tower A & B
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | P51800035093
Project location details |  | DCPR 2034, for propoesd 1) Ganesh Nagar Magathane SRA CHS Ltd on plot bearing CTS No.182(Pt) & 191(Pt), 2) Siddharth Welfare SRA CHS Ltd on plot bearing CTS No. 182A(Pt), 183(Pt) & 191(Pt) of village magathane, Ganesh Nagar, Tata Power House at Borivali(East), Mumbai - 400066 and S.R.Scheme under 3) Reg.33(11) DCPR-2034 on plot bearing CTS No. 181/A of Jai Maharashtra Nagar Road No.1, Village-Magathane, Borivali(East) Mumbai- 400066
CTS No |  | 182A(Pt), 182B(Pt) & 191(Pt), 183(Pt) 181/A
Locality |  | Ganesh Nagar
Road |  | Western Express Highway |  | Village |  | Magathane
City |  | Borivali East |  | District |  | Mumbai
Taluka |  | Borivali |  | Pin Code |  | 400066
Nearby Landmark |  | Magathane Bus Depot |  | Distance from city centre: |  | 3.1KM from Borivali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | 18.30 M W Road |  |  | Jai Maharashtra Nagar Road No.1
West | NA | 61 M W Road |  |  | Western Express Highway
North | NA | Other Plot |  |  | Magathane Depot
South | NA | Nala |  |  | Devalapada
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.2190066,72.8665959
Location Link |  | https://goo.gl/maps/DmLj2EKWUzZJsW5t9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 15803.75
Permissible FSI |  |  |  | 4
Permissible TDR/Paid FSI |  |  |  | 2.3581
Total FSI availaible for the project |  |  |  | 6.3581
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 100482.08
Total number of Buildings |  |  |  | 02 Tower
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Slum Rehabilitation Authority (SRA)
Layout Approval No |  | R-C/MHADA/0005/20050623/AP/S-1 |  |  | Dated | 2025-03-07 |  | R-C/MHADA/0005/20050623/AP/S |  |  | 2024-02-21
Approved Floor plan No. |  | R-C/MHADA/0005/20050623/AP/S-1 |  |  | Dated | 2025-03-07
Commencement-CC No Valid Up to: |  | RC/MHADA /0005/20050623/AP /5-1 |  |  | Dated | 2025-03-07
This C.C. is further extended for Gr t0 14th upper Floors for brick work and 26th to 40th upper floors for R.C.C. frame work only lor Sale Bldg. Ne,1 Tower A & B as per approved amended plans dtd, 07/03/2025. Further this C,C. is lssued in the name of new Develeper M/s. Saroj Landmark Realty LLP Vide Hon'ble CEO(SRA) 's approval in Revised LOI dtd,08/11/2023, Revised LOI has been issued on 30/01/2024.
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 100482.08
Approved no of units |  |  | Flats - 810, Commercial Units - 192
Approved no of Floors |  |  | Sale Tower A = 2B + G + 1st to 10th Floor (Comm.) + 11th Floor For Amenities + 12th to 46th Floor For Residential Sale Tower B = 2B + G + 1st to 10th Floor (Comm.) + 11th Floor For Amenities + 12th to 46th Floor For Residential
Proposed no of Floors |  |  | Sale Tower A = 2B + G + 1st to 10th Floor (Comm.) + 11th Floor For Amenities + 12th to 55th Floor For Residential | [5 empty] | Proposed floors from rera
Sale Tower B = 2B + G + 1st to 10th Floor (Comm.) + 11th Floor For Amenities + 12th to 55th Floor For Residential
Expected Completion |  |  | As per RERA - 30/06/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Sale Tower A = 2B + G + 1st to 10th Floor (Comm.) + 11th Floor For Amenities + 12th to 55th Floor For Residential | [5 empty] | Excavation, Plinth Completed, RCC upto 36 Slab, Brickwork upto 33 Floor, Internal Plaster upto 24.75 Floor, External Plaster upto 21.45 Floor Completed | , RCC upto 36 Slab, Brickwork upto 33 Floor, Internal Plaster upto 24.75 Floor, External Plaster upto 21.45 Floor
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 55 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 36 Slab, Brickwork upto 33 Floor, Internal Plaster upto 24.75 Floor, External Plaster upto 21.45 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 13.75
Excavation |  | 55 | 100% | 47.49% |  | 71.49% |  | Excavation in process | 27.5
Plinth |  | 55 | 100% |  |  |  |  | Excavation Completed | 55
RCC (Including podiums) |  | 36 | 64.29% |  |  |  |  | Footing in Process | 13.75
Brickwork | Brickwork & Internal Plaster | 33 | 60% |  |  |  |  | Footing Completed | 27.5
Internal Plaster | Brickwork & Internal Plaster | 24.75 | 45% |  |  |  |  | Basement 1 | 41.25
Ext. Plaster & Plumbing | External Plaster & Plumbing | 21.45 | 39% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 55
Construction details: |  | Sale Tower B = 2B + G + 1st to 10th Floor (Comm.) + 11th Floor For Amenities + 12th to 55th Floor For Residential | [5 empty] | Excavation, Plinth Completed, RCC upto 39 Slab, Brickwork upto 36 Floor, Internal Plaster upto 27 Floor, External Plaster upto 23.4 Floor Completed | , RCC upto 39 Slab, Brickwork upto 36 Floor, Internal Plaster upto 27 Floor, External Plaster upto 23.4 Floor
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 55 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 39 Slab, Brickwork upto 36 Floor, Internal Plaster upto 27 Floor, External Plaster upto 23.4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 13.75
Excavation |  | 55 | 100% | 50.7% |  | 73.75% |  | Excavation in process | 27.5
Plinth |  | 55 | 100% |  |  |  |  | Excavation Completed | 55
RCC (Including podiums) |  | 39 | 69.64% |  |  |  |  | Footing in Process | 13.75
Brickwork | Brickwork & Internal Plaster | 36 | 65.45% |  |  |  |  | Footing Completed | 27.5
Internal Plaster | Brickwork & Internal Plaster | 27 | 49.09% |  |  |  |  | Basement 1 | 41.25
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23.4 | 42.55% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 55
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 21000 |  |  | 18000 to 19000 | Trupti | Staff case | B3802 | Area Changes and park
Recommended rate of the Mart in Basement Per Sq. Ft. |  |  |  |  | 26000
Recommended rate of the Retail of Ground Floor Per Sq. Ft. |  |  |  |  | 30000
Recommended rate of the Retail & Office above floor Per Sq. Ft. |  |  |  |  | 23000
Floor Rise Rate |  |  |  |  | 80/- from 12th Floor
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Corpus Charges |  |  |  |  | 200000
Advance Maintenance Charges |  |  |  |  | 150000 |  |  | 350000
Recommended rate of Parking |  |  |  |  | 1000000
Distressed valuation of the Property |  |  |  |  | 24000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Sale Tower A | Unit | 96 |  | 73896.5822 |  | 120044.4336
Sale Tower B | Unit | 96 |  | 75531.3109 |  | 122659.9995
Total |  | 192 |  | 149427.8932 |  | 242704.4331 |  |  | 927370.6116
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Sale Tower A |  | 405 |  | 220860.0576 |  | 342333.0893
Sale Tower B |  | 405 |  | 220860.0576 |  | 342333.0893
Total |  | 810 |  | 441720.1152 |  | 684666.1786
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Tower A + B
1st & 2nd Basement Floor For Parking & Water Tank & Flushing Tank
Tower A
Ground Floor For Commercial, Meter Room, Service Room & Double Heighted Entrance Lobby
1 |  | Unit | 3023.7152 | 0 | 4837.9444 | Ground Floor For Commercial, Meter Room, Service Room & Double Heighted Entrance Lobby
2 |  | Unit | 3004.5553 | 0 | 4807.2885
3 |  | Unit | 3921.6481 | 0 | 6274.637
1st Floor For Commercial & Service Area
1 |  | Unit | 3368.5938 | 0 | 5389.7501 | 1st Floor For Commercial & Service Area
2 |  | Unit | 3698.1875 | 0 | 5917.1
3 |  | Unit | 640.3504 | 0 | 1024.5606
4A |  | Unit | 774.7927 | 0 | 1239.6684
4B |  | Unit | 592.5582 | 0 | 948.0931
5 |  | Unit | 825.8141 | 0 | 1321.3025
- |  | Double Heighte Entrance Lobby Below
6 |  | Unit | 567.4781 | 0 | 907.9649
2nd Floor For Commercials & Parking
1 |  | Parking |  |  |  | 2nd Floor For Commercials & Parking
2
3 |  | Unit | 2468.7234 | 0 | 3949.9574
4A |  | Unit | 849.8178 | 0 | 1359.7085
4B |  | Unit | 758.9696 | 0 | 1214.3514
4C |  | Unit | 592.5582 | 0 | 948.0931
5 |  | Unit | 705.9031 | 0 | 1129.445
6 |  | Unit | 297.194 | 0 | 475.5105
7 |  | Unit | 286.5377 | 0 | 458.4603
8 |  | Unit | 291.2738 | 0 | 466.0381
9 |  | Unit | 457.1471 | 0 | 731.4353
3rd Floor For Commercials & Parking
1 |  | Unit | 1505.5607 | 1131.1888 | 4218.7991 | 3rd Floor For Commercials & Parking
2 |  | Unit | 404.1882 | 0 | 646.7011
3 |  | Unit | 557.3599 | 0 | 891.7759
4 |  | Unit | 780.4976 | 0 | 1248.7962
5 |  | Unit | 609.1348 | 0 | 974.6156
6 |  | Unit | 724.9554 | 0 | 1159.9286
7 |  | Unit | 322.92 | 0 | 516.672
8 |  | Unit | 286.9682 | 0 | 459.1492
9 |  | Unit | 321.413 | 0 | 514.2609
10 |  | Unit | 483.8418 | 0 | 774.1469
4th to 6th, 8th & 9th Floor For Commercials & Parking
1 |  | Unit | 1505.5607 | 0 | 2408.8971 | 4th to 6th, 8th & 9th Floor For Commercials & Parking
2 |  | Unit | 404.1882 | 0 | 646.7011
3 |  | Unit | 557.3599 | 0 | 891.7759
4 |  | Unit | 780.4976 | 0 | 1248.7962
5 |  | Unit | 609.1348 | 0 | 974.6156
6 |  | Unit | 724.9554 | 0 | 1159.9286
7 |  | Unit | 322.92 | 0 | 516.672
8 |  | Unit | 286.9682 | 0 | 459.1492
9 |  | Unit | 321.413 | 0 | 514.2609
10 |  | Unit | 483.8418 | 0 | 774.1469
7th Floor For Commercials & Parking (Part Refuge Area)
1 |  | Unit | 1505.5607 | 0 | 2408.8971 | 7th Floor For Commercials & Parking (Part Refuge Area)
2 |  | Unit | 404.1882 | 0 | 646.7011
3 |  | Unit | 557.3599 | 0 | 891.7759
4 |  | Unit | 780.4976 | 0 | 1248.7962
5 |  | Unit | 609.1348 | 0 | 974.6156
6 |  | Unit | 724.9554 | 0 | 1159.9286
7 |  | Unit | 211.1897 | 0 | 337.9035
8 |  | Refuge Area
9
10
10th Floor For Commercials & Parking
1 |  | Unit | 1505.5607 | 0 | 2408.8971 | 10th Floor For Commercials & Parking
2 |  | Unit | 404.1882 | 0 | 646.7011
3 |  | Unit | 557.3599 | 0 | 891.7759
4 |  | Unit | 780.4976 | 0 | 1248.7962
5 |  | Unit | 609.1348 | 0 | 974.6156
6 |  | Unit | 724.9554 | 0 | 1159.9286
7 |  | Unit | 322.92 | 0 | 516.672
8 |  | Unit | 286.9682 | 0 | 459.1492
9 |  | Unit | 321.413 | 0 | 514.2609
10 |  | Unit | 483.8418 | 0 | 774.1469
Tower B
Ground Floor For Commercial, Meter Room, Service Room & Double Heighted Entrance Lobby
1 |  | Unit | 2767.4244 | 0 | 4427.879 | Ground Floor For Commercial, Meter Room, Service Room & Double Heighted Entrance Lobby
2 |  | Unit | 2756.2298 | 0 | 4409.9677
3 |  | Unit | 3921.6481 | 0 | 6274.637
1st Floor For Commercial & Service Area
1 |  | Unit | 3368.5938 | 0 | 5389.7501 | 1st Floor For Commercial & Service Area
2 |  | Unit | 3698.1875 | 0 | 5917.1
3 |  | Unit | 640.3504 | 0 | 1024.5606
4A |  | Unit | 774.7927 | 0 | 1239.6684
4B |  | Unit | 618.3918 | 0 | 989.4269
5 |  | Unit | 886.0925 | 0 | 1417.748
- |  | Double Heighte Entrance Lobby Below
6 |  | Unit | 567.4781 | 0 | 907.9649
2nd Floor For Commercials & Parking
1 |  | Parking |  |  |  | 2nd Floor For Commercials & Parking
2
3 |  | Unit | 2468.7234 | 0 | 3949.9574
4A |  | Unit | 2226.5334 | 0 | 3562.4534
4B |  | Unit | 758.9696 | 0 | 1214.3514
4C |  | Unit | 618.3918 | 0 | 989.4269
5 |  | Unit | 750.5737 | 0 | 1200.918
6 |  | Unit | 310.8643 | 0 | 497.3829
7 |  | Unit | 281.9092 | 0 | 451.0547
8 |  | Unit | 302.899 | 0 | 484.6383
9 |  | Unit | 482.9807 | 0 | 772.7691
3rd Floor For Commercials & Parking
1 |  | Unit | 1505.5607 | 1131.1888 | 4218.7991 | 3rd Floor For Commercials & Parking
2 |  | Unit | 404.1882 | 0 | 646.7011
3 |  | Unit | 557.3599 | 0 | 891.7759
4 |  | Unit | 780.4976 | 0 | 1248.7962
5 |  | Unit | 623.2356 | 0 | 997.177
6 |  | Unit | 749.9279 | 0 | 1199.8846
7 |  | Unit | 327.0103 | 0 | 523.2165
8 |  | Unit | 286.1071 | 0 | 457.7714
9 |  | Unit | 326.6874 | 0 | 522.6998
10 |  | Unit | 508.0608 | 0 | 812.8973
4th to 6th, 8th & 9th Floor For Residential & Parking
1 |  | Unit | 1505.5607 | 0 | 2408.8971 | 4th to 6th, 8th & 9th Floor For Residential & Parking
2 |  | Unit | 404.1882 | 0 | 646.7011
3 |  | Unit | 557.3599 | 0 | 891.7759
4 |  | Unit | 780.4976 | 0 | 1248.7962
5 |  | Unit | 623.2356 | 0 | 997.177
6 |  | Unit | 749.9279 | 0 | 1199.8846
7 |  | Unit | 327.0103 | 0 | 523.2165
8 |  | Unit | 286.1071 | 0 | 457.7714
9 |  | Unit | 326.6874 | 0 | 522.6998
10 |  | Unit | 508.0608 | 0 | 812.8973
7th Floor (Part Refuge Area)
1 |  | Unit | 1505.5607 | 0 | 2408.8971 | 7th Floor (Part Refuge Area)
2 |  | Unit | 404.1882 | 0 | 646.7011
3 |  | Unit | 557.3599 | 0 | 891.7759
4 |  | Unit | 780.4976 | 0 | 1248.7962
5 |  | Unit | 623.2356 | 0 | 997.177
6 |  | Unit | 749.9279 | 0 | 1199.8846
7 |  | Unit | 229.0579 | 0 | 366.4927
8 |  | Refuge Area
9
10
10th Floor For Residential & Parking
1 |  | Unit | 1505.5607 | 0 | 2408.8971 | 10th Floor For Residential & Parking
2 |  | Unit | 404.1882 | 0 | 646.7011
3 |  | Unit | 557.3599 | 0 | 891.7759
4 |  | Unit | 780.4976 | 0 | 1248.7962
5 |  | Unit | 623.2356 | 0 | 997.177
6 |  | Unit | 749.9279 | 0 | 1199.8846
7 |  | Unit | 327.0103 | 0 | 523.2165
8 |  | Unit | 286.1071 | 0 | 457.7714
9 |  | Unit | 326.6874 | 0 | 522.6998
10 |  | Unit | 508.0608 | 0 | 812.8973
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Tower A
11th Floor For Amenities
12th, 13th, 15th to 20th, 22nd to 27th, 29th to 34th & 36th Floor For Residential | [7 empty] | 21
1 |  | 1 | 402.5736 | 0 | 623.9891 | 12th, 13th, 15th to 20th, 22nd to 27th, 29th to 34th & 36th Floor For Residential |  | 37.4385
2 |  | 1 | 402.5736 | 0 | 623.9891
3 |  | 2 | 594.3881 | 0 | 921.3015
4 |  | 2 | 594.3881 | 0 | 921.3015 |  |  | 55.1768
5 |  | 2 | 602.0305 | 0 | 933.1473
6 |  | 1 | 411.5077 | 0 | 637.837
7 |  | 2 | 630.2322 | 0 | 976.8599
8 |  | 2 | 630.2322 | 0 | 976.8599
9 |  | 1 | 413.1223 | 0 | 640.3396
10 |  | 2 | 581.5789 | 0 | 901.4473
11 |  | 2 | 580.7178 | 0 | 900.1126
12 |  | 2 | 582.44 | 0 | 902.7821
14th, 21st, 28th & 35th Floor (Part Refuge Area)
1 |  | 1 | 402.5736 | 0 | 623.9891 | 14th, 21st, 28th & 35th Floor (Part Refuge Area)
2 |  | 1 | 402.5736 | 0 | 623.9891
3 |  | 2 | 594.3881 | 0 | 921.3015
4 |  | 2 | 594.3881 | 0 | 921.3015
5 |  | 2 | 602.0305 | 0 | 933.1473 |  |  | 55.9025
6 |  | 1 | 411.5077 | 0 | 637.837 |  |  | 38.2155
7 |  | 2 | 630.2322 | 0 | 976.8599
8 |  | 2 | 630.2322 | 0 | 976.8599
9 |  | 1 | 413.1223 | 0 | 640.3396
10 |  | Refuge Area
11
12
37th to 41st & 43rd to 46th Floor | [7 empty] | 9
1 |  | 1 | 430.4524 | 0 | 667.2012 | 37th to 41st & 43rd to 46th Floor |  | 39.9974
2 |  | 1 | 430.4524 | 0 | 667.2012
3 |  | 2 | 640.8886 | 0 | 993.3773 |  |  | 59.5196
4 |  | 2 | 640.8886 | 0 | 993.3773
5 |  | 2 | 648.531 | 0 | 1005.223
6 |  | 1 | 455.8554 | 0 | 706.5759
7 |  | 2 | 665.861 | 0 | 1032.0846
8 |  | 2 | 665.861 | 0 | 1032.0846
9 |  | 1 | 454.1332 | 0 | 703.9064
10 |  | 2 | 624.6349 | 0 | 968.1841
11 |  | 2 | 623.7738 | 0 | 966.8494
12 |  | 2 | 625.496 | 0 | 969.5189
42nd Floor (Part Refuge Area) | [7 empty] | 1
1 |  | 1 | 430.4524 | 0 | 667.2012 | 42nd Floor (Part Refuge Area)
2 |  | 1 | 430.4524 | 0 | 667.2012
3 |  | 2 | 640.8886 | 0 | 993.3773
4 |  | 2 | 640.8886 | 0 | 993.3773
5 |  | 2 | 648.531 | 0 | 1005.223
6 |  | 1 | 455.8554 | 0 | 706.5759
7 |  | 2 | 665.861 | 0 | 1032.0846
8 |  | 2 | 665.861 | 0 | 1032.0846
9 |  | 1 | 454.1332 | 0 | 703.9064
10 |  | Refuge Area
11
12
Tower B
11th Floor For Amenities
12th, 13th, 15th to 20th, 22nd to 27th, 29th to 34th & 36th Floor For Residential | [7 empty] | 21
1 |  | 1 | 402.5736 | 0 | 623.9891 | 12th, 13th, 15th to 20th, 22nd to 27th, 29th to 34th & 36th Floor For Residential
2 |  | 1 | 402.5736 | 0 | 623.9891 |  |  | 37.4259
3 |  | 2 | 594.3881 | 0 | 921.3015
4 |  | 2 | 594.3881 | 0 | 921.3015 |  |  | 55.1768
5 |  | 2 | 602.0305 | 0 | 933.1473
6 |  | 1 | 411.5077 | 0 | 637.837
7 |  | 2 | 630.2322 | 0 | 976.8599
8 |  | 2 | 630.2322 | 0 | 976.8599
9 |  | 1 | 413.1223 | 0 | 640.3396
10 |  | 2 | 581.5789 | 0 | 901.4473
11 |  | 2 | 580.7178 | 0 | 900.1126
12 |  | 2 | 582.44 | 0 | 902.7821
14th, 21st, 28th & 35th Floor (Part Refuge Area) | [7 empty] | 4
1 |  | 1 | 402.5736 | 0 | 623.9891 | 14th, 21st, 28th & 35th Floor (Part Refuge Area)
2 |  | 1 | 402.5736 | 0 | 623.9891
3 |  | 2 | 594.3881 | 0 | 921.3015
4 |  | 2 | 594.3881 | 0 | 921.3015
5 |  | 2 | 602.0305 | 0 | 933.1473
6 |  | 1 | 411.5077 | 0 | 637.837
7 |  | 2 | 630.2322 | 0 | 976.8599
8 |  | 2 | 630.2322 | 0 | 976.8599 |  |  | 57.872
9 |  | 1 | 413.1223 | 0 | 640.3396
10 |  | Refuge Area
11
12
G
1 |  |  |  | 0 | 0 | G
2 |  |  |  | 0 | 0 | G
3 |  |  |  | 0 | 0 | G
4 |  |  |  | 0 | 0 | G
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
37th, 39th to 41st & 43rd to 46th Floor | [7 empty] | 9
1 |  | 1 | 430.4524 | 0 | 667.2012 | 37th, 39th to 41st & 43rd to 46th Floor
2 |  | 1 | 430.4524 | 0 | 667.2012
3 |  | 2 | 640.8886 | 0 | 993.3773
4 |  | 2 | 640.8886 | 0 | 993.3773
5 |  | 2 | 648.531 | 0 | 1005.223
6 |  | 1 | 455.8554 | 0 | 706.5759
7 |  | 2 | 665.861 | 0 | 1032.0846
8 |  | 2 | 665.861 | 0 | 1032.0846
9 |  | 1 | 454.1332 | 0 | 703.9064
10 |  | 2 | 624.6349 | 0 | 968.1841
11 |  | 2 | 623.7738 | 0 | 966.8494
12 |  | 2 | 625.496 | 0 | 969.5189
38th Floor | [7 empty] | 9
1 |  | 1 | 430.4524 | 0 | 667.2012 | 38th Floor
2 |  | 1 | 430.4524 | 0 | 728 |  |  | 16678400 | 12508800
3 |  | 2 | 640.8886 | 0 | 993.3773 |  |  | Sale area changes to 728 from 667 for staff case B3802 by Trupti 27/03/2025
4 |  | 2 | 640.8886 | 0 | 993.3773
5 |  | 2 | 648.531 | 0 | 1005.223
6 |  | 1 | 455.8554 | 0 | 706.5759
7 |  | 2 | 665.861 | 0 | 1032.0846
8 |  | 2 | 665.861 | 0 | 1032.0846
9 |  | 1 | 454.1332 | 0 | 703.9064
10 |  | 2 | 624.6349 | 0 | 968.1841
11 |  | 2 | 623.7738 | 0 | 966.8494
12 |  | 2 | 625.496 | 0 | 969.5189
42nd Floor (Part Refuge Area) | [7 empty] | 1
1 |  | 1 | 430.4524 | 0 | 667.2012 | 42nd Floor (Part Refuge Area)
2 |  | 1 | 430.4524 | 0 | 667.2012
3 |  | 2 | 640.8886 | 0 | 993.3773
4 |  | 2 | 640.8886 | 0 | 993.3773
5 |  | 2 | 648.531 | 0 | 1005.223
6 |  | 1 | 455.8554 | 0 | 706.5759
7 |  | 2 | 665.861 | 0 | 1032.0846
8 |  | 2 | 665.861 | 0 | 1032.0846 |  |  | 57.872
9 |  | 1 | 454.1332 | 0 | 703.9064
10 |  | Refuge Area
11
12
Remarks:
1 | Tower A & B = Construction work is in process at the time of visit.
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet
6 | We have considered proposed No. of Floor for Stage Calculation.
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | High Tension Line Passing Near by the Greenairy Project. Please Provide Transmission Line Noc (Power Noc).
11 | We have updated revised Approved Plans & C.C (on 19/03/2025).
12 | We have changed the promoter name "Saroj Landmark Realty Llp" with reference to RERA Certificate & CC, which is provided in the mail by bank officials.
13 | Please check for Fire Noc & Environmental Clearance Certificate. | [6 empty] | We have refered visit data dated 08/03/2025.
14 | Recommended Rates / Other charges of the Property have been revised on 27/03/2025 & 10/09/2025
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Rahul Salve |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Greenairy
Remark No.10 :
Layout :
Google Map :
Formulas:
Magathane = [Magathane, row above]
N
N
High Tension Line
Site
HT Lines
Wing B
Tower A
Tower B

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value |  |  | 418 CA
Magic Brick |  |  |  | 0 | #DIV/0! |  |  |  | 19576.9854
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0! |  | 2 | 16768.2927
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted