## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 12/09/2025
CPC Name: |  |  |  |  | Axis Kalina
Date Of Property Visit |  |  |  |  | 2025-09-10
Name of the builder group |  |  |  |  | M/s.Omkar
Name of the builder company |  |  |  |  | M/s.Omkar Ventures Pvt.Ltd
Name of the Project |  |  |  |  | Lawns & Beyond |  |  |  | as per watchman work Stop 13/09/2024
RERA Number |  | Lawns And Beyond - Phase 1 (A & B) = P51800014195 Lawns And Beyond - Phase 2 (C to H) = P51800014105 Lawns And Beyond - Phase 3 (I to K) = P51800014037
Docouments Provided |  |  |  |  | 1. Copy of Plans. 2. Copy of Revised LOI. 3. Copy Of Intimation.
Approved Layout Plan : |  | KE/MCGM/0026/200506161/AP/S1 |  |  |  |  | Dated | 29/09/2017.
Project location details |  | Lawn & Beyond Omkar international District, Plot No. 431, CTS. Nos. 3 of Village Ismalia, CTS. Nos. 324, 325, 326, 327(Part), 327/1 To 4, 328/1 To 4 of Village Mogra, CTS. Nos. 135(Part), 135/1 To 25, 135/27 To 29, 135/31 To 93, 135/99 To 141, 135/143 To 213, 135/219 To 242, 135/247 To 297, 135/316 To 318, 135/332 To 335, W. E. Highway, Majaswadi, Andheri East, Mumbai.
CTS No | CTS. Nos. 324, 325, 326, 327(Part), 327/1 To 4, 328/1 To 4 of Village Mogra, CTS. Nos. 135(Part), 135/1 To 25, 135/27 To 29, 135/31 To 93, 135/99 To 141, 135/143 To 213, 135/219 To 242, 135/247 To 297, 135/316 To 318, 135/332 To 335. |  |  | Plot No | 431 | Locality | Majaswadi.
Road | W. E. Highway. |  |  |  | District | Mumbai.
City | Andheri |  |  |  | Pin Code | 400 060.
Near by Landmark |  | Lal Building |  |  | Distance from city centre: |  | Abour 3.6 Km from Jogeshwari Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Building |  | Road |  | Road |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | Latitude |  | 19.1319 |  | Longitude |  | 72.8557
Location Link |  | https://goo.gl/maps/yYe3RkCxoTEgz6sM6
Approval details:
Approved usage of the Property: Residential + Commercial. (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 110006.83 (Net plot Area = Slum Area + Non slum Area)
Permissible FSI |  |  |  |  | 3 + 3 ( Slum + Non Slum)
Permissible TDR/Paid FSI |  |  |  |  | NA
Total FSI availaible for the project |  |  |  |  | 6
Total Approved Builtup area of the project in Sq. Mt. (Sale BUA) |  |  |  |  | 180288.52
Total number of Buildings |  |  |  |  | 1(13 Wings )
Approval Detail : Plan approval
Layout Approval No |  | KE/MCGM/0026/200506161/AP/S1 |  |  |  | Dated | 29/09/2017.
Building plan approval No |  | KE/MCGM/0026/200506161/AP/S1 |  |  |  | Dated | 29/09/2017.
Revised LOI |  | SRA/ENG/1115/KE/ML/PL/LOI |  |  |  | Dated | 17/05/2017.
Intimation |  | SRA/ENG/KE/MCGM/0026/20050616/ML/PL/AP |  |  |  | Dated | 29/09/2017.
C.certificate No |  | KE/MCGM/0026/200506161/ML/PL/AP/S1 Valid Upto : This CC is re-endored upto Plinth level i.e. upto top of basement for wing A to K and portion of fitness center except wing L to P as per amended plans approved dated 10/12/2018. |  |  |  | Dated | 09/01/2019. | Expiry date: One year from date of issue
C.certificate No |  | KE/MCGM/0026/200506161/ML/PL/AP/S1 Valid Upto : This CC extended upto 6th Floors i.e 1st Floor/Podium + 2nd to 6th floor for wing A,B,C,D & K by regularizing the work done beyond C.C as per approved amended plans dated 10/12/2018. |  |  |  | Dated | 28/09/2020. | Expiry date: One year from date of issue
O. Certificate No.: NA |  | NA |  |  | Date of approval: NA | Dated | NA
Commencement date of construction |  |  | 28/09/2020. |  | Expected Completion |  | Phase I = 31/03/2026 Phase II & III = 31/03/2027
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 180288.52 |  | Approved no of units residential |  |  | 610
Approved no of Floors |  |  | All wings = B + Lower Gr. + Gr. + 1st to 19th Floor.
Quality of construction: Good |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: Building No.1-Wing A & B = B + Lower Gr. + Gr. + 1st to 19th Floor. | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 21 Slab completed, Brickwork upto 19 Floor completed, Internal Plaster upto 12 Floor completed, External Plaster upto 12 Floor completed
Ground |  | 2 | Podium |  | 0 |  | Floors | 19 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 21 Slab completed, Brickwork upto 19 Floor completed, Internal Plaster upto 12 Floor completed, External Plaster upto 12 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 19 | 100% |  | 68.55% |  | 86.32%
Plinth |  | 19 | 100%
RCC |  | 21 | 100% | [5 empty] | Excavation in process |  | 9.5 | 2%
Brickwork | Brickwork & Internal Plaster | 19 | 100% | [5 empty] | Excavation Completed |  | 19 | 4%
Internal Plaster | Brickwork & Internal Plaster | 12 | 63.16% | [8 empty] | 8%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 63.16% | [5 empty] | Footing in Process |  | 4.75 | 15%
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 9.5 | 20%
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 14.25 | 30%
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 19
Possession |  | 0 | 0%
Construction details: Building No.1-Wing B = B + Lower Gr. + Gr. + 1st to 19th Floor. | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 12 Slab completed, Brickwork upto 2 Floor completed , External Plaster upto 2 Floor completed
Ground |  | 2 | Podium |  | 0 |  | Floors | 19 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 12 Slab completed, Brickwork upto 2 Floor completed , External Plaster upto 2 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 19 | 100% |  | 34.7% |  | 63.2%
Plinth |  | 19 | 100%
RCC |  | 12 | 57.14% | [5 empty] | Excavation in process |  | 9.5 | 2%
Brickwork | Brickwork & Internal Plaster | 2 | 10.53% | [5 empty] | Excavation Completed |  | 19 | 4%
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [8 empty] | 8%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 10.53% | [5 empty] | Footing in Process |  | 4.75 | 15%
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 9.5 | 20%
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 14.25 | 30%
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 19
Possession |  | 0 | 0%
Construction details: Building No.1-Wing C & D = B + Lower Gr. + Gr. + 1st to 19th Floor. | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 21 Slab completed, Brickwork upto 19 Floor completed, Internal Plaster upto 19 Floor completed, External Plaster upto 18 Floor completed
Ground |  | 2 | Podium |  | 0 |  | Floors | 19 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 21 Slab completed, Brickwork upto 19 Floor completed, Internal Plaster upto 19 Floor completed, External Plaster upto 18 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 19 | 100% |  | 74.47% |  | 89.74%
Plinth |  | 19 | 100%
RCC |  | 21 | 100% | [5 empty] | Excavation in process |  | 9.5 | 2%
Brickwork | Brickwork & Internal Plaster | 19 | 100% | [5 empty] | Excavation Completed |  | 19 | 4%
Internal Plaster | Brickwork & Internal Plaster | 19 | 100% | [8 empty] | 8%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 18 | 94.74% | [5 empty] | Footing in Process |  | 4.75 | 15%
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 9.5 | 20%
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 14.25 | 30%
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 19
Possession |  | 0 | 0%
Construction details: Building No.1-Wing D = B + Lower Gr. + Gr. + 1st to 19th Floor. | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 12 Slab completed, Brickwork upto 9 Floor completed, Internal Plaster upto 2 Floor completed, External Plaster upto 9 Floor completed
Ground |  | 2 | Podium |  | 0 |  | Floors | 19 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 12 Slab completed, Brickwork upto 9 Floor completed, Internal Plaster upto 2 Floor completed, External Plaster upto 9 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 19 | 100% |  | 41.94% |  | 67.41%
Plinth |  | 19 | 100%
RCC |  | 12 | 57.14% | [5 empty] | Excavation in process |  | 9.5 | 2%
Brickwork | Brickwork & Internal Plaster | 9 | 47.37% | [5 empty] | Excavation Completed |  | 19 | 4%
Internal Plaster | Brickwork & Internal Plaster | 2 | 10.53% | [8 empty] | 8%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9 | 47.37% | [5 empty] | Footing in Process |  | 4.75 | 15%
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 9.5 | 20%
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 14.25 | 30%
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 19
Possession |  | 0 | 0%
Construction details: |  | Building No.1- Wing E = B + Lower Gr. + Gr. + 1st to 19th Floor. | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 8 Slab Completed
Basement | 2 | Ground | 1 | Podium |  | 0 | Floors | 19
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 8 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 4.75 |  |  |  | Building No.1-Wing Wing E = B + Lower Gr. + Gr. + 1st to 19th Floor.
Excavation |  | 19 | 100% |  | 26% |  | 57% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% | [5 empty] | Excavation Completed | 19
RCC (Including podiums) |  | 8 | 40% | [5 empty] | Footing in Process | 4.75 | 9.5 | 2%
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 9.5 | 19 | 4%
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 14.25 |  | 8%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0 | 4.75 | 15%
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0 | 9.5 | 20%
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0 | 14.25 | 30%
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 0 | 19
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 19
Construction details: Building No.1-Wing F = B + Lower Gr. + Gr. + 1st to 19th Floor. | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 13 Slab completed, Brickwork upto 11 Floor completed, Internal Plaster upto 7.7 Floor completed, External Plaster upto 7.7 Floor completed
Ground |  | 2 | Podium |  | 0 |  | Floors | 19 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 13 Slab completed, Brickwork upto 11 Floor completed, Internal Plaster upto 7.7 Floor completed, External Plaster upto 7.7 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 19 | 100% |  | 46.2% |  | 70.52%
Plinth |  | 19 | 100%
RCC |  | 13 | 61.9% | [5 empty] | Excavation in process |  | 9.5 | 2%
Brickwork | Brickwork & Internal Plaster | 11 | 57.89% | [5 empty] | Excavation Completed |  | 19 | 4%
Internal Plaster | Brickwork & Internal Plaster | 7.7 | 40.53% | [8 empty] | 8%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7.7 | 40.53% | [5 empty] | Footing in Process |  | 4.75 | 15%
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 9.5 | 20%
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 14.25 | 30%
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 19
Possession |  | 0 | 0%
Construction details: Building No.1-Wing H = B + Lower Gr. + Gr. + 1st to 19th Floor. | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 2 Slab completed | [5 empty] | 16
Ground |  | 2 | Podium |  | 0 |  | Floors | 19 | All work Completed. Wait For OC. | [5 empty] | 49.5
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 2 Slab completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 19 | 100% |  | 13.81% |  | 47.86%
Plinth |  | 19 | 100%
RCC |  | 2 | 9.524% | [5 empty] | Excavation in process |  | 9.5 | 2%
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Excavation Completed |  | 19 | 4%
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [8 empty] | 8%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Footing in Process |  | 4.75 | 15%
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 9.5 | 20%
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 14.25 | 30%
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 19
Possession |  | 0 | 0%
Construction details: Building No.1-Wing I = B + Lower Gr. + Gr. + 1st to 19th Floor. | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 2 Slab completed | [5 empty] | 16
Ground |  | 2 | Podium |  | 0 |  | Floors | 19 | All work Completed. Wait For OC. | [5 empty] | 49.5
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 2 Slab completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 19 | 100% |  | 13.81% |  | 47.86%
Plinth |  | 19 | 100%
RCC |  | 2 | 9.524% | [5 empty] | Excavation in process |  | 9.5 | 2%
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Excavation Completed |  | 19 | 4%
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [8 empty] | 8%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Footing in Process |  | 4.75 | 15%
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 9.5 | 20%
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 14.25 | 30%
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 19
Possession |  | 0 | 0%
Construction details: Building No.1-Wing J = B + Lower Gr. + Gr. + 1st to 19th Floor. | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 21 Slab completed, Brickwork upto 19 Floor completed, Internal Plaster upto 13.3 Floor completed, External Plaster upto 13.3 Floor completed
Ground |  | 2 | Podium |  | 0 |  | Floors | 19 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 21 Slab completed, Brickwork upto 19 Floor completed, Internal Plaster upto 13.3 Floor completed, External Plaster upto 13.3 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 19 | 100% |  | 69.75% |  | 87%
Plinth |  | 19 | 100%
RCC |  | 21 | 100% | [5 empty] | Excavation in process |  | 9.5 | 2%
Brickwork | Brickwork & Internal Plaster | 19 | 100% | [5 empty] | Excavation Completed |  | 19 | 4%
Internal Plaster | Brickwork & Internal Plaster | 13.3 | 70% | [8 empty] | 8%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 13.3 | 70% | [5 empty] | Footing in Process |  | 4.75 | 15%
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 9.5 | 20%
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 14.25 | 30%
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 19
Possession |  | 0 | 0%
Construction details: Building No.1-Wing K = B + Lower Gr. + Gr. + 1st to 19th Floor. | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 21 Slab completed, Brickwork upto 19 Floor completed, Internal Plaster upto 15 Floor completed, External Plaster upto 14 Floor completed
Ground |  | 2 | Podium |  | 0 |  | Floors | 19 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 21 Slab completed, Brickwork upto 19 Floor completed, Internal Plaster upto 15 Floor completed, External Plaster upto 14 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 19 | 100% |  | 70.79% |  | 87.63%
Plinth |  | 19 | 100%
RCC |  | 21 | 100% | [5 empty] | Excavation in process |  | 9.5 | 2%
Brickwork | Brickwork & Internal Plaster | 19 | 100% | [5 empty] | Excavation Completed |  | 19 | 4%
Internal Plaster | Brickwork & Internal Plaster | 15 | 78.95% | [8 empty] | 8%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 73.68% | [5 empty] | Footing in Process |  | 4.75 | 15%
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 9.5 | 20%
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 14.25 | 30%
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 19
Possession |  | 0 | 0%
Construction details: Building No.1-Wing K (Part II)= B + Lower Gr. + Gr. + 1st to 19th Floor. | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 18 Slab completed, Brickwork upto 16 Floor completed, Internal Plaster upto 12 Floor completed, External Plaster upto 12 Floor completed
Ground |  | 2 | Podium |  | 0 |  | Floors | 19 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 18 Slab completed, Brickwork upto 16 Floor completed, Internal Plaster upto 12 Floor completed, External Plaster upto 12 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 19 | 100% |  | 61.65% |  | 81.24%
Plinth |  | 19 | 100%
RCC |  | 18 | 85.71% | [5 empty] | Excavation in process |  | 9.5 | 2%
Brickwork | Brickwork & Internal Plaster | 16 | 84.21% | [5 empty] | Excavation Completed |  | 19 | 4%
Internal Plaster | Brickwork & Internal Plaster | 12 | 63.16% | [8 empty] | 8%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 63.16% | [5 empty] | Footing in Process |  | 4.75 | 15%
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 9.5 | 20%
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 14.25 | 30%
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 19
Possession |  | 0 | 0%
Construction details: Average Building No.1 - Wing K = (Part I) & (Part II) | [8 empty] | #REF!
Progress % |  | 66.22% |  | Disbursement% |  |  | 84.44% |  | #REF!
Construction details: Building No.1 - Wing G, L & M = B + Lower Gr. + Gr. + 1st to 19th Floor. | [8 empty] | Work not yet Started. | [5 empty] | 16
Ground |  | 2 | Podium |  | 0 |  | Floors | 19 | All work Completed. Wait For OC. | [5 empty] | 49.5
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 0 | 0% |  | 0% |  | 0%
Plinth |  | 0 | 0%
RCC |  | 0 | 0% | [5 empty] | Excavation in process |  | 9.5 | 2%
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Excavation Completed |  | 19 | 4%
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [8 empty] | 8%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Footing in Process |  | 4.75 | 15%
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 9.5 | 20%
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 14.25 | 30%
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 19
Possession |  | 0 | 0%
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 19000
Floor rise rate Per Sq. Ft. | [5 empty] | 200/- From 1st Floor
Recommended rate of Parking | [5 empty] | 5,00,000/-
Club Charges | [5 empty] | 10,00,000/-
1 Year Advance Maintenance | [5 empty] | 90000/-
Other Charges | [5 empty] | 1,25,600/-
Distress valuation of the property Per Sq. Ft. | [5 empty] | 15200
Building details floor wise
Details of Flats in Building
Sr. | Flat No. | Description | RERA Carpet/ Net Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area | PLC Y/N
Basement Floor For Parking (All Wings)
Stilt/Ground/Lower Ground Floor For Parking & Commercial (All Wings)
1st/Podium Floor For Residential, Parking & Commercial.
Sale Building- 1(Wing A)
1st Floor For Residential & Amenities
1 | 1 | 2BHK | 806 | 0 | 806 | 0 | 1168.7 | NA
2 | 2 | Welfare Hall/So. Office
3 | 3 | 2BHK | 806 | 0 | 806 | 0 | 1168.7 | NA
4 | 4 | 2BHK | 806 | 0 | 806 | 0 | 1168.7 | NA
2nd to 7th, 9th to 14th & 16th to 19th Floor
5 | 1 | 2BHK | 806 | 0 | 806 | 0 | 1168.7 | NA
6 | 2 | 3BHK | 1102 | 0 | 1102 | 0 | 1597.9 | NA |  | 21391.2895
7 | 3 | 2BHK | 806 | 0 | 806 | 0 | 1168.7 | NA |  | 22205300 | 1000000 | 60.0667 | 233740
8 | 4 | 2BHK | 806 | 0 | 806 | 0 | 1168.7 | NA |  | 3272360
8th Floor
9 | 1 | 2BHK | 806 | 0 | 806 | 0 | 1168.7 | NA
10 | 2 | 3BHK | 1102 | 0 | 1102 | 0 | 1597.9 | NA
11 | 3 | Refuge Area
12 | 4 | 2BHK | 806 | 0 | 806 | 0 | 1168.7 | NA
15th Floor
13 | 1 | 2BHK | 806 | 0 | 806 | 0 | 1168.7 | NA
14 | 2 | 3BHK | 1102 | 0 | 1102 | 0 | 1597.9 | NA
15 | 3 | Refuge Area
16 | 4 | 2BHK | 806 | 0 | 806 | 0 | 1168.7 | NA
Sale Building- 1(Wing B)
1st Floor
17 | 1 | 2BHK | 794 | 0 | 794 | 0 | 1151.3 | NA
18 | 2 | 2BHK | 794 | 0 | 794 | 0 | 1151.3 | NA
19 | 3 | 2BHK | 794 | 0 | 794 | 0 | 1151.3 | NA
20 | 4 | 2BHK | 794 | 0 | 794 | 0 | 1151.3 | NA
2nd to 7th, 9th to 14th & 16th to 19th Floor
21 | 1 | 2BHK | 794 | 0 | 794 | 0 | 1151.3 | NA
22 | 2 | 2BHK | 794 | 0 | 794 | 0 | 1151.3 | NA
23 | 3 | 2BHK | 794 | 0 | 794 | 0 | 1151.3 | NA
24 | 4 | 2BHK | 794 | 0 | 794 | 0 | 1151.3 | NA
8th Floor
25 | 1 | 2BHK | 794 | 0 | 794 | 0 | 1151.3 | NA
26 | 2 | Refuge Area
27 | 3 | 2BHK | 794 | 0 | 794 | 0 | 1151.3 | NA
28 | 4 | 2BHK | 794 | 0 | 794 | 0 | 1151.3 | NA
15th Floor
29 | 1 | 2BHK | 794 | 0 | 794 | 0 | 1151.3 | NA
30 | 2 | Refuge Area
31 | 3 | 2BHK | 794 | 0 | 794 | 0 | 1151.3 | NA
32 | 4 | 2BHK | 794 | 0 | 794 | 0 | 1151.3 | NA
Sale Building- 1(Wing C)
1st Floor
33 | 1 | 2BHK | 497.1892 | 0 | 497.1892 | 0 | 720.9243 | NA
34 | 2 | 3BHK | 639 | 0 | 639 | 0 | 926.55 | NA
35 | 3 | 2BHK | 494 | 0 | 494 | 0 | 716.3 | NA
36 | 4 | 2BHK | 494 | 0 | 494 | 0 | 716.3 | NA
2nd to 7th, 9th to 14th & 16th to 19th Floor
37 | 1 | 2BHK | 497.1892 | 0 | 497.1892 | 0 | 720.9243 | NA
38 | 2 | 3BHK | 639 | 0 | 639 | 0 | 926.55 | NA
39 | 3 | 2BHK | 494 | 0 | 494 | 0 | 716.3 | NA
40 | 4 | 2BHK | 494 | 0 | 494 | 0 | 716.3 | NA
8th Floor
41 | 1 | 2BHK | 497.1892 | 0 | 497.1892 | 0 | 720.9243 | NA
42 | 2 | 3BHK | 639 | 0 | 639 | 0 | 926.55 | NA
43 | 3 | 2BHK | 494 | 0 | 494 | 0 | 716.3 | NA
44 | 4 | Refuge Area
15th Floor
45 | 1 | 2BHK | 497.1892 | 0 | 497.1892 | 0 | 720.9243 | NA
46 | 2 | 3BHK | 639 | 0 | 639 | 0 | 926.55 | NA
47 | 3 | 2BHK | 494 | 0 | 494 | 0 | 716.3 | NA
48 | 4 | Refuge Area
Sale Building- 1(Wing D)
1st Floor
49 | 1 | 1BHK | 354.1356 | 0 | 354.1356 | 0 | 513.4966 | NA
50 | 2 | 1BHK | 354.1356 | 0 | 354.1356 | 0 | 513.4966 | NA
51 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
52 | 4 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
2nd to 7th, 9th to 14th & 16th to 19th Floor
53 | 1 | 1BHK | 354.1356 | 0 | 354.1356 | 0 | 513.4966 | NA
54 | 2 | 1BHK | 354.1356 | 0 | 354.1356 | 0 | 513.4966 | NA
55 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
56 | 4 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
8th & 15th Floor
57 | 1 | 1BHK | 354.1356 | 0 | 354.1356 | 0 | 513.4966 | NA
58 | 2 | 1BHK | 354.1356 | 0 | 354.1356 | 0 | 513.4966 | NA
59 | 3 | Refuge Area
60 | 4 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
Sale Building- 1(Wing E)
1st Floor
61 | 1 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
62 | 2 | 3BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
63 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
64 | 4 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
2nd to 7th, 9th to 14th & 16th to 19th Floor
65 | 1 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
66 | 2 | 3BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
67 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
68 | 4 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
8th Floor
69 | 1 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
70 | 2 | 3BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
71 | 3 | Refuge Area
72 | 4 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
15th Floor
73 | 1 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
74 | 2 | 3BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
75 | 3 | Refuge Area
76 | 4 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
Sale Building- 1(Wing F)
1st Floor
77 | 1 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
78 | 2 | Society Office
79 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
80 | 4 | 3BHK | 635.5066 | 0 | 635.5066 | 0 | 921.4845 | NA
81 | 5 | 3BHK | 635.5066 | 0 | 635.5066 | 0 | 921.4845 | NA
82 | 6 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
2nd to 7th, 9th to 14th & 16th to 19th Floor
83 | 1 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
84 | 2 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
85 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
86 | 4 | 3BHK | 635.5066 | 0 | 635.5066 | 0 | 921.4845 | NA
87 | 5 | 3BHK | 635.5066 | 0 | 635.5066 | 0 | 921.4845 | NA
88 | 6 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
8th Floor
89 | 1 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
90 | 2 | Refuge Area
91 | 3
92 | 4 | 3BHK | 635.5066 | 0 | 635.5066 | 0 | 921.4845 | NA
93 | 5 | 3BHK | 635.5066 | 0 | 635.5066 | 0 | 921.4845 | NA
94 | 6 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
15th Floor
95 | 1 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
96 | 2 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
97 | 3 | Refuge Area
98 | 4 | 3BHK | 635.5066 | 0 | 635.5066 | 0 | 921.4845 | NA
99 | 5 | 3BHK | 635.5066 | 0 | 635.5066 | 0 | 921.4845 | NA
100 | 6 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
Sale Building- 1(Wing G)
1st Floor
101 | 1 | 3BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
102 | 2 | 2BHK | 497.1892 | 0 | 497.1892 | 0 | 720.9243 | NA
103 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
104 | 4 | Society Office
105 | 5 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
106 | 6 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
2nd to 7th, 9th to 14th & 16th to 19th Floor
107 | 1 | 3BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
108 | 2 | 2BHK | 497.1892 | 0 | 497.1892 | 0 | 720.9243 | NA
109 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
110 | 4 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
111 | 5 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
112 | 6 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
8th Floor
113 | 1 | 3BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
114 | 2 | 2BHK | 497.1892 | 0 | 497.1892 | 0 | 720.9243 | NA
115 | 3 | Refuge Area
116 | 4
117 | 5 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
118 | 6 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
15th Floor
119 | 1 | 3BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
120 | 2 | 2BHK | 497.1892 | 0 | 497.1892 | 0 | 720.9243 | NA
121 | 3 | Refuge Area
122 | 4 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
123 | 5 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
124 | 6 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
Sale Building- 1(Wing H)
1st Floor
125 | 1 | 1BHK | 354.1356 | 0 | 354.1356 | 0 | 513.4966 | NA
126 | 2 | 1BHK | 354.1356 | 0 | 354.1356 | 0 | 513.4966 | NA
127 | 3 | Society Office/Meter Room
128 | 4 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
2nd to 7th, 9th to 14th & 16th to 19th Floor
129 | 1 | 1BHK | 354.1356 | 0 | 354.1356 | 0 | 513.4966 | NA
130 | 2 | 1BHK | 354.1356 | 0 | 354.1356 | 0 | 513.4966 | NA
131 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
132 | 4 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
8th & 15th Floor
133 | 1 | 1BHK | 354.1356 | 0 | 354.1356 | 0 | 513.4966 | NA
134 | 2 | 1BHK | 354.1356 | 0 | 354.1356 | 0 | 513.4966 | NA
135 | 3 | Refuge Area
136 | 4 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
Sale Building- 1(Wing I)
1st Floor
137 | 1 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
2nd & 3rd Floor
138 | 1 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
139 | 4 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
4th to 7th, 9th to 14th & 16th to 19th Floor
140 | 1 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
141 | 2 | 3BHK | 644.7636 | 0 | 644.7636 | 0 | 934.9072 | NA
142 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
143 | 4 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
8th Floor
144 | 1 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
145 | 2 | 3BHK | 644.7636 | 0 | 644.7636 | 0 | 934.9072 | NA
146 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
147 | 4 | Refuge Area
15th Floor
148 | 1 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
149 | 2 | 3BHK | 644.7636 | 0 | 644.7636 | 0 | 934.9072 | NA
150 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
151 | 4 | Refuge Area
Sale Building- 1(Wing J)
1st Floor
152 | 4 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
2nd Floor
153 | 4 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
154 | 7 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
3rd Floor
155 | 4 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
156 | 5 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
157 | 6 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
158 | 7 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
4th to 7th, 9th to 14th & 16th to 19th Floor
159 | 1 | 2BHK | 497.1892 | 0 | 497.1892 | 0 | 720.9243 | NA
160 | 2 | 2BHK | 497.1892 | 0 | 497.1892 | 0 | 720.9243 | NA
161 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
162 | 4 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
163 | 5 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
164 | 6 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
165 | 7 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
166 | 8 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
8th Floor
167 | 1 | 2BHK | 497.1892 | 0 | 497.1892 | 0 | 720.9243 | NA
168 | 2 | 2BHK | 497.1892 | 0 | 497.1892 | 0 | 720.9243 | NA
169 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
170 | 4 | Refuge Area
171 | 5
172 | 6 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
173 | 7 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
174 | 8 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
15th Floor
175 | 1 | 2BHK | 497.1892 | 0 | 497.1892 | 0 | 720.9243 | NA
176 | 2 | 2BHK | 497.1892 | 0 | 497.1892 | 0 | 720.9243 | NA
177 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
178 | 4 | Refuge Area
179 | 5
180 | 6 | 1BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
181 | 7 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
182 | 8 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
Sale Building- 1(Wing K)
1st Floor
183 | 1 | Lobby
184 | 2 | Society Office
185 | 3 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
186 | 4 | 3BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
187 | 5 | 3BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
188 | 6 | 2BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
2nd Floor
189 | 3 | 2 BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
190 | 4 | 3 BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
191 | 5 | 3 BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
192 | 6 | 2 BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
3rd To 7th, 9th To 14th, 16th To 19th Floor
193 | 1 | 1 BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
194 | 2 | 1 BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
195 | 3 | 2 BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
196 | 4 | 3 BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
197 | 5 | 3 BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
198 | 6 | 2 BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA |  | 34919.6255
8th Floor
199 | 1 | 1 BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
200 | 2 | Refuge Area
201 | 3
202 | 4 | 3 BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
203 | 5 | 3 BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
204 | 6 | 2 BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
15th Floor
205 | 1 | 1 BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
206 | 2 | 1 BHK | 346.9237 | 0 | 346.9237 | 0 | 503.0394 | NA
207 | 3 | Refuge Area
208 | 4 | 3 BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
209 | 5 | 3 BHK | 639.3816 | 0 | 639.3816 | 0 | 927.1033 | NA
210 | 6 | 2 BHK | 493.7447 | 0 | 493.7447 | 0 | 715.9298 | NA
Sale Building- 1(Wing L)
1st Floor
211 | 2 | 2 BHK | 463.8208 | 0 | 463.8208 | 0 | 672.5401 | NA
212 | 3 | Society Office
2nd & 3rd Floor
213 | 2 | 2 BHK | 463.8208 | 0 | 463.8208 | 0 | 672.5401 | NA
214 | 3 | 2 BHK | 463.8208 | 0 | 463.8208 | 0 | 672.5401 | NA
4th to 7th, 9th to 14th & 16th to 19th Floor
215 | 1 | 3 BHK | 656.8193 | 0 | 656.8193 | 0 | 952.388 | NA
216 | 2 | 2 BHK | 463.8208 | 0 | 463.8208 | 0 | 672.5401 | NA
217 | 3 | 2 BHK | 463.8208 | 0 | 463.8208 | 0 | 672.5401 | NA
218 | 4 | 2 BHK | 463.8208 | 0 | 463.8208 | 0 | 672.5401 | NA
8th Floor
219 | 1 | 3 BHK | 656.8193 | 0 | 656.8193 | 0 | 952.388 | NA
220 | 2 | 2 BHK | 463.8208 | 0 | 463.8208 | 0 | 672.5401 | NA
221 | 3 | Refuge Area
222 | 4 | 2 BHK | 463.8208 | 0 | 463.8208 | 0 | 672.5401 | NA
15th Floor
223 | 1 | 3 BHK | 656.8193 | 0 | 656.8193 | 0 | 952.388 | NA
224 | 2 | 2 BHK | 463.8208 | 0 | 463.8208 | 0 | 672.5401 | NA
225 | 3 | Refuge Area
226 | 4 | 2 BHK | 463.8208 | 0 | 463.8208 | 0 | 672.5401 | NA
Sale Building- 1(Wing M)
1st Floor
227 | 1 | 1 BHK | 334.6528 | 0 | 334.6528 | 0 | 485.2465 | NA
228 | 2 | 1 BHK | 334.6528 | 0 | 334.6528 | 0 | 485.2465 | NA
229 | 3 | 2 BHK | 463.8208 | 0 | 463.8208 | 0 | 672.5401 | NA
230 | 4 | Society Office/Meter Room
2nd To 7th, 9th To 14th, 16th To 19th Floor
231 | 1 | 1 BHK | 334.6528 | 0 | 334.6528 | 0 | 485.2465 | NA
232 | 2 | 1 BHK | 334.6528 | 0 | 334.6528 | 0 | 485.2465 | NA
233 | 3 | 2 BHK | 463.8208 | 0 | 463.8208 | 0 | 672.5401 | NA
234 | 4 | 2 BHK | 463.8208 | 0 | 463.8208 | 0 | 672.5401 | NA
8th & 15th Floor
235 | 1 | 1 BHK | 334.6528 | 0 | 334.6528 | 0 | 485.2465 | NA
236 | 2 | 1 BHK | 334.6528 | 0 | 334.6528 | 0 | 485.2465 | NA
237 | 3 | 2 BHK | 463.8208 | 0 | 463.8208 | 0 | 672.5401 | NA
238 | 4 | Refuge Area
Remarks: 1. Wing A to F, H to K - Construction work was stopped. Work is same as last visit(15/09/2023). Internal Visit was not allowed. Wing G, L & M - Work not yet started. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered rate as per Market Inquire. 5. L & M wings are not registered on RERA. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 7. Please provide latest amended Plans as mentioned in CC. 8. We have considered Other charges from cost sheet. 9. Car parking is subjected to authentic documentation. 10. Please provide revised approved CC. 11. The Ministry of Environment and Forest Department Notice has been placed in project premisses by BMC, which is attached below. 12. The project has received first CC on 09/01/2019, But construction work is not yet completed.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY: |  |  | Lawns & Beyond
42.57
36.2055
[10 empty] | 78.7755 | 5.58 | 84.3555
Notice From BMC :
GOOGLE MAP:

## Sheet3
2020-02-01
Stage of construction Sale Building No.1-Wing A : RCC work of Basement Floor's Slab, Lower Ground Floor's Slab, Ground Floor's Slab, 1st + 3rd Floor's Slab work completed. Brick work & Plaster of 1st & 3rd Floor completed. (Mivan Technology) | [5 empty] | 27.9904 | 44.8086
Stage of construction Sale Building No.1-Wing B : RCC work of Basement Floor's Slab, Lower Ground Floor's Slab, Ground Floor's Slab, 1st +4th Floor's Slab work completed. Brick work & Plaster of 1st & 4th Floor completed. (Mivan Technology) | [5 empty] | 27.9904 | 44.8086
Stage of construction Sale Building No.1-Wing C : RCC work of Basement Floor's Slab, Lower Ground Floor's Slab, Ground Floor's Slab, 1st + 2nd Floor's Slab work completed. Brick work & Plaster of 1st & 2nd Floor completed. (Mivan Technology) | [5 empty] | 21.7225 | 39.4498
Stage of construction Sale Building No.1-Wing D : RCC work of Basement Floor's Slab, Lower Ground Floor's Slab, Ground Floor's Slab, 1st + 2nd Floor's Slab work completed. Brick work & Plaster of 1st & 2nd Floor completed. (Mivan Technology) | [5 empty] | 21.7225 | 39.4498
Stage of construction Sale Building No.1-Wing F : RCC work OF Basement Floor's Slab, Lower Ground Floor's Slab, Ground Floor's Slab work completed. (Mivan Technology) | [5 empty] | 13.6364 | 32.7273
Stage of construction Sale Building No.1-Wing K : RCC work of Basement Floor's Slab, Lower Ground Floor's Slab, Ground Floor's Slab, 1st + 2nd Floor's Slab work & partially 3rd Floor's Slab completed. Brick work & Plaster of 1st & 2nd Floor completed. (Mivan Technology) | [5 empty] | 22.6316 | 40.1316
Stage of construction Sale Building No.1-Wing J : RCC work OF Basement Floor's Slab, Lower Ground Floor's Slab work completed. (Mivan Technology) | [5 empty] | 12.7273 | 32.0455
2020-10-01
Stage of construction Sale Building No.1-Wing A : RCC work of B + Lower Gr. + Gr. + 3rd Floor's Slab work completed. Brick work & Plaster of 1st & 3rd Floor completed. (Mivan Technology) | [5 empty] | 27.9904 | 44.8086
Stage of construction Sale Building No.1-Wing B : RCC work of B + Lower Gr. + Gr. + 4th Floor's Slab work completed. Brick work & Plaster of 1st & 4th Floor completed. (Mivan Technology) | [5 empty] | 27.9904 | 44.8086
Stage of construction Sale Building No.1-Wing C : RCC work of B + Lower Gr. + Gr. + 3rd Floor's Slab work completed. Brick work & Plaster of 1st & 3rd Floor completed. (Mivan Technology) | [5 empty] | 24.3301 | 41.6029
Stage of construction Sale Building No.1-Wing D : RCC work of B + Lower Gr. + Gr. + 3rd Floor's Slab work completed. Brick work & Plaster of 1st & 3rd Floor completed. (Mivan Technology) | [5 empty] | 24.3301 | 41.6029
Stage of construction Sale Building No.1-Wing F : RCC work OF Basement Floor's Slab, Lower Ground Floor's Slab, Ground Floor's Slab work completed. (Mivan Technology) | [5 empty] | 13.6364 | 32.7273
Stage of construction Sale Building No.1-Wing K : RCC work of B + Lower Gr. + Gr. + 4th Floor's Slab work completed. Brick work & Plaster of 1st & 3rd Floor completed. (Mivan Technology) | [5 empty] | 26.6746 | 43.4928
Stage of construction Sale Building No.1-Wing J (Part 1) : RCC work OF Basement Floor's Slab work completed. (Mivan Technology) | [5 empty] | 12.7273 | 32.0455
Stage of construction Sale Building No.1-Wing J (Part 2) : RCC work of B + Lower Gr. + Gr. + 2nd Floor's Slab work completed. Brick work & Plaster of 1st & 2nd Floor completed. (Mivan Technology) | [5 empty] | 19.0909 | 36.8182
#REF!
All work Completed. Wait For OC.
All work Completed. Part OC Received.
All work Completed. OC Received.
| Excavation in process | 1% | 2%
| Excavation Completed | 2% | 4%
| Footing in Process | 4% | 8%
| Footing Completed | 5% | 15%
| Plinth in process | 7% | 20%
| Plinth completed | 10% | 30%
| Wing | Feb |  | Oct
|  | P% | D% | P% | D%
| A | 28 | 45 | 28 | 45
| B | 28 | 45 | 28 | 45
| C | 22 | 39 | 24 | 42
| D | 22 | 39 | 24 | 42
| F | 14 | 33 | 14 | 33
| J-1 | 13 | 32 | 13 | 32
| J-2 |  |  | 19 | 37
| K | 23 | 40 | 27 | 43

## A%
|  |  | Total Slab | Basement | Podium | Ground | Upper Floor
Particulars | totaL floor | 19 | 22 | 1 | 1 | 1 | 19
| total | completed
plinth | 10 | 10 |  | 100
slab | total slab | completed slab |  | 45.4545 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 22 | 10 |  | 10.5263 | Progress |  |  | 10 | 18.1818 | 1.5789 | 1.0526 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | 10.5263 | Recommended |  |  | 30 | 13.6364 | 1.5789 | 1.0526 | 0 | 0 | 0
| 19 | 2 |  | 0
plaster | Total Floor | completed Floor |  | 0
| 19 | 2 |  | 0
Flooring | Total Floor | completed Floor
| 19 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 19 | 0 |  |  | RCC | 18.1818 | 13.6364
Finishing | Total Floor | completed Floor |  |  | Bricks | 1.5789 | 1.5789
| 19 | 0 |  |  | Plaster | 1.0526 | 1.0526
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 30.8134 | 46.2679

## B%
|  |  | Total Slab | Basement | Podium | Ground | Upper Floor
Particulars | totaL floor | 19 | 22 | 1 | 1 | 1 | 19
| total | completed
plinth | 10 | 10 |  | 100
slab | total slab | completed slab |  | 45.4545 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 22 | 10 |  | 10.5263 | Progress |  |  | 10 | 18.1818 | 1.5789 | 1.0526 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | 10.5263 | Recommended |  |  | 30 | 13.6364 | 1.5789 | 1.0526 | 0 | 0 | 0
| 19 | 2 |  | 0
plaster | Total Floor | completed Floor |  | 0
| 19 | 2 |  | 0
Flooring | Total Floor | completed Floor
| 19 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 19 | 0 |  |  | RCC | 18.1818 | 13.6364
Finishing | Total Floor | completed Floor |  |  | Bricks | 1.5789 | 1.5789
| 19 | 0 |  |  | Plaster | 1.0526 | 1.0526
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 30.8134 | 46.2679

## C%
|  |  | Total Slab | Basement | Podium | Ground | Upper Floor
Particulars | totaL floor | 19 | 22 | 1 | 1 | 1 | 19
| total | completed
plinth | 10 | 10 |  | 100
slab | total slab | completed slab |  | 40.9091 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 22 | 9 |  | 26.3158 | Progress |  |  | 10 | 16.3636 | 3.9474 | 1.3158 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | 13.1579 | Recommended |  |  | 30 | 12.2727 | 3.9474 | 1.3158 | 0 | 0 | 0
| 19 | 5 |  | 0
plaster | Total Floor | completed Floor |  | 0
| 19 | 2.5 |  | 0
Flooring | Total Floor | completed Floor
| 19 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 19 | 0 |  |  | RCC | 16.3636 | 12.2727
Finishing | Total Floor | completed Floor |  |  | Bricks | 3.9474 | 3.9474
| 19 | 0 |  |  | Plaster | 1.3158 | 1.3158
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 31.6268 | 47.5359

## D%
|  |  | Total Slab | Basement | Podium | Ground | Upper Floor
Particulars | totaL floor | 19 | 22 | 1 | 1 | 1 | 19
| total | completed
plinth | 10 | 10 |  | 100
slab | total slab | completed slab |  | 40.9091 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 22 | 9 |  | 26.3158 | Progress |  |  | 10 | 16.3636 | 3.9474 | 1.3158 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | 13.1579 | Recommended |  |  | 30 | 12.2727 | 3.9474 | 1.3158 | 0 | 0 | 0
| 19 | 5 |  | 0
plaster | Total Floor | completed Floor |  | 0
| 19 | 2.5 |  | 0
Flooring | Total Floor | completed Floor
| 19 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 19 | 0 |  |  | RCC | 16.3636 | 12.2727
Finishing | Total Floor | completed Floor |  |  | Bricks | 3.9474 | 3.9474
| 19 | 0 |  |  | Plaster | 1.3158 | 1.3158
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 31.6268 | 47.5359

## F%
|  |  | Total Slab | Basement | Podium | Ground | Upper Floor
Particulars | totaL floor | 19 | 22 | 1 | 1 | 1 | 19
| total | completed
plinth | 10 | 10 |  | 100
slab | total slab | completed slab |  | 13.6364 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 22 | 3 |  | 0 | Progress |  |  | 10 | 5.4545 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | 0 | Recommended |  |  | 30 | 4.0909 | 0 | 0 | 0 | 0 | 0
| 19 | 0 |  | 0
plaster | Total Floor | completed Floor |  | 0
| 19 | 0 |  | 0
Flooring | Total Floor | completed Floor
| 19 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 19 | 0 |  |  | RCC | 5.4545 | 4.0909
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 19 | 0 |  |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 15.4545 | 34.0909

## K%
|  |  | Total Slab | Basement | Podium | Ground | Upper Floor
Particulars | totaL floor | 19 | 22 | 1 | 1 | 1 | 19
| total | completed
plinth | 10 | 10 |  | 100
slab | total slab | completed slab |  | 50 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 22 | 11 |  | 36.8421 | Progress |  |  | 10 | 20 | 5.5263 | 1.8421 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | 18.4211 | Recommended |  |  | 30 | 15 | 5.5263 | 1.8421 | 0 | 0 | 0
| 19 | 7 |  | 0
plaster | Total Floor | completed Floor |  | 0
| 19 | 3.5 |  | 0
Flooring | Total Floor | completed Floor
| 19 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 19 | 0 |  |  | RCC | 20 | 15
Finishing | Total Floor | completed Floor |  |  | Bricks | 5.5263 | 5.5263
| 19 | 0 |  |  | Plaster | 1.8421 | 1.8421
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 37.3684 | 52.3684

## J-1%
|  |  | Total Slab | Basement | Podium | Ground | Upper Floor
Particulars | totaL floor | 19 | 22 | 1 | 1 | 1 | 19
| total | completed
plinth | 10 | 10 |  | 100
slab | total slab | completed slab |  | 13.6364 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 22 | 3 |  | 0 | Progress |  |  | 10 | 5.4545 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor |  |  | 0 | Recommended |  |  | 30 | 4.0909 | 0 | 0 | 0 | 0 | 0
| 19 | 0 |  | 0
plaster | Total Floor | completed Floor |  | 0
| 19 | 0 |  | 0
Flooring | Total Floor | completed Floor
| 19 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 19 | 0 |  |  | RCC | 5.4545 | 4.0909
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 19 | 0 |  |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 15.4545 | 34.0909

## J-2%
|  |  | Total Slab | Basement | Podium | Ground | Upper Floor
Particulars | totaL floor | 19 | 22 | 1 | 1 | 1 | 19
| total | completed
plinth | 10 | 10 |  | 100
slab | total slab | completed slab |  | 22.7273 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 22 | 5 |  | 0 | Progress |  |  | 10 | 9.0909 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | 0 | Recommended |  |  | 30 | 6.8182 | 0 | 0 | 0 | 0 | 0
| 19 | 0 |  | 0
plaster | Total Floor | completed Floor |  | 0
| 19 | 0 |  | 0
Flooring | Total Floor | completed Floor
| 19 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 19 | 0 |  |  | RCC | 9.0909 | 6.8182
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 19 | 0 |  |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 19.0909 | 36.8182

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick | Lawns & Beyond | 2BHK | 0 | 1250 | 20000 | 25000000
commonfloor | Lawns & Beyond | 1BHK | 335 | 485.75 | 17539.8868 | 8520000
commonfloor | Lawns & Beyond | 2BHK | 480 | 696 | 16522.9885 | 11500000
commonfloor | Lawns & Beyond | 2BHK | 500 | 725 | 16551.7241 | 12000000
commonfloor | Lawns & Beyond | 3BHK | 630 | 913.5 | 16529.8303 | 15100000
commonfloor | Lawns & Beyond | 3BHK | 710 | 1029.5 | 16512.8703 | 17000000
99acres | Lawns & Beyond | 2BHK | 806.0083 | 1289.6133 | 19385.656 | 25000000
Magicbrick | Lawns & Beyond | 2BHK | 800 | 1280 | 19531.25 | 25000000
Average |  |  |  |  | 17276.2167
Valuation Adopted |  |  |  |  | 17300