## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 10/09/2025
Bank Name: |  |  |  | Axis Bank
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-08
Name of the builder group |  |  |  | M/s.Mahaavir Superstructures Private Limited
Name of the builder company |  |  |  | M/s.Mahaavir Superstructures Private Limited |  |  |  |  | Wing F is Same as Wing D 20/04/2024
Name of the Project |  |  |  | Mahaavir Exotique Phase I & II
Contact Details ( Name & Contact No.) |  |  |  | Mr. Mithilesh Pandey 9987688867
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Somnath 9702108280
Name / No of the Building |  |  |  | Wing A (Camellias) Wing B (Iris) Wing C (Jasmine) Wing D (Lilac) Wing E (Marigold)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet.
RERA No. |  |  |  | Phase I = P52000031173 Phase II = P52000053208
Project location details |  | Mahaavir Exotique Phase I & II, Survey No.19/1, 20, 24/A/8/B, near Ekvira apartment, Pisarve road, Rohinjan, Taloja west, Panvel, Raigad - 410208.
Survey No |  | 19/1, 20, 24/A/8/B
Road |  | Pisarve road |  | Locality/Village |  | Rohinjan
City |  | Taloja west |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410208
Nearby Landmark |  | Ekvira apartment |  | Distance from city centre: |  | 2.40 Km from Taloja Panchnand Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | S. No. 25/1 |  |  | Open land
West | NA | S. No. 24A/8 |  |  | Ekvira apartment
North | NA | S. No. 24A/4 |  |  | Open land
South | NA | 15.00 M. Wide Road |  |  | Turbhe rohinjan road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.092582,73.080321
Location Link |  | https://goo.gl/maps/SY5LzJwJ3ZkiAQXM9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 21592
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.908
Total FSI availaible for the project |  |  |  | 3.008
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 64948.75
Total number of Buildings |  |  |  | 05 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation (PMC)
Layout Approval No |  | PMP/NRV/16030/JK-1906/2021 |  |  | Dated | 2021-09-17
Approved Floor plan No. |  | PMP/NRV/16030/JK-1906/2021 |  |  | Dated | 2021-09-17
Commencement Certificate No. Valid Up to: |  | PMC/TP/Rohinjan/19/1,20,24/A/8/B/ 16030/1906/2021 |  |  | Dated | 2021-09-17
Building No. A = G/St + 1st to 29th Upper Floor Building No. B, C, D, E = G/St + 1st to 22nd Upper Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 54310.43
Approved no of units |  |  | Flats - 807, Shops - 12
Approved no of Floors |  |  | Wing A (Camellias) = G/St + 1st to 29th Upper Floor Wing B (Iris) = G/St + 1st to 22nd Upper Floor Wing C (Jasmine) = G/St + 1st to 22nd Upper Floor Wing D (Lilac) = G/St + 1st to 22nd Upper Floor Wing E (Marigold) = G/St + 1st to 22nd Upper Floor
Proposed no of Floors |  |  | Wing A (Camellias) = G/St + 1st to 29th Upper Floor
Wing B (Iris) = G/St + 1st to 22nd Upper Floor
Wing C (Jasmine) = G/St + 1st to 22nd Upper Floor
Wing D (Lilac) = G/St + 1st to 22nd Upper Floor
Wing E (Marigold) = G/St + 1st to 22nd Upper Floor
Expected Completion |  |  | As per RERA - Phase I = 31/12/2026 Phase II = 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A (Camellias) = G/St + 1st to 29th Upper Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 29
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.25
Excavation |  | 29 | 100% | 93.1% |  | 95% |  | Excavation in process | 14.5
Plinth |  | 29 | 100% |  |  |  |  | Excavation Completed | 29
RCC (Including podiums) |  | 30 | 100% |  |  |  |  | Footing in Process | 7.25
Brickwork | Brickwork & Internal Plaster | 29 | 100% |  |  |  |  | Footing Completed | 14.5
Internal Plaster | Brickwork & Internal Plaster | 29 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 29 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 29 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 27 | 93.1% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 20 | 68.97% |  |  |  |  | Plinth in process | 21.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 29
Construction details: |  | Wing B (Iris) = G/St + 1st to 22nd Upper Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 94.32% |  | 95% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 22 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 21 | 95.45% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 20 | 90.91% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | Wing C (Jasmine) = G/St + 1st to 22nd Upper Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 15 Floor, Painting upto 9 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 15 Floor, Painting upto 9 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 83.86% |  | 93.41% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 15 | 68.18% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 9 | 40.91% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | Wing D (Lilac) = G/St + 1st to 22nd Upper Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 18.7 Floor, External Plaster upto 16.5 Floor, Flooring upto 8 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 18.7 Floor, External Plaster upto 16.5 Floor, Flooring upto 8 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 75.01% |  | 89.82% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 18.7 | 85% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16.5 | 75% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 8 | 36.36% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | Wing E (Marigold) = G/St + 1st to 22nd Upper Floor | [5 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22
Stage of construction: |  | Excavation work Completed. Plinth work completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 10% |  | 45% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Recommended Rates of the Property : | [7 empty] | 7400 to 8400 | 2023-12-30 | Viraj
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 8600 |  |  | 8400 to 8600 by viraj on 25/06/2025
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 12000
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | 25/- from 2nd Floor
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 4,00,000/-
Distressed valuation of the Property |  |  |  |  | 6880
Commercial Area Details :
Building & Wing |  |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Shop Line |  |  | 12 | 3880.5296 |  | 6208.8474
Residential Area Details :
Building & Wing |  |  | No. of Units | Total Carpet Area |  | Total Saleable Area
A Wing (Camellias) |  |  | 163 | 100613.0724 |  | 150919.6086
B Wing (Iris) |  |  | 161 | 78166.9194 |  | 117250.3791
C Wing (Jasmine) |  |  | 161 | 78166.9194 |  | 117250.3791
D Wing (Lilac) |  |  | 161 | 78166.9194 |  | 117250.3791
E Wing (Marigold) |  |  | 161 | 78166.9194 |  | 117250.3791
Total |  |  | 807 | 413280.7499 |  | 619921.1249
Grand Total |  |  | 819 | 417161.2796 |  | 626129.9723
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) |  | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Shop Line
Ground Floor for Commercial & Parking
1 |  | Shop | 323.3775 | 0 | 517.404 | Ground Floor for Commercial & Parking
2 |  | Shop | 323.3775 | 0 | 517.404
3 |  | Shop | 323.3775 | 0 | 517.404
4 |  | Shop | 323.3775 | 0 | 517.404
5 |  | Shop | 323.3775 | 0 | 517.404
6 |  | Shop | 323.3775 | 0 | 517.404
7 |  | Shop | 323.3775 | 0 | 517.404
8 |  | Shop | 323.3775 | 0 | 517.404
9 |  | Shop | 323.3775 | 0 | 517.404
10 |  | Shop | 323.3775 | 0 | 517.404
11 |  | Shop | 323.3775 | 0 | 517.404
12 |  | Shop | 323.3775 | 0 | 517.404
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
A Wing (Camellias)
1st & 2nd Floor for Residential & Parking | [7 empty] | 174 | 163
1 |  | 2BHK | 572.4026 | 0 | 858.6039 | 1st & 2nd Floor for Residential & Parking |  |  |  |  | 101 & 201 | 101 | 201
2 |  | 2BHK | 572.4026 | 0 | 858.6039 | [5 empty] | 102 & 202 | 102 | 202
3 |  | 3BHK | 638.8703 | 0 | 958.3055 | [5 empty] | 103 & 203 | 103 | 203
4 |  | 3BHK | 638.8703 | 0 | 958.3055 | [5 empty] | 104 & 204 | 104 | 204
- |  | Parking
-
3rd Floor For Residential, Society Office, Creche & Amenities
1 |  | 2BHK | 572.4026 | 0 | 858.6039 | 3rd Floor For Residential, Society Office, Creche & Amenities
2 |  | 2BHK | 572.4026 | 0 | 858.6039
3 |  | 3BHK | 638.8703 | 0 | 958.3055
4 |  | 3BHK | 638.8703 | 0 | 958.3055
5 |  | Society Office
6 |  | Creche
4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor
1 |  | 2BHK | 572.4026 | 0 | 858.6039 | 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th Floor |  |  |  |  | 4701,..,2901 | 4701 | 2901
2 |  | 2BHK | 572.4026 | 0 | 858.6039 |  |  | 6857000 | 7986.2203 |  | 4702,..,2902 | 4702 | 2902
3 |  | 3BHK | 638.8703 | 0 | 958.3055 |  |  | 8200000 | 8556.7706
4 |  | 3BHK | 638.8703 | 0 | 958.3055
5 |  | 3BHK | 638.8703 | 0 | 958.3055 | [5 empty] | 1,..,1 | 1 | 1
6 |  | 3BHK | 638.8703 | 0 | 958.3055 | [5 empty] | 2,..,2 | 2 | 2
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
1 |  | 2BHK | 572.4026 | 0 | 858.6039 | 8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area) |  |  |  |  | 801,..,2801 | 801 | 2801
- |  | Refuge Area | [8 empty] | #REF! | #REF! | #REF!
2 |  | 3BHK | 638.8703 | 0 | 958.3055 | [5 empty] | #REF! | #REF! | #REF!
3 |  | 3BHK | 638.8703 | 0 | 958.3055 | [5 empty] | #REF! | #REF! | #REF!
4 |  | 3BHK | 638.8703 | 0 | 958.3055 | [5 empty] | #REF! | #REF! | #REF!
5 |  | 3BHK | 638.8703 | 0 | 958.3055 | [5 empty] | #REF! | #REF! | #REF!
B Wing (Iris)
1st, 2nd & 3rd Floor for Residential & Parking
- |  | Parking |  |  |  | 1st, 2nd & 3rd Floor for Residential & Parking |  |  |  |  | #REF! | #REF! | 401
- | [10 empty] | #REF! | #REF! | 501
- | [10 empty] | #REF! | #REF! | #NUM!
1 | 4 | 2BHK | 564.9432 | 0 | 847.4147 |  |  | 161 |  |  | 101 to 301 | 101 | 301
2 | 5 | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 102 to 302 | 102 | 302
3 | 6 | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 103 to 303 | 103 | 303
4 | 7 | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 104 to 304 | 104 | 304
- |  | Parking | [8 empty] | 105 to 305 | 105 | 305
4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor
1 |  | 1BHK | 403.058 | 0 | 604.587 | 4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor |  | 4600000 | 7608.5001 |  | 401 & 2201 | 401 | 2201
2 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 402 & 2202 | 402 | 2202
3 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 403 & 2203 | 403 | 2203
4 |  | 2BHK | 564.9432 | 0 | 847.4147 |  |  | 7670.3882 |  |  | 404 & 2204 | 404 | 2204
5 |  | 1BHK | 403.058 | 0 | 604.587 |  |  | 7525.799 |  |  | 405 & 2205 | 405 | 2205
6 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 406 & 2206 | 406 | 2206
7 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 407 & 2207 | 407 | 2207
8 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 408 & 2208 | 408 | 2208
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 1BHK | 403.058 | 0 | 604.587 | 8th, 13th & 18th Floor (Part Refuge Area) |  |  |  |  | 801 & 1801 | 801 | 1801
2 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 802 & 1802 | 802 | 1802
3 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 803 & 1803 | 803 | 1803
4 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 804 & 1804 | 804 | 1804
- |  | Refuge Area | [8 empty] | #REF! | #REF! | #REF!
5 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | #REF! | #REF! | #REF!
6 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | #REF! | #REF! | #REF!
7 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | #REF! | #REF! | #REF!
C Wing (Jasmine)
Ground Floor for Parking
1st, 2nd & 3rd Floor for Residential & Parking
- |  | Parking |  |  |  | 1st, 2nd & 3rd Floor for Residential & Parking |  |  |  |  | #REF! | #REF! | 701
- | [10 empty] | #REF! | #REF! | #NUM!
- | [10 empty] | #REF! | #REF! | #NUM!
1 | 4 | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 101 to 301 | 101 | 301
2 | 5 | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 102 to 302 | 102 | 302
3 | 6 | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 103 to 303 | 103 | 303
4 | 7 | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 104 to 304 | 104 | 304
- |  | Parking | [8 empty] | 105 to 305 | 105 | 305
4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor
1 |  | 1BHK | 403.058 | 0 | 604.587 | 4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor |  | 4600000 | 7608.5001 |  | 401 & 2201 | 401 | 2201
2 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 402 & 2202 | 402 | 2202
3 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 403 & 2203 | 403 | 2203
4 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 404 & 2204 | 404 | 2204
5 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 405 & 2205 | 405 | 2205
6 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 406 & 2206 | 406 | 2206
7 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 407 & 2207 | 407 | 2207
8 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 408 & 2208 | 408 | 2208
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 1BHK | 403.058 | 0 | 604.587 | 8th, 13th & 18th Floor (Part Refuge Area) |  |  |  |  | 801 & 1801 | 801 | 1801
2 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 802 & 1802 | 802 | 1802
3 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 803 & 1803 | 803 | 1803
4 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 804 & 1804 | 804 | 1804
- |  | Refuge Area | [8 empty] | #REF! | #REF! | #REF!
5 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | #REF! | #REF! | #REF!
6 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | #REF! | #REF! | #REF!
7 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | #REF! | #REF! | #REF!
D Wing (Lilac)
Ground Floor for Parking
1st, 2nd Floor for Residential & Parking
- |  | Parking |  |  |  | 1st, 2nd Floor for Residential & Parking |  |  |  |  | #REF! | #REF! | 701
- | [10 empty] | #REF! | #REF! | #NUM!
- | [10 empty] | #REF! | #REF! | #NUM!
1 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 101 to 201 | 101 | 201
2 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 102 to 202 | 102 | 202
3 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 103 to 203 | 103 | 203
4 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 104 to 204 | 104 | 204
- |  | Parking | [8 empty] | 105 to 205 | 105 | 205
3rd Floor For Residential, Society Office, Creche & Amenities
- |  | Amenities |  |  |  | 3rd Floor For Residential, Society Office, Creche & Amenities
-
- |  | Creche
1 |  | 2BHK | 564.9432 | 0 | 847.4147
2 |  | 1BHK | 403.058 | 0 | 604.587
3 |  | 1BHK | 403.058 | 0 | 604.587
4 |  | 2BHK | 564.9432 | 0 | 847.4147
- |  | Society Office
4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor
1 |  | 1BHK | 403.058 | 0 | 604.587 | 4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor |  | 4600000 | 7608.5001 |  | 401 & 2201 | 401 | 2201
2 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 402 & 2202 | 402 | 2202
3 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 403 & 2203 | 403 | 2203
4 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 404 & 2204 | 404 | 2204
5 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 405 & 2205 | 405 | 2205
6 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 406 & 2206 | 406 | 2206
7 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 407 & 2207 | 407 | 2207
8 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 408 & 2208 | 408 | 2208
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 1BHK | 403.058 | 0 | 604.587 | 8th, 13th & 18th Floor (Part Refuge Area) |  |  |  |  | 801 & 1801 | 801 | 1801
2 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 802 & 1802 | 802 | 1802
3 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 803 & 1803 | 803 | 1803
4 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 804 & 1804 | 804 | 1804
- |  | Refuge Area | [8 empty] | #REF! | #REF! | #REF!
5 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | #REF! | #REF! | #REF!
6 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | #REF! | #REF! | #REF!
7 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | #REF! | #REF! | #REF!
E Wing (Marigold)
Ground Floor for Parking
1st, 2nd & 3rd Floor for Residential & Parking
- |  | Parking |  |  |  | 1st, 2nd & 3rd Floor for Residential & Parking |  |  |  |  | #REF! | #REF! | 701
- | [10 empty] | #REF! | #REF! | #NUM!
- | [10 empty] | #REF! | #REF! | #NUM!
1 | 4 | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 101 to 301 | 101 | 301
2 | 5 | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 102 to 302 | 102 | 302
3 | 6 | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 103 to 303 | 103 | 303
4 | 7 | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 104 to 304 | 104 | 304
- |  | Parking | [8 empty] | 105 to 305 | 105 | 305
4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor
1 |  | 1BHK | 403.058 | 0 | 604.587 | 4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor |  | 4600000 | 7608.5001 |  | 401 & 2201 | 401 | 2201
2 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 402 & 2202 | 402 | 2202
3 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 403 & 2203 | 403 | 2203
4 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 404 & 2204 | 404 | 2204
5 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 405 & 2205 | 405 | 2205
6 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 406 & 2206 | 406 | 2206
7 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 407 & 2207 | 407 | 2207
8 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 408 & 2208 | 408 | 2208
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 1BHK | 403.058 | 0 | 604.587 | 8th, 13th & 18th Floor (Part Refuge Area) |  |  |  |  | 801 & 1801 | 801 | 1801
2 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 802 & 1802 | 802 | 1802
3 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 803 & 1803 | 803 | 1803
4 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 804 & 1804 | 804 | 1804
- |  | Refuge Area | [8 empty] | #REF! | #REF! | #REF!
5 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | #REF! | #REF! | #REF!
6 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | #REF! | #REF! | #REF!
7 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | #REF! | #REF! | #REF!
F Wing
Ground Floor for Parking
1st, 2nd Floor for Residential & Parking
1 |  | 2BHK | 564.9432 | 0 | 847.4147 | 1st, 2nd Floor for Residential & Parking |  |  |  |  | 101 to 201 | 101 | 201
2 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 102 to 202 | 102 | 202
3 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 103 to 203 | 103 | 203
4 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 104 to 204 | 104 | 204
3rd Floor For Residential, Society Office & Creche & Parking
- |  | Parking |  |  |  | 3rd Floor For Residential, Society Office & Creche & Parking
-
- |  | Creche
1 |  | 2BHK | 564.9432 | 0 | 847.4147
2 |  | 1BHK | 403.058 | 0 | 604.587
3 |  | 1BHK | 403.058 | 0 | 604.587
4 |  | 2BHK | 564.9432 | 0 | 847.4147
- |  | Society Office
4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor
1 |  | 1BHK | 403.058 | 0 | 604.587 | 4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor |  | 4600000 | 7608.5001 |  | 401 & 2201 | 401 | 2201
2 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 402 & 2202 | 402 | 2202
3 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 403 & 2203 | 403 | 2203
4 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 404 & 2204 | 404 | 2204
5 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 405 & 2205 | 405 | 2205
6 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 406 & 2206 | 406 | 2206
7 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 407 & 2207 | 407 | 2207
8 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 408 & 2208 | 408 | 2208
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 1BHK | 403.058 | 0 | 604.587 | 8th, 13th & 18th Floor (Part Refuge Area) |  |  |  |  | 801 & 1801 | 801 | 1801
2 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | 802 & 1802 | 802 | 1802
3 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 803 & 1803 | 803 | 1803
4 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | 804 & 1804 | 804 | 1804
- |  | Refuge Area | [8 empty] | #REF! | #REF! | #REF!
5 |  | 1BHK | 403.058 | 0 | 604.587 | [5 empty] | #REF! | #REF! | #REF!
6 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | #REF! | #REF! | #REF!
7 |  | 2BHK | 564.9432 | 0 | 847.4147 | [5 empty] | #REF! | #REF! | #REF!
Remarks:
1 | Wing A to D = Construction work is in process at the time of Visit. (Internal photos was not allowed.) Wing E = Plinth slab demolishing work is in the process at the time of Visit. | [6 empty] | As per site meet person, on 10/09/2025 plinth slab construction is wrong thefore it dimolished
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We have considered proposed No. of Floor for Stage Calculation.
6 | We considered Gross carpet area = Net carpet + Balcony.
7 | We have considered rate by verifying it from market inquire.
8 | Car parking is subjected to authentic documentation.
9 | On Site, we meet Mr. sachin - 9004674069.
9 | We have updated revised approved floor plan & C.C for C wing (on 13/04/2023).
10 | Project consist of A to F Wings but on RERA only A to E Wings are registered.
11 | Recommended Rates/Other Charges of the Property have been revised on 30/12/2023 & 25/06/2025.
12 | We have updated Wing D & E (On 20/04/2024).
13 | Flat numbering is given as per the sale plan, which is provided by the bank officials on mail for Building No. B, C, & E for 1st to 3rd floor.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Mahaavir Exotique Phase I & II
Layout :
Google Map :
Formulas:
Rohinjan = [Rohinjan, row above]
A
B
WING A
WING F
WING E
WING D
WING C
WING B
A
B
C
A
A Wing
C Wing
B Wing
D Wing
E Wing
A Wing
B Wing
C Wing
D Wing
D Wing
A Wing
B Wing
C Wing
D Wing
E Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted