## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/09/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-09-08
Name of the builder group |  |  |  | Mountain Residency Private Limited
Name of the builder company |  |  |  | Mountain Residency Private Limited
Name of the Project |  |  |  | Mountain Greens
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Aniket Pal – 7767962810
Site Person - Contact Details (Name & Contact No.) |  |  |  | Miss. Yogita 8928589464 |  |  |  | Mr. Surabh Tiwari : 8898250154
Name / No of the Building |  |  |  | 01 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | P51700048979
Project location details |  | Mountain Greens, Survey No.45/15/16/C/3, 16/C/4, 16/C/5, near Sai urmila apartments, Internal Road, , Adivali Dhokali, Kalyan East, Ambernath, Thane - 421306.
Survey No |  | 45/15/16/C/3, 16/C/4, 16/C/5
Locality |  | NA
Road |  | Internal Road |  | Locality/Village |  | Adivali Dhokali
City |  | Kalyan East |  | District |  | Thane
Taluka |  | Ambernath |  | Pin Code |  | 421306
Nearby Landmark |  | Sai urmila apartments |  | Distance from city centre: |  | 5.6 KM from Kalyan Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | L.H.No.16 |  |  | Open Plot
West | NA | S.No.45 |  |  | Internal Road
North | NA | L.H.No.16A |  |  | Sai urmila apartments
South | NA | 24.00 M.W. D.P. Road |  |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.203109,73.127733
Location Link |  | https://maps.app.goo.gl/crQkkLPXSvicMbLu8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3192
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 3.1689
Total FSI availaible for the project |  |  |  | 4.2689
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 13626.39
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kalyan-Dombivli Municipal Corporation
Layout Approval No |  | KDMC/TPD/BP/27 Village/2022-23/27/383 |  |  | Dated | 2024-03-11
Approved Floor plan No. |  | KDMC/TPD/BP/27 Village/2022-23/27/383 |  |  | Dated | 2024-03-11
Commencement-CC No Valid Up to: |  | KDMC/TPD/BP/27 Village/2022-23/27/385 |  |  | Dated | 2024-03-11
Gr/Stilt + 1st to 24th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 13626.39
Approved no of units |  |  | Flats - 240, Shops - 13
Approved no of Floors |  |  | Gr/St + 1st to 24th Floor
Proposed no of Floors |  |  | Gr/St + 1st to 24th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Community area, Outdoor gym, Game zone, Kids play area, Yoga & Meditation zone, Sitout area, Power back up for lifts & common area, Fire fighting system.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Gr/St + 1st to 24th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 3 Floor Completed | , Internal Plaster upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 24 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6
Excavation |  | 24 | 100% | 58.44% |  | 80.62% |  | Excavation in process | 12
Plinth |  | 24 | 100% |  |  |  |  | Excavation Completed | 24
RCC (Including podiums) |  | 25 | 100% |  |  |  |  | Footing in Process | 6
Brickwork | Brickwork & Internal Plaster | 24 | 100% |  |  |  |  | Footing Completed | 12
Internal Plaster | Brickwork & Internal Plaster | 3 | 12.5% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0 |  | MIS | Inspection | Online | Builder
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18 | 5799.2329 | 7000 | 6000 | 4996.9314 | 5200
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 24
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 5750 |  |  | 5400 to 5750 | Rushikesh | 2023-11-28 | Verbal
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 11500
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 4600
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop |  | 13 |  | 1888.0056 |  | 4414.4258
Total |  | 13 |  | 1888.0056 |  | 4414.4258
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 240 |  | 104837.9155 |  | 157256.8733 |  |  | 240
Total |  | 240 |  | 79233.804 |  | 157256.8733
Grand Total |  | 253 |  | 81121.8096 |  | 161671.299 |  |  | 10.764
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Ground Floor for Commercial & Parking
1 |  | Shop | 199.3493 | 111.7034 | 482.1317 | Ground Floor for Commercial & Parking |  | 17.5375 | 10.224
2 |  | Shop | 79.546 | 40.1228 | 185.4866
3 |  | Shop | 179.2206 | 100.2344 | 433.1552
4 |  | Shop | 169.4254 | 85.2509 | 394.7482 |  |  |  | 15.8125
5 |  | Shop | 110.4386 | 46.5392 | 243.3157
6 |  | Shop | 137.9945 | 62.6465 | 310.9935
7 |  | Shop | 137.9945 | 62.6465 | 310.9935
8 |  | Shop | 110.4386 | 46.5392 | 243.3157
9 |  | Shop | 169.4254 | 85.2509 | 394.7482
10 |  | Shop | 182.7727 | 91.7631 | 425.5305
11 |  | Shop | 129.2756 | 58.427 | 290.9391
12 |  | Shop | 201.7174 | 128.3069 | 511.5376
13 |  | Shop | 80.4071 | 40.5803 | 187.5304
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Ground Floor for Commercial & Parking
Podium Floor for Parking
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd & 24th Floor for Residential
1 |  | 1BHK | 406.5563 | 0 | 609.8344 | 1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd & 24th Floor for Residential |  | 27.0152 | 2.75 | 5.095 | 322.0589 | 5081.7073
2 |  | 2BHK | 562.9572 | 0 | 844.4358 | [5 empty] | 430.2371 | 4912.1555
3 |  | 1BHK | 406.5563 | 0 | 609.8344 |  |  |  |  | 5903.2417
4 |  | 1BHK | 406.5563 | 0 | 609.8344
5 |  | 2BHK | 552.839 | 0 | 829.2586
6 |  | 1BHK | 406.5563 | 0 | 609.8344
7 |  | 1BHK | 406.5563 | 0 | 609.8344
8 |  | 1BHK | 406.5563 | 0 | 609.8344
9 |  | 1BHK | 406.5563 | 0 | 609.8344
10 |  | 1BHK | 406.5563 | 0 | 609.8344
8th, 13th, 18th & 23rd Floor (Part Refuge Area)
1 |  | 1BHK | 406.5563 | 0 | 609.8344 | 8th, 13th, 18th & 23rd Floor (Part Refuge Area) |  |  |  |  | 322.0589 | 5081.7073
2 |  | 2BHK | 562.9572 | 0 | 844.4358 | [5 empty] | 430.2371 | 4912.1555
3 |  | 1BHK | 406.5563 | 0 | 609.8344
4 |  | 1BHK | 406.5563 | 0 | 609.8344
5 |  | 2BHK | 552.839 | 0 | 829.2586
6 |  | 1BHK | 406.5563 | 0 | 609.8344
7 |  | 1BHK | 406.5563 | 0 | 609.8344
8 |  | 1BHK | 406.5563 | 0 | 609.8344
9 |  | 1BHK | 406.5563 | 0 | 609.8344
10 |  | 1BHK | 406.5563 | 0 | 609.8344
8th, 13th, 18th & 23rd Floor (Part Refuge Area)
1 |  | 1BHK | 406.5563 | 0 | 609.8344 | 8th, 13th, 18th & 23rd Floor (Part Refuge Area) |  | 28.2527 | 2.75 | 5.04
2 |  | 2BHK | 562.9572 | 0 | 844.4358
3 |  | Refuge Area
4 |  | 1BHK | 406.5563 | 0 | 609.8344
5 |  | 2BHK | 552.839 | 0 | 829.2586
6 |  | 1BHK | 406.5563 | 0 | 609.8344 |  |  |  |  | 5083.3471
7 |  | 1BHK | 406.5563 | 0 | 609.8344 |  |  |  |  | 5411.3049
8 |  | 1BHK | 406.5563 | 0 | 609.8344
9 |  | 1BHK | 406.5563 | 0 | 609.8344
10 |  | 1BHK | 406.5563 | 0 | 609.8344
Remarks:
1 | Construction work is in process at the time of Visit. (Slow Speed)
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Enclose balcony + Balcony.
6 | We have considered proposed No. of Floor for Stage Calculation.
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | Recommended Rates / Other charges of the Property have been revised on 28/11/2023.
11 | We have updated revised approved CC fron RERA Site on 16/01/2025
12 | We have updated revised approved floor plans (On 26/03/2025).
13 | Survey numbers nomenclature has been rectified with reference to the latest approved plans, CC, title certificate & RERA.
14 | As per the site visit dtd. 28/03/2025, we have observed that the terrace area is constructed for the 1st floor above the shop line for Flat No. 2 to 5, but as per the approved floor plan, the terrace area is not mentioned for Flat No. 2 to 5. Please check from your end.
15 | With reference to remark no. 14, we have received a builder clarification letter, which is provided by the bank officials on mail; Documents states that the flat no. 102, 103, 104, 105, 106, & 107 will be used for the builder's own purposes, so do not consider these flats for valuation purpose. Documents are attached below.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Mountain Greens
Remark No. 13:
Remark No. 14:
Remark No. 15:
Layout :
Google Map :
Formulas:
Adivali Dhokali = [Adivali Dhokali, row above]
Terrace Line
Terrace Line
Old Plan
New Plan

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted