## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 19/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-10
Name of the builder group |  |  |  | M/s. Navkar Estate & Homes Pvt. Ltd.
Name of the builder company |  |  |  | M/s. Navkar Estate & Homes Pvt. Ltd.
Name of the Project |  |  |  | Navkar City Phase I & Phase II
Contact Details ( Name & Contact No.) |  |  |  | 9930055014 / 9167200720 / 8879688487
Site Meet Person Details ( Name & Contact No.) |  |  |  | Mr. Nitin - 8956402642
Name / No of the Building |  |  |  | Navkar City Phase I A Type Building = A1, A2 & A3 B Type Building = B1 & B2 C1 Building C2 Building C3 Building C4 Building D1 Building H Type Building = H1, H2 & H3 G Building R1 Type Building R2 Type Building Navkar City Phase II A Type Building B Type Building = B1 & B2 C Type Building = C1, C2 & C3 D Type Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. | Navkar City Phase I Part 1 = P99000011999 = B1, B2, C1, C2 (G + 8th Floor) Part 2 = P99000010920 = B1, B2, C1, C2 (8th to 14th Floor) Part 3 = P99000004573 = A1, A2 & A3 (G + 8th Floor) Part 4 = P99000008528 = A1, A2 & A3 (8th to 14th Floor) Part 5 = P99000034105 = D1 (G + 23rd Floor) & H1 (G + 27th Floor) Part 6 = P99000050162 = G (G + 23rd Floor) Part 8 = P99000033433 = C3 & C4 (G + 23rd Floor) Part 9 = P99000034013 = H2 & H3 (G + 23rd Floor) Part 14 = P99000054543 = R1 & R2 (G + 23rd Floor) Navkar City Phase II Part 1 = P99000009437 = A, B1, B2, D (G + 8th Floor) Part 2 = P99000004423 = A, B1, B2, D (8th to 14th Floor) Part 3 = P99000009716 = C1, C2 & C3 (G + 8th Floor) Part 4 = P99000005905 = C1, C2 & C3 (8th to 14th Floor)
Project location details |  | Navkar City Phase I & Phase II, Survey No.332, H No. 1, 3, 4, 7 & 8, S No. 333, H. No. 1 & 2, S No. 332, H. No. 2 & 6A, S No. 335, H. No. 2, S No. 336, H. No. 2, Don Bosco Rd, Juchandra, Naigaon, Vasai, Palghar.
Survey No |  | 332, H No. 1, 3, 4, 7 & 8, S No. 333, H. No. 1 & 2, S No. 332, H. No. 2 & 6A, S No. 335, H. No. 2, S No. 336, H. No. 2
Road |  | Don Bosco Rd |  | Locality/Village |  | Juchandra
City |  | Naigaon |  | District |  | Palghar
Taluka |  | Vasai |  | Pin Code |  | 401208
Near by Landmark |  | Don Bosco High School |  | Distance from city centre: |  | 1.7km from Naigaon Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | Road |  |  | Naigaon East Vasai Link Road
West | NA | Open Plot |  |  | Open Plot
North | NA | Open Plot |  |  | Open Plot
South | NA | Road |  |  | Don Bosco Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.3599712,72.8533273
Location Link |  | https://goo.gl/maps/G2NtASKCFpw9b3cf6?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 30049.36
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 1.794
Total FSI availaible for the project |  |  |  | 2.794
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 83957.52
Total number of Buildings |  |  |  | 23 Wings
Approval Detail : Plan approval
Layout Approval No |  | VVCMC/AMEND/BP/VP0093/13/2021 |  |  | Dated | 2021-05-31
Approved Floor plan No. |  | VVCMC/AMEND/BP/VP0093/13/2021 |  |  | Dated | 2021-05-31 |  |  |  | VVCMC/TP/CC/VP-0093/201/2023-24
Commencement Certificate No. |  | VVCMC/AMEND/BP/VP0093/13/2021 |  |  | Dated | 2020-09-17
Valid Up to: Phase 1 Building Type A (Wing A1, A2, A3) = St + Gr + 1st to 14th Floor Building Type B1 = St + Gr + 1st to 14th Floor Building Type B2 = St + Gr + 1st to 14th Floor Building Type C1 = St + Gr + 1st to 14th Floor Building Type C2 = St + Gr + 1st to 14th Floor Phase 2 Building Type A = St + Gr + 1st to 14th Floor Building Type B (Wing B1 & B2) = St + Gr + 1st to 14th Floor Building Type C ( Wing C1, C2, C3) = Gr + 1st to 12th Floors Building Type D = St + Gr + 1st to 14th Floor
O. Certificate No.: |  | VVCMC/AMEND/BP/VP0093/41/2021 |  | Date of approval: | Dated | 15/06/2021.
Approved upto : Phase 1 Building Type A (Wing A1, A2, A3) = St + Gr + 1st to 7th Floor Building Type B1 = St + Gr + 1st to 7th Floor Building Type B2 = St + Gr + 1st to 7th Floor Building Type C1 = St + Gr + 1st to 7th Floor Building Type C2 = St + Gr + 1st to 7th Floor Phase 2 Building Type A = St + Gr + 1st to 7th Floor Building Type B (Wing B1 & B2) = St + Gr + 1st to 7th Floor Building Type C ( Wing C1, C2, C3) = Gr + 1st to 7th Floor Building Type D = St + Gr + 1st to 7th Floor
Building Type C3, C4, D1, H1, H2 & H3
Layout Approval No |  | VVCMC/TP/CC/VP/0093/530/2021-22 |  |  | Dated | 2022-01-05
Approved Floor plan No. |  | VVCMC/TP/CC/VP/0093/530/2021-22 |  |  | Dated | 2022-01-05
Commencement Certificate No. |  | VVCMC/TP/CC/VP/0093/530/2021-22 |  |  | Dated | 2022-01-05
Valid Up to: Phase 1 Building Type C3 = St + Gr + 23 Floor Building Type C4 = St + Gr + 23 Floor Building Type D1 = St + Gr + 23 Floor Building Type H1, H2 & H3 = St + Gr + 23 Floor Building Type G = St + Gr + 23 Floor
Building Type R1 & R2
Layout Approval No |  | VVCMC/TP/AMEND/VP-0093/159/ 2023-24 |  |  | Dated | 2023-11-09
Approved Floor plan No. |  | VVCMC/TP/AMEND/VP-0093/159/ 2023-24 |  |  | Dated | 2023-11-09
Commencement Certificate No. Valid Up to: |  | VVCMC/TP/CC/VP-0093/201/2023-24 |  |  | Dated | 2023-11-09
Phase 1 Building Type R1 & R2= St + Gr + 1st to 23rd Floor Building Type R2 = St + Gr + 1st to 23rd Floor
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 83957.52
Approved no of units |  |  | Phase I = Flats - 1858, Shops - 82, Offices - 36 Phase II = Flats - 471, Shops - 9
Approved no of Floors |  |  | Phase 1 Building Type A (Wing A1, A2, A3) = Gr + 1st to 14 Floor Building Type B1 = Gr + 1st to 14 Floor Building Type B2 = Gr + 1st to 14 Floor Building Type C1 = Gr + 1st to 14 Floor Building Type C2 = Gr + 1st to 14 Floor Building Type C3 = Gr + 1st to 23 Floor Building Type C4 = Gr + 1st to 23 Floor Building Type D1 = Gr + 1st to 23 Floor Building Type H1, H2 & H3 = Gr + 1st to 23 Floor Building Type G = Gr + 1st to 23 Floor Building Type R1 = St + Gr + 1st to 23rd Floor Building Type R2 = St + Gr + 1st to 23rd Floor Phase 2 Building Type A = Gr + 1st to 14 Floor Building Type B (Wing B1 & B2) = Gr + 1st to 14 Floor Building Type C ( Wing C1, C2, C3) = Gr + 1st to 14 Floor Building Type D = Gr + 1st to 14 Floor
Proposed no of Floors |  |  | Phase 1 Building Type A (Wing A1, A2, A3) = Gr + 1st to 14 Floor Building Type B1 = Gr + 1st to 14 Floor Building Type B2 = Gr + 1st to 14 Floor Building Type C1 = Gr + 1st to 14 Floor Building Type C2 = Gr + 1st to 14 Floor Building Type C3 = Gr + 1st to 23rd Floor Building Type C4 = Gr + 1st to 23rd Floor Building Type D1, G = Gr + 1st to 23rd Floor Building Type H1 = Gr + 1st to 27th Floor Building Type H2 & H3 = Gr + 1st to 23rd Floor Building Type R1 = St + Gr + 1st to 23rd Floor Building Type R2 = St + Gr + 1st to 23rd Floor Phase 2 Building Type A = Gr + 1st to 14 Floor Building Type B (Wing B1 & B2) =Gr + 1st to 14 Floor Building Type C ( Wing C1, C2, C3) = Gr + 1st to 14 Floor Building Type D = Gr + 1st to 14 Floor
Expected Completion |  |  | As per RERA - Navkar City Phase I (Part 5, 8 & 9) - 30/06/2026 Navkar City Phase I (Part 6) - 30/06/2027 Navkar City Phase I (Part 14) - 31/12/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Brick, Sand, Cement
Construction details: Phase II |  | Building Type A = St + Gr +1st to 14th Floor Building Type B (Wing B1 & B2) = St + Gr + 1st to 14th Floor Building Type C ( Wing C1, C2, C3) = Gr + 1st to 14th Floor Building Type D = St + Gr + 1st to 14th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14
Stage of construction: |  | All work Completed. OC Received upto 7th Floor | [5 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  | 100%
Construction details: Phase I |  | Building Type A (Wing A1, A2, A3) = Gr + 1st to 14th Floor Building Type B1 & B2 = Gr + 1st to 14th Floor Building Type C1 & C2 = Gr + 1st to 14th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14
Stage of construction: |  | All work Completed. OC Received upto 7th Floor | [5 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 100% |  | 100% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 14 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 14 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 14 | 100% |  |  |  |  | Plinth in process | 10.5
Possession |  | 14 | 100% |  |  |  |  | Plinth completed | 14
Construction details: Phase I |  | Elite - Building Type C3 = Gr + 1st to 23rd Floor Elite - Building Type C4 = Gr + 1st to 23rd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 20 Floor, Painting upto 18 Floor, Finishing upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 20 Floor, Painting upto 18 Floor, Finishing upto 5 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 88.7% |  | 94.35% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 20 | 86.96% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 18 | 78.26% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 5 | 21.74% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: Phase I |  | Blossom - Building Type D1 = Gr + 1st to 23rd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 20 Floor, Painting upto 18 Floor, Finishing upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 20 Floor, Painting upto 18 Floor, Finishing upto 3 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 88.26% |  | 94.35% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 20 | 86.96% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 18 | 78.26% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 13.04% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: Phase I |  | Empire - Building Type H1 = Gr + 1st to 27th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 22.95 Floor, External Plaster upto 20.25 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 27
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 22.95 Floor, External Plaster upto 20.25 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.75
Excavation |  | 27 | 100% | 71.38% |  | 88% |  | Excavation in process | 13.5
Plinth |  | 27 | 100% |  |  |  |  | Excavation Completed | 27
RCC (Including podiums) |  | 28 | 100% |  |  |  |  | Footing in Process | 6.75
Brickwork | Brickwork & Internal Plaster | 27 | 100% |  |  |  |  | Footing Completed | 13.5
Internal Plaster | Brickwork & Internal Plaster | 22.95 | 85% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20.25 | 75% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 20.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 27
Construction details: Phase I |  | Empire - Building Type H2 = Gr + 1st to 23rd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 5 Slab, Brickwork upto 4 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 5 Slab, Brickwork upto 4 Floor Completed | [5 empty] | All work Completed. OC Received. |  | As per visit dt 08/03/2025, construction stage of bldg type H2 = 1st slab completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75 | Please check before release the report
Excavation |  | 23 | 100% | 19.64% |  | 52.12% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 5 | 20.83% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 4 | 17.39% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: Phase I |  | Empire - Building Type H3 = Gr + 1st to 23rd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 5 Slab, Brickwork upto 4 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 5 Slab, Brickwork upto 4 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 19.64% |  | 52.12% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 5 | 20.83% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 4 | 17.39% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: Phase I |  | Harmony - G Type = Gr + 1st to 23rd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 3 Slab, Brickwork upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab, Brickwork upto 2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 15.65% |  | 49.18% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 3 | 12.5% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 2 | 8.696% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: Phase I |  | Building Type R1 = St + Gr +1st to 23rd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 7 Slab, Brickwork upto 6 Floor, Internal Plaster upto 4.5 Floor, External Plaster upto 3.3 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 7 Slab, Brickwork upto 6 Floor, Internal Plaster upto 4.5 Floor, External Plaster upto 3.3 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 26.53% |  | 56.75% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 7 | 29.17% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 6 | 26.09% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 4.5 | 19.57% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3.3 | 14.35% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 100% |  | 100% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 14 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 14 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 14 | 100% |  |  |  |  | Plinth in process | 10.5
Possession |  | 14 | 100% |  |  |  |  | Plinth completed | 14
Construction details: Phase I |  | Building Type R2 = St + Gr +1st to 23rd Floor | [5 empty] | Excavation work Completed. Footing work Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23
Stage of construction: |  | Excavation work Completed. Footing work Completed | [5 empty] | All work Completed. OC Received. |  | Construction stage is more. Please check before release the report
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 5% |  | 32.5% |  | Excavation in process | 11.5
Plinth |  | 11.5 | 50% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Wheather the construction is as per approved Building plan : Under Construcion
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property : | [7 empty] | Rate Changed to 6800 from 6800 by rakesh by cost sheet on 20/10/2022
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) (Including Parking) |  |  |  |  | 6900 |  |  | 6800 to 6900 | 2024-06-18 | smith
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 7500 |  |  | Rate Changed to 6400 from 5600 by rakesh by cost sheet on 30/12/2021
Recommended rate of the Office Per Sq. Ft. ( on Saleable area) |  |  |  |  | 6000
Development Charges |  |  |  |  | 155000
Other Charges |  |  |  |  | 51640/-
Legal Services Charges |  |  |  |  | 9500/-
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 200000/-
Distressed valuation of the Property |  |  |  |  | 5520 |  |  |  |  | s
Commercial Area Details : Phase I
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Type A1, A2, A3 (Shop) | Wing A1 | 8 |  | 1406.3166 |  | 2250.1066 |  |  | #VALUE!
| Wing A2 | 8 |  | 1406.8548 |  | 2250.9677
| Wing A3 | 8 |  | 1435.81 |  | 2297.2959
Type B (Shop) | Wing B1 | 6 |  | 1042.4934 |  | 1667.9894
| Wing B2 | 6 |  | 1042.1705 |  | 1667.4728
Type B (Office) | Wing B1 | 5 |  | 896.3183 |  | 1434.1092
| Wing B2 | 6 |  | 1002.7742 |  | 1604.4388
Wing C3 (Shop) |  | 10 |  | 1911.6864 |  | 3058.6982 |  |  | 22
Wing C4 (Shop) |  | 9 |  | 1641.3916 |  | 2626.2266
Wing H1 (Shop) |  | 12 |  | 3114.2943 |  | 4982.8709
Wing H1 (Office) |  | 11 |  | 2517.1743 |  | 4027.4789
Wing H2 + H3 (Shop) |  | 15 |  | 3486.4704 |  | 5578.3526
Wing H2 + H3 (Office) |  | 14 |  | 2658.525 |  | 4253.64
Total |  | 118 |  | 23562.2797 |  | 37699.6476 |  |  | 1071244.2743
Commercial Area Details : Phase II
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Type A (Shop) |  | 9 |  | 4784.4904 |  | 7655.1846
Residential Area Details : Phase I
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Type A1, A2, A3 | Wing A1 | 56 |  | 27669.9384 |  | 43972.3393
| Wing A2 | 53 |  | 26363.5655 |  | 41902.9872
| Wing A3 | 56 |  | 27660.1432 |  | 43243.8318
Type B1 |  | 53 |  | 19244.9287 |  | 31131.6363
Type B2 |  | 52 |  | 18881.9935 |  | 30540.8945
Type C1 |  | 54 |  | 17062.0971 |  | 27395.3299
Type C2 |  | 54 |  | 18440.239 |  | 29535.1674
Wing C3 |  | 138 |  | 62671.1619 |  | 94197.3067
Wing C4 |  | 112 |  | 43451.394 |  | 65482.9517 |  |  |  | 250 | 19
Type D1 |  | 181 |  | 81166.0496 |  | 121749.0745
Type G |  | 273 |  | 119303.752 |  | 178955.628
Wing H1 |  | 175 |  | 91205.7455 |  | 137053.6176 | [5 empty] | 242
Wing H2 + H3 |  | 239 |  | 118228.5253 |  | 189165.6404
Wing R1 |  | 181 |  | 78869.4157 |  | 118304.1235
Wing R2 |  | 181 |  | 78869.4157 |  | 118304.1235
Total |  | 1858 |  | 829088.365 |  | 1270934.6524
Residential Area Details : Phase II
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  |  | 175
Type A |  | 62 |  | 41767.4545 |  | 64323.6541
Type B1 |  | 54 |  | 30929.3314 |  | 48703.8439 |  | 2329
Type B2 |  | 55 |  | 31532.0347 |  | 49644.2273
Type C1, C2, C3 | Wing C1 | 82 |  | 31011.7568 |  | 50068.1405
| Wing C2 | 82 |  | 29071.2228 |  | 46957.1292
| Wing C3 | 82 |  | 29096.8412 |  | 47003.6297
Type D |  | 54 |  | 20400.4979 |  | 32889.4424
Total |  | 471 |  | 213809.1392 |  | 339590.0672
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
Phase I
Type A1, A2, A3
Wing A1
Ground Floor for Parking & Commercial
17 |  | Shop | 195.259 | 0 | 312.4143 | Ground Floor for Parking & Commercial
18 |  | Shop | 169.4254 | 0 | 271.0806
19 |  | Shop | 169.4254 | 0 | 271.0806
20 |  | Shop | 169.4254 | 0 | 271.0806
21 |  | Shop | 169.4254 | 0 | 271.0806
22 |  | Shop | 169.4254 | 0 | 271.0806
23 |  | Shop | 169.4254 | 0 | 271.0806
24 |  | Shop | 194.5055 | 0 | 311.2088
1st Floor for Residential
1 |  | 2BHK | 499.5034 | 38.7504 | 788.0055 | 1st Floor for Residential
2 |  | 2BHK | 492.2915 | 38.7504 | 777.1877
3 |  | 2BHK | 437.9549 | 232.6639 | 889.5962
4 |  | 2BHK | 444.424 | 232.6639 | 899.2999
2nd, 4th, 6th, 10th & 12th Floor
1 |  | 2BHK | 499.5034 | 35.5212 | 784.7763 | 2nd, 4th, 6th, 10th & 12th Floor
2 |  | 2BHK | 492.2915 | 35.5212 | 773.9585
3 |  | 2BHK | 493.0127 | 35.5212 | 775.0403
4 |  | 2BHK | 499.4819 | 35.5212 | 784.744
8th Floor
1 |  | 2BHK | 499.5034 | 35.5212 | 784.7763 | 8th Floor
2 |  | 2BHK | 492.2915 | 35.5212 | 773.9585
3 |  | 2BHK | 493.0127 | 35.5212 | 775.0403
4 |  | 2BHK | 499.4819 | 35.5212 | 784.744
3rd, 5th, 7th, 9th & 11th Floor
1 |  | 2BHK | 499.5034 | 38.7504 | 788.0055 | 3rd, 5th, 7th, 9th & 11th Floor
2 |  | 2BHK | 492.2915 | 38.7504 | 777.1877
3 |  | 2BHK | 493.0127 | 38.7504 | 778.2695
4 |  | 2BHK | 499.4819 | 38.7504 | 787.9732
13th Floor
1 |  | 2BHK | 499.5034 | 38.7504 | 788.0055 | 13th Floor
2 |  | 2BHK | 492.2915 | 38.7504 | 777.1877
3 |  | 2BHK | 493.0127 | 38.7504 | 778.2695
4 |  | 2BHK | 499.4819 | 38.7504 | 787.9732
14th Floor
1 |  | 2BHK | 499.5034 | 35.5212 | 784.7763 | 14th Floor
2 |  | 2BHK | 492.2915 | 35.5212 | 773.9585
3 |  | 2BHK | 493.0127 | 35.5212 | 775.0403
4 |  | 2BHK | 499.4819 | 35.5212 | 784.744
Wing A2
Ground Floor for Parking & Commercial
9 |  | Shop | 199.3493 | 0 | 318.9588 | Ground Floor for Parking & Commercial
10 |  | Shop | 169.4254 | 0 | 271.0806
11 |  | Shop | 169.4254 | 0 | 271.0806
12 |  | Shop | 169.4254 | 0 | 271.0806
13 |  | Shop | 169.4254 | 0 | 271.0806
14 |  | Shop | 169.4254 | 0 | 271.0806
15 |  | Shop | 169.4254 | 0 | 271.0806
16 |  | Shop | 190.9534 | 0 | 305.5254
1st Floor for Residential
1 |  | 2BHK | 444.4456 | 232.6639 | 899.3322 | 1st Floor for Residential
2 |  | 2BHK | 444.4456 | 232.6639 | 899.3322
3 |  | 2BHK | 499.5034 | 38.7504 | 788.0055 |  |  | 3824.2117
4 |  | 2BHK | 499.5034 | 38.7504 | 788.0055
2nd, 4th, 6th, 10th & 12th Floor
1 |  | 2BHK | 499.5034 | 35.5212 | 784.7763 | 2nd, 4th, 6th, 10th & 12th Floor
2 |  | 2BHK | 499.5034 | 35.5212 | 784.7763
3 |  | 2BHK | 499.5034 | 35.5212 | 784.7763
4 |  | 2BHK | 499.5034 | 35.5212 | 784.7763
8th Floor (Part Refuge Area)
1 | 4 | 2BHK | 499.5034 | 35.5212 | 784.7763 | 8th Floor (Part Refuge Area)
2 | 3 | 2BHK | 499.5034 | 35.5212 | 784.7763
3 | 2 | Refuge Area
4 | 1
3rd, 5th, 7th, 9th & 11th Floor
1 |  | 2BHK | 499.5034 | 38.7504 | 788.0055 | 3rd, 5th, 7th, 9th & 11th Floor
2 |  | 2BHK | 499.5034 | 38.7504 | 788.0055
3 |  | 2BHK | 499.5034 | 38.7504 | 788.0055
4 |  | 2BHK | 499.5034 | 38.7504 | 788.0055
13th Floor(Part Refuge Area)
1 |  | Refuge Area |  |  |  | 13th Floor(Part Refuge Area)
2 |  | 2BHK | 499.5034 | 38.7504 | 788.0055
3 |  | 2BHK | 499.5034 | 38.7504 | 788.0055
4 |  | 2BHK | 499.5034 | 38.7504 | 788.0055
14th Floor
1 |  | 2BHK | 499.5034 | 35.5212 | 784.7763 | 14th Floor
2 |  | 2BHK | 499.5034 | 35.5212 | 784.7763
3 |  | 2BHK | 499.5034 | 35.5212 | 784.7763
4 |  | 2BHK | 499.5034 | 35.5212 | 784.7763
Wing A3
Ground Floor for Parking & Commercial
1 |  | Shop | 194.1826 | 0 | 310.6921 | Ground Floor for Parking & Commercial
2 |  | Shop | 169.4254 | 0 | 271.0806
3 |  | Shop | 169.4254 | 0 | 271.0806
4 |  | Shop | 169.4254 | 0 | 271.0806
5 |  | Shop | 169.4254 | 0 | 271.0806
6 |  | Shop | 169.4254 | 0 | 271.0806
7 |  | Shop | 195.1513 | 0 | 312.2421
8 |  | Shop | 199.3493 | 0 | 318.9588
1st Floor for Residential
1 |  | 2BHK | 444.4456 | 232.6639 | 783.0003 | 1st Floor for Residential
2 |  | 2BHK | 437.2337 | 232.6639 | 772.1825
3 |  | 2BHK | 492.2915 | 38.7504 | 777.1877
4 |  | 2BHK | 499.5034 | 38.7504 | 788.0055
2nd, 4th, 6th, 10th & 12th Floor
1 |  | 2BHK | 499.5034 | 35.5212 | 767.0157 | 2nd, 4th, 6th, 10th & 12th Floor
2 |  | 2BHK | 492.2915 | 35.5212 | 756.1979
3 |  | 2BHK | 492.2915 | 35.5212 | 773.9585
4 |  | 2BHK | 499.5034 | 35.5212 | 784.7763
8th Floor
1 |  | 2BHK | 499.5034 | 35.5212 | 767.0157 | 8th Floor
2 |  | 2BHK | 492.2915 | 35.5212 | 756.1979
3 |  | 2BHK | 492.2915 | 35.5212 | 773.9585
4 |  | 2BHK | 499.5034 | 35.5212 | 784.7763
3rd, 5th, 7th, 9th & 11th Floor
1 |  | 2BHK | 499.5034 | 38.7504 | 768.6303 | 3rd, 5th, 7th, 9th & 11th Floor
2 |  | 2BHK | 492.2915 | 38.7504 | 757.8125
3 |  | 2BHK | 492.2915 | 38.7504 | 777.1877
4 |  | 2BHK | 499.5034 | 38.7504 | 788.0055
13th Floor
1 |  | 2BHK | 499.5034 | 38.7504 | 768.6303 | 13th Floor
2 |  | 2BHK | 492.2915 | 38.7504 | 757.8125
3 |  | 2BHK | 492.2915 | 38.7504 | 777.1877
4 |  | 2BHK | 499.5034 | 38.7504 | 788.0055
14th Floor
1 |  | 2BHK | 499.5034 | 35.5212 | 767.0157 | 14th Floor
2 |  | 2BHK | 492.2915 | 35.5212 | 756.1979
3 |  | 2BHK | 492.2915 | 35.5212 | 773.9585
4 |  | 2BHK | 499.5034 | 35.5212 | 784.7763
Type B
Wing B1
Ground Floor for Commercial & Parking
7 |  | Shop | 175.6685 | 0 | 281.0696 | Ground Floor for Commercial & Parking
8 |  | Shop | 206.6688 | 0 | 330.6701
9 |  | Shop | 139.0709 | 0 | 222.5134
10 |  | Shop | 139.0709 | 0 | 222.5134
11 |  | Shop | 206.3459 | 0 | 330.1534
12 |  | Shop | 175.6685 | 0 | 281.0696
1st Floor for Commercial & Residential
106 |  | Office | 169.2101 | 0 | 270.7361 | 1st Floor for Commercial & Residential
107 |  | Office | 198.7034 | 0 | 317.9255
108 |  | Office | 133.4736 | 0 | 213.5578
109 |  | Office | 133.4736 | 0 | 213.5578
110 |  | Office | 261.4576 | 0 | 418.3321
1 |  | 1BHK | 362.9352 | 46.339 | 590.7418
2 |  | 1BHK | 362.9352 | 46.339 | 590.7418
2nd Floor for Residential
1 |  | 1BHK | 362.9352 | 46.339 | 590.7418 | 2nd Floor for Residential |  | 544.4028 | 1.5
2 |  | 1BHK | 362.9352 | 46.339 | 590.7418
3 |  | 1BHK | 298.9163 | 261.9958 | 535.7063
4 |  | 1BHK | 298.9163 | 176.8525 | 536.8007
3rd, 5th, 7th, 9th & 11th Floor
1 |  | 1BHK | 362.9352 | 46.339 | 590.7418 | 3rd, 5th, 7th, 9th & 11th Floor
2 |  | 1BHK | 362.9352 | 46.339 | 590.7418
3 |  | 1BHK | 362.9352 | 46.339 | 590.7418
4 |  | 1BHK | 362.9352 | 46.339 | 590.7418
4th, 6th, 10th, 12th Floor
1 |  | 1BHK | 368.9092 | 34.391 | 587.7548 | 4th, 6th, 10th, 12th Floor
2 |  | 1BHK | 368.9092 | 34.391 | 587.7548
3 |  | 1BHK | 368.9092 | 34.391 | 587.7548
4 |  | 1BHK | 368.9092 | 34.391 | 587.7548
8th Floor(Part Refuge Area)
1 |  | 1BHK | 368.9092 | 34.391 | 587.7548 | 8th Floor(Part Refuge Area)
2 |  | 1BHK | 368.9092 | 34.391 | 587.7548
3 |  | 1BHK | 368.9092 | 34.391 | 587.7548
4 |  | Refuge Area
13th Floor(Part Refuge Area)
1 |  | 1BHK | 362.9352 | 46.339 | 590.7418 | 13th Floor(Part Refuge Area)
2 |  | 1BHK | 362.9352 | 46.339 | 590.7418
3 |  | 1BHK | 362.9352 | 46.339 | 590.7418
4 |  | 1BHK | 362.9352 | 46.339 | 590.7418
14th Floor
1 |  | 1BHK | 368.9092 | 34.391 | 587.7548 | 14th Floor
2 |  | 1BHK | 368.9092 | 34.391 | 587.7548
3 |  | 1BHK | 368.9092 | 34.391 | 587.7548 |  |  | 4
4 |  | 1BHK | 368.9092 | 34.391 | 587.7548
Wing B2
Ground Floor for Commercial & Parking
1 |  | Shop | 175.6685 | 0 | 281.0696 | Ground Floor for Commercial & Parking
2 |  | Shop | 206.3459 | 0 | 330.1534
3 |  | Shop | 139.0709 | 0 | 222.5134
4 |  | Shop | 139.0709 | 0 | 222.5134
5 |  | Shop | 206.5612 | 0 | 330.4979
6 |  | Shop | 175.4532 | 0 | 280.7251
1st Floor for Commercial & Residential
101 |  | Office | 169.2101 | 0 | 270.7361 | 1st Floor for Commercial & Residential
102 |  | Office | 198.7034 | 0 | 317.9255
103 |  | Office | 133.4736 | 0 | 213.5578
103A |  | Office | 133.4736 | 0 | 213.5578
104 |  | Office | 198.7034 | 0 | 317.9255
105 |  | Office | 169.2101 | 0 | 270.7361
1 |  | 1BHK | 362.9352 | 46.339 | 590.7418
2 |  | 1BHK | 362.9352 | 46.339 | 590.7418
2nd Floor for Residential
1 |  | 1BHK | 362.9352 | 46.339 | 590.7418 | 2nd Floor for Residential
2 |  | 1BHK | 362.9352 | 46.339 | 590.7418
3 |  | 1BHK | 298.9163 | 176.8525 | 536.8007
4 |  | 1BHK | 298.9163 | 261.9958 | 535.7063
3rd, 5th, 7th, 9th & 11th Floor
1 |  | 1BHK | 362.9352 | 46.339 | 590.7418 | 3rd, 5th, 7th, 9th & 11th Floor
2 |  | 1BHK | 362.9352 | 46.339 | 590.7418
3 |  | 1BHK | 362.9352 | 46.339 | 590.7418
4 |  | 1BHK | 362.9352 | 46.339 | 590.7418
4th, 6th, 10th, 12th Floor
1 |  | 1BHK | 368.9092 | 34.391 | 587.7548 | 4th, 6th, 10th, 12th Floor
2 |  | 1BHK | 368.9092 | 34.391 | 587.7548
3 |  | 1BHK | 368.9092 | 34.391 | 587.7548
4 |  | 1BHK | 368.9092 | 34.391 | 587.7548
8th Floor(Part Refuge Area)
1 |  | 1BHK | 368.9092 | 34.391 | 587.7548 | 8th Floor(Part Refuge Area)
2 |  | 1BHK | 368.9092 | 34.391 | 587.7548
3 |  | Refuge Area
4 |  | 1BHK | 368.9092 | 34.391 | 587.7548
13th Floor(Part Refuge Area)
1 |  | 1BHK | 362.9352 | 46.339 | 590.7418 | 13th Floor(Part Refuge Area)
2 |  | 1BHK | 362.9352 | 46.339 | 590.7418
3 |  | Refuge Area
4 |  | 1BHK | 362.9352 | 46.339 | 590.7418
14th Floor
1 |  | 1BHK | 368.9092 | 34.391 | 587.7548 | 14th Floor
2 |  | 1BHK | 368.9092 | 34.391 | 587.7548
3 |  | 1BHK | 368.9092 | 34.391 | 587.7548
4 |  | 1BHK | 368.9092 | 34.391 | 587.7548
Type C1
Ground Floor for Parking
1st, 3rd, 5th, 7th, 9th & 11th Floor
1 |  | 1BHK | 314.3088 | 39.4608 | 510.924 | 1st, 3rd, 5th, 7th, 9th & 11th Floor
2 |  | 1BHK | 312.2636 | 39.4608 | 507.8563
3 |  | 1BHK | 313.2324 | 39.4608 | 509.3094
4 |  | 1BHK | 313.2324 | 39.4608 | 509.3094
2nd, 4th, 6th, 10th & 12th Floor
1 |  | 1BHK | 319.7177 | 27.2867 | 506.8633 | 2nd, 4th, 6th, 10th & 12th Floor |  | 5918.7556
2 |  | 1BHK | 317.6726 | 27.2867 | 503.7956
3 |  | 1BHK | 318.6413 | 27.2867 | 505.2487
4 |  | 1BHK | 318.6413 | 27.2867 | 505.2487
8th Floor(Part Refuge Area)
1 |  | 1BHK | 319.7177 | 27.2867 | 506.8633 | 8th Floor(Part Refuge Area)
2 |  | 1BHK | 317.6726 | 27.2867 | 503.7956
3 |  | Refuge Area
4 |  | 1BHK | 318.6413 | 27.2867 | 505.2487
13th Floor(Part Refuge Area)
1 |  | 1BHK | 314.3088 | 39.4608 | 510.924 | 13th Floor(Part Refuge Area)
2 |  | 1BHK | 312.2636 | 39.4608 | 507.8563
3 |  | Refuge Area
4 |  | 1BHK | 313.2324 | 39.4608 | 509.3094
14th Floor
1 |  | 1BHK | 319.7177 | 27.2867 | 506.8633 | 14th Floor
2 |  | 1BHK | 317.6726 | 27.2867 | 503.7956
3 |  | 1BHK | 318.6413 | 27.2867 | 505.2487
4 |  | 1BHK | 318.6413 | 27.2867 | 505.2487
Type C2
Ground Floor for Parking
1st, 3rd, 5th, 7th, 9th & 11th Floor
1 |  | 1BHK | 314.8201 | 39.4608 | 511.691 | 1st, 3rd, 5th, 7th, 9th & 11th Floor
2 |  | 1BHK | 314.8201 | 39.4608 | 511.691
3 |  | 1BHK | 314.9008 | 39.4608 | 511.8121
4 |  | 1BHK | 314.847 | 39.4608 | 511.7313
2nd, 4th, 6th, 10th & 12th Floor
1 |  | 1BHK | 320.229 | 27.2867 | 507.6302 | 2nd, 4th, 6th, 10th & 12th Floor
2 |  | 1BHK | 320.229 | 27.2867 | 507.6302
3 |  | 1BHK | 320.3097 | 27.2867 | 507.7513
4 |  | 1BHK | 320.2559 | 27.2867 | 507.6706
8th Floor(Part Refuge Area)
1 |  | 1BHK | 319.7177 | 27.2867 | 506.8633 | 8th Floor(Part Refuge Area)
2 |  | 1BHK | 317.6726 | 27.2867 | 503.7956
3 |  | Refuge Area
4 |  | 1BHK | 318.6413 | 27.2867 | 505.2487
13th Floor(Part Refuge Area)
1 |  | 1BHK | 320.229 | 27.2867 | 507.6302 | 13th Floor(Part Refuge Area)
2 |  | 1BHK | 320.229 | 27.2867 | 507.6302
3 |  | Refuge Area
4 |  | 1BHK | 320.2559 | 27.2867 | 507.6706
14th Floor
1 |  | 1BHK | 320.229 | 27.2867 | 507.6302 | 14th Floor
2 |  | 1BHK | 320.229 | 27.2867 | 507.6302
3 |  | 1BHK | 320.3097 | 27.2867 | 507.7513
4 |  | 1BHK | 320.2559 | 27.2867 | 507.6706
Wing C3
Ground Floor for Parking & Commercial
1 |  | Shop | 212.0939 | 0 | 339.3502 | Ground Floor for Parking & Commercial
2 |  | Shop | 174.7212 | 0 | 279.554
3 |  | Shop | 174.7212 | 0 | 279.554
4 |  | Shop | 187.1752 | 0 | 299.4803
5 |  | Shop | 187.1752 | 0 | 299.4803
6 |  | Shop | 180.0602 | 0 | 288.0963
7 |  | Shop | 171.8042 | 0 | 274.8867
8 |  | Shop | 178.93 | 0 | 286.288
9 |  | Shop | 178.93 | 0 | 286.288
10 |  | Shop | 266.0753 | 0 | 425.7205
1st Floor for Residential
1 |  | 1BHK | 389.6891 | 0 | 584.5336 | 1st Floor for Residential |  | 31.02 | 4.55
2 |  | 1BHK | 389.6891 | 0 | 584.5336 |  |  | 26.47
3 |  | 1BHK | 326.0416 | 238.8209 | 568.6693
4 |  | 1BHK | 389.6891 | 67.0398 | 651.5734
5 |  | 2BHK | 584.4529 | 21.9586 | 898.6379 |  |  |  | 44.6525
6 |  | 2BHK | 584.4529 | 21.9586 | 898.6379
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 1BHK | 389.6891 | 0 | 584.5336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
2 |  | 1BHK | 389.6568 | 0 | 584.4852
3 |  | 1BHK | 389.6568 | 0 | 584.4852
4 |  | 1BHK | 389.6891 | 0 | 584.5336
5 |  | 2BHK | 584.4529 | 0 | 876.6794
6 |  | 2BHK | 584.4529 | 0 | 876.6794
8th, 13th & 18th Floor
1 |  | 1BHK | 389.6891 | 0 | 584.5336 | 8th, 13th & 18th Floor
2 |  | 1BHK | 389.6568 | 0 | 584.4852
3 |  | 1BHK | 389.6568 | 0 | 584.4852
4 |  | 1BHK | 389.6891 | 0 | 584.5336
5 |  | 2BHK | 584.4529 | 0 | 876.6794
6 |  | 2BHK | 584.4529 | 0 | 876.6794
Wing C4
Ground Floor for Parking & Commercial
11 |  | Shop | 178.93 | 0 | 286.288 | Ground Floor for Parking & Commercial
12 |  | Shop | 174.7212 | 0 | 279.554
13 |  | Shop | 171.8042 | 0 | 274.8867
14 |  | Shop | 168.9302 | 0 | 270.2883
15 |  | Shop | 176.056 | 0 | 281.6896
16 |  | Shop | 209.4244 | 0 | 335.079
17 |  | Shop | 187.1752 | 0 | 299.4803
18 |  | Shop | 187.1752 | 0 | 299.4803
19 |  | Shop | 187.1752 | 0 | 299.4803
1st Floor for Residential
1 |  | 1BHK | 389.6891 | 0 | 584.5336 | 1st Floor for Residential |  | 31.02 | 4.55
2 |  | 1BHK | 389.6891 | 0 | 584.5336 |  |  | 26.47
3 |  | 1BHK | 326.0416 | 0 | 489.0623
4 |  | 1BHK | 326.0416 | 238.8209 | 727.8832
5 |  | 1BHK | 326.0416 | 67.0398 | 556.1021 |  |  |  | 44.6525
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 1BHK | 389.6891 | 0 | 584.5336 | 2nd to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
2 |  | 1BHK | 389.6568 | 0 | 584.4852
3 |  | 1BHK | 389.6568 | 0 | 584.4852
4 |  | 1BHK | 389.6568 | 0 | 584.4852
5 |  | 1BHK | 389.6568 | 0 | 584.4852
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 1BHK | 389.6568 | 0 | 584.4852
3 |  | 1BHK | 389.6568 | 0 | 584.4852
4 |  | 1BHK | 389.6568 | 0 | 584.4852
5 |  | 1BHK | 389.6568 | 0 | 584.4852
Type D1
Ground Floor for Parking
1st to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 2BHK | 587.0147 | 0 | 880.5221 | 1st to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor |  | 46.9232
2 |  | 2BHK | 587.0147 | 0 | 880.5221
3 |  | 1BHK | 389.6568 | 0 | 584.4852
4 |  | 1BHK | 389.6568 | 0 | 584.4852
5 |  | 1BHK | 423.5634 | 0 | 635.3451 |  |  |  | 35.575 | 9.165
6 |  | 1BHK | 423.5634 | 0 | 635.3451 |  |  |  | 26.41
7 |  | 1BHK | 389.6568 | 0 | 584.4852
8 |  | 1BHK | 389.6568 | 0 | 584.4852
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2BHK | 587.0147 | 0 | 880.5221 | 8th, 13th & 18th Floor (Part Refuge Area) |  | 46.9232
2 |  | 2BHK | 587.0147 | 0 | 880.5221
3 |  | Refuge Area
4 |  | 1BHK | 389.6568 | 0 | 584.4852
5 |  | 1BHK | 423.5634 | 0 | 635.3451 |  |  |  | 35.575 | 9.165
6 |  | 1BHK | 423.5634 | 0 | 635.3451 |  |  |  | 26.41
7 |  | 1BHK | 389.6568 | 0 | 584.4852
8 |  | 1BHK | 389.6568 | 0 | 584.4852
Wing H1 - Navkar Empire
Ground Floor for Parking & Commercial
1 |  | Shop | 311.4994 | 0 | 498.399 | Ground Floor for Parking & Commercial
2 |  | Shop | 325.794 | 0 | 521.2704
3 |  | Shop | 292.8023 | 0 | 468.4837
4 |  | Shop | 251.5654 | 0 | 402.5047
5 |  | Shop | 217.2713 | 0 | 347.6341
6 |  | Shop | 186.1311 | 0 | 297.8097
7 |  | Shop | 179.0161 | 0 | 286.4257
8 |  | Shop | 179.0161 | 0 | 286.4257
9 |  | Shop | 186.1311 | 0 | 297.8097
10 |  | Shop | 254.2672 | 0 | 406.8275
11 |  | Shop | 373.9306 | 0 | 598.289
12 |  | Shop | 356.8697 | 0 | 570.9914
1st Floor for Parking, Commercial & Residential
1 |  | Office | 309.5403 | 0 | 495.2646 | 1st Floor for Parking, Commercial & Residential
2 |  | Office | 277.5713 | 0 | 444.114
3 |  | Office | 249.4686 | 0 | 399.1498
4 |  | Office | 212.7182 | 0 | 340.3491
5 |  | Office | 178.4133 | 0 | 285.4613
6 |  | Office | 145.6154 | 0 | 232.9846
7 |  | Office | 138.4896 | 0 | 221.5834
8 |  | Office | 138.4896 | 0 | 221.5834
9 |  | Office | 145.6154 | 0 | 232.9846
10 |  | Office | 372.2406 | 0 | 595.585
11 |  | Office | 349.0119 | 0 | 558.4191
1 |  | 2BHK | 587.0147 | 0 | 880.5221
2 |  | 2BHK | 587.0147 | 0 | 880.5221
2nd Floor
1 |  | 2BHK | 587.0147 | 0 | 880.5221 | 2nd Floor
2 |  | 2BHK | 587.0147 | 0 | 880.5221
3 |  | 3BHK | 675.0051 | 72.9261 | 1085.4337
4 |  | 3BHK | 675.0051 | 99.7285 | 1062.3718
5 |  | 1BHK | 400.4343 | 22.2007 | 622.8521
6 |  | 1BHK | 400.4343 | 22.2007 | 622.8521
7 |  | 1BHK | 326.0416 | 155.6151 | 566.8699
8 |  | 1BHK | 389.6568 | 0 | 584.4852
3rd to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 2BHK | 587.0147 | 0 | 880.5221 | 3rd to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
2 |  | 2BHK | 587.0147 | 0 | 880.5221
3 |  | 3BHK | 675.0051 | 0 | 1012.5076
4 |  | 3BHK | 675.0051 | 0 | 1012.5076
5 |  | 1BHK | 423.5634 | 0 | 635.3451
6 |  | 1BHK | 423.5634 | 0 | 635.3451
7 |  | 1BHK | 389.6568 | 0 | 584.4852
8 |  | 1BHK | 389.6568 | 0 | 584.4852
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2BHK | 587.0147 | 0 | 880.5221 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 2BHK | 587.0147 | 0 | 880.5221
3 |  | 3BHK | 675.0051 | 0 | 1012.5076
4 |  | 3BHK | 675.0051 | 0 | 1012.5076
5 |  | 1BHK | 423.5634 | 0 | 635.3451
6 |  | 1BHK | 423.5634 | 0 | 635.3451
7 |  | 1BHK | 389.6568 | 0 | 584.4852
8 |  | Refuge Area
Part 6
Wing/Type G - Navkar Harmony
Ground Floor for Parking
1st to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor for Residential
1 |  | 2BHK | 587.4453 | 0 | 881.168 | 1st to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor for Residential |  |  | 45.7636
2 |  | 2BHK | 521.2036 | 0 | 781.8055
3 |  | 2BHK | 521.2036 | 0 | 781.8055
4 |  | 2BHK | 587.4453 | 0 | 881.168
5 |  | 1BHK | 325.6218 | 0 | 488.4326
6 |  | 1BHK | 326.0416 | 0 | 489.0623
7 |  | 1BHK | 332.0694 | 0 | 498.1041
8 |  | 2BHK | 536.1441 | 0 | 804.2161
9 |  | 2BHK | 536.1441 | 0 | 804.2161
10 |  | 1BHK | 332.0694 | 0 | 498.1041
11 |  | 1BHK | 325.6218 | 0 | 488.4326
12 |  | 1BHK | 326.0416 | 0 | 489.0623
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2BHK | 587.4453 | 0 | 881.168 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 2BHK | 521.2036 | 0 | 781.8055
3 |  | 2BHK | 521.2036 | 0 | 781.8055
4 |  | 2BHK | 587.4453 | 0 | 881.168
5 |  | 1BHK | 325.6218 | 0 | 488.4326
6 |  | 1BHK | 326.0416 | 0 | 489.0623
7 |  | 1BHK | 332.0694 | 0 | 498.1041
8 |  | Refuge Area
9 |  | 2BHK | 536.1441 | 0 | 804.2161
10 |  | 1BHK | 332.0694 | 0 | 498.1041
11 |  | 1BHK | 325.6218 | 0 | 488.4326
12 |  | 1BHK | 326.0416 | 0 | 489.0623
Part 9
Wing H2 + H3
Ground Floor for Parking & Commercial | [8 empty] | 10.764
13 |  | Shop | 264.0624 | 0 | 422.4999 | Ground Floor for Parking & Commercial |  |  | 22.2702
14 |  | Shop | 270.7146 | 0 | 433.1434 |  |  |  | 24.8511
15 |  | Shop | 322.0266 | 0 | 515.2425
16 |  | Shop | 268.6587 | 0 | 429.8539
17 |  | Shop | 219.6609 | 0 | 351.4575
18 |  | Shop | 178.2088 | 0 | 285.1341
19 |  | Shop | 181.2442 | 0 | 289.9908
20 |  | Shop | 191.5992 | 0 | 306.5587
21 |  | Shop | 188.37 | 0 | 301.392
22 |  | Shop | 279.864 | 0 | 447.7824
23 |  | Shop | 221.6631 | 0 | 354.6609
24 |  | Shop | 214.5265 | 0 | 343.2424
25 |  | Shop | 178.2088 | 0 | 285.1341
26 |  | Shop | 214.3328 | 0 | 342.9324
27 |  | Shop | 293.3298 | 0 | 469.3276
1st Floor for Commercial & Fitness Center
12 |  | Office | 223.7297 | 0 | 357.9676 | 1st Floor for Commercial & Fitness Center
13 |  | Office | 230.1128 | 0 | 368.1805
14 |  | Office | 273.7393 | 0 | 437.9829
15 |  | Office | 220.436 | 0 | 352.6975
16 |  | Office | 179.1991 | 0 | 286.7185
17 |  | Office | 137.6608 | 0 | 220.2573
18 |  | Office | 140.0396 | 0 | 224.0634
19 |  | Office | 149.3182 | 0 | 238.9091
20 |  | Office | 270.8545 | 0 | 433.3673
21 |  | Office | 173.1712 | 0 | 277.074
22 |  | Office | 166.0562 | 0 | 265.69
23 |  | Office | 137.6716 | 0 | 220.2745
24 |  | Office | 131.2239 | 0 | 209.9583
25 |  | Office | 225.312 | 0 | 360.4993
2nd Floor for Residential
1 |  | 2BHK | 595.2061 | 0 | 952.3298 | 2nd Floor for Residential |  |  | 44.7835
2 |  | 2BHK | 587.0147 | 0 | 939.2236
3 |  | 1BHK | 383.7474 | 0 | 613.9958 |  |  |  | 23.43
4 |  | 1BHK | 360.0827 | 155.0016 | 576.1323
5 |  | 1BHK | 399.9095 | 59.202 | 639.8552
6 |  | 2BHK | 576.0032 | 25.8336 | 921.6051
7 |  | 2BHK | 576.0032 | 25.8336 | 921.6051
8 |  | 1BHK | 379.0435 | 0 | 606.4696
9 |  | 1BHK | 383.7474 | 0 | 613.9958
10 |  | 2BHK | 587.0147 | 0 | 939.2236
11 |  | 2BHK | 595.2061 | 0 | 952.3298
3rd to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 2BHK | 595.2061 | 0 | 952.3298 | 3rd to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
2 |  | 2BHK | 587.0147 | 0 | 939.2236
3 |  | 1BHK | 383.7474 | 0 | 613.9958
4 |  | 1BHK | 360.0827 | 0 | 576.1323
5 |  | 1BHK | 430.9098 | 0 | 689.4557
6 |  | 2BHK | 576.0032 | 0 | 921.6051
7 |  | 2BHK | 576.0032 | 0 | 921.6051
8 |  | 1BHK | 379.0435 | 0 | 606.4696
9 |  | 1BHK | 383.7474 | 0 | 613.9958
10 |  | 2BHK | 587.0147 | 0 | 939.2236
11 |  | 2BHK | 595.2061 | 0 | 952.3298
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2BHK | 595.2061 | 0 | 952.3298 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 2BHK | 587.0147 | 0 | 939.2236
3 |  | 1BHK | 383.7474 | 0 | 613.9958
4 |  | 1BHK | 360.0827 | 0 | 576.1323
5 |  | 1BHK | 430.9098 | 0 | 689.4557
6 |  | 2BHK | 576.0032 | 0 | 921.6051
- |  | Refuge Area
7 |  | 1BHK | 379.0435 | 0 | 606.4696
8 |  | 1BHK | 383.7474 | 0 | 613.9958
9 |  | 2BHK | 587.0147 | 0 | 939.2236
10 |  | 2BHK | 595.2061 | 0 | 952.3298
Type R1 | [8 empty] | 10.764
Ground Floor for Parking
1st to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 2BHK | 596.4332 | 0 | 894.6499 | 1st to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor |  | 44.9436 | 9.5 | 54.4436
2 |  | 2BHK | 596.4332 | 0 | 894.6499
3 |  | 1BHK | 360.0827 | 0 | 540.1241 |  |  | 23.395 | 7.7625 | 31.1575
4 |  | 1BHK | 360.0827 | 0 | 540.1241
5 |  | 1BHK | 421.4375 | 0 | 632.1563
6 |  | 1BHK | 421.4375 | 0 | 632.1563
7 |  | 1BHK | 360.0827 | 0 | 540.1241
8 |  | 1BHK | 360.0827 | 0 | 540.1241
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2BHK | 596.4332 | 0 | 894.6499 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 2BHK | 596.4332 | 0 | 894.6499
3 |  | Refuge Area
4 |  | 1BHK | 360.0827 | 0 | 540.1241
5 |  | 1BHK | 421.4375 | 0 | 632.1563
6 |  | 1BHK | 421.4375 | 0 | 632.1563
7 |  | 1BHK | 360.0827 | 0 | 540.1241
8 |  | 1BHK | 360.0827 | 0 | 540.1241
Type R2 | [8 empty] | 10.764
Ground Floor for Parking
1st to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor
1 |  | 2BHK | 596.4332 | 0 | 894.6499 | 1st to 7th, 9th to 12th, 14th to 17th, 19th to 23rd Floor |  | 44.9436 | 9.5 | 54.4436
2 |  | 2BHK | 596.4332 | 0 | 894.6499
3 |  | 1BHK | 360.0827 | 0 | 540.1241 |  |  | 23.395 | 7.7625 | 31.1575
4 |  | 1BHK | 360.0827 | 0 | 540.1241
5 |  | 1BHK | 421.4375 | 0 | 632.1563
6 |  | 1BHK | 421.4375 | 0 | 632.1563
7 |  | 1BHK | 360.0827 | 0 | 540.1241
8 |  | 1BHK | 360.0827 | 0 | 540.1241
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2BHK | 596.4332 | 0 | 894.6499 | 8th, 13th & 18th Floor (Part Refuge Area)
2 |  | 2BHK | 596.4332 | 0 | 894.6499
3 |  | Refuge Area
4 |  | 1BHK | 360.0827 | 0 | 540.1241
5 |  | 1BHK | 421.4375 | 0 | 632.1563
6 |  | 1BHK | 421.4375 | 0 | 632.1563
7 |  | 1BHK | 360.0827 | 0 | 540.1241
8 |  | 1BHK | 360.0827 | 0 | 540.1241
Phase II
Type A
Ground Floor for Parking & Commercial
1&2 |  | Shop | 2797.2407 | 0 | 4475.5851 | Ground Floor for Parking & Commercial
3 |  | Shop | 213.8807 | 0 | 342.2091
4 |  | Shop | 244.5581 | 0 | 391.2929
5 |  | Shop | 289.7669 | 0 | 463.627
5A |  | Shop | 213.8807 | 0 | 342.2091
6 |  | Shop | 213.8807 | 0 | 342.2091
7 |  | Shop | 287.2912 | 0 | 459.6659
8 |  | Shop | 260.1659 | 0 | 416.2654
9 |  | Shop | 263.8256 | 0 | 422.121
1st Floor for Residential
1 |  | 3BHK | 751.8385 | 758.1085 | 1236.059 | 1st Floor for Residential
2 |  | 3BHK | 825.1682 | 48.438 | 1286.1904
MP Room-1 |  | 1RK | 369.5443 | 0 | 554.3164
MP Room-2 |  | 1RK | 242.9941 | 0 | 364.4911
MP Room-3 |  | 1RK | 247.7894 | 0 | 371.6841
MP Room-4 |  | 1RK | 323.4754 | 0 | 485.2131
MP Room-5 |  | 1RK | 244.4504 | 0 | 366.6757
MP Room-6 |  | 1RK | 189.4216 | 0 | 284.1325
MP Room-7 |  | 1RK | 223.4499 | 0 | 335.1748
MP Room-8 |  | 1RK | 173.8117 | 0 | 260.7175
MP Room-9 |  | 1RK | 178.9946 | 0 | 268.4918
2nd Floor
1 |  | 2BHK | 634.188 | 214.1509 | 1022.6656 | 2nd Floor
2 |  | 2BHK | 610.1304 | 161.0908 | 995.741
3 |  | 3BHK | 723.4484 | 449.0741 | 1174.9875
4 |  | 3BHK | 735.8809 | 967.6836 | 1200.5896
3rd Floor
1 |  | 2BHK | 609.969 | 48.438 | 931.0995 | 3rd Floor
2 |  | 2BHK | 610.1304 | 48.438 | 939.4146
3 |  | 3BHK | 836.4704 | 0 | 1254.7057 |  |  | 4940.2025
4 |  | 3BHK | 835.9861 | 0 | 1253.9791
4th & 10th Floor
1 |  | 3BHK | 815.9112 | 54.0891 | 1241.8965 | 4th & 10th Floor
2 |  | 3BHK | 817.4182 | 54.0891 | 1253.1718
3 |  | 3BHK | 836.4704 | 54.0891 | 1265.5235
4 |  | 3BHK | 835.9861 | 54.0891 | 1259.388
5th & 11th Floor
1 |  | 2BHK | 608.5696 | 262.5889 | 1000.3841 | 5th & 11th Floor
2 |  | 2BHK | 610.1304 | 209.5288 | 1019.96 |  |  | 4395.7604
3 |  | 3BHK | 836.4704 | 48.438 | 1264.3933
4 |  | 3BHK | 835.9861 | 48.438 | 1258.8229
6th, 12th Floor
1 |  | 2BHK | 609.969 | 48.438 | 931.0995 | 6th, 12th Floor
2 |  | 2BHK | 610.1304 | 48.438 | 939.4146
3 |  | 3BHK | 812.2514 | 48.438 | 1228.0648
4 |  | 3BHK | 811.7671 | 48.438 | 1222.4944
7th Floor
1 |  | 3BHK | 815.9112 | 48.438 | 1240.0128 | 7th Floor
2 |  | 3BHK | 817.4182 | 48.438 | 1250.3462
3 |  | 3BHK | 812.2514 | 48.438 | 1228.0648
4 |  | 3BHK | 811.7671 | 48.438 | 1222.4944
8th Floor(Part Refuge Area)
1 |  | Refuge Area |  |  |  | 8th Floor(Part Refuge Area)
2 |  | 2BHK | 600.1737 | 209.5288 | 1005.025
3 |  | 3BHK | 812.2514 | 48.438 | 1228.0648
4 |  | 3BHK | 816.7185 | 48.438 | 1229.9215
9th Floor
1 |  | 2BHK | 608.5696 | 48.438 | 929.0005 | 9th Floor
2 |  | 2BHK | 581.9287 | 48.438 | 897.1121
3 |  | 3BHK | 812.2514 | 48.438 | 1228.0648
4 |  | 3BHK | 811.7671 | 48.438 | 1222.4944
13th Floor(Part Refuge Area)
1 |  | 3BHK | 816.1265 | 48.438 | 1240.3357 | 13th Floor(Part Refuge Area)
2 |  | 3BHK | 815.8036 | 48.438 | 1247.9243
3 |  | 3BHK | 729.3686 | 48.438 | 1103.7406
4 |  | 3BHK | 811.7671 | 48.438 | 1222.4944
14th Floor
1 |  | 2BHK | 609.969 | 262.5889 | 1002.4831 | 14th Floor
2 |  | 2BHK | 610.1304 | 209.5288 | 1019.96
3 |  | 3BHK | 812.2514 | 48.438 | 1228.0648
4 |  | 3BHK | 811.7671 | 48.438 | 1222.4944
Type B1 & B2
Type B1
Ground Floor for Parking
1st, 3rd, 5th, 7th, 9th & 11th Floor
1 |  | 2BHK | 567.8548 | 48.7609 | 900.5431 | 1st, 3rd, 5th, 7th, 9th & 11th Floor
2 |  | 2BHK | 575.8202 | 48.7609 | 912.4912
3 |  | 2BHK | 567.7472 | 48.7609 | 900.3817
4 |  | 2BHK | 567.9625 | 48.7609 | 900.7046
2nd, 4th, 6th, 10th, 12th & 14th Floor
1 |  | 2BHK | 574.071 | 36.3285 | 897.435 | 2nd, 4th, 6th, 10th, 12th & 14th Floor
2 |  | 2BHK | 582.0364 | 36.3285 | 909.3831
3 |  | 2BHK | 573.9634 | 36.3285 | 897.2736
4 |  | 2BHK | 574.1787 | 36.3285 | 897.5965
8th Floor(Part Refuge Area)
1 |  | Refuge Area |  |  |  | 8th Floor(Part Refuge Area)
2 |  | 2BHK | 582.0364 | 36.3285 | 909.3831
3 |  | 2BHK | 573.9634 | 36.3285 | 897.2736
4 |  | 2BHK | 574.1787 | 36.3285 | 897.5965
13th Floor
1 |  | 2BHK | 567.8548 | 48.7609 | 900.5431 | 13th Floor
2 |  | 2BHK | 575.8202 | 48.7609 | 912.4912
3 |  | 2BHK | 567.7472 | 48.7609 | 900.3817
4 |  | 2BHK | 567.9625 | 48.7609 | 900.7046
Type B2
Ground Floor for Parking
1st, 3rd, 5th, 7th, 9th & 11th Floor
1 |  | 2BHK | 572.8063 | 48.7609 | 907.9703 | 1st, 3rd, 5th, 7th, 9th & 11th Floor
2 |  | 2BHK | 572.8063 | 48.7609 | 907.9703
3 |  | 2BHK | 572.8063 | 48.7609 | 907.9703
4 |  | 2BHK | 562.7957 | 48.7609 | 892.9545
2nd, 4th, 6th, 10th, 12th & 14th Floor
1 |  | 2BHK | 579.0225 | 36.3285 | 904.8622 | 2nd, 4th, 6th, 10th, 12th & 14th Floor
2 |  | 2BHK | 579.0225 | 36.3285 | 904.8622
3 |  | 2BHK | 579.0225 | 36.3285 | 904.8622
4 |  | 2BHK | 569.0119 | 36.3285 | 889.8464
8th Floor(Part Refuge Area)
1 |  | 2BHK | 579.0225 | 36.3285 | 904.8622 | 8th Floor(Part Refuge Area)
2 |  | Refuge Area
3 |  | 2BHK | 579.0225 | 36.3285 | 904.8622
4 |  | 2BHK | 569.0119 | 36.3285 | 889.8464
13th Floor(Part Refuge Area)
1 |  | 2BHK | 572.8063 | 48.7609 | 907.9703 | 13th Floor(Part Refuge Area)
2 |  | 2BHK | 572.8063 | 48.7609 | 907.9703
3 |  | 2BHK | 572.8063 | 48.7609 | 907.9703
4 |  | 2BHK | 562.7957 | 48.7609 | 892.9545
Type C1, C2, C3
Wing C1
Ground Floor for Parking
1st, 3rd, 5th, 7th & 9th Floor
1 |  | 1BHK | 380.938 | 40.365 | 611.7719 | 1st, 3rd, 5th, 7th & 9th Floor
2 |  | 1BHK | 380.938 | 37.1358 | 608.5427
3 |  | 1BHK | 380.938 | 37.1358 | 608.5427
4 |  | 1BHK | 380.938 | 37.1358 | 608.5427
5 |  | 1BHK | 380.938 | 37.1358 | 608.5427
6 |  | 1BHK | 380.938 | 40.365 | 611.7719
2nd, 4th & 6th Floor
1 |  | 1BHK | 375.2869 | 48.438 | 611.3683 | 2nd, 4th & 6th Floor
2 |  | 1BHK | 375.529 | 48.438 | 611.7316
3 |  | 1BHK | 375.529 | 48.438 | 611.7316
4 |  | 1BHK | 375.529 | 48.438 | 611.7316
5 |  | 1BHK | 375.2869 | 48.438 | 611.3683
6 |  | 1BHK | 375.529 | 48.438 | 611.7316
8th Floor(Part Refuge Area)
1 |  | 1BHK | 375.2869 | 48.438 | 611.3683 | 8th Floor(Part Refuge Area)
2 |  | 1BHK | 375.529 | 48.438 | 611.7316
3 |  | 1BHK | 375.529 | 48.438 | 611.7316
4 |  | 1BHK | 375.529 | 48.438 | 611.7316
5 |  | 1BHK | 375.2869 | 48.438 | 611.3683
6 |  | Refuge Area
10th Floor
1 |  | 1BHK | 375.2869 | 48.438 | 611.3683 | 10th Floor
2 |  | 1BHK | 375.529 | 48.438 | 611.7316
3 |  | 1BHK | 375.529 | 48.438 | 611.7316
4 |  | 1BHK | 375.529 | 48.438 | 611.7316
5 |  | 1BHK | 375.2869 | 48.438 | 611.3683
6 |  | 1BHK | 375.529 | 48.438 | 611.7316
11th Floor
1 |  | 1BHK | 380.938 | 40.365 | 611.7719 | 11th Floor
2 |  | 1BHK | 380.938 | 37.1358 | 608.5427
3 |  | 1BHK | 380.938 | 37.1358 | 608.5427
4 |  | 1BHK | 380.938 | 37.1358 | 608.5427
5 |  | 1BHK | 380.938 | 37.1358 | 608.5427
6 |  | 1BHK | 380.938 | 40.365 | 611.7719
12th Floor
1 |  | 1BHK | 375.2869 | 48.438 | 611.3683 | 12th Floor
2 |  | 1BHK | 375.529 | 48.438 | 611.7316
3 |  | 1BHK | 375.529 | 48.438 | 611.7316
4 |  | 1BHK | 375.529 | 48.438 | 611.7316
5 |  | 1BHK | 375.2869 | 48.438 | 611.3683
6 |  | 1BHK | 375.529 | 48.438 | 611.7316
14th Floor
1 |  | 1BHK | 375.2869 | 48.438 | 611.3683 | 14th Floor
2 |  | 1BHK | 375.529 | 48.438 | 611.7316
3 |  | 1BHK | 375.529 | 48.438 | 611.7316
4 |  | 1BHK | 375.529 | 48.438 | 611.7316
5 |  | 1BHK | 375.2869 | 48.438 | 611.3683
6 |  | 1BHK | 375.529 | 48.438 | 611.7316
13th Floor
1 |  | 1BHK | 380.938 | 40.365 | 611.7719 | 13th Floor
2 |  | 1BHK | 380.938 | 37.1358 | 608.5427
3 |  | 1BHK | 380.938 | 37.1358 | 608.5427
4 |  | 1BHK | 380.938 | 37.1358 | 608.5427
5 |  | 1BHK | 380.938 | 37.1358 | 608.5427
6 |  | Refuge Area
Wing C2
Ground Floor for Parking
1st, 3rd, 5th, 7th & 9th Floor
1 |  | 1BHK | 380.938 | 40.365 | 611.7719 | 1st, 3rd, 5th, 7th & 9th Floor
2 |  | 1BHK | 325.4764 | 32.292 | 520.5067
3 |  | 1BHK | 325.5034 | 32.292 | 520.547
4 |  | 1BHK | 366.5142 | 36.3285 | 586.0998
5 |  | 1BHK | 366.5142 | 36.3285 | 586.0998
6 |  | 1BHK | 380.938 | 40.365 | 611.7719
2nd, 4th & 6th Floor
1 |  | 1BHK | 375.2869 | 48.438 | 611.3683 | 2nd, 4th & 6th Floor
2 |  | 1BHK | 319.4217 | 44.4015 | 523.534
3 |  | 1BHK | 319.4217 | 44.4015 | 523.534
4 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
5 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
6 |  | 1BHK | 375.2869 | 48.438 | 611.3683
8th Floor(Part Refuge Area)
1 |  | Refuge Area |  |  |  | 8th Floor(Part Refuge Area)
2 |  | 1BHK | 319.4217 | 44.4015 | 523.534
3 |  | 1BHK | 319.4217 | 44.4015 | 523.534
4 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
5 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
6 |  | Refuge Area
10th Floor
1 |  | 1BHK | 375.2869 | 48.438 | 611.3683 | 10th Floor
2 |  | 1BHK | 319.4217 | 44.4015 | 523.534
3 |  | 1BHK | 319.4217 | 44.4015 | 523.534
4 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
5 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
6 |  | 1BHK | 375.2869 | 48.438 | 611.3683
11th Floor
1 |  | 1BHK | 380.938 | 40.365 | 611.7719 | 11th Floor
2 |  | 1BHK | 325.4764 | 32.292 | 520.5067
3 |  | 1BHK | 325.5034 | 32.292 | 520.547
4 |  | 1BHK | 366.5142 | 36.3285 | 586.0998
5 |  | 1BHK | 366.5142 | 36.3285 | 586.0998
6 |  | 1BHK | 380.938 | 40.365 | 611.7719
12th & 14th Floor
1 |  | 1BHK | 375.2869 | 48.438 | 611.3683 | 12th & 14th Floor
2 |  | 1BHK | 319.4217 | 44.4015 | 523.534
3 |  | 1BHK | 319.4217 | 44.4015 | 523.534
4 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
5 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
6 |  | 1BHK | 375.2869 | 48.438 | 611.3683
13th Floor
1 |  | 1BHK | 380.938 | 40.365 | 611.7719 | 13th Floor
2 |  | 1BHK | 325.4764 | 32.292 | 520.5067
3 |  | 1BHK | 325.5034 | 32.292 | 520.547
4 |  | 1BHK | 366.5142 | 36.3285 | 586.0998
5 |  | 1BHK | 366.5142 | 36.3285 | 586.0998
6 |  | 1BHK | 380.938 | 40.365 | 611.7719
Wing C3
Ground Floor for Parking
1st, 3rd, 5th, 7th & 9th Floor
1 |  | 1BHK | 380.938 | 40.365 | 611.7719 | 1st, 3rd, 5th, 7th & 9th Floor
2 |  | 1BHK | 325.5034 | 32.292 | 520.547 |  |  | 5789.1022
3 |  | 1BHK | 329.8897 | 32.292 | 527.1265
4 |  | 1BHK | 366.5142 | 36.3285 | 586.0998
5 |  | 1BHK | 366.5142 | 36.3285 | 586.0998
6 |  | 1BHK | 380.938 | 40.365 | 611.7719
2nd, 4th & 6th Floor
1 |  | 1BHK | 375.2869 | 48.438 | 611.3683 | 2nd, 4th & 6th Floor
2 |  | 1BHK | 319.4486 | 44.4015 | 523.5744
3 |  | 1BHK | 319.4486 | 44.4015 | 523.5744
4 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
5 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
6 |  | 1BHK | 375.2869 | 48.438 | 611.3683
8th Floor(Part Refuge Area)
1 |  | Refuge Area |  |  |  | 8th Floor(Part Refuge Area)
2 |  | 1BHK | 319.4486 | 44.4015 | 523.5744
3 |  | 1BHK | 319.4486 | 44.4015 | 523.5744
4 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
5 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
6 |  | 1BHK | 375.2869 | 48.438 | 611.3683
10th Floor
1 |  | 1BHK | 375.2869 | 48.438 | 611.3683 | 10th Floor
2 |  | 1BHK | 319.4486 | 44.4015 | 523.5744
3 |  | 1BHK | 319.4486 | 44.4015 | 523.5744
4 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
5 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
6 |  | 1BHK | 375.2869 | 48.438 | 611.3683
11th Floor
1 |  | 1BHK | 380.938 | 40.365 | 611.7719 | 11th Floor
2 |  | 1BHK | 325.5034 | 32.292 | 520.547
3 |  | 1BHK | 329.8897 | 32.292 | 527.1265
4 |  | 1BHK | 366.5142 | 36.3285 | 586.0998
5 |  | 1BHK | 366.5142 | 36.3285 | 586.0998
6 |  | 1BHK | 380.938 | 40.365 | 611.7719
12th & 14th Floor
1 |  | 1BHK | 375.2869 | 48.438 | 611.3683 | 12th & 14th Floor
2 |  | 1BHK | 319.4486 | 44.4015 | 523.5744
3 |  | 1BHK | 319.4486 | 44.4015 | 523.5744
4 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
5 |  | 1BHK | 362.4777 | 44.4015 | 588.1181
6 |  | 1BHK | 375.2869 | 48.438 | 611.3683
13th Floor
1 |  | Refuge Area |  |  |  | 13th Floor
2 |  | 1BHK | 325.5034 | 32.292 | 520.547
3 |  | 1BHK | 329.8897 | 32.292 | 527.1265
4 |  | 1BHK | 366.5142 | 36.3285 | 586.0998
5 |  | 1BHK | 366.5142 | 36.3285 | 586.0998
6 |  | 1BHK | 380.938 | 40.365 | 611.7719
Type D
Ground Floor for Parking
1st, 3rd, 5th, 7th, 9th & 11th Floor
1 |  | 1BHK | 381.2609 | 36.3285 | 608.2198 | 1st, 3rd, 5th, 7th, 9th & 11th Floor |  | 2.245
2 |  | 1BHK | 381.2609 | 36.3285 | 608.2198
3 |  | 1BHK | 380.3998 | 36.3285 | 606.9281
4 |  | 1BHK | 380.3998 | 36.3285 | 606.9281
2nd, 4th, 6th, 10th, 12th & 14th Floor
1 |  | 1BHK | 375.2061 | 48.438 | 611.2472 | 2nd, 4th, 6th, 10th, 12th & 14th Floor
2 |  | 1BHK | 375.2061 | 48.438 | 611.2472
3 |  | 1BHK | 374.345 | 48.438 | 609.9555
4 |  | 1BHK | 374.345 | 48.438 | 609.9555
8th Floor(Part Refuge Area)
1 |  | 1BHK | 375.2061 | 48.438 | 611.2472 | 8th Floor(Part Refuge Area)
2 |  | Refuge Area
3 |  | 1BHK | 374.345 | 48.438 | 609.9555
4 |  | 1BHK | 374.345 | 48.438 | 609.9555
13th Floor(Part Refuge Area)
1 |  | 1BHK | 381.2609 | 36.3285 | 608.2198 | 13th Floor(Part Refuge Area)
2 |  | Refuge Area
3 |  | 1BHK | 380.3998 | 36.3285 | 606.9281
4 |  | 1BHK | 380.3998 | 36.3285 | 606.9281
Remarks:
* | Navkar City Phase I (A Type, B Type, C1 Building & C2 Building), Navkar City Phase II (A Type Building, B Type Building, C Type, D Type) = All work Completed. Please Provide Full OC.
* | Navkar City Phase I (Wing C3, C4, D1, G, H1, H2, H3, R1 & R2) |  |  | Construction work is in process at the time of Visit. (labour found)
* | Navkar City Phase I (R1 & R2) |  |  | Construction stage is same as last visit dtd.08/03/2025 but work is in the process at the time of Visit.
* | We considered Saleable area as per our calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + E.P Area + C.B Area.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Mr. Manish - 9930055014.
* | We update revised Approved plan & CC of
| Wing C3, Wing C4,Wing H1 & Type D1 |  |  |  | 2022-11-21
| Part 9 i.e Wing H2 & H3 |  |  |  | 2023-01-28
| Part 6 i.e Wing/Type G |  |  |  | 2023-10-09
| Part 14 i.e Wing/Type R1 & R2 |  |  |  | 2024-03-22
* | Recommended Rates/Other Charges of the Property have been revised on 18/06/2024.
* | As per site visit dated 05/06/2025, we have observed that construction work progress of Building H1 is more than Building H2 and H3 (i.e Building H1 is constructed upto 24th slab, Building H2 and H3 is constructed upto the 2nd slab) we have confirmed this construction stage with meet person Mr Nitin - 8956402642 and approved layout plan. Earlier their was error in construction stage of Building H2 due to internal visits were not allowed or no official person available on site. We have rectified construction stage of Building H2 in above subsequent report | [6 empty] | These remark not removed till H2 & H3 Stage is completed as its Building H1 (i.e completed upto 24th slab) dicuss with sir on 19/09/2025
* | Construction work of Phase I (Wing H1) is goes beyond approved plan & CC permission. Provide revised approved plans & CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Navnath Bhatkar |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Navkar City Phase I & Phase II
PHOTOGRAPHS OF PROPERTY : |  |  | Navkar City Phase I & Phase II
Layout Plan:
Google Map :
Formulas:
Juchandra = [Juchandra, row above]
Navkar Harmomy (Building Type G)
Wing H3
Wing H2
Wing H1
Wing C3
Wing C4
Navkar Elite
Navkar Empire
Navkar Blossom (Building Type D)
Wing R1 & R2
Navkar Elite (Wing C3 & C4)
Navkar Empire
(Wing H1 & H2)
Navkar Empire
(Wing H1 & H2)
Navkar Blossom (Building Type D)
Navkar Empire
(Wing H3)
Navkar Blossom (Building Type D)
Navkar Harmomy (Building Type G)
Navkar Empire
(Wing H3)
Navkar Majestic
(Wing R1 & R2)

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
99 Acres | Navkar City Phase I & Phase II | 1BHK | 0 | 625 | 4480 | 2800000
Magic Brick | Navkar City Phase I & Phase II | 1BHK | 0 | 515 | 5825.2427 | 3000000
Average |  |  |  |  | 5152.6214
Valuation Adopted |  |  |  |  | 5100

## Flat detail
| Floor No | B type Odd Floor | [10 empty] | Floor No | B type Even Floor
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace |  |  | Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1, 2, 3, 4 |  | L | W | A |  | L | W | A | L | W | A | 1, 2, 3, 4 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.2 | 3 | 12.6 | CB | 2.13 | 0.75 | 1.5975 | 2.87 | 1.5 | 4.305 |  | Hall | 4.2 | 3 | 12.6 | CB | 2.87 | 0.75 | 2.1525 | 2.13 | 1.5 | 3.195
|  |  |  | 0 | FB | 2.3 | 0.75 | 1.725 |  |  | 0 |  |  |  |  | 0 | FB | 2.3 | 0.75 | 1.725 |  |  | 0
|  |  |  | 0 | Balcony | 1.25 | 2.1 | 2.625 |  |  | 0 |  |  |  |  | 0 | Balcony | 1.25 | 2.1 | 2.625 |  |  | 0
| kitch | 2.1 | 1.2 | 2.52 | CB |  |  | 0 |  |  | 0 |  | kitch | 2.1 | 1.2 | 2.52 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0 |  |  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.75 | 3 | 8.25 | CB |  |  | 0 |  |  | 0 |  | Bed1 | 2.75 | 3 | 8.25 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0 |  |  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0 |  | Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0 |  |  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0 |  | Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0 |  |  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 0.9 | 1.2 | 1.08 | DB |  |  | 0 |  |  | 0 |  | toilet1 | 0.9 | 1.2 | 1.08 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.2 | 1.25 | 1.5 | DB |  |  | 0 |  |  | 0 |  | toilet2 | 1.2 | 1.25 | 1.5 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0 |  | toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.43 | 0.9 | 1.287 |  |  |  | 0 |  |  | 0 |  | passage1 | 1.43 | 0.9 | 1.287 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 293.1791 | 27.237 |  |  | 64.0189 | 5.9475 |  | 46.339 | 4.305 |  | Total |  | 293.1791 | 27.237 |  |  | 69.9929 | 6.5025 |  | 34.391 | 3.195
|  |  | 357.198 | 33.1845 | [10 empty] | 363.172 | 33.7395
| Floor No | B1 & B2 type Odd Floor
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1, 2, 3, 4 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.5 | 3 | 13.5 | CB | 2 | 0.75 | 1.5 | 3 | 1.5 | 4.5
|  |  |  | 0 | FB | 2.77 | 0.75 | 2.0775 |  |  | 0
|  |  |  | 0 | Balcony | 1.35 | 1.35 | 1.8225 |  |  | 0
| kitch | 2 | 3 | 6 | Balcony | 0.9 | 0.85 | 0.765 |  |  | 0
|  |  |  | 0 | FB | 2.05 | 0.75 | 1.5375 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.77 | 2.17 | 6.0109 | CB |  |  | 0 |  |  | 0
|  | 1.77 | 0.85 | 1.5045 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3 | 3 | 9 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.09 | 2 | 2.18 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.2 | 2 | 2.4 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.4 | 0.9 | 1.26 |  |  |  | 0 |  |  | 0
| passage2 | 1.07 | 0.9 | 0.963 |  |  |  | 0 |  |  | 0
| passage3 | 0.9 | 0.85 | 0.765 |  |  |  | 0 |  |  | 0
| passage4 | 1.35 | 3 | 4.05 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 512.7259 | 47.6334 |  |  | 82.9097 | 7.7025 |  | 48.438 | 4.5
|  |  | 595.6356 | 55.3359