## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 17/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-12
Name of the builder group |  |  |  | Nine Homemakers
Name of the builder company |  |  |  | Nine Homemakers
Name of the Project |  |  |  | Ninestar Crown
Provided Contact Details (Name & Contact No.) |  |  |  | 9860281916
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Ashish : 7977676633 |  |  |  | 8329389713
Name / No of the Building |  |  |  | Bldg No. 2 (Ruby) Bldg No. 5 (Emerald) |  |  |  | Ninestar Crown( Building No. 2 & 5)
Docouments Provided |  |  |  | Approved Plans, NA order/CC, Sale Plans, Builder Salable Area, Cost Sheet
RERA No. |  |  |  | Ninestar Crown Bldg No2 Ruby = P99000046388 Ninestar Crown Bldg No 5 Emerald = P99000049308
Project location details |  | Ninestar Crown, Gut No.203/2, 268/1, 271, near Pashwan Auto Garage, Internal Rd, Saphale, Makane, Saphale West, Palghar, Palghar - 401404.
Gut No |  | 203/2, 268/1, 271
Locality |  | Saphale
Road |  | Internal Rd |  | Locality/Village |  | Makane
City |  | Saphale West |  | District |  | Palghar
Taluka |  | Palghar |  | Pin Code |  | 401404
Nearby Landmark |  | Pashwan Auto Garage |  | Distance from city centre: |  | 1.2KM from Saphale Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Internal Road /Open Plot
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Road/House
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.574139, 72.811194
Location Link |  | https://goo.gl/maps/7eHRocCfPJ3nJnHV8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 11283.24
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.66741
Total FSI availaible for the project |  |  |  | 1.7674
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 19942.07
Total number of Buildings |  |  |  | 02 Buildings (4 Wings)
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Collector Of Plghar
Layout Approval No |  | Mahasul/K-1/Mej1/B.S.P/S.R/C.R/168/19 |  |  | Dated | 2021-10-29
Approved Floor plan No. |  | Mahasul/K-1/Mej1/B.S.P/S.R/C.R/168/19 |  |  | Dated | 2021-10-29
NA Order/ CC No Valid Up to: |  | Mahasul/K.1/T.1/NAP/S.R-168/2019 |  |  | Dated | 2021-10-29
Building No. 2 (Ruby) Wing A & B = Gr + 1st to 7th Floor Building No. 5 (Emrald) Wing A & B = Gr + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 7088.06 |  |  |  |  | 76295.8778
Approved no of units |  |  | Flats - 152
Approved no of Floors |  |  | Building No. 2 & 5 Wing A & B = Gr + 1st to 7th Floor
Proposed no of Floors |  |  | Building No. 2 Wing A & B = Gr + 1st to 7th Floor
Building No. 5 Wing A & B = Gr + 1st to 7th Floor
Expected Completion |  |  | As per RERA - Ninestar Crown Bldg No 2 & 5 = 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Kids Play Area, Park, Power Backup, 24*7 Water Supply
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No. 2 Wing A & B = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 6 Floor, Painting upto 5 Floor, Finishing upto 2 Floor Completed | , Flooring upto 6 Floor, Painting upto 5 Floor, Finishing upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 6 Floor, Painting upto 5 Floor, Finishing upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 88.57% |  | 94.29% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 6 | 85.71% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 71.43% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 28.57% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No. 2 Wing B = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, External Plaster upto 1 Floor Completed | , External Plaster upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, External Plaster upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 58.93% |  | 80.71% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 1 | 14.29% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No. 5 Wing A & B = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 2 Slab Completed | , RCC upto 2 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 2 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 20% |  | 52.5% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 2 | 25% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3500
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges + Society Formation & Maintenance Charges |  |  |  |  | 200000
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation & Maintenance Charges |  |  |  |  | 90000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 2800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | Cost Sheet
BLDG No. 02 | Wing A | 31 |  | 14675.6376 |  | 22280 |  | 4000
| Wing B | 31 |  | 12716.5896 |  | 19215 |  | 4000
BLDG No. 05 | Wing A | 45 |  | 16218.1188 |  | 24485 |  | 4000
| Wing B | 45 |  | 16157.0869 |  | 24485 |  | 4000
Total |  | 152 |  | 59767.4329 |  | 90465
Grand Total |  | 152 |  | 59767.4329 |  | 90465 |  | Ninestar Heaven | 0.950Km | 50% | 3200 + Charges 3.5L
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building No. 2 (Rubby)
Wing A
Ground Floor For Entrance Lobby, Residential & Parking | [8 empty] | 10.764 | 1.5013 | 2340000 | 1.5013
1 |  | 1BHK | 389.6568 | 0 | 585 | Ground Floor For Entrance Lobby, Residential & Parking |  | 33.8375 | 2047500
2 |  | 1BHK | 363.285 | 0 | 560 | Ground Floor For Entrance Lobby, Residential & Parking |  |  | 1960000 | 3418.8034
3 |  | 2BHK | 527.3284 | 0 | 800 | Ground Floor For Entrance Lobby, Residential & Parking |  |  | 2800000
4 |  | Entrance Lobby & Parking |  |  |  | Ground Floor For Entrance Lobby, Residential & Parking
1st to 7th Floor
1 |  | 1BHK | 389.6568 | 0 | 585 | 1st to 7th Floor
2 |  | 1.5BHK | 469.3104 | 0 | 720 | 1st to 7th Floor
3 |  | 2BHK | 527.3284 | 0 | 800 | 1st to 7th Floor |  |  | 1.5171
4 |  | 2BHK | 527.3284 | 0 | 800 | 1st to 7th Floor
Wing B
Ground Floor For Entrance Lobby, Society Office & Residential | [8 empty] | 10.764
1 |  | 1BHK | 389.6568 | 0 | 585 | Ground Floor For Entrance Lobby, Society Office & Residential |  | 33.8375
2 |  | 1.5BHK | 469.3104 | 0 | 720 | Ground Floor For Entrance Lobby, Society Office & Residential
3 |  | 1BHK | 389.6568 | 0 | 585 | Ground Floor For Entrance Lobby, Society Office & Residential
4 |  | Society Office |  |  |  | Ground Floor For Entrance Lobby, Society Office & Residential
1st to 7th Floor
1 |  | 1BHK | 389.6568 | 0 | 585 | 1st to 7th Floor
2 |  | 1.5BHK | 469.3104 | 0 | 720 | 1st to 7th Floor
3 |  | 1BHK | 389.6568 | 0 | 585 | 1st to 7th Floor
4 |  | 1BHK | 389.6568 | 0 | 585 | 1st to 7th Floor
Building No. 5 (Emrald)
Wing A
Ground Floor For Entrance Lobby, Residential & Parking
1 |  | 1BHK | 389.6568 | 0 | 585 | Ground Floor For Entrance Lobby, Residential & Parking
2 |  | 1.5BHK | 472.5396 | 0 | 720 | Ground Floor For Entrance Lobby, Residential & Parking
3 |  | 1BHK | 377.4935 | 0 | 570 | Ground Floor For Entrance Lobby, Residential & Parking
4 |  | Entrance Lobby |  |  |  | Ground Floor For Entrance Lobby, Residential & Parking
5 |  | Parking |  |  |  | Ground Floor For Entrance Lobby, Residential & Parking
6 | [5 empty] | Ground Floor For Entrance Lobby, Residential & Parking
1st to 7th Floor
1 |  | 1BHK | 389.6568 | 0 | 585 | 1st to 7th Floor
2 |  | 1BHK | 389.6568 | 0 | 585 | 1st to 7th Floor
3 |  | 1.5BHK | 472.5396 | 0 | 720 | 1st to 7th Floor
4 |  | 1BHK | 377.4935 | 0 | 570 | 1st to 7th Floor
5 |  | 1RK | 255.2144 | 0 | 385 | 1st to 7th Floor
6 |  | 1RK | 255.2144 | 0 | 385 | 1st to 7th Floor
Wing B
Ground Floor For Entrance Lobby, Residential & Parking
1 |  | 1BHK | 377.4935 | 0 | 570 | Ground Floor For Entrance Lobby, Residential & Parking
2 |  | 1.5BHK | 472.5396 | 0 | 720 | Ground Floor For Entrance Lobby, Residential & Parking
3 |  | 1BHK | 389.6568 | 0 | 585 | Ground Floor For Entrance Lobby, Residential & Parking
4 |  | Entrance Lobby |  |  |  | Ground Floor For Entrance Lobby, Residential & Parking
5 |  | Parking |  |  |  | Ground Floor For Entrance Lobby, Residential & Parking
6 | [5 empty] | Ground Floor For Entrance Lobby, Residential & Parking
1st to 7th Floor
1 |  | 1RK | 255.2144 | 0 | 385 | 1st to 7th Floor
2 |  | 1RK | 255.2144 | 0 | 385 | 1st to 7th Floor
3 |  | 1BHK | 377.4935 | 0 | 570 | 1st to 7th Floor
4 |  | 1.5BHK | 463.8208 | 0 | 720 | 1st to 7th Floor
5 |  | 1BHK | 389.6568 | 0 | 585 | 1st to 7th Floor
6 |  | 1BHK | 389.6568 | 0 | 585 | 1st to 7th Floor
Remarks:
* | Building No.2 & 5 = Construction work is in process at the time of visit. (labour found) | [6 empty] | Building No.5 = Construction of 1st slab work is in process at the time of Visit. Building No. 05 = Work is same as last visit (08/11/2023).
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Harshad Pawade |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Ninestar Crown
Layout :
Google Map :
BLDG No. 02
BLDG No. 05
Bldg No.2
Bldg No.5
Bldg No.5
Bldg No.2
Bldg No.5
Bldg No.2
Bldg No.5
Bldg No.5
Bldg No.5
Bldg No.5
Bldg No.2

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted