## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 23/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-09
Name of the builder group |  |  |  | Palacio Ventures
Name of the builder company |  |  |  | Palacio Ventures
Name of the Project |  |  |  | Platinum Parksyde
Contact Details ( Name & Contact No.) |  |  |  | Mr. Niraj 9820979700
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Jignesh 9820979700 |  |  |  | Mr. Akshay 9820979700 |  | Mr. Jagruti 9820979700
Name / No of the Building |  |  |  | 01 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P52000046110
Project location details |  | Platinum Parksyde, Plot No.62C, Sector No.30, near Mahaavir Heritage CHS, Utsav Chowk - CISF Road, Kharghar, Kharghar, Kharghar East, Panvel, Raigad - 410210.
Plot No |  | 62C, Sector No.30
Locality |  | Kharghar
Road |  | Utsav Chowk - CISF Road |  | Village |  | Kharghar
City |  | Kharghar East |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410210
Nearby Landmark |  | Mahaavir Heritage CHS |  | Distance from city centre: |  | 5.5KM from Kharghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Internal Road
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Utsav Chowk - CISF Road
South | NA | NA |  |  | Green Court
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude : |  | 19.0690216,73.0708013
Location Link |  | https://goo.gl/maps/kFmaqU5URvt8E8RD8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1886.74
Permissible FSI |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  | 4.1362
Total FSI availaible for the project |  |  |  | 5.6362
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 10634.12
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | CIDCO
Layout Approval No |  | CIDCO/BP-18002/TPO(NM & K)/2021/11362 |  |  | Dated | 2023-09-18
Approved Floor plan No. |  | CIDCO/BP-18002/TPO(NM & K)/2021/11362 |  |  | Dated | 2023-09-18
Commencement-CC No Valid Up to: |  | CIDCO/BP-18002/TPO(NM & K)/2021/11362 |  |  | Dated | 2023-09-18
Gr + 5P + 6th to 22nd Floor
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 10634.12
Approved no of units |  |  | Flats -102, Shops -15
Approved no of Floors |  |  | Gr + 5P + 6th to 22nd Floor
Proposed no of Floors |  |  | Gr + 5P + 6th to 22nd Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Gym, Club House, Kids Play Area, Party Lawn... & Etc
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Gr + 5P + 6th to 22nd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 20 Floor, Finishing upto 12 Floor Completed | , Painting upto 20 Floor, Finishing upto 12 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 20 Floor, Finishing upto 12 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 92.27% |  | 95% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 22 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 20 | 90.91% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 12 | 54.55% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 13000 |  |  | 9500 Rate By Smith |  | On 31/03/2024
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 15000 |  |  | 9500 to 12800 7L | Smith | 2024-10-25 | Verbal | Flat 1804
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges |  |  |  |  | 400000
Club Charges |  |  |  |  | 500000
Legal Charges
Gas Connection Charges
Safety Grill Charges |  |  |  |  | 115000
Society Formation Charges |  |  |  |  | 350000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 700000
Distressed valuation of the Property |  |  |  |  | 10400
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 15 |  | 6671.0536 |  | 14617.8061
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 102 |  | 87834.1324 |  | 153795
Grand Total |  | 117 |  | 94505.1859 |  | 168412.8061
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Builder Saleable area | Floor
Ground Floor For Commercial,Society Office & Driver Room | [8 empty] | 10.764
1 |  | Shop | 432.2607 | 0 | 935 | Ground Floor For Commercial,Society Office & Driver Room |  | 40.16 | 43.36 | 466.727 | 2.163 |  | 2.163
2 |  | Shop | 432.2607 | 0 | 935 | [5 empty] | 2.163
3 |  | Shop | 432.2607 | 0 | 935 | [5 empty] | 2.163
4 |  | Shop | 470.3653 | 0 | 1034.8036 |  |  | 43.7 |  |  | 2.2
5 |  | Shop | 453.0029 | 0 | 996.6065 |  |  | 42.94 |  |  | 2.2
6 |  | Shop | 329.6798 | 0 | 720 | [5 empty] | 2.1839
7 |  | Shop | 329.6798 | 0 | 720 | [5 empty] | 2.1839
8 |  | Shop | 541.6445 | 0 | 1191.6179 | [5 empty] | 2.2
9 |  | Shop | 580.8039 | 0 | 1277.7686 | [5 empty] | 2.2
10 |  | Shop | 489.0946 | 0 | 1076.0082 | [5 empty] | 2.2
11 |  | Shop | 992.7422 | 0 | 2184.0328 | [5 empty] | 2.2
12 |  | Shop | 216.9377 | 0 | 477.2628 | [5 empty] | 2.2
13 |  | Shop | 329.7121 | 0 | 725.3666 | [5 empty] | 2.2
14 |  | Shop | 330.9822 | 0 | 728.1609 | [5 empty] | 2.2
15 |  | Shop | 309.6265 | 0 | 681.1782 | [5 empty] | 2.2
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
1st to 4th Podium Floor For Parking
5th Podium Floor For Parking & Amenities
6th Floor For Residential | [8 empty] | 10.764
1 |  | 3.5BHK | 1062.0839 | 430.8291 | 2100 | 6th Floor For Residential |  | 90.735 | 1.5716 | 4.02
2 |  | 2 | 736.3114 | 0 | 1325 |  |  |  | 1.7995 |  |  | 12830.1887
3 |  | 2 | 736.3114 | 0 | 1325 |  |  |  | 1.7995 |  |  | 12679.2453
4 |  | 3.5BHK | 1088.2404 | 0 | 1815 |  |  | 9531.6804 | 1.6678 |  | 10468.3196
5 |  | 2 | 708.5403 | 0 | 1275 |  |  | 9725.4902 | 1.7995 |  | 9725.4902
6 |  | 2 | 708.5403 | 0 | 1275 |  |  |  | 1.7995 |  | 9725.4902
7th to 12th Floor (Fire Rescue Balcony At Mid Landing At 7th, 9th, 11th Floor)
1 |  | 3.5BHK | 1088.2404 | 0 | 1815 | 7th to 12th Floor (Fire Rescue Balcony At Mid Landing At 7th, 9th, 11th Floor) |  | 8044.0771 | 1.6678
2 |  | 2 | 736.3114 | 0 | 1325 | 7th to 12th Floor (Fire Rescue Balcony At Mid Landing At 7th, 9th, 11th Floor) |  |  | 1.7995
3 |  | 2 | 736.3114 | 0 | 1325 | 7th to 12th Floor (Fire Rescue Balcony At Mid Landing At 7th, 9th, 11th Floor) |  |  | 1.7995
4 |  | 3.5BHK | 1088.2404 | 0 | 1815 | 7th to 12th Floor (Fire Rescue Balcony At Mid Landing At 7th, 9th, 11th Floor) |  |  | 1.6678
5 |  | 2 | 708.5403 | 0 | 1275 | 7th to 12th Floor (Fire Rescue Balcony At Mid Landing At 7th, 9th, 11th Floor) |  |  | 1.7995
6 |  | 2 | 708.5403 | 0 | 1275 | 7th to 12th Floor (Fire Rescue Balcony At Mid Landing At 7th, 9th, 11th Floor) |  |  | 1.7995
Ground Floor
1 |  |  |  | 0 | #REF! | Ground Floor
2 |  |  |  | 0 | #REF! | Ground Floor
3 |  |  |  | 0 | #REF! | Ground Floor
4 |  |  |  | 0 | #REF! | Ground Floor
2nd Floor
201 |  |  |  | 0 | #REF! | 2nd Floor
202 |  |  |  | 0 | #REF! | 2nd Floor
203 |  |  |  | 0 | #REF! | 2nd Floor
204 |  |  |  | 0 | #REF! | 2nd Floor
205 |  |  |  | 0 | #REF! | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | #REF! | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | #REF! | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | #REF! | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | #REF! | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | #REF! | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | #REF! | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | #REF! | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | #REF! | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | #REF! | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | #REF! | 2nd & 5th Floor
13th to 22nd Floor (Fire Rescue Balcony At Mid Landing At 13th, 15th, 17th, 19th & 21st Floor)
1 |  | 3.5BHK | 1129.036 | 0 | 1885 | 13th to 22nd Floor (Fire Rescue Balcony At Mid Landing At 13th, 15th, 17th, 19th & 21st Floor) |  | 7745.3581 | 1.6696
2 |  | 2 | 755.2561 | 0 | 1365 | 13th to 22nd Floor (Fire Rescue Balcony At Mid Landing At 13th, 15th, 17th, 19th & 21st Floor) |  |  | 1.8073 |  |  | 12820.5128
3 |  | 2 | 755.2561 | 0 | 1365 | 13th to 22nd Floor (Fire Rescue Balcony At Mid Landing At 13th, 15th, 17th, 19th & 21st Floor) |  |  | 1.8073
4 |  | 3.5BHK | 1129.036 | 0 | 1885 | 13th to 22nd Floor (Fire Rescue Balcony At Mid Landing At 13th, 15th, 17th, 19th & 21st Floor) |  |  | 1.6696
5 |  | 2 | 735.5579 | 0 | 1335 | 13th to 22nd Floor (Fire Rescue Balcony At Mid Landing At 13th, 15th, 17th, 19th & 21st Floor) |  |  | 1.8149 | 1324.0043
6 |  | 2 | 735.5579 | 0 | 1335 | 13th to 22nd Floor (Fire Rescue Balcony At Mid Landing At 13th, 15th, 17th, 19th & 21st Floor) |  |  | 1.8149
Remarks:
* | Construction work is in process at the time of Visit. (labour found) Internal visit was not allowed.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We considered Saleable area of Commercial as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony Area + A.P Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | We have updated layout plan, floor plan & CC on 24/11/2023.
* | Recommended Rates / Other charges of the Property have been revised on 31/03/2024 & 25/10/2024 & 29/06/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Platinum Parksyde
Layout :
Google Map :
Formulas:
Kharghar = [Kharghar, row above]

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted