## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/09/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-09-08
Name of the builder group |  |  |  | Pride Enterprises
Name of the builder company |  |  |  | Pride Enterprises
Name of the Project |  |  |  | Pride Heights
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Paresh - 9870588110
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Chandrakant 7678062153
Name / No of the Building |  |  |  | Building No.1 & 2
Name / No of the Existing Building |  |  |  | NA | [5 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC | [5 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51700046305 |  |  |  | #N/A |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Pride Heights, Survey No.12, H.No.11, near Empire Residency, Internal Road, , Pisavali, Kalyan, Kalyan, Thane - 421306. | [7 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 12, H.No.11 | [7 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | NA | [7 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Road |  | Locality/Village |  | Pisavali |  |  |  | Ambernath | Dahanu |  | Pen | Shirur
City |  | Kalyan |  | District |  | Thane |  |  |  | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Kalyan |  | Pin Code |  | 421306 | [6 empty] | Mahad | Daund
Nearby Landmark |  | Empire Residency |  | Distance from city centre: |  | 3.1 KM from Kalyan Railway Station | [6 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [8 empty] | Mangaon | Ambegaon
[13 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [8 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [8 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [8 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Other Plot
West | NA | Other Plot |  |  | Houses
North | NA | Pipeline Road |  |  | Pipeline Road
South | NA | Other Plot |  |  | Empire Residency
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.220555, 73.122750
Location Link |  | https://maps.app.goo.gl/E4SHFC3q6VzvWhDN9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3669.13
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.5159
Total FSI availaible for the project |  |  |  | 2.6159
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 9598.14
Total number of Buildings |  |  |  | 2 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kalyan-Dombivli Municipal Corporation
Layout Approval No |  | KDMC/TPD/BP/27Village/2022-23/02/176 |  |  | Dated | 2023-08-10
Approved Floor plan No. |  | KDMC/TPD/BP/27Village/2022-23/02/176 |  |  | Dated | 2023-08-10
Commencement-CC No Valid Up to: |  | KDMC/TPD/BP/27Village/2022-23/02/176 |  |  | Dated | 2023-08-10
Building No.1 = Stilt/Gr + 1st to 20th Floor Building No.2 = Stilt + 1st to 7th Floor
O. Certificate No.: |  | KDMC/TPD/CC/27Village/01 Bldg No.2 = Gr/St + 1st to 7th Floor Total Flats = 35 Nos. Approved upto : NA |  |  | Dated | 2024-04-02
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 9598.14
Approved no of units |  |  | Flats - 210, Shops - 20
Approved no of Floors |  |  | Building No.1 = Stilt/Gr + 1st to 20th Floor Building No.2 = Stilt + 1st to 7th Floor
Proposed no of Floors |  |  | Building No.1 = Stilt/Gr + 1st to 20th Floor
Building No.2 = Stilt + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | CCTV Camera, Kids play area, Gymnasium, Indoor Games Room
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1 = Stilt/Gr + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 14 Floor, External Plaster upto 8 Floor Completed | , Internal Plaster upto 14 Floor, External Plaster upto 8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 14 Floor, External Plaster upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 66.75% |  | 85.5% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 14 | 70% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8 | 40% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | Building No.2 = Stilt + 1st to 7th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 11000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 350000
Distressed valuation of the Property |  |  |  |  | 4800
Commercial Area Details : | [7 empty] | Sheet | Magic Brick
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | 5500 | 5480.6364
Building No.1 |  | 20 |  | 3108.993 |  | 6438.3911 |  |  | 5476.7654
Residential Area Details : | [8 empty] | 5478.7009
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 |  | 175 |  | 92699.0298 |  | 139048.5447
Building No.2 |  | 35 |  | 14651.2302 |  | 21976.8453
Total |  | 210 |  | 107350.26 |  | 161025.39
Grand Total |  | 230 |  | 110459.2531 |  | 167463.7811 |  | https://www.magicbricks.com/pride-heights-kalyan-east-thane-pdpid-4d4235333934333735
Building details Floor Wise | [7 empty] | https://housing.com/in/buy/projects/page/285444-pride-heights-by-pride-enterprises-mumbai-in-kalyan-east
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Building No.1
Ground Floor/Stilt Floor for Commercial, Parking, Society office, Meter Room, Drivers Room & Entrace Lobby
1 |  | Shop | 186.4863 | 62.1621 | 385.405 | Ground Floor/Stilt Floor for Commercial, Parking, Society office, Meter Room, Drivers Room & Entrace Lobby
2 |  | Shop | 186.4863 | 62.1621 | 385.405
3 |  | Shop | 206.8303 | 68.9434 | 427.4492
4 |  | Shop | 186.4863 | 62.1621 | 385.405
5 |  | Shop | 206.8303 | 68.9434 | 427.4492
6 |  | Shop | 152.5797 | 50.8599 | 315.3314
7 |  | Shop | 133.2045 | 44.4015 | 275.2893
8 |  | Shop | 133.2045 | 44.4015 | 275.2893
9 |  | Shop | 108.9855 | 36.3285 | 225.2367
10 |  | Shop | 227.6586 | 75.8862 | 470.4944 |  |  | 10.764
11 |  | Shop | 147.7359 | 49.2453 | 305.3209
12 |  | Shop | 108.9855 | 36.3285 | 225.2367
13 |  | Shop | 133.2045 | 44.4015 | 275.2893
14 |  | Shop | 133.2045 | 44.4015 | 275.2893
15 |  | Shop | 127.1497 | 50.8599 | 275.915
16 |  | Shop | 206.8303 | 68.9434 | 427.4492
17 |  | Shop | 186.4863 | 62.1621 | 385.405
18 |  | Shop | 147.7359 | 49.2453 | 305.3209
19 |  | Shop | 108.9855 | 36.3285 | 225.2367
20 |  | Shop | 79.9227 | 26.6409 | 165.1736
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Building No.1
1st to 7th, 9th to 12th, 14th to 17th Floor for Residential
1 |  | 1BHK | 456.1514 | 0 | 684.2271 | 1st to 7th, 9th to 12th, 14th to 17th Floor for Residential |  | 36.6075
2 |  | 2BHK | 592.612 | 0 | 888.918 |  |  | 5.65
3 |  | 1BHK | 466.8078 | 0 | 700.2117 |  |  | 42.2575 | 45.43
4 |  | 1BHK | 466.8078 | 0 | 700.2117
5 |  | 1BHK | 466.8078 | 0 | 700.2117 |  |  | 41.4075
6 |  | 1BHK | 466.8078 | 0 | 700.2117
7 |  | 2BHK | 592.612 | 0 | 888.918
8 |  | 2BHK | 632.977 | 0 | 949.4655
9 |  | 2BHK | 632.977 | 0 | 949.4655 |  |  | 49.605
8th, 13th, & 18th Floors (Part Refuge Area at Midlanding)
1 |  | 1BHK | 456.1514 | 0 | 684.2271 | 8th, 13th, & 18th Floors (Part Refuge Area at Midlanding) |  | 36.6075
2 |  | 2BHK | 592.612 | 0 | 888.918 |  |  | 5.65
3 |  | 1BHK | 466.8078 | 0 | 700.2117 |  |  | 42.2575 | 45.43
4 |  | 1BHK | 466.8078 | 0 | 700.2117
5 |  | 1BHK | 466.8078 | 0 | 700.2117 |  |  | 41.4075
6 |  | 1BHK | 466.8078 | 0 | 700.2117
7 |  | 2BHK | 592.612 | 0 | 888.918
8 |  | 2BHK | 632.977 | 0 | 949.4655
9 |  | 2BHK | 632.977 | 0 | 949.4655 |  |  | 49.605
20th Floor (Part Recreational Floor) | [7 empty] | 5.9
1 |  | 1BHK | 456.1514 | 0 | 684.2271 | 20th Floor (Part Recreational Floor) |  | 231.0325 | 60.08
2 |  | 2BHK | 592.612 | 0 | 888.918
3 |  | 1BHK | 466.8078 | 0 | 700.2117
4 |  | 1BHK | 466.8078 | 0 | 700.2117
Building No.2
Stilt Floor for Parking
1st to 7th Floor for Residential
1 |  | 1BHK | 415.3289 | 0 | 622.9934 | 1st to 7th Floor for Residential |  | 34.82
2 |  | 1BHK | 415.3289 | 0 | 622.9934
3 |  | 1BHK | 425.1511 | 0 | 637.7266
4 |  | 1BHK | 418.612 | 0 | 627.9179 |  |  | 10.764
5 |  | 1BHK | 418.612 | 0 | 627.9179
Remarks:
* | Bldg No.1 = Construction work is in process at the time of Visit. Bldg No.2 = All work Completed. OC Received.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Balcony + A P Area + C.B Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | We have updated OC from Rera for Building no.2 (On 06/03/2025).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Pride Heights
Layout :
Google Map :
Formulas:
Pisavali = [Pisavali, row above]
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building
Building No.1
Building No.2
Bldg 01
Bldg 02

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC