## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-08
Name of the builder group |  |  |  | Chariot Properties LLP
Name of the builder company |  |  |  | Chariot Properties LLP
Name of the Project |  |  |  | Sai Suncity Phase 1
Provided Contact Details (Name & Contact No.) |  |  |  | Ms. Vrushali 9152014816
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Rupesh 9819806895
Name / No of the Building |  |  |  | Cluster 1 = Tower 1 (Type A) Vega, Tower 2 (Type B) Carina
Name / No of the Existing Building |  |  |  | NA | [9 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC & EC. | [9 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | Sai Suncity Phase 1 = P52000033880 |  |  |  | #N/A | [5 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Sai Suncity Phase 1, Survey No.33(PT), 61(PT), 62/1(PT), near Arihant Anshula Taloja, Internal Road, Ghot, Ghot, Taloja East, Panvel, Raigad - 410208. | [11 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 33(PT), 61(PT), 62/1(PT) | [11 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Ghot | [11 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Road |  | Locality/Village |  | Ghot | [7 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Taloja East |  | District |  | Raigad | [7 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Panvel |  | Pin Code |  | 410208 | [10 empty] | Mahad | Daund
Nearby Landmark |  | Arihant Anshula Taloja |  | Distance from city centre: |  | 3.80KM from Taloja Metro Station | [10 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [12 empty] | Mangaon | Ambegaon
[17 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [12 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [12 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [12 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | S. No 27 to 32 |  |  | Open Plot
West | NA | S. No 60 |  |  | Internal Road
North | NA | S. No 34 |  |  | Open Plot
South | NA | S. No 25, 63, 67 &68 |  |  | Arihant Anshula Taloja
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.088611,73.111650
Location Link |  | https://goo.gl/maps/Me3ic76m3MNjFLEn9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 83672.2
Permissible FSI |  |  |  | 1.1 |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 2.6127
Total FSI availaible for the project |  |  |  | 3.7127
Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 310646.68 |  |  |  | 172454.19
Total number of Buildings |  |  |  | 02 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation, Panvel-Raigad
Layout Approval No |  | PMP/NRV/16179/2719/2023 |  |  | Dated | 2023-08-22
Approved Floor plan No. |  | PMP/NRV/16179/2719/2023 |  |  | Dated | 2023-08-22
Commencement-CC No. |  | PMC/TP/Ghot/33(Pt.),61,62/1(Pt.)/ 21-23/16179/2719/2023 |  |  | Dated | 2023-08-22
Valid Up to: Cluster 1 |  | Tower 1 (Vega) = 1B + Gr + 2P + 2nd to 16th Floor Tower 2 (Carina) = 1B + Gr + 2P + 2nd to 16th Floor
Environmental Clearance No. |  | SIA/MH/INFRA2/430547/2023 |  |  | Dated | 18/18/2023
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 19508.82
Approved no of units |  |  | Flats - 236, Shops - 24
Approved no of Floors |  |  | Tower 1 (Vega) = 1B + Gr + 2P + 2nd to 16th Floor Tower 2 (Carina) = 1B + Gr + 2P + 2nd to 16th Floor
Proposed no of Floors |  |  | Tower 1 & 2 = 1B + Gr + 2P + 2nd to 16th Floor
Expected Completion |  |  | As per RERA - 30/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Basketball Court, Jogging Track, Billiards Table, Swimming Pools, Gymnasium, Tennis Court | [5 empty] | https://housing.com/in/buy/projects/page/276381-paradise-sai-suncity-by-paradise-group-in-taloja
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Tower 1 (Vega) = 1B + Gr + 2P + 2nd to 16th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 3 Slab Completed | , RCC upto 3 Slab
Basement | 1 | Ground | 1 | Podium | 1 | Floors | 16 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 3 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4
Excavation |  | 16 | 100% | 16.67% |  | 50% |  | Excavation in process | 8
Plinth |  | 16 | 100% |  |  |  |  | Excavation Completed | 16
RCC (Including podiums) |  | 3 | 16.67% |  |  |  |  | Footing in Process | 4
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 8
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 12
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 16
Construction details: |  | Tower 2 (Carina) = 1B + Gr + 2P + 2nd to 16th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 3 Slab Completed | , RCC upto 3 Slab
Basement | 1 | Ground | 1 | Podium | 1 | Floors | 16 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 3 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4
Excavation |  | 16 | 100% | 16.67% |  | 50% |  | Excavation in process | 8
Plinth |  | 16 | 100% |  |  |  |  | Excavation Completed | 16
RCC (Including podiums) |  | 3 | 16.67% |  |  |  |  | Footing in Process | 4
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 8
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 12
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 16
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. (Inclusive of all other charges) |  |  |  |  | 5900 |  |  | Builder sale area added that’s why rate is decresed on 30/11/2023 by smith |  |  |  |  | 70% loading for flats
Recommended rate of the Shop Per Sq. Ft. (Inclusive of all other charges) |  |  |  |  | 10000
Floor Rise Rate from 3rd Floor |  |  |  |  | 20
Development + Amenities Charges |  |  |  |  | 300000 |  |  |  |  | Rate 5800 to 6103
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 4720
Commercial Area Details (Shops) :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower 1 (Type A ) Vega |  | 12 |  | 2823.8019 |  | 4518.0831
Tower 2 (Type B ) Carina |  | 12 |  | 3344.9959 |  | 5351.9934
Total |  | 24 |  | 6168.7978 |  | 9870.0765
Residential Area Details (Flats) :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower 1 (Type A ) Vega |  | 118 |  | 65813.6686 |  | 112300
Tower 2 (Type B ) Carina |  | 118 |  | 65813.6686 |  | 112300
Total |  | 236 |  | 131627.3372 |  | 224600
Grand Total |  | 260 |  | 137796.135 |  | 234470.0765
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Tower 1 (Type A ) Vega
Basement Floor For Parking
Ground Floor For Commercial, Meter Room, Drivers Room & Creche Room
1A |  | Shop | 398.5371 | 0 | 637.6594 | Ground Floor For Commercial, Meter Room, Drivers Room & Creche Room
1 |  | Shop | 167.8108 | 0 | 268.4972
2 |  | Shop | 184.439 | 0 | 295.1024
3 |  | Shop | 201.2093 | 0 | 321.9349
4 |  | Shop | 208.3889 | 0 | 333.4222
5 |  | Shop | 296.7549 | 0 | 474.8078
6 |  | Shop | 217.9904 | 0 | 348.7846
7 |  | Shop | 231.5681 | 0 | 370.5089
8 |  | Shop | 207.0391 | 0 | 331.2625
9 |  | Shop | 246.8756 | 0 | 395.0009
10 |  | Shop | 244.74 | 0 | 391.584
11 |  | Shop | 218.4489 | 0 | 349.5183
Tower 2 (Type B ) Carina
Basement Floor For Parking
Ground Floor For Commercial, Meter Room, Fitness Centre & Society Office
12 |  | Shop | 221.3143 | 0 | 354.1029 | Ground Floor For Commercial, Meter Room, Fitness Centre & Society Office
13 |  | Shop | 258.6643 | 0 | 413.8629
14 |  | Shop | 265.0796 | 0 | 424.1274
15 |  | Shop | 236.1622 | 0 | 377.8595
16 |  | Shop | 262.5426 | 0 | 420.0681
17 |  | Shop | 251.7118 | 0 | 402.7389
18 |  | Shop | 355.4951 | 0 | 568.7921
19 |  | Shop | 254.7344 | 0 | 407.575
20 |  | Shop | 256.4706 | 0 | 410.353
21 |  | Shop | 241.6518 | 0 | 386.6429
22 |  | Shop | 230.8749 | 0 | 369.3998
22A |  | Shop | 510.2943 | 0 | 816.4709
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
50%
Tower 1 (Type A ) Vega
1st & 2nd Podium Floor For Parking
2nd to 6th, 8th to 11th & 13th to 16th Floor For Residential
1 |  | 1BHK | 443.5468 | 0 | 760 | 2nd to 6th, 8th to 11th & 13th to 16th Floor For Residential |  | 41.2065 | 5394.7368 | 1.7135 | 760 | 1.7135
2 |  | 2BHK | 675.8769 | 0 | 1150 |  |  | 62.6495 | 5217.3913 | 1.7015
3 |  | 2BHK | 675.8769 | 0 | 1150
4 |  | 1BHK | 443.5468 | 0 | 760
5 |  | 1BHK | 443.5468 | 0 | 760
6 |  | 2BHK | 675.8769 | 0 | 1150
7 |  | 2BHK | 675.8769 | 0 | 1150
8 |  | 1BHK | 443.5468 | 0 | 760
7th & 12th Floor (Part Refuge Area)
1 |  | 1BHK | 443.5468 | 0 | 760 | 7th & 12th Floor (Part Refuge Area)
2 |  | Refuge Area
3 |  | 2BHK | 675.8769 | 0 | 1150
4 |  | 1BHK | 443.5468 | 0 | 760
5 |  | 1BHK | 443.5468 | 0 | 760
6 |  | 2BHK | 675.8769 | 0 | 1150
7 |  | 2BHK | 675.8769 | 0 | 1150
8 |  | 1BHK | 443.5468 | 0 | 760
Tower 2 (Type B ) Carina
1st & 2nd Podium Floor For Parking
2nd to 6th, 8th to 11th & 13th to 16th Floor For Residential
1 |  | 1BHK | 443.5468 | 0 | 760 | 2nd to 6th, 8th to 11th & 13th to 16th Floor For Residential
2 |  | 2BHK | 675.8769 | 0 | 1150
3 |  | 2BHK | 675.8769 | 0 | 1150
4 |  | 1BHK | 443.5468 | 0 | 760
5 |  | 1BHK | 443.5468 | 0 | 760
6 |  | 2BHK | 675.8769 | 0 | 1150
7 |  | 2BHK | 675.8769 | 0 | 1150
8 |  | 1BHK | 443.5468 | 0 | 760
7th & 12th Floor (Part Refuge Area)
1 |  | 1BHK | 443.5468 | 0 | 760 | 7th & 12th Floor (Part Refuge Area)
2 |  | Refuge Area
3 |  | 2BHK | 675.8769 | 0 | 1150
4 |  | 1BHK | 443.5468 | 0 | 760
5 |  | 1BHK | 443.5468 | 0 | 760
6 |  | 2BHK | 675.8769 | 0 | 1150
7 |  | 2BHK | 675.8769 | 0 | 1150
8 |  | 1BHK | 443.5468 | 0 | 760
Remarks:
* | Construction work is in process at the time of Visit. (Slow Speed) labour found.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As per Rera |  |  | As per Approved Plan
* | Phase I |  |  | Cluster 1
* | As per Previous Layout Plan |  |  | As per Revised Layout Plan
* | Tower 1 A |  |  | Tower 1 (Vega)
* | Tower 1 B |  |  | Tower 2 (Carina)
* | Recommended Rates/ Other charges of the Property have been revised on 30/11/2023 due to addition of builder sale area provided by bank.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sai Suncity Phase 1
Layout :
Google Map :
Formulas:
Ghot = [Ghot, row above]
Tower 1 & 2
Vega & Carina
Cluster 1
Cluster 2 & 3
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D56: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC