## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-08
Name of the builder group |  |  |  | M/s. Metro Satyam Developers
Name of the builder company |  |  |  | M/s. Metro Satyam Developers
Name of the Project |  |  |  | Regents Park Kharghar
Contact Details ( Name & Contact No.) |  |  |  | 9819081463
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  | Mr. Soham 9819081463 |  |  |  | Mr. Baban 9561280683 |  |  |  | Mr. Harsh Shreevardhan 9819081463
Name / No of the Building |  |  |  | Building A & B, Commercial Building
Docouments Provided |  |  |  | Approved Plans, CC, Builder Salable Area, Cost Sheet.
RERA No. |  |  |  | P52000031227
Project location details |  | Regents Park Kharghar, Survey No.13/1, 14/5B, 14/6, 15/5, 15/6 &15/8, near Oxyfresh Homes, Panvel road, Rohinjan, Kharghar West, Panvel, Raigad.
Survey No |  | 13/1, 14/5B, 14/6, 15/5, 15/6 &15/8
Road |  | Panvel road |  | Locality/Village |  | Rohinjan
City |  | Kharghar West |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410208
Nearby Landmark |  | Oxyfresh Homes |  | Distance from city centre: |  | 2 Km from Taloja Panchnand Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Panvel road
West | NA | NA |  |  | Oxyfresh Homes
North | NA | NA |  |  | Open plot
South | NA | NA |  |  | Open plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.0909638,73.0753774 | [5 empty] | https://goo.gl/maps/X5Qswz5EpwCLg4AAA
Location Link |  | https://goo.gl/maps/X5Qswz5EpwCLg4AAA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 7721
Permissible FSI |  |  |  | 1.1 |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 2.9376
Total FSI availaible for the project |  |  |  | 4.0376
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 31173.938
Total number of Buildings |  |  |  | 3 Building
Approval Detail : Plan approval
Layout Approval No |  | PMP/NRV/16026/JK-1213/2024 |  |  | Dated | 2024-04-10
Approved Floor plan No. |  | PMP/NRV/16026/JK-1213/2024 |  |  | Dated | 2024-04-10
Commencement Certificate No. Valid Up to: |  | PMC/TP/Rohinjan/13/1 & Others/21-24/16026/1213/2024 |  |  | Dated | 2024-04-10
Building A = Gr/Stilt + 1st to 33rd upper floor Building B = Gr/Stilt + 1st to 34th upper Floor Commercial Building = G + 1st upper Floor (Total Built Up Area = 31173.938 Sq.M.)
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 31173.938
Approved no of units |  |  | Flats - 462, Shops - 7
Approved no of Floors |  |  | Building A = Gr/St + 4P + 5th to 33rd Floor Building B = Gr/St + 4P + 5th to 34th Floor Commercial Building = Gr/St + 1st Floor
Proposed no of Floors |  |  | Building A = Gr/St + 4P + 5th to 34th Floor
Building B = Gr/St + 4P + 5th to 34th Floor
Commercial Building = Gr/St + 1st to 2nd Floor
Expected Completion |  |  | As per RERA - 30/06/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Building A = Gr/St + 4P + 5th to 34th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 30 Floor, External Plaster upto 28 Floor, Flooring upto 25 Floor, Painting upto 8 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 34
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 30 Floor, External Plaster upto 28 Floor, Flooring upto 25 Floor, Painting upto 8 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8.5
Excavation |  | 34 | 100% | 80.88% |  | 92.21% |  | Excavation in process | 17
Plinth |  | 34 | 100% |  |  |  |  | Excavation Completed | 34
RCC (Including podiums) |  | 35 | 100% |  |  |  |  | Footing in Process | 8.5
Brickwork | Brickwork & Internal Plaster | 34 | 100% |  |  |  |  | Footing Completed | 17
Internal Plaster | Brickwork & Internal Plaster | 30 | 88.24% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 28 | 82.35% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 25 | 73.53% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 8 | 23.53% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 25.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 34
Construction details: |  | Building B = Gr/St + 4P + 5th to 34th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 29 Floor, Painting upto 28 Floor, Finishing upto 12 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 34
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 29 Floor, Painting upto 28 Floor, Finishing upto 12 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8.5
Excavation |  | 34 | 100% | 89.41% |  | 94.26% |  | Excavation in process | 17
Plinth |  | 34 | 100% |  |  |  |  | Excavation Completed | 34
RCC (Including podiums) |  | 35 | 100% |  |  |  |  | Footing in Process | 8.5
Brickwork | Brickwork & Internal Plaster | 34 | 100% |  |  |  |  | Footing Completed | 17
Internal Plaster | Brickwork & Internal Plaster | 34 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 34 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 29 | 85.29% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 28 | 82.35% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 12 | 35.29% |  |  |  |  | Plinth in process | 25.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 34
Construction details: |  | Commercial Building = Gr/St + 1st to 2nd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 2
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 1 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.5
Excavation |  | 2 | 100% | 53.75% |  | 77.5% |  | Excavation in process | 1
Plinth |  | 2 | 100% |  |  |  |  | Excavation Completed | 2
RCC (Including podiums) |  | 3 | 100% |  |  |  |  | Footing in Process | 0.5
Brickwork | Brickwork & Internal Plaster | 1 | 50% |  |  |  |  | Footing Completed | 1
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 1.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 2
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property : | [8 empty] | From 6400 to 8000 | by cost sheet | akash sir | 2022-09-03
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 8700 |  |  | 8000 to 8700 | smith | 2024-07-10 | verbal
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 12000
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | 200000 |  |  | 477000
Legal Services Charges |  |  |  |  | 30,000/-
Club House Charges |  |  |  |  | 200000
Society Formation Charges |  |  |  |  | 50000
Share Application Charges |  |  |  |  | 2000
Water, Electricity, Drainages, Sewerage Connection Charges |  |  |  |  | 75000
Advance Maintenance Charges |  |  |  |  | 100000
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 6960
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | AS PER SITE MEET PERSON 34 FLOOR TWO TOWERS
Commercial Building |  | 7 |  | 7652.8699 |  | 12244.5919
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building A |  | 227 |  | 120398.0552 |  | 192666
Building B |  | 235 |  | 124672.7383 |  | 199470
Total |  | 462 |  | 245070.7935 |  | 392136
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Commercial Building | [8 empty] | 627000
Ground Floor for Commercial
1 |  | Shop | 340.8152 | 0 | 545.3042 | Ground Floor for Commercial |  | 6543650.88
2 |  | Shop (Duplex with 1st Floor) | 1684.4853 | 0 | 2695.1764 |  |  | 32342117.184
3 |  | Shop (Duplex with 1st Floor) | 1342.6744 | 0 | 2148.2791 |  |  | 25779349.44
4 |  | Shop (Duplex with 1st Floor) | 2818.004 | 0 | 4508.8065 |  |  | 54105677.7311
5 |  | Shop | 507.7917 | 0 | 812.4667 |  |  | 9749600.64
6 |  | Shop | 507.7917 | 0 | 812.4667 |  |  | 9749600.64
7 |  | Shop | 451.3076 | 0 | 722.0922 |  |  | 8665106.112
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building A
Ground Floor for Drivers Room, Meter Room & Parking
1st to 3rd Podium Floor for Parking
4th Podium Floor for Fitness Center, Society Office & Other Amenities
5th to 8th, 10th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 33rd Floor for Residential
501 to 3301 |  | 2BHK | 601.2259 | 0 | 983 | 5th to 8th, 10th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 33rd Floor for Residential | [6 empty] | 501 to 3301 | 501 | 3301
502 to 3302 |  | 2BHK | 586.2424 | 0 | 930 | [7 empty] | 502 to 3302 | 502 | 3302
503 to 3303 |  | 1BHK | 436.8381 | 0 | 678 |  |  | 7374.6313 | 5424000 | 8112.0944 |  |  | 503 to 3303 | 503 | 3303
504 to 3304 |  | 1BHK | 436.8381 | 0 | 678 | [7 empty] | 504 to 3304 | 504 | 3304
505 to 3305 |  | 2BHK | 640.6275 | 0 | 1019 |  |  |  | 8152000 |  |  |  | 505 to 3305 | 505 | 3305
506 to 3306 |  | 2BHK | 657.5485 | 0 | 1078 |  |  |  | 8624000 |  |  |  | 506 to 3306 | 506 | 3306
507 to 3307 |  | 1BHK | 446.3723 | 0 | 719 | [7 empty] | 507 to 3307 | 507 | 3307
508 to 3308 |  | 1BHK | 446.3723 | 0 | 719 | [7 empty] | 508 to 3308 | 508 | 3308
9th, 14th, 19th, 24th & 29th Floor (Part Refuge Area)
901,..,2901 |  | 2BHK | 605.101 | 0 | 983 | 9th, 14th, 19th, 24th & 29th Floor (Part Refuge Area) |  | 1.6245 |  |  |  |  | 901,..,2901 | 901 | 2901
902,..,2902 |  | Refuge Area | [5 empty] | #DIV/0! |  |  |  |  | 902,..,2902 | 902 | 2902
903,..,2903 |  | 1BHK | 436.8381 | 0 | 678 |  |  | 1.5521 |  |  |  |  | 903,..,2903 | 903 | 2903
904,..,2904 |  | 1BHK | 436.8381 | 0 | 678 |  |  | 1.5521 |  |  |  |  | 904,..,2904 | 904 | 2904
905,..,2905 |  | 2BHK | 640.6275 | 0 | 1019 |  |  | 1.5906 |  |  |  |  | 905,..,2905 | 905 | 2905
906,..,2906 |  | 2BHK | 657.5485 | 0 | 1078 |  |  | 1.6394 |  |  |  |  | 906,..,2906 | 906 | 2906
907,..,2907 |  | 1BHK | 446.3723 | 0 | 719 |  |  | 1.6108 |  |  |  |  | 907,..,2907 | 907 | 2907
908,..,2908 |  | 1BHK | 446.3723 | 0 | 719 |  |  | 1.6108 |  |  |  |  | 908,..,2908 | 908 | 2908
Building B
Ground Floor for Meter Room & Parking
1st to 3rd Podium Floor for Parking
4th Podium Floor for Amenities
5th to 8th, 10th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 34h Floor for Residential
501 to 3401 |  | 2BHK | 673.8264 | 0 | 983 | 5th to 8th, 10th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 34h Floor for Residential |  |  | 10.764 |  |  |  | 501 to 3401 | 501 | 3401
502 to 3402 |  | 2BHK | 637.0135 | 0 | 930 |  |  |  |  | 61.3978 | 62.6 |  | 502 to 3402 | 502 | 3402
503 to 3403 |  | 1BHK | 423.5096 | 0 | 678 |  |  |  |  | 59.8258 | 59.18 |  | 503 to 3403 | 503 | 3403
504 to 3404 |  | 1BHK | 423.5096 | 0 | 678 |  |  |  | 1.7522 | 40.5713 | 39.345 |  | 504 to 3404 | 504 | 3404
505 to 3405 |  | 2BHK | 581.5574 | 0 | 1019 |  |  |  |  | 40.5713 | 39.345 |  | 505 to 3405 | 505 | 3405
506 to 3406 |  | 2BHK | 614.4952 | 0 | 1078 |  |  |  |  | 54.3513 | 54.028 |  | 506 to 3406 | 506 | 3406
507 to 3407 |  | 1BHK | 449.3862 | 0 | 719 |  |  |  |  | 55.7852 | 57.088 |  | 507 to 3407 | 507 | 3407
508 to 3408 |  | 1BHK | 449.3862 | 0 | 719 |  |  |  |  | 41.529 | 41.749 |  | 508 to 3408 | 508 | 3408
9th, 14th, 19th, 24th & 29th Floor (Part Refuge Area) | [9 empty] | 41.529 | 41.749
901,..,2901 |  | 2BHK | 614.4952 | 0 | 983 | 9th, 14th, 19th, 24th & 29th Floor (Part Refuge Area) | [6 empty] | 901,..,2901 | 901 | 2901
902,..,2902 |  | Refuge Area | [10 empty] | 902,..,2902 | 902 | 2902
903,..,2903 |  | 1BHK | 423.5096 | 0 | 678 | [7 empty] | 903,..,2903 | 903 | 2903
904,..,2904 |  | 1BHK | 423.5096 | 0 | 678 | [7 empty] | 904,..,2904 | 904 | 2904
905,..,2905 |  | 2BHK | 637.0135 | 0 | 1019 |  |  |  | 8152000 | 8470.0687 | 163040 |  | 905,..,2905 | 905 | 2905
906,..,2906 |  | 2BHK | 673.8264 | 0 | 1078 |  |  |  | 8715040 |  |  |  | 906,..,2906 | 906 | 2906
907,..,2907 |  | 1BHK | 449.3862 | 0 | 719 | [7 empty] | 907,..,2907 | 907 | 2907
908,..,2908 |  | 1BHK | 449.3862 | 0 | 719 | [7 empty] | 908,..,2908 | 908 | 2908
Remarks:
1 | Wing A & B = Construction work is in process at the time of Visit. (Internal visit not allowed). Commercial Building = Construction stage is same as last visit (dtd. 10/03/2025) but work is in process (Slow Speed). (Internal visit not allowed)
2 | We considered Saleable area as per our calculation for Commercial.
3 | We considered Saleable area as per Builder Area Sheet for Flats.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Balcony + Chajja Area.
6 | We have considered rate by verifying it from market inquire.
7 | Car parking is subjected to authentic documentation.
8 | On Site, we meet Mr. Ishtihar (9819081463)
9 | We have updated latest approved floor plans & CC (On 27/06/2024).
10 | The clockwise method is followed for flat numbering in Building A and For Building B, as per the typical floor plan, e.g., 5th to 8th, 10th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 34h Floor, flat numbering is considered by the clockwise method and As per the refuge floor plan, e.g., 9th, 14th, 19th, 24th, and 29th floors, flat numbering is considered by the anticlockwise method.
11 | Recommended Rates/Other Charges of the Property have been revised on 10/07/2024.
12 | Construction work goes beyond Approved plan & CC permission of Building A & Commercial Building. Please provide revised approved CC & Plans
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Regents Park Kharghar
Google Map :
Formulas:
Rohinjan = [Rohinjan, row above]
Commercial
Bldg A
Bldg B
Bldg A
Bldg B
Bldg A
Bldg B

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted