## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 30/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-08
Name of the builder group |  |  |  |  | M/s. Ashtvinayak Homes
Name of the builder company |  |  |  |  | M/s. Ashtvinayak Homes
Name of the Project |  |  |  |  | Sarvam
Contact Details ( Name & Contact No.) |  |  |  |  | 2740078500
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  |  | Mr. Ajay 9513446092
Name / No of the Building |  |  |  |  | Building No.1 (A & B Wing) Building No.2 (C Wing)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | P52000023662
Project location details |  | Sarvam, Survey No.35/2, 35/3, 36/2, Ghot Road, Koyana Velhe, Taloja Panchnand, Panvel, Raigad.
Survey No |  | 35/2, 35/3, 36/2
Road |  | Ghot Road |  |  | Locality/Village |  | Koyana Velhe
City |  | Taloja Panchnand |  |  | District |  | Raigad
Taluka |  | Panvel |  |  | Pin Code |  | 410208
Near by Landmark |  | Arihant Anaika |  |  | Distance from city centre: |  | 3.4 Km from Taloja Panchnand Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Road |  | Taloja River |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.082347,73.112256
Location Link |  | https://goo.gl/maps/7S5N8KKg2r9mmtwz5
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 7411.645
Permissible FSI |  |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1.1
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 8152.8095
Total number of Buildings |  |  |  |  | 3 Wings
Approval Detail : Plan approval
Layout Approval No |  | PMP/NRV/16194/JK-2177/2021 |  |  |  | Dated | 2021-10-27
Approved Floor plan No. |  | PMP/NRV/16194/JK-2177/2021 |  |  |  | Dated | 2021-10-27
Commencement Certificate No. |  | PMC/TP/Koyanavele/35/2,35/3&36/2/21-21/16194/2177/2021 |  |  |  | Dated | 2021-10-27
Valid Up to: Blg No.1 (A & B Wing) & Blg No.2 (C Wing) = G/St + 1st to 11th Floor.
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 2021-10-27 |  | Expected Completion |  | Completed |  | 2025-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 8152.8095 |  | Approved no of units |  | Flats = 240
Approved no of Floors |  | Blg No.1 (A & B Wing) & Blg No.2 (C Wing) = G/St + 1st to 11th Floor.
Proposed no of Floors |  | Blg No.1 (A & B Wing) & Blg No.2 (C Wing) = G/St + 1st to 11th Floor.
Quality of construction: Good |  |  | Projected life of the structure: 60 Years
Material laying at Site: NA | [8 empty] | Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | Blg No.1 (A & B Wing) = G/St + 1st to 11th Floor. | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 11
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% |  | 100% |  | 100% |  | Excavation in process | 5.5
Plinth |  | 11 | 100% | [5 empty] | Excavation Completed | 11
RCC (Including podiums) |  | 12 | 100% | [5 empty] | Footing in Process | 2.75 |  |  | s
Brickwork | Brickwork & Internal Plaster | 11 | 100% | [5 empty] | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 11 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 11 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 11 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 11 | 100% | [5 empty] | Plinth in process | 8.25
Possession |  | 11 | 100% | [5 empty] | Plinth completed | 11
Construction details: |  | Blg No.1 (B Wing) = G/St + 1st to 11th Floor. | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 9 Floor, Painting upto 8 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 11
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 9 Floor, Painting upto 8 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% |  | 86.82% |  | 94.09% |  | Excavation in process | 5.5
Plinth |  | 11 | 100% | [5 empty] | Excavation Completed | 11
RCC (Including podiums) |  | 12 | 100% | [5 empty] | Footing in Process | 2.75 |  |  | s
Brickwork | Brickwork & Internal Plaster | 11 | 100% | [5 empty] | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 11 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 9 | 81.82% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 8 | 72.73% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 8.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 11
Construction details: |  | Blg No.2 (C Wing) = G/St + 1st to 11th Floor. | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 11
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% |  | 100% |  | 100% |  | Excavation in process | 5.5
Plinth |  | 11 | 100% | [5 empty] | Excavation Completed | 11
RCC (Including podiums) |  | 12 | 100% | [5 empty] | Footing in Process | 2.75
Brickwork | Brickwork & Internal Plaster | 11 | 100% | [5 empty] | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 11 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 11 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 11 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 11 | 100% | [5 empty] | Plinth in process | 8.25
Possession |  | 11 | 100% | [5 empty] | Plinth completed | 11
Wheather the construction is as per approved Building plan :Yes
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc. | [6 empty] | Rate has been changed from 4500/- to 5100/- (on 03/02/2022). |  |  |  |  | By Akash Sir
Recommended Rates of the Property : | [8 empty] | Other Charges | Smith Pal Sir | 2023-02-13
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 5300 |  |  | 5100 to 5300 | Smith Pal Sir | 2024-04-12
Development Charges | [5 empty] | 2,00,000/-
Maintenance Charges @ 36 Months | [5 empty] | 54,000/-
Grill & Society Formation Charges | [5 empty] | 110000/-
Recommended rate of Parking | [5 empty] | 2,00,000/-
Distressed valuation of the Property | [5 empty] | 4240
Residential Area Details :
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
Blg No.1 (A Wing) |  | 33 | 14505.2004 |  |  | 23730
Blg No.1 (B Wing) |  | 98 | 39631.1159 |  |  | 65830
Blg No.2 (C Wing) |  | 109 | 42859.6162 |  |  | 72260
Total |  | 240 | 96995.9325 |  |  | 161820
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building No.1
A Wing
Ground Floor for Parking
1st, 3rd, 5th, 7th, 9th & 11th Floor for Residential
101,…,1101 |  | 1BHK | 473.4761 |  | 0 | 735 | N | 1st, 3rd, 5th, 7th, 9th & 11th Floor for Residential | 326.2837 | 735 | 1.5523 | 101 | 1101 |  | 101,…,1101
102,…,1102 |  | 1BHK | 423.6387 |  | 54.4927 | 750 | N |  |  | 750 | 1.7704 | 102 | 1102 |  | 102,…,1102
103,…,1103 |  | 1BHK | 421.5398 |  | 52.313 | 745 | N |  |  | 745 | 1.7673 | 103 | 1103 |  | 103,…,1103
2nd, 4th, 6th & 10th Floor
201,…,1001 |  | 1BHK | 473.4761 |  | 0 | 735 | N | 2nd, 4th, 6th & 10th Floor | 1.5523 |  |  | 201 | 1001 |  | 201,…,1001
202,…,1002 |  | 1BHK | 423.6387 |  | 0 | 670 | N |  | 1.5815 |  |  | 202 | 1002 |  | 202,…,1002
203,…,1003 |  | 1BHK | 421.5398 |  | 0 | 665 | N |  | 1.5775 |  |  | 203 | 1003 |  | 203,…,1003
8th Floor (Part Refuge Area)
801 |  | 1BHK | 473.4761 |  | 0 | 735 | N | 8th Floor (Part Refuge Area) | 1.5523
802 |  | 1BHK | 423.6387 |  | 0 | 670 | N |  | 1.5815
803 |  | 1BHK | 421.5398 |  | 0 | 665 | N |  | 1.5775
B Wing
Ground Floor for Parking
1st, 3rd, 5th, 7th, 9th & 11th Floor for Residential
101,…,1101 |  | 1BHK | 371.4118 |  | 46.5005 | 655 | N | 1st, 3rd, 5th, 7th, 9th & 11th Floor for Residential | 2947500 | 655 | 1.7635 | 101 | 1101 |  | 101,…,1101
102,…,1102 |  | 2BHK | 546.0039 |  | 53.2818 | 935 | N |  |  | 935 | 1.7124 | 102 | 1102 |  | 102,…,1102
103,…,1103 |  | 1RK | 290.5634 |  | 0 | 455 | N |  |  | 455 | 1.5659 | 103 | 1103 |  | 103,…,1103
104,…,1104 |  | 1BHK | 402.5951 |  | 59.7402 | 715 | N |  |  | 715 | 1.776 | 104 | 1104 |  | 104,…,1104
105,…,1105 |  | 1BHK | 418.5797 |  | 59.7402 | 750 | N |  |  | 750 | 1.7918 | 105 | 1105 |  | 105,…,1105
106,…,1106 |  | 1BHK | 391.1853 |  | 46.2987 | 675 | N |  |  | 675 | 1.7255 | 106 | 1106 |  | 106,…,1106
107,…,1107 |  | 1BHK | 372.7788 |  | 46.2987 | 645 | N |  | 367.2946 | 645 | 1.7302 | 107 | 1107 |  | 107,…,1107
108,…,1108 |  | 1BHK | 426.1683 |  | 45.0473 | 740 | N |  |  | 740 | 1.7364 | 108 | 1108 |  | 108,…,1108
109,…,1109 |  | 1BHK | 419.1071 |  | 33.7451 | 715 | N |  |  | 715 | 1.706 | 109 | 1109 |  | 109,…,1109
2nd, 4th, 6th & 10th Floor
201,…,1001 |  | 1BHK | 371.4118 |  | 0 | 585 | N | 2nd, 4th, 6th & 10th Floor | 1.5751 |  |  | 201 | 1001 |  | 201,…,1001
202,…,1002 |  | 2BHK | 545.9985 |  | 0 | 850 | N |  | 1.5568 |  |  | 202 | 1002 |  | 202,…,1002
203,…,1003 |  | 1RK | 290.5634 |  | 0 | 455 | N |  | 1.5659 |  |  | 203 | 1003 |  | 203,…,1003
204,…,1004 |  | 1BHK | 402.5951 |  | 0 | 625 | N |  | 1.5524 |  |  | 204 | 1004 |  | 204,…,1004
205,…,1005 |  | 1BHK | 418.5797 |  | 0 | 660 | N |  | 1.5768 |  |  | 205 | 1005 |  | 205,…,1005
206,…,1006 |  | 1BHK | 391.1853 |  | 0 | 605 | N |  | 1.5466 |  |  | 206 | 1006 |  | 206,…,1006
207,…,1007 |  | 1BHK | 372.7788 |  | 0 | 570 | N |  | 1.5291 |  |  | 207 | 1007 |  | 207,…,1007
208,…,1008 |  | 1BHK | 426.1683 |  | 0 | 670 | N |  | 1.5721 |  |  | 208 | 1008 |  | 208,…,1008
209,…,1009 |  | 1BHK | 419.1071 |  | 41.4468 | 725 | N |  | 1.7299 |  |  | 209 | 1009 |  | 209,…,1009
8th Floor (Part Refuge Area)
801 |  | 1BHK | 371.4118 |  | 0 | 585 | N | 8th Floor (Part Refuge Area) | 1.5751
802 |  | 2BHK | 545.9985 |  | 0 | 850 | N |  | 1.5568
803 |  | 1RK | 290.5634 |  | 0 | 455 | N |  | 1.5659
804 |  | 1BHK | 402.5951 |  | 0 | 625 | N |  | 1.5524
805 |  | 1BHK | 418.5797 |  | 0 | 660 | N |  | 1.5768
806 |  | 1BHK | 372.7788 |  | 0 | 570 | N |  | 1.5291
807 |  | 1BHK | 426.1683 |  | 0 | 670 | N |  | 1.5721
808 |  | 1BHK | 419.1071 |  | 41.4468 | 725 | N |  | 1.7299
Building No.2
C Wing
Ground Floor for Parking
1st, 3rd, 5th, 7th 9th & 11th Floor for Residential
101,…,1101 |  | 2BHK | 561.8243 |  | 64.1803 | 980 | N | 1st, 3rd, 5th, 7th 9th & 11th Floor for Residential | 1.7443 |  |  | 101 | 1101 |  | 101,…,1101
102,…,1102 |  | 1RK | 264.8159 |  | 0 | 405 | N |  | 1.5294 |  |  | 102 | 1102 |  | 102,…,1102
103,…,1103 |  | 1BHK | 398.3756 |  | 61.3548 | 720 | N |  | 1.8073 |  |  | 103 | 1103 |  | 103,…,1103
104,…,1104 |  | 1BHK | 342.6181 |  | 68.7012 | 650 | N |  | 1.8972 |  |  | 104 | 1104 |  | 104,…,1104
105,…,1105 |  | 1BHK | 417.8208 |  | 68.7012 | 765 | N |  | 1.8309 |  |  | 105 | 1105 |  | 105,…,1105
106,…,1106 |  | 1BHK | 415.6142 |  | 44.0584 | 725 | N |  | 1.7444 |  |  | 106 | 1106 |  | 106,…,1106
107,…,1107 |  | 1BHK | 422.261 |  | 44.0584 | 735 | N |  | 1.7406 |  |  | 107 | 1107 |  | 107,…,1107
108,…,1108 |  | 1BHK | 412.8855 |  | 54.4524 | 735 | N |  | 1.7802 |  |  | 108 | 1108 |  | 108,…,1108
109,…,1109 |  | 1BHK | 372.0361 |  | 42.8676 | 645 | N |  | 1.7337 |  |  | 109 | 1109 |  | 109,…,1109
110,…,1110 |  | 1BHK | 339.1521 |  | 34.1488 | 580 | N |  | 1.7101 |  |  | 110 | 1110 |  | 110,…,1110
2nd, 4th, 6th & 10th Floor
201,…,1001 |  | 2BHK | 561.8243 |  | 0 | 880 | N | 2nd, 4th, 6th & 10th Floor | 1.5663 |  |  | 201 | 1001 |  | 201,…,1001
202,…,1002 |  | 1RK | 264.8159 |  | 0 | 405 | N |  | 1.5294 |  |  | 202 | 1002 |  | 202,…,1002
203,…,1003 |  | 1BHK | 398.3756 |  | 0 | 625 | N |  | 1.5689 |  |  | 203 | 1003 |  | 203,…,1003
204,…,1004 |  | 1BHK | 342.6181 |  | 0 | 545 | N |  | 1.5907 |  |  | 204 | 1004 |  | 204,…,1004
205,…,1005 |  | 1BHK | 417.8208 |  | 0 | 655 | N |  | 1.5677 |  |  | 205 | 1005 |  | 205,…,1005
206,…,1006 |  | 1BHK | 415.6142 |  | 0 | 655 | N |  | 1.576 |  |  | 206 | 1006 |  | 206,…,1006
207,…,1007 |  | 1BHK | 422.261 |  | 75.0251 | 780 | N |  | 1.8472 |  |  | 207 | 1007 |  | 207,…,1007
208,…,1008 |  | 1BHK | 412.8855 |  | 0 | 650 | N |  | 1.5743 |  |  | 208 | 1008 |  | 208,…,1008
209,…,1009 |  | 1BHK | 372.0361 |  | 28.2555 | 580 | N |  | 1.559 |  |  | 209 | 1009 |  | 209,…,1009
210,…,1010 |  | 1BHK | 339.1521 |  | 28.2555 | 525 | N |  | 1.548 |  |  | 210 | 1010 |  | 210,…,1010
8th Floor (Part Refuge Area)
801 |  | 1RK | 264.8159 |  | 0 | 405 | N | 8th Floor (Part Refuge Area) | 1.5294
802 |  | 1BHK | 398.3756 |  | 0 | 625 | N |  | 1.5689
803 |  | 1BHK | 342.6181 |  | 0 | 545 | N |  | 1.5907
804 |  | 1BHK | 417.8208 |  | 0 | 655 | N |  | 1.5677
805 |  | 1BHK | 415.6142 |  | 0 | 655 | N |  | 1.576
806 |  | 1BHK | 422.261 |  | 75.0251 | 780 | N |  | 1.8472
807 |  | 1BHK | 412.8855 |  | 0 | 650 | N |  | 1.5743
808 |  | 1BHK | 372.0361 |  | 28.2555 | 580 | N |  | 1.559
809 |  | 1BHK | 339.1521 |  | 28.2555 | 525 | N |  | 1.548
Remarks:
1. Wing A, B & C = All work completed. Please provide OC. 2. We considered Saleable area as per Builder Area Sheet. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + Balcony. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. We have updated Revised Approved CC & Plans ( on 08/01/2022). 8. Recommended Rates/Other Charges of the Property have been revised on 12/04/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report Prepared By : |  |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sarvam
Google Map :
Formulas:
Koyana Velhe = [Koyana Velhe, row above]
B Wing
A Wing
B Wing
C Wing

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate (on Saleable Area) | Market Value
Housing | Sarvam | 1BHK | 476 | 690.2 | 4137.931 | 2856000
Housing | Sarvam | 1BHK | 507 | 735.15 | 4137.931 | 3042000
Proptiger | Sarvam | 1BHK | 228 | 330.6 | 4137.931 | 1368000
Proptiger | Sarvam | 1BHK | 329 | 477.05 | 2867.6239 | 1368000
Proptiger | Sarvam | 1BHK | 343 | 497.35 | 3969.0359 | 1974000
Proptiger | Sarvam | 2BHK | 453 | 656.85 | 4137.931 | 2718000
Proptiger | Sarvam | 2BHK | 469 | 680.05 | 4137.931 | 2814000
Average |  |  |  |  | 3932.3307
Valuation Adopted |  |  |  |  | 4000

## NOTE
15/10/2020. | Dhanashree | OLD APF
Rate has not Changed
2021-12-03 | Pratiksha

## A & B%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 1 | 12.5% |  | Parking |  | Rate
Bricks | 7 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 5 | 0 | 0 | 0 | 0 | 0
RCC | 5 | 3.75 |  | Recommended |  | 30 | 3.75 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 15% | 33.75% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B2
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 7 | 70%
slab | 8 | 0 | 0% |  | Parking |  | Rate
Bricks | 7 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 7 | 27 |  | Progress |  | 7 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 27 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 7% | 27% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## C% (2)
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 0 | 0%
slab | 8 | 0 | 0% |  | Parking |  | Rate
Bricks | 7 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 7 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 0 | 20 |  | Progress |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 0% | 20% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.85 | 3.45 | 9.8325 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.8 | 2 | 3.6 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 3.2 | 2.75 | 8.8 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.2 | 2.2 | 2.64 | DB |  |  | 0 |  |  | 0
| toilet2 | 2 | 1.2 | 2.4 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.2 | 3 | 3.6 |  |  |  | 0 |  |  | 0
| passage2 | 0.45 | 2 | 0.9 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 341.9992 | 31.7725 |  |  | 0 | 0 |  | 0 | 0
|  |  | 341.9992 | 31.7725