## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 10/09/2025
CPC Name: |  |  |  |  | Axis Goregoan
Date Of Property Visit |  |  |  |  | 2025-09-08
Name of the builder group |  |  |  |  | M/s.Shree Sai Jivdani Developers
Name of the builder company |  |  |  |  | M/s.Shree Sai Jivdani Developers
Name of the Project |  |  |  |  | Shree Sai Apartment
Contact Details ( Name & Contact No.) |  |  |  |  | 9673735635
Name / no of the Building |  |  |  |  | Building no.5 Wing C (Type M1)
Docouments Provided |  |  |  |  | Approved Layout & NA Order cum CC
RERA No. |  |  |  |  | P99000019094
Project location details |  | Shree Sai Apartment, Building no.5, Wing C, GUT NO. 133, Umroli, Palghar.
Plot No | NA |  |  | G. No |  | 133 | Locality | Umroli
Road | Padghe Road |  |  |  | District | Palghar
City | Palghar |  |  |  | Pin Code | 401404
Near by Landmark |  | Umroli Railway Station |  |  | Distance from city centre: |  | About 0.85 Km from Umroli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | A&B Wing |  | Open Plot |  | Building |  | Under Construction buillding
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.750549,72.763238
Location Link |  | https://goo.gl/maps/BL3Xdy6uBmz3XfJo8
Approval details:
Approved usage of the Property: Residential + Commercial (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 14987.49
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 14987.49
Total number of Buildings |  |  |  |  | 1 Wing
Approval Detail : Plan approval
Layout Approval No |  | MHSL/KS.1/T.1/NP/SR-232/2017 |  |  |  | Dated | 29/11/2017.
Building plan approval No |  | MHSL/KS.1/T.1/NP/SR-232/2017 |  |  |  | Dated | 29/11/2017. | Expiry date:NA
NA Order Cum Commencement of Construction |  | MHSL/KS.1/T.1/NP/SR-232/2017 Valid Upto: Building no.5 Wing C (Type M1) = Gr + 1st to 4th Floor. |  |  |  | Dated | 29/11/2017. | Expiry date: One year from date of issue
O. Certificate No.: NA |  |  |  |  | Date of approval: NA |  |  | Expiry date: NA
Commencement date of construction |  |  | 29/11/2017. |  | Expected Completion |  | 2026-07-30
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 14987.49 |  | Approved no of units |  |  | Flats = 26 Shops = 09
Approved no of Floors |  | Gr. + 1st to 4th floor |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: Building no.5 Wing C (Type M1) = Gr. + 1st to 4th floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 4 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 4 | 100% |  | 57.5% |  | 80%
Plinth |  | 4 | 100%
RCC |  | 5 | 100% | [5 empty] | Excavation in process |  | 2
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Excavation Completed |  | 4
Internal Plaster | Brickwork & Internal Plaster | 0 | 0%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Footing in Process |  | 1
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 2
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 3
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 4
Possession |  | 0 | 0%
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 2800
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 4600
Recommended rate of Parking | [5 empty] | 100000
PLC charges | [5 empty] | NA
Club Charges | [5 empty] | NA
Any Other amenities | [5 empty] | NA
Society formation charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | NA
Development charges Per Sq. Ft. | [5 empty] | NA
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 2240
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building No 5
Wing C (Type M1)
Ground Floor
9 |  | Shop | 182.0192 |  | 0 | 273.0289 | N | Ground Floor |  | 16.91 | 10.764
10 |  | Shop | 142.3001 |  | 0 | 213.4501 | N |  |  | 13.22 | 10.764
11 |  | Shop | 182.0192 |  | 0 | 273.0289 | N |  |  | 16.91 | 10.764
12 |  | Shop | 148.005 |  | 0 | 222.0075 | N |  |  | 13.75 | 10.764
13 |  | Shop | 115.713 |  | 0 | 173.5695 | N |  |  | 10.75 | 10.764
14 |  | Shop | 148.005 |  | 0 | 222.0075 | N |  |  | 13.75 | 10.764
15 |  | Shop | 130.7826 |  | 0 | 196.1739 | N |  |  | 12.15 | 10.764
16 |  | Shop | 130.7826 |  | 0 | 196.1739 | N |  |  | 12.15 | 10.764
17 |  | Shop | 131.859 |  | 0 | 197.7885 | N |  |  | 12.25 | 10.764 | 14.47
1 |  | 1BHK | 395.3617 |  | 0 | 640 | N |  |  | 36.73 | 10.764
2 |  | 1RK | 251.447 |  | 0 | 410 | N |  | 2 | 23.36 | 10.764
1st to 4th Floor
1 |  | 1BHK | 395.3617 |  | 0 | 640 | N | 1st to 4th Floor |  |  | 10.764 | 36.73
2 |  | 1RK | 250.3706 |  | 0 | 410 | N |  |  |  | 10.764 | 23.26
3 |  | 1BHK | 392.886 |  | 0 | 640 | N |  |  |  | 10.764 | 36.5
4 |  | 1BHK | 392.886 |  | 0 | 640 | N |  |  |  | 10.764 | 36.5 | 2468.75
5 |  | 1BHK | 392.886 |  | 0 | 640 | N |  |  | 2467.1875 | 10.764 | 36.5
6 |  | 2BHK | 523.561 |  | 0 | 850 | N |  | 24 |  | 10.764 | 48.64
Remarks: 1. Construction work is stopped. Work is same as last visit (13/03/2024). 2. We considered Saleable area as per Builder area sheet. 3. We considered Carpet area as per Approved Plan. 4. We have given rate verify by Market Inquire. 5. Since The project has received first CC on 29/11/2017, But construction work is not yet Completed. | [9 empty] | 5. As per RERA, completion period of project Shree Sai Apartment is expired on 30/12/2023 but still project work is pending.7. The project is not available on RERA site (Checked on 10/06/2025 ).
Undertaking : | [9 empty] | 1.57
1) We have personally visited the property & identified the same based on the documents provided | [9 empty] | 1.4358
2) I/We have no direct or Indirect Interest in the property being valued | [9 empty] | 1.6021
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY OF CUSTOMER: |  |  |  | Shree Sai Apartment
Google Map :
C Wing
C Wing

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing. | Shree Sai Apartment | 1BHK | 385 | 558.25 | 2828.4819 | 1579000
Average |  |  |  |  | 2828.4819
Valuation Adopted |  |  |  |  | 2800

## Construction %
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 40 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 2 | 0 | Progress |  |  | 10 | 16 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 12 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 16 | 12
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 4 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 26 | 42

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 3.55 | 9.7625 | CB | 0 | 0 | 0 |  |  | 0
|  | 0 | 0 | 0 | FB | 0 | 0 | 0 |  |  | 0
|  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0
| kitch | 2.15 | 2.6 | 5.59 | CB | 0 | 0 | 0 |  |  | 0
|  | 0 | 0 | 0 | FB | 0 | 0 | 0 |  |  | 0
|  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0
|  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0
| Bed1 | 2.75 | 2.6 | 7.15 | CB | 0 | 0 | 0 |  |  | 0
|  | 0 | 0 | 0 | FB |  |  | 0 |  |  | 0
|  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0
|  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 0 | 0 | 0 | CB |  |  | 0 |  |  | 0
|  | 0 | 0 | 0 | FB |  |  | 0 |  |  | 0
|  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 0 | 0 | 0 | CB |  |  | 0 |  |  | 0
|  | 0 | 0 | 0 | FB |  |  | 0 |  |  | 0
|  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 2.35 | 1.2 | 2.82 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.2 | 2.35 | 2.82 | DB |  |  | 0 |  |  | 0
| toilet3 | 0 | 0 | 0 | DB |  |  | 0 |  |  | 0
|  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0
| passage1 | 0.9 | 2.3 | 2.07 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 325.2073 | 30.2125 |  |  | 0 | 0 |  | 0 | 0
30.2125

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.1 | 2.75 | 8.525 | CB | 1 | 2.75 | 2.75 |  |  | 0
|  | 1.2 | 0.45 | 0.54 | FB |  |  | 0 |  |  | 0
|  | 1.4 | 0.45 | 0.63 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  | 2.6 | 2.15 | 5.59 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.65 | 2.75 | 7.2875 | CB | 1 | 2.75 | 2.75 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.2 | 2.45 | 2.94 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.2 | 2.45 | 2.94 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 2.8 | 1 | 2.8 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 336.4019 | 31.2525 |  |  | 59.202 | 5.5 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 3.55 | 9.7625 | CB | 1.25 | 2.75 | 3.4375 |  |  | 0
|  |  |  | 0 | FB | 1 | 2.75 | 2.75 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.15 | 2.6 | 5.59 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.75 | 2.4 | 6.6 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 2.35 | 1.2 | 2.82 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.2 | 2.35 | 2.82 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1 | 2.15 | 2.15 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 320.1483 | 29.7425 |  |  | 66.6022 | 6.1875 |  | 0 | 0
35.93