## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 17/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-09-11
Name of the builder |  |  |  | Mr.Suresh Shivshankar Sharma
Name of the builder company |  |  |  | M/s. Abhishek Enterprises Builders & Developers
Name of the Project |  |  |  | Shiv Shankar Residency
Contact Details ( Name & Contact No.) |  |  |  | 9594244505
Name / No of the Building |  |  |  | 1 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P52000025032
Project location details |  | Shiv Shankar Residency, Plot No.15, Sector - 19, Internal Road, NearPacific Tower, Taloja(New), Taloja, Panvel, Raigad - 410208.
Plot No |  | 15, Sector - 19
Road |  | Internal Road |  | Locality/Village |  | Taloja(New)
City |  | Taloja |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410208
Nearby Landmark |  | Pacific Tower |  | Distance from city centre: |  | 1.7Km from Taloja Panchanand Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Internal Road
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | City Height Building
South | NA | NA |  |  | L.K. Exotica Apartment
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.070604459,73.095466424
Location Link |  | https://goo.gl/maps/jdY8niKBKpvtoGzc6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1349.7
Permissible FSI |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 1.5
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 2024.55
Total number of Buildings |  |  |  | 1 Building
Approval Detail : Plan approval
Layout Approval No |  | CIDCO/BP-17355/TPO(NM & K)/2020/6894 |  |  | Dated | 2020-02-29
Approved Floor plan No. |  | CIDCO/BP-17355/TPO(NM & K)/2020/6894 |  |  | Dated | 2020-02-29
Commencement Certificate No. |  | CIDCO/BP-17355/TPO(NM & K)/2020/6894 |  |  | Dated | 29/02/2020
Valid Up to: Gr + 1st to 13th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 2024.55
Approved no of units |  |  | Flats - 48, Shops - 12
Approved no of Floors |  |  | Gr + 1st to 13th Floor
Proposed no of Floors |  |  | Gr + 1st to 13th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Gr + 1st to 13th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 13
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.25
Excavation |  | 13 | 100% | 93.08% |  | 95% |  | Excavation in process | 6.5
Plinth |  | 13 | 100% |  |  |  |  | Excavation Completed | 13
RCC (Including podiums) |  | 14 | 100% |  |  |  |  | Footing in Process | 3.25
Brickwork | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Footing Completed | 6.5
Internal Plaster | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 13 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 13 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 12 | 92.31% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 9 | 69.23% |  |  |  |  | Plinth in process | 9.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 13
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. (on Saleable area) |  |  |  |  | 7000
Recommended rate of the shop Per Sq. Ft. (on Saleable area) |  |  |  |  | 10000/-
Development Charges |  |  |  |  | 225000/-
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | 125000/-
Recommended rate of Parking |  |  |  |  | 200000/-
Distressed valuation of the Property |  |  |  |  | 5600
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop |  | 12 |  | 3417.1534 |  | 6150.8762
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flat |  | 48 |  | 22827.5377 |  | 41060
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Ground Floor for Commecial & Parking
1 |  | Shop | 367.4937 | 0 | 661.4887 | Ground Floor for Commecial & Parking |  | 306.1277 | 1.8
2 |  | Shop | 331.9941 | 0 | 597.5893 | Ground Floor for Commecial & Parking |  | 305.3937 | 1.8
3 |  | Shop | 331.9941 | 0 | 597.5893 | Ground Floor for Commecial & Parking |  |  | 1.8
4 |  | Shop | 331.9941 | 0 | 597.5893 | Ground Floor for Commecial & Parking |  |  | 1.8
5 |  | Shop | 331.9941 | 0 | 597.5893 | Ground Floor for Commecial & Parking |  |  | 1.8
6 |  | Shop | 331.9941 | 0 | 597.5893 | Ground Floor for Commecial & Parking |  |  | 1.8
7 |  | Shop | 331.9941 | 0 | 597.5893 | Ground Floor for Commecial & Parking |  |  | 1.8
8 |  | Shop | 281.6777 | 0 | 507.0199 | Ground Floor for Commecial & Parking |  |  | 1.8
9 |  | Shop | 188.9243 | 0 | 340.0638 | Ground Floor for Commecial & Parking |  |  | 1.8
10 |  | Shop | 188.9243 | 0 | 340.0638 | Ground Floor for Commecial & Parking |  |  | 1.8
11 |  | Shop | 199.0845 | 0 | 358.3521 | Ground Floor for Commecial & Parking |  |  | 1.8
12 |  | Shop | 199.0845 | 0 | 358.3521 | Ground Floor for Commecial & Parking |  |  | 1.8
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
1st Floor for Amenities
2nd, 4th, 6th, 8th, 10th & 12th Floor for Residential | [9 empty] | ,.., |  | 2nd, 4th | 12
201,..,1201 | 201,..,1201 | 2BHK | 585.1849 | 0 | 1055 | 2nd, 4th, 6th, 8th, 10th & 12th Floor for Residential |  | 250 | 1.8028 | 2401,..,1201 | 1 | 2401 | 1201
202,..,1202 | 202,..,1202 | 1BHK | 375.556 | 0 | 665 |  |  |  | 1.7707 | 2402,..,1202 | 2 | 2402 | 1202
203,..,1203 | 203,..,1203 | 1BHK | 375.556 | 0 | 665 |  |  |  | 1.7707 | 2403,..,1203 | 3 | 2403 | 1203
204,..,1204 | 204,..,1204 | 2BHK | 585.1849 | 0 | 1055 |  |  |  | 1.8028 | 2404,..,1204 | 4 | 2404 | 1204
3rd, 5th, 7th, 9th & 11th Floor | [9 empty] | ,.., |  | 3rd, 5 | 11
301,..,1101 | 301,..,1101 | 2BHK | 585.1849 | 0 | 1050 | 3rd, 5th, 7th, 9th & 11th Floor |  | 1.8028 |  | 3501,..,1101 | 1 | 3501 | 1101
302,..,1102 | 302,..,1102 | 1BHK | 375.556 | 0 | 665 | 3rd, 5th, 7th, 9th & 11th Floor |  |  |  | 3502,..,1102 | 2 | 3502 | 1102
303,..,1103 | 303,..,1103 | 1BHK | 375.556 | 0 | 665 | 3rd, 5th, 7th, 9th & 11th Floor |  |  |  | 3503,..,1103 | 3 | 3503 | 1103
304,..,1104 | 304,..,1104 | 2BHK | 585.1849 | 0 | 1050 | 3rd, 5th, 7th, 9th & 11th Floor |  |  |  | 3504,..,1104 | 4 | 3504 | 1104
13th Floor | [11 empty] | 13
1301 |  | 1BHK | 470.0639 | 104.3032 | 980 | 13th Floor |  |  |  | 1301 | 1 | 1301
1302 |  | 1BHK | 375.556 | 0 | 655 | 13th Floor |  |  |  | 1302 | 2 | 1302
1303 |  | 1BHK | 375.556 | 0 | 655 | 13th Floor |  |  |  | 1303 | 3 | 1303
1304 |  | 1BHK | 470.0639 | 104.3032 | 980 | 13th Floor |  |  |  | 1304 | 4 | 1304
Remarks:
1. Lift & Finishing work is pending. 2. We considered Flat Saleable area as per Builder area sheet & Shop area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + Chajja/Cornice. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. On Site, we meet Mr. Sandip : 8108443441. 7. The project has received first CC on 29/02/2020, But construction workis not yet completed.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mayur Ranvare |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Shiv Shankar Residency
Google Map :
Formulas:
Taloja(New) = [Taloja(New), row above]

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.5 | 2.9 | 13.05 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.88 | 2.13 | 4.0044 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.9 | 1.07 | 2.033 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 205.4568 | 19.0874 |  |  | 0 | 0 |  | 0 | 0
|  |  | 205.4568 | 19.0874

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted