## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 18/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Sammaan Capital | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | SCL Kalyan
CPC Name: |  |  |  | Axis Goregaon | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | SCL Badlapur
Date Of Property Visit |  |  |  | 2025-09-08 | [6 empty] | Axis Sanpada | PNB Panvel |  | SCL Vashi
Name of the builder group |  |  |  | M/s. Caroa Properties LLP | [6 empty] | Axis Badlapur |  |  | SCL Vashi
Name of the builder company |  |  |  | M/s. Caroa Properties LLP | [9 empty] | SCL Thane
Name of the Project |  |  |  | Green Terraces | [9 empty] | SCL Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | 9821422860 | [9 empty] | SCL Borivali
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr.Arunima Sen 9819558028 | [9 empty] | SCL Virar
Name / No of the Building |  |  |  | Tower 1 to 5 & MLCP Commercial
Name / No of the Existing Building |  |  |  | NA | [13 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC & Fire Noc | [13 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA Name & No. |  |  |  | Green Terraces (Tower 1, 2 & 3) |  | P52000077918
|  |  |  | Tower 4 Green Terraces |  | P52000077924 |  | #N/A | [9 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
|  |  |  | Tower 5 Green Terraces & MLCP Commercial |  | PM1272022500305 |  | #N/A | [9 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Green Terraces, Survey No.Proposed Residential Building on Plot RZ-3 of ITP3 Layout on Survey No.38/0, 74/0, 36/1, 73/0, 30/1, 75/0, 42/4, 42/1, 42/3, 32/2, 39/0, 43/0, 44/4, 70/1, 70/2, 72/0, 76/1, 76/2, 68/0, 81/2A, 81/2B, 40/0, 47/2, 50/12, 50/13, 69/0, 41/1, 41/2, 44/3, 47/1, 71/0, 36/2, 37/1, 37/2, 78/0, 27/1, 29/2, 29/3, 29/5, 30/2, 31/0, 33/1 (Partly), 33/2, 34/1A (Partly), 42/2, 44/1, 44/2, 45/0, 46/0, 50/4, 50/5, 50/6B, (Partly), 64/0, 81/3, 82/2A (Partly), 82/4 and 82/5 of Village Khanavale, Taluka - Panvel, Dist - Raigad and Survey No.6/1, 6/5, 7/1, 6/6, 7/2, 7/3A, 7/4, 5/2A, 5/2B, 9/2, 4/1, 4/2, 4/3, 4/5, 4/6, 7/3B, 7/B1, 7/B2, 7/B3, 7/B4, 7/B5, 7/B6, 7/B7, 7C1, 7/C2, 7/C3, 7/C4, 7/C5, 7/C6, 7/C7, 7/C8, 7/C9, 7/C10, 8/3A1, 8/3A2, 8/3A3, 8/3A4, 8/3A5, 8/3A6, 8/3A7, 8/3A8, 8/3A9, 8/3A10, 8/D1 to 8/D8, 8/B1 to B6, 8/C1, 8/C2, 8/1A1 to 8/1A6, 9/B1 to 9/B8, 9/D1 to 9/D8, 9/C1 to 9/C9, Survey No.6/2, 7/3/B/8, 7/3/B/9, 7/C/11, 7/C/12, 8/1/A/7, 8/3/A/11, 8/3/A/12, 8/B/7, 8/D/10, 8/D/9, 9/1, 9/B/9, 9/B/10, 9/C/10, 9/C/11, 9/D/9, 9/D/10 Of village - Talegaon, Taluka - Khalapur, Dist - Raigad., near Woods, Godrej City, Internal Road, Khanavale, Khanavale, Mohope, Panvel, Raigad - 410221. | [15 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | Proposed Residential Building on Plot RZ-3 of ITP3 Layout on Survey No.38/0, 74/0, 36/1, 73/0, 30/1, 75/0, 42/4, 42/1, 42/3, 32/2, 39/0, 43/0, 44/4, 70/1, 70/2, 72/0, 76/1, 76/2, 68/0, 81/2A, 81/2B, 40/0, 47/2, 50/12, 50/13, 69/0, 41/1, 41/2, 44/3, 47/1, 71/0, 36/2, 37/1, 37/2, 78/0, 27/1, 29/2, 29/3, 29/5, 30/2, 31/0, 33/1 (Partly), 33/2, 34/1A (Partly), 42/2, 44/1, 44/2, 45/0, 46/0, 50/4, 50/5, 50/6B, (Partly), 64/0, 81/3, 82/2A (Partly), 82/4 and 82/5 of Village Khanavale, Taluka - Panvel, Dist - Raigad and Survey No.6/1, 6/5, 7/1, 6/6, 7/2, 7/3A, 7/4, 5/2A, 5/2B, 9/2, 4/1, 4/2, 4/3, 4/5, 4/6, 7/3B, 7/B1, 7/B2, 7/B3, 7/B4, 7/B5, 7/B6, 7/B7, 7C1, 7/C2, 7/C3, 7/C4, 7/C5, 7/C6, 7/C7, 7/C8, 7/C9, 7/C10, 8/3A1, 8/3A2, 8/3A3, 8/3A4, 8/3A5, 8/3A6, 8/3A7, 8/3A8, 8/3A9, 8/3A10, 8/D1 to 8/D8, 8/B1 to B6, 8/C1, 8/C2, 8/1A1 to 8/1A6, 9/B1 to 9/B8, 9/D1 to 9/D8, 9/C1 to 9/C9, Survey No.6/2, 7/3/B/8, 7/3/B/9, 7/C/11, 7/C/12, 8/1/A/7, 8/3/A/11, 8/3/A/12, 8/B/7, 8/D/10, 8/D/9, 9/1, 9/B/9, 9/B/10, 9/C/10, 9/C/11, 9/D/9, 9/D/10 Of village - Talegaon, Taluka - Khalapur, Dist - Raigad. | [15 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Khanavale | [15 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Road |  | Locality/Village |  | Khanavale | [11 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Mohope |  | District |  | Raigad | [11 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Panvel |  | Pin Code |  | 410221 | [14 empty] | Mahad | Daund
Nearby Landmark |  | Woods, Godrej City |  | Distance from city centre: |  | 5.1KM from Mohope Railway Station | [14 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [16 empty] | Mangaon | Ambegaon
[21 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [16 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [16 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [16 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [12 empty] | #VALUE!
East | NA | 18M Wide Road |  |  | Internal Road
West | NA | Other Plot |  |  | Open Plot
North | NA | Other Plot |  |  | Open Plot
South | NA | Other Plot |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 18.932001,73.183341 |  | 18.932001,73.183341 |  | 18.932001,73.183341
Location Link |  | https://maps.app.goo.gl/6uA7L3XU8n68NQM27
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 521312.28 |  |  |  | As per Layout
Permissible FSI |  |  |  | 0.99261
Permissible TDR/Paid FSI |  |  |  | 0.23377
Total FSI availaible for the project |  |  |  | 1.2264
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 639329.23 |  |  |  | As per Layout
Total number of Buildings |  |  |  | 06 Towers
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra State Road Development Corporation Limited (MSRDC) | [14 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | MSRDC/SPA/ITP-3/RZ-3/CC/2024/1801 |  |  | Dated | 2024-10-10 | [11 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | MSRDC/SPA/ITP-3/RZ-3/CC/2024/1801 |  |  | Dated | 2024-10-10 | [11 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | MSRDC/SPA/ITP-3/RZ-3/CC/2024/1801 |  |  | Dated | 2024-10-10 |  | NO REMARK | [9 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Tower 1 to 5 = Gr + 1st to 42nd Floor MLCP Commercial = Gr. + 1st Floor Total BUA = 1,68,862.95 Sq.mt | [15 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA) | Palghar Muncipal Council
Fire Noc No Valid Up to: |  | MSRDC/FIRE/PFA/04124/6432 |  |  | Dated | 2024-09-16 |  |  |  | 2020-10-10 | NO REMARK | [6 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Tower 1 to 5 = Gr + 1st to 42nd Floor (Height = 128.30 Mtrs) MLCP Commercial = Gr. + 1st Floor | [15 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | SEIAA-EC-0000002285 |  |  | Dated | 2020-06-25 |  |  | 126 | [9 empty] | Town Planning Thane | Raigad Zilha Parishad
|  | Net Plot Area = 534652 Sq.mt Total BUA = 1263710 Sq.mt | [16 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up for: |  |  |  |  | Dated | [13 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
|  | Site Elevation = Permissible Top Elevation = |  |  | Valid upto Dated | [13 empty] | Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [12 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [18 empty] | Mira-Bhayandar Municipal Corporation
Approved Builtup Area of Tower 1 to 4 (Sq.Mt) |  |  | 126420.788
Approved no of units |  |  | Flats - 1645, Shop - 35
Approved no of Floors |  |  | Tower 1 to 5 = Gr + 1st to 42nd Floor MLCP Commercial = Gr. + 1st Floor
Proposed no of Floors |  |  | Tower 1 to 5 = Gr + 1st to 42nd Floor
MLCP Commercial = Gr. + 1st Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion (As per RERA ) |  |  | Green Terraces - 31/12/2032 Tower 4 Green Terraces - 30/04/2033 Tower 5 Green Terraces & MLCP Commercial - 31/05/2033
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Indoor Kids Play Area, Gym, Kids Pool, Flower Garden, Badminton Court, Spa, Gaming Arcade, Lawnside Multipurpose Hall, Parking, Lifts, jacuzzi, Jogging Track, Meditation Zone, Seating Area, Club House etc. |  |  |  |  | https://godrejhomz.com/godrej-green-terraces/?source=google&medium=ppc&keyword=godrej%20green%20terraces&matchtype=p&device=c&&location=&gad_source=1&gclid=Cj0KCQiAgJa6BhCOARIsAMiL7V8kZjkijBp9UfFp4MOSjmzd6o1LKRnu2QA3QlhBHRDC7G6hFpZbrA8aAhoDEALw_wcB#amenities
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Work not yet Started
Wheather the construction is as per approved Building plan : |  |  | Work not yet Started |  | Work not yet Started
Construction details: |  | Tower 1 to 5 = Gr + 1st to 42nd Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 42 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 10.5
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 21
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 42
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 10.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 21
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 31.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 42 |  | 8333.3333 | 9333.3333
Construction details: |  | MLCP Commercial = Gr. + 1st Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 1 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 0.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 1
Construction details: |  | C Wing = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 10% |  | 45% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [11 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 9700 |  |  | 8500 | [9 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Ground Floor Shop Per Sq. Ft. |  |  |  |  | 15000 | [12 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the 1st Floor Shop Per Sq. Ft. |  |  |  |  | 12000 | [12 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [17 empty] | 1100000 | 300000 | 250000 | 250000
Water & Electricity Charges |  |  |  |  | 125000 |  |  | 9500 Rate Revised from cost sheet Smith on 30/12/2024 | [9 empty] | 1200000 | 350000 | 300000 | 300000
Township Maintenance Charges |  |  |  |  | 75000 |  |  | 9550 rate revised on 27/2/25 | [9 empty] | 1300000 | 400000 | 350000 | 400000
Corpus Fund |  |  |  |  | 40000 |  |  | Rate 9700 OC total should be 500000 by smith for staff case Tower 2 Flat 1602 on 26/03/2025 | [9 empty] | 1400000 | 500000 | 400000
Gas Connection Charges |  |  |  |  | 40000 | [12 empty] | 1500000 | 600000 | 500000
Society Formation Charges |  |  |  |  | 20000 | [5 empty] | Water & Electricity Charges |  |  |  |  | 65000 |  |  | 700000 | 600000
Advance Society Maintenance Charges |  |  |  |  | 200000 | [5 empty] | Township Maintenance Charges |  |  |  |  | 36000 |  |  | 800000
Recommended rate of Parking |  |  |  |  | 500000 | [5 empty] | Corpus Fund |  |  |  |  | 25000 |  |  | 900000
Distressed valuation of the Property |  |  |  |  | 7760 | [5 empty] | Gas Connection Charges |  |  |  |  | 25000 |  |  | 1000000
Commercial Area Details : | [10 empty] | Society Formation Charges |  |  |  |  | 7000
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  |  |  | Advance Society Maintenance Charges |  |  |  |  | 110000
MLCP Commercial |  | 35 |  | 44197.9958 |  | 66296.9937
Total |  | 35 |  | 44197.9958 |  | 66296.9937
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower 1 |  | 329 |  | 280943.683 |  | 421415.5245 |  |  | 1316
Tower 2 |  | 329 |  | 290341.7637 |  | 435512.6456
Tower 3 |  | 329 |  | 208364.2699 |  | 312546.4049
Tower 4 |  | 329 |  | 208439.6179 |  | 312659.4269
Tower 5 |  | 329 |  | 290341.7637 |  | 435512.6456
Total |  | 1645 |  | 1278431.0983 |  | 1917646.6475
Grand Total |  | 1680 |  | 1322629.0941 |  | 1983943.6412
Building Details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
MLCP Commercial
Ground Floor for Commercial | [8 empty] | 10.764
1 |  | Shop | 1466.5412 | 0 | 1466.5412 | 0 | 2199.8118
2 |  | Shop | 1513.4184 | 0 | 1513.4184 | 0 | 2270.1276
3 |  | Shop | 1689.3022 | 0 | 1689.3022 | 0 | 2533.9532
4 |  | Shop | 1689.3022 | 0 | 1689.3022 | 0 | 2533.9532
5 |  | Shop | 1689.3022 | 0 | 1689.3022 | 0 | 2533.9532
6 |  | Shop | 1689.3022 | 0 | 1689.3022 | 0 | 2533.9532
7 |  | Shop | 1689.3022 | 0 | 1689.3022 | 0 | 2533.9532
8 |  | Shop | 1689.3022 | 0 | 1689.3022 | 0 | 2533.9532
9 |  | Shop | 1689.3022 | 0 | 1689.3022 | 0 | 2533.9532
10 |  | Shop | 1689.3022 | 0 | 1689.3022 | 0 | 2533.9532
11 |  | Shop | 1689.3022 | 0 | 1689.3022 | 0 | 2533.9532
12 |  | Shop | 1689.3022 | 0 | 1689.3022 | 0 | 2533.9532
13 |  | Shop | 1474.5819 | 0 | 1474.5819 | 0 | 2211.8728
14 |  | Shop | 1466.3151 | 0 | 1466.3151 | 0 | 2199.4727
15 |  | Shop | 1466.3151 | 0 | 1466.3151 | 0 | 2199.4727
1st Floor for Commercial
16 |  | Shop | 1016.6275 | 0 | 1016.6275 | 0 | 1524.9413
17 |  | Shop | 1018.4897 | 0 | 1018.4897 | 0 | 1527.7345
18 |  | Shop | 1018.4897 | 0 | 1018.4897 | 0 | 1527.7345
19 |  | Shop | 1018.4897 | 0 | 1018.4897 | 0 | 1527.7345
20 |  | Shop | 1018.4897 | 0 | 1018.4897 | 0 | 1527.7345
21 |  | Shop | 1018.4897 | 0 | 1018.4897 | 0 | 1527.7345
22 |  | Shop | 1018.4897 | 0 | 1018.4897 | 0 | 1527.7345
23 |  | Shop | 1018.4897 | 0 | 1018.4897 | 0 | 1527.7345
24 |  | Shop | 879.4188 | 0 | 879.4188 | 0 | 1319.1282
25 |  | Shop | 879.4188 | 0 | 879.4188 | 0 | 1319.1282
26 |  | Shop | 1018.4897 | 0 | 1018.4897 | 0 | 1527.7345
27 |  | Shop | 1018.4897 | 0 | 1018.4897 | 0 | 1527.7345
28 |  | Shop | 997.037 | 0 | 997.037 | 0 | 1495.5555
29 |  | Shop | 997.0155 | 0 | 997.0155 | 0 | 1495.5232
30 |  | Shop | 997.0155 | 0 | 997.0155 | 0 | 1495.5232
31 |  | Shop | 997.0155 | 0 | 997.0155 | 0 | 1495.5232
32 |  | Shop | 996.9617 | 0 | 996.9617 | 0 | 1495.4425
33 |  | Shop | 996.9617 | 0 | 996.9617 | 0 | 1495.4425
34 |  | Shop | 996.9617 | 0 | 996.9617 | 0 | 1495.4425
35 |  | Shop | 996.9617 | 0 | 996.9617 | 0 | 1495.4425
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | RERA Carpet area | Balcony Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Tower 1
Ground Floor For Entrance Lobby, Electrical Room, BMS Room & Parking
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd to 36th, 38th to 42nd Floor For Residential | [7 empty] | 35
1 |  | 2BHK | 694.6547 | 69.6 | 764.2548 | 0 | 1146.3821 | 60.2218 | 5.4507
2 |  | 2BHK | 694.6547 | 69.6 | 764.2548 | 0 | 1146.3821
3 |  | 3BHK | 1083.7518 | 96.8114 | 1180.5632 | 0 | 1770.8448
4 |  | 3BHK | 1083.7518 | 96.8114 | 1180.5632 | 0 | 1770.8448
5 |  | 2BHK | 635.668 | 65.2083 | 700.8763 | 0 | 1051.3145
6 |  | 2BHK | 635.668 | 65.2083 | 700.8763 | 0 | 1051.3145
7 |  | 2BHK | 691.5332 | 65.7465 | 757.2797 | 0 | 1135.9195
8 |  | 2BHK | 691.5332 | 65.7465 | 757.2797 | 0 | 1135.9195
7th, 12th, 17th, 22nd, 27th, 32nd & 37th Floor For Part Refuge Area | [7 empty] | 7
1 |  | 2BHK | 694.6547 | 69.6 | 764.2548 | 0 | 1146.3821
2 |  | 2BHK | 694.6547 | 69.6 | 764.2548 | 0 | 1146.3821
3 |  | 3BHK | 1083.7518 | 96.8114 | 1180.5632 | 0 | 1770.8448
4 |  | 3BHK | 1083.7518 | 96.8114 | 1180.5632 | 0 | 1770.8448
5 |  | Refuge Area
6 |  | 2BHK | 635.668 | 65.2083 | 700.8763 | 0 | 1051.3145
7 |  | 2BHK | 691.5332 | 65.7465 | 757.2797 | 0 | 1135.9195
8 |  | 2BHK | 691.5332 | 65.7465 | 757.2797 | 0 | 1135.9195
Tower 2
Ground Floor For Entrance Lobby, Electrical Room, BMS Room & Parking
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd to 36th, 38th to 42nd Floor For Residential
1 |  | 2BHK | 613.8709 | 53.9276 | 667.7986 | 0 | 1001.6978 | 9883.2199
2 |  | 2BHK | 613.8709 | 53.9276 | 667.7986 | 0 | 1001.6978
3 |  | 3BHK | 1001.2027 | 80.7085 | 1081.9112 | 0 | 1622.8668 | 9058.045
4 |  | 3BHK | 1001.2027 | 80.7085 | 1081.9112 | 0 | 1622.8668
5 |  | 2BHK | 694.6547 | 69.6 | 764.2548 | 0 | 1146.3821
6 |  | 2BHK | 694.6547 | 69.6 | 764.2548 | 0 | 1146.3821
7 |  | 3BHK | 923.7772 | 74.3577 | 998.135 | 0 | 1497.2024 | 10352.6415
8 |  | 3BHK | 923.7772 | 74.3577 | 998.135 | 0 | 1497.2024
7th, 12th, 17th, 22nd, 27th, 32nd & 37th Floor For Part Refuge Area
1 |  | 2BHK | 613.8709 | 53.9276 | 667.7986 | 0 | 1001.6978
2 |  | Refuge Area
3 |  | 3BHK | 1001.2027 | 80.7085 | 1081.9112 | 0 | 1622.8668 | 11707.6772
4 |  | 3BHK | 1001.2027 | 80.7085 | 1081.9112 | 0 | 1622.8668 | 10250.3959
5 |  | 2BHK | 694.6547 | 69.6 | 764.2548 | 0 | 1146.3821
6 |  | 2BHK | 694.6547 | 69.6 | 764.2548 | 0 | 1146.3821
7 |  | 3BHK | 923.7772 | 74.3577 | 998.135 | 0 | 1497.2024
8 |  | 3BHK | 923.7772 | 74.3577 | 998.135 | 0 | 1497.2024
Tower 3
Ground Floor For Entrance Lobby, Electrical Room, Society Office & Parking
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd to 36th, 38th to 42nd Floor For Residential
1 |  | 1BHK | 429.376 | 31.3771 | 460.753 | 0 | 691.1295
2 |  | 1BHK | 429.376 | 31.3771 | 460.753 | 0 | 691.1295
3 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
4 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
5 |  | 2BHK | 613.8709 | 53.9276 | 667.7986 | 0 | 1001.6978
6 |  | 2BHK | 613.8709 | 53.9276 | 667.7986 | 0 | 1001.6978
7 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
8 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
7th, 12th, 17th, 22nd, 27th, 32nd, 37th Floor For Part Refuge Area
1 |  | 1BHK | 418.612 | 31.3771 | 449.989 | 0 | 674.9835
2 |  | Refuge Area
3 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
4 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
5 |  | 2BHK | 613.8709 | 53.9276 | 667.7986 | 0 | 1001.6978
6 |  | 2BHK | 613.8709 | 53.9276 | 667.7986 | 0 | 1001.6978
7 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
8 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
Tower 4
Ground Floor For Entrance Lobby, Electrical Room, Society Office & Parking
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd to 36th, 38th to 42nd Floor For Residential
1 |  | 2BHK | 613.8709 | 53.9276 | 667.7986 | 0 | 1001.6978 | 9883.2199
2 |  | 2BHK | 613.8709 | 53.9276 | 667.7986 | 0 | 1001.6978
3 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
4 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
5 |  | 1BHK | 429.376 | 31.3771 | 460.753 | 0 | 691.1295
6 |  | 1BHK | 429.376 | 31.3771 | 460.753 | 0 | 691.1295
7 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
8 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
7th, 12th, 17th, 22nd, 27th, 32nd & 37th Floor For Part Refuge Area
1 |  | 2BHK | 613.8709 | 53.9276 | 667.7986 | 0 | 1001.6978
2 |  | 2BHK | 613.8709 | 53.9276 | 667.7986 | 0 | 1001.6978
3 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
4 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
5 |  | Refuge Area
6 |  | 1BHK | 429.376 | 31.3771 | 460.753 | 0 | 691.1295
7 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
8 |  | 2BHK | 634.5486 | 61.0857 | 695.6343 | 0 | 1043.4514
Tower 5
Ground Floor For Entrance Lobby, Electrical Room, Society Office & Parking
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 26th, 28th to 31st, 33rd to 36th, 38th to 42nd Floor For Residential
1 |  | 2BHK | 613.8709 | 53.9276 | 667.7986 | 0 | 1001.6978 | 9883.2199
2 |  | 2BHK | 613.8709 | 53.9276 | 667.7986 | 0 | 1001.6978
3 |  | 3BHK | 1001.2027 | 80.7085 | 1081.9112 | 0 | 1622.8668
4 |  | 3BHK | 1001.2027 | 80.7085 | 1081.9112 | 0 | 1622.8668
5 |  | 2BHK | 694.6547 | 69.6 | 764.2548 | 0 | 1146.3821
6 |  | 2BHK | 694.6547 | 69.6 | 764.2548 | 0 | 1146.3821
7 |  | 3BHK | 923.7772 | 74.3577 | 998.135 | 0 | 1497.2024
8 |  | 3BHK | 923.7772 | 74.3577 | 998.135 | 0 | 1497.2024
7th, 12th, 17th, 22nd, 27th, 32nd & 37th Floor For Part Refuge Area
1 |  | 2BHK | 613.8709 | 53.9276 | 667.7986 | 0 | 1001.6978
2 |  | Refuge Area
3 |  | 3BHK | 1001.2027 | 80.7085 | 1081.9112 | 0 | 1622.8668
4 |  | 3BHK | 1001.2027 | 80.7085 | 1081.9112 | 0 | 1622.8668
5 |  | 2BHK | 694.6547 | 69.6 | 764.2548 | 0 | 1146.3821
6 |  | 2BHK | 694.6547 | 69.6 | 764.2548 | 0 | 1146.3821
7 |  | 3BHK | 923.7772 | 74.3577 | 998.135 | 0 | 1497.2024
8 |  | 3BHK | 923.7772 | 74.3577 | 998.135 | 0 | 1497.2024
Remarks:
* | Tower 1 to 5 & Commercial = Work not yet Started.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | We have referred Environmental Clearance Certificate from PARIVESH Portal on 04/12/2024 | [6 empty] | Airport NOC expired
* | We have updated Fire Noc on 18/12/2024 | [6 empty] | We have referred Environmental Clearance Certificate from PARIVESH Portal.
* | Recommended Rates & Other Charges of the Property have been revised on 30/12/2024 & 27/02/2025 & 26/03/2025.
* | We have added Approved Floor Plan, CC and Fire Noc of Tower 5 and MLCP Commercial Tower on 18/09/2025. | [6 empty] | We have referred Environmental Clearance Certificate from PARIVESH Portal.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nilesh Patil |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Green Terraces
Layout :
Google Map :
Formulas:
P52000077918 = [P52000077918, row above]
Green Terraces
Tower 1
Tower 2
Tower 3
Tower 4
N
Tower 5
MLCP Commercial
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C57: SACHIN: Floor with height
Note on C59: SACHIN: Survey Nos.
Note on C61: SACHIN: Height from AMSL
Note on D64: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F124: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on Q128: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H189: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34 | As per Approved Floor Plan, In C to E wing on Ground floor Shop No. 19 & 20 are merged into single shop.
35 | There are guest houses, villas, resorts, etc. in a range of 200 to 300 meters. There are few residential buildings available in the surrounding areas. (within 500 meters) There are inadequate transportation options to get to the project and the area is not developed
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0