## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/09/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-09-08
Name of the builder group |  |  |  | Vaishnavi Developers
Name of the builder company |  |  |  | Vaishnavi Developers
Name of the Project |  |  |  | Vaishnavi Pride |  |  |  | VAISHNAVI PRIDE
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr. Meet Patel (8928556341)
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Miss. Rani : 9867207680 |  |  |  | Mr. Saurabh : 8976462939
Name / No of the Building |  |  |  | 01 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans,Cost Sheet
RERA No. |  |  |  | P51700046405
Project location details |  | Vaishnavi Pride, Survey No.36, H. No. 6, near Govindham Chs / Saket Clg, Internal Rd, Chinchpada, Chinchpada, Kalyan East, Kalyan, Thane - 421306.
Survey No |  | 36, H. No. 6
Locality |  | Chinchpada
Road |  | Internal Rd |  | Locality/Village |  | Chinchpada
City |  | Kalyan East |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421306
Nearby Landmark |  | Govindham Chs / Saket Clg |  | Distance from city centre: |  | 3KM from Kalyan Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Nidhi Apartments
West | NA | NA |  |  | Govindham Chs-B
North | NA | NA |  |  | Saket College
South | NA | NA |  |  | Rd/Saku Aai Apartment
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.2164 |  | Longitude |  | 73.1429
Location Link |  | https://goo.gl/maps/m4Nk86hJYLCMAoM87
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2442
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 2.8779
Total FSI availaible for the project |  |  |  | 3.9779
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 9713.91
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | KDMC
Layout Approval No |  | KDMC/TPD/BP/27 Village/2022-23/04/242 |  |  | Dated | 2023-10-31
Approved Floor plan No. |  | KDMC/TPD/BP/27 Village/2022-23/04/242 |  |  | Dated | 2023-10-31
Commencement-CC No Valid Up to: |  | KDMC/TPD/BP/27 Village/2022-23/04/242 |  |  | Dated | 2023-10-31
Stilt + 1st to 22nd Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 9713.91
Approved no of units |  |  | Flats - 154
Approved no of Floors |  |  | Gr/Stilt + 1st to 22nd Floor
Proposed no of Floors |  |  | Gr/Stilt + 1st to 22nd Floor
B Wing = G + 1st to 20th Floor
C Wing = G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative Entrance
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Gr/Stilt + 1st to 22nd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 19 Floor, Painting upto 18 Floor, Finishing upto 8 Floor Completed | , Flooring upto 19 Floor, Painting upto 18 Floor, Finishing upto 8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 19 Floor, Painting upto 18 Floor, Finishing upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 89.55% |  | 94.32% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 19 | 86.36% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 18 | 81.82% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 8 | 36.36% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | B Wing = G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | C Wing = G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 5000
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges |  |  |  |  | 375000
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges (for 24 months) |  |  |  |  | 60000
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 4000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 154 |  | 78639.2006 |  | 121890.761
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Ground Floor For Society Office, Meter Room , Drivers Room & Parking
1st to 7th & 9th to 12th, 14th to 17th, 19th to 22nd Floor For Residential
1 |  | 1BHK | 440.8934 | 0 | 683.3848 | 1st to 7th & 9th to 12th, 14th to 17th, 19th to 22nd Floor For Residential |  | 28.5875 | 10.49 | 10.764
2 |  | 2BHK | 715.9136 | 0 | 1109.6661 |  |  | 4911.3871 | 19.4
3 |  | 2BHK | 720.2192 | 0 | 1116.3398
4 |  | 1BHK | 411.5077 | 0 | 637.837 |  |  | 12.9625
5 |  | 1BHK | 433.3586 | 0 | 671.7059
6 |  | 1BHK | 411.0772 | 0 | 637.1696 |  |  | 5100.6828
7 |  | 1BHK | 441.5393 | 0 | 684.3859
8th, 13th, 18th Floor (Part Refuge Area)
1 |  | 1BHK | 440.8934 | 0 | 683.3848 | 8th, 13th, 18th Floor (Part Refuge Area)
2 |  | 2BHK | 715.9136 | 0 | 1109.6661
3 |  | 2BHK | 720.2192 | 0 | 1116.3398
4 |  | 1BHK | 411.5077 | 0 | 637.837
5 |  | 1BHK | 433.3586 | 0 | 671.7059
6 |  | 1BHK | 411.0772 | 0 | 637.1696
7 |  | 1BHK | 441.5393 | 0 | 684.3859
8th Floor (Part Refuge Area)
1 |  | 1BHK | 441.5393 | 0 | 684.3859 | 8th Floor (Part Refuge Area)
2 |  | 2BHK | 717.5282 | 0 | 1112.1688 | 8th Floor (Part Refuge Area)
3 |  | 2BHK | 721.9415 | 0 | 1119.0093 | 8th Floor (Part Refuge Area)
4 |  | 1BHK | 413.8758 | 0 | 641.5075 | 8th Floor (Part Refuge Area)
5 |  | 1BHK | 435.8344 | 0 | 675.5433 | 8th Floor (Part Refuge Area)
6 |  | 1BHK | 411.8306 | 0 | 638.3375 | 8th Floor (Part Refuge Area) |  | 5091.3506
7 |  | 1BHK | 442.1851 | 0 | 685.3869 | 8th Floor (Part Refuge Area)
10th Floor (Part Terrace Area)
1 |  | 1BHK | 441.5393 | 0 | 684.3859 | 10th Floor (Part Terrace Area)
2 |  | 2BHK | 717.5282 | 0 | 1112.1688 | 10th Floor (Part Terrace Area) |  | 4900.3354
4 |  | 1BHK | 413.8758 | 0 | 641.5075 | 10th Floor (Part Terrace Area)
5 |  | 1BHK | 435.8344 | 0 | 675.5433 | 10th Floor (Part Terrace Area)
6 |  | 1BHK | 411.8306 | 0 | 638.3375 | 10th Floor (Part Terrace Area)
7 |  | 1BHK | 442.1851 | 0 | 685.3869 | 10th Floor (Part Terrace Area)
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated latest CC from Rera (On 04/07/2024).
* | We have updated latest CC & approved floor plans (On 11/07/2024).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Bapardekar |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Vaishnavi Pride
Layout :
Google Map :
Formulas:
Chinchpada = [Chinchpada, row above]
N
Vaishnavi Pride

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted