## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/09/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-09-08
Name of the builder group |  |  |  | Sethia Developers
Name of the builder company |  |  |  | Sethia Developers
Name of the Project |  |  |  | Sethia Marine View
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr.Vivek Shetty - 8828828553
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Twinkle : 9082736084
Name / No of the Building |  |  |  | Wing A & B
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | P51800047794
Project location details |  | Sethia Marine View, Plot No.63, CTS No.18(pt), S.No.164, Redevlopement of "Goeai Mulshi CHSL", near Neelam's Pride, Lokmanya Tilak Road, Gorai 2, Borivali, Borivali (West), Borivali, Mumbai - 400092.
Plot No |  | 63, CTS No.18(pt), S.No.164, Redevlopement of "Goeai Mulshi CHSL"
Locality |  | Gorai 2
Road |  | Lokmanya Tilak Road |  | Locality/Village |  | Borivali
City |  | Borivali (West) |  | District |  | Mumbai
Taluka |  | Borivali |  | Pin Code |  | 400092
Nearby Landmark |  | Neelam's Pride |  | Distance from city centre: |  | 1.8KM from Borivali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | Other plot |  |  | Neelam's Pride
West | NA | Other plot |  |  | Gorai Shreeji
North | NA | Other plot |  |  | Gorai Rd
South | NA | Other plot |  |  | Ak's fashion
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.2327 |  | Longitude |  | 72.8253
Location Link |  | https://goo.gl/maps/fXwAsegYEc5iyEYh7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1756.25
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 1.7211
Total FSI availaible for the project |  |  |  | 4.7211
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 8291.5
Total number of Buildings |  |  |  | 02 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development (MHADA)
Layout Approval No |  | MHADA-71/1035/2024 |  |  | Dated | 2024-03-28
Approved Floor plan No. |  | MHADA-71/1035/2024 |  |  | Dated | 2024-03-28
Commencement-CC No Valid Up to: |  | MH/EE/(BP)/GM/MHADA-71/1035/2025/FCC/7/Amend |  |  | Dated | 2025-06-19
|  | This F.C.C. is now further extended for Building comprising of Wing A upto 23rd upper Residential Floors + LMR/OHT with height 75.75mt. and Wing B upto 23rd upper Residential Floors + LMR/OHT with height 75.75mt. along with parking Tower with height 72.20mt. (i.e. for entire work ) As per approved Amended plans issued dated.28.03.2024. |  |  | Valid Upto Date | 2026-03-04
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 8291.5
Approved no of units |  |  | Flats - 216
Approved no of Floors |  |  | A Wing = Ground Floor + 1st to 23rd Floor B Wing = Ground Floor + 1st to 23rd Floor
Proposed no of Floors |  |  | A Wing = Ground Floor + 1st to 23rd Floor
B Wing = Ground Floor + 1st to 23rd Floor
Expected Completion |  |  | As per RERA - 30/06/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Club House, Swimming Pool, Gym & Spa, Banquet Hall, Yoga and meditation zone, Roof top Garden.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing = Ground Floor + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed, Brickwork upto 22 Floor, Internal Plaster upto 18 Floor, External Plaster upto 9 Floor, Flooring upto 6 Floor Completed | , Brickwork upto 22 Floor, Internal Plaster upto 18 Floor, External Plaster upto 9 Floor, Flooring upto 6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed, Brickwork upto 22 Floor, Internal Plaster upto 18 Floor, External Plaster upto 9 Floor, Flooring upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 69.57% |  | 86.96% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 22 | 95.65% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 18 | 78.26% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9 | 39.13% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 6 | 26.09% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | B Wing = Ground Floor + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed, Brickwork upto 22 Floor, Internal Plaster upto 18 Floor, External Plaster upto 9 Floor, Flooring upto 6 Floor Completed | , Brickwork upto 22 Floor, Internal Plaster upto 18 Floor, External Plaster upto 9 Floor, Flooring upto 6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed, Brickwork upto 22 Floor, Internal Plaster upto 18 Floor, External Plaster upto 9 Floor, Flooring upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 69.57% |  | 86.96% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 22 | 95.65% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 18 | 78.26% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9 | 39.13% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 6 | 26.09% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 16000
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development & Club Membership Charges |  |  |  |  | 215000 |  |  |  | 2.15L charges | 2024-04-15 | trupti
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 700000
Distressed valuation of the Property |  |  |  |  | 12800
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing |  | 106 |  | 51774.6247 |  | 77661.9371
B Wing |  | 110 |  | 57109.0478 |  | 85663.5718
Total |  | 216 |  | 108883.6726 |  | 163325.5088
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
A Wing
Ground Floor For Parking, Restaurant
1st Floor For Residential, Restaurant
1 |  | 1BHK | 386.6429 | 0 | 579.9643 | 1st Floor For Residential, Restaurant
2nd Floor for Residential
1 |  | 1BHK | 386.6429 | 0 | 579.9643 | 2nd Floor for Residential
2 |  | 2BHK | 550.0404 | 0 | 825.0606
3 |  | 1BHK | 388.1498 | 0 | 582.2248
4 |  | 2BHK | 551.9779 | 0 | 827.9669
5 |  | 2BHK | 551.9779 | 0 | 827.9669
3rd to 7th Floor For Residential
1 |  | 1BHK | 386.6429 | 0 | 579.9643 | 3rd to 7th Floor For Residential
2 |  | 2BHK | 550.0404 | 0 | 825.0606
3 |  | 1BHK | 388.1498 | 0 | 582.2248
4 |  | 2BHK | 551.9779 | 0 | 827.9669
5 |  | 2BHK | 551.9779 | 0 | 827.9669
9th to 14th, 16th to 21st Floor Residential
1 |  | 1BHK | 386.6429 | 0 | 579.9643 | 9th to 14th, 16th to 21st Floor Residential
2 |  | 2BHK | 550.0404 | 0 | 825.0606
3 |  | 1BHK | 388.1498 | 0 | 582.2248
4 |  | 2BHK | 551.9779 | 0 | 827.9669
5 |  | 2BHK | 556.1759 | 0 | 834.2638
8th & 15th Floor For Residential (Part Refuge Area)
1 |  | 1BHK | 382.3373 | 0 | 573.5059 | 8th & 15th Floor For Residential (Part Refuge Area)
2 |  | 2BHK | 566.0788 | 0 | 849.1181
3 |  | 1BHK | 403.0042 | 0 | 604.5062
4 |  | 2BHK | 556.1759 | 0 | 834.2638
22nd Floor For Residential (Part Refuge Area)
1 |  | 1BHK | 382.3373 | 0 | 573.5059 | 22nd Floor For Residential (Part Refuge Area)
2 |  | 2BHK | 566.0788 | 0 | 849.1181
3 |  | 1BHK | 403.0042 | 0 | 604.5062
4 |  | 4BHK | 962.3016 | 0 | 1443.4524
23rd Floor For Residential
1 |  | 1BHK | 382.3373 | 0 | 573.5059 | 23rd Floor For Residential
2 |  | Fitness Center
3
4 |  | 2BHK | 551.9779 | 0 | 827.9669
5 |  | 2BHK | 556.1759 | 0 | 834.2638
B Wing
Basement Floor For Rain Water Tank, Fire Fighting Water Tank & Pump Room
Ground Floor For Parking
1st Floor For Residential (Part Terrace)
1 |  | 1BHK | 385.4588 | 0 | 578.1883 | 1st Floor For Residential (Part Terrace)
2 |  | 1BHK | 385.4588 | 0 | 578.1883
3 |  | 1BHK | 385.1359 | 0 | 577.7039
4 |  | 1BHK | 550.0404 | 0 | 825.0606
5 |  | 1BHK | 385.997 | 0 | 578.9956
2nd Floor For Residential
1 |  | 1BHK | 385.4588 | 0 | 578.1883 | 2nd Floor For Residential
2 |  | 1BHK | 385.4588 | 0 | 578.1883
3 |  | 1BHK | 385.1359 | 0 | 577.7039
4 |  | 1BHK | 550.0404 | 0 | 825.0606
5 |  | 1BHK | 385.997 | 0 | 578.9956
3rd to 7th Floor For Residential
1 |  | 1BHK | 385.4588 | 0 | 578.1883 | 3rd to 7th Floor For Residential
2 |  | 1BHK | 385.4588 | 0 | 578.1883
3 |  | 1BHK | 385.1359 | 0 | 577.7039
4 |  | 1BHK | 550.0404 | 0 | 825.0606
5 |  | 1BHK | 385.997 | 0 | 578.9956
9th to 14th, 16th to 21st Floor Residential
1 |  | 1BHK | 392.0249 | 0 | 588.0373 | 9th to 14th, 16th to 21st Floor Residential
2 |  | 1BHK | 392.0249 | 0 | 588.0373
3 |  | 1BHK | 385.1359 | 0 | 577.7039
4 |  | 1BHK | 550.0404 | 0 | 825.0606
5 |  | 1BHK | 385.997 | 0 | 578.9956
8th & 15th Floor For Residential (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 8th & 15th Floor For Residential (Part Refuge Area)
2 |  | 1BHK | 392.0249 | 0 | 588.0373
3 |  | 1BHK | 400.959 | 0 | 601.4385
4 |  | 1BHK | 566.0788 | 0 | 849.1181
5 |  | 1BHK | 392.6707 | 0 | 589.0061
22nd Floor For Residential (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 22nd Floor For Residential (Part Refuge Area)
2 |  | 2BHK | 659.8332 | 0 | 989.7498
3 |  | 1BHK | 400.959 | 0 | 601.4385
4 |  | 1BHK | 566.0788 | 0 | 849.1181
5 |  | 1BHK | 381.9067 | 0 | 572.8601
23rd Floor For Residential & Fitness Centre
1 |  | 1BHK | 385.4588 | 0 | 578.1883 | 23rd Floor For Residential & Fitness Centre
2 |  | 1BHK | 400.959 | 0 | 601.4385
3 |  | Fitness Center
4
5 |  | 1BHK | 392.6707 | 0 | 589.0061
Remarks:
* | Construction work is in process at the time of Visit. (Internal photographs was not allowed.)
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated revised approved floor plan (on 06/04/2024)
* | Other Charges of the Property have been revised on 15/04/2024.
* | We have updated revised approved CC (on 17/07/2024).
* | We have updated latest CC from Mhada site (On 09/10/2024).
* | We have updated latest CC from Mhada site (On 18/01/2025, 27/03/2025 & 20/06/2025).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sanket Salvi |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sethia Marine View
Layout :
Google Map :
Formulas:
Borivali = [Borivali, row above]
Wing B
Wing A
Wing A
Wing A
Wing B

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted