## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-09-07
Branch Name/ID |  | Mahindra Rural Housing Finance - Panvel |  |  | Date & Time of Site Visit | 09/09/2025 at 12:16
Name of the person met at site & Contact No |  | Miss. Khushi 9326243836 |  |  | Date of Report Release | 10/09/2025
Project Details
Name of the project |  | Rumah Bali Phase 4
Address |  | Rumah Bali Phase 4, New Survey No.100, H.No. 12/A, 12/B, 14/A, 14B/1, 14B/2, 15/A, 15/B/1, 15/B/2, 15/B/3, 17/A, 17/B, 18, 19, 20, 21, 22, 23, 24, N.S.N. 101, H.No. 5, 109/30/3, 98/1/A/1, 98/1/A/2, 98/3/A(Pt.), 98/3/B, 100/11/1/A/1, 100/11/1/A/2, 100/11/1/B, 100/11/2, near Girikunj Housing Society, Ghodbandar Road, Bhayandarpada, Thane West, Thane, Thane - 400615. | [7 empty] | Thane | Palghar | Mumbai | Raigad | Pune
New Survey No |  | 100, H.No. 12/A, 12/B, 14/A, 14B/1, 14B/2, 15/A, 15/B/1, 15/B/2, 15/B/3, 17/A, 17/B, 18, 19, 20, 21, 22, 23, 24, N.S.N. 101, H.No. 5, 109/30/3, 98/1/A/1, 98/1/A/2, 98/3/A(Pt.), 98/3/B, 100/11/1/A/1, 100/11/1/A/2, 100/11/1/B, 100/11/2 | [7 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Bhayandarpada | [7 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Ghodbandar Road | [7 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Thane West | [7 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Thane | [7 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Thane | [7 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 400615 | [7 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P51700046777 | [10 empty] | Mahad | Daund
Landmark |  | Girikunj Housing Society | [10 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.2805230,72.9542336 | [7 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/431zTazoa46JYRVm6 | [10 empty] | Poladpur | Purandhar
Name of the builder / developer |  | Puranik Builders Limited | [10 empty] | Mahasala | Bhor
Office address (agreement) |  | Puraniks One, Ghodbunder Road, Near Kanchan Pushpa, Opp. Suraj Water Park, Maharashtra, Thane, Thane 400615. | [10 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [10 empty] | Murud | Velhe
Builder Bank Details |  | HDFC0001440
Contact No. |  | 8424022831/8976849136
Location of the project Municipal Limit : |  | Thane Municipal Corporation
Project Type (Apartments/Plot/ Combined) |  | Apartments
No of Wings / Buildings |  | Building Type A3 (Megah) Building Type A4 (Santai) |  |  | Other HFC's Approval / Funding | None
No. of Tenements / Units in Project |  | Sale Flat - 370, Mhada Flat - 60 |  |  | Exposure Limit (Proposed) | 55.5 |  | 430 | 64.5
Approved No. of Floor |  | Building A3 & Building A4 = Lower Ground + 1P + 2P + Gr/P + 1 st to 36th Floor
Proposed No. of Floor |  | Building A3 & Building A4 = Lower Ground + 1P + 2P + Gr/P + 1 st to 36th Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | Other Plot | Club House | Type A5 | S.T.P
|  | Physical on site |  | Open Plot | Vihang Vermont Apartments | Type B3 Kerasi | JVM Sky Court/ Godrej Emrald
Verification of survey No. (Title document) |  | 98/1/A/1, 98/1/A/2, 98/3/A(Pt.), 98/3/B, 100/11/1/A/1, 100/11/1/A/2, 100/11/1/B, 100/11/2, Survey No. 100, H.No. 12/A, 12/B, 13, 14/A, 14B/1, 14B/2, 15/A, 15/B/1, 15/B/2, 15/B/3, 17/A, 17/B, 18, 19, 20, 21, 22, 23, 24, N.S.N. 101, H.No. 5, 109/30/3.
Plot area mentioned in the sale deed (As per 7/12) |  | 52950 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 41967.52
Approach road |  | Yes, Approx 200ft
Connectivity |  | 1. Trimurti English School - 0.900 Km 2. Shree Rajarshi Shahu Vidyalay - 1.4 Km 3. Vedant Hospital - 1.9 Km 4. Oscar Hospital - 1.9 Km 5. HD Mart - 0.800 Km 6. Welcome Supermart - 1.2 Km 7. Thane Railway Station - 11.7 Km 8. Paushmata Mandir Bus Stop - 0.450 Km 9. Shree Khandoba Temple - 1.0 Km 10. Indian Oil Petrol Pump - 1.0 Km
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 41967.52
|  | Permissible FSI |  |  |  | 1.1
|  | Permissible TDR/Paid FSI |  |  |  | 1.5229
|  | Total FSI availaible for the project |  |  |  | 2.6229
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 110078.63
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 110078.63
Building plan approvals - Approval No : |  | S06/0200/14/TMC/TD-DP/TPS/4474/23 Date - 12/10/2023
Building height / No. of Floors |  | Building No. A3 & Type A4 = Lower Gr + 1P to 2P + Gr/3P + 1st to 36th Floor (Total Height = 117.10 Mtrs.)
Construction/Building Permission |  | S06/0200/14(2006/168)/TMC/TDD/4033/22 Date - 22/04/2022 Valid Upto : Building No. A3 & A4 = LG + 1P + 2P + Gr/P + 1st to 22nd Floor
S06/0200/14(2006/168)/TMC/TDD/4474/23 Valid Upto - 12/10/2023 Building No. A3 & A4 = 23rd to 36th Floor
NA / Land conversion |  | Name of the authority : |  | NA
|  | Reference No : |  | Not Provided
|  | Validity & area : mentioned |  | NA
Fire NOC Certificate No. - |  | TMC/CFO/M/HR/198/186 Date - 03/10/2023 Bldg No. A3 & Type A4 = Lower Gr + 1P to 2P + Gr/3P + 1st to 36th Floor(Height = 117.10 M)
Environmental Clearance Certificate No. Valid Upto. |  | SIA/MH/MIS/77180/2015 Date : 12/04/2023 Survey No. 100, H.No. 12/A, 12/B, 13, 14/A, 14B/1, 14B/2, 15/A, 15/B/1, 15/B/2, 15/B/3, 17/A, 17/B, 18, 19, 20, 21, 22, 23, 24, N.S.N. 101, H.No. 5, 109/30/3, 98/1/A/1, 98/1/A/2, 98/3/A(Pt.), 98/3/B, 100/11/1/A/1, 100/11/1/A/2, 100/11/1/B, 100/11/2 Poposed Builtup Area = 272318.80 Sq.M. Building A3 & A4 = L.G + 2P + Gr. + 1st to 28th Floor (Total Height = 91.95 Mtrs.)
Other statutory permissions (Fire NOC/ Environmental Clearance/ Airport NOC)
CONSTRUCTION PROGRESS
Baseline start date |  | 2022-09-05 |  | Baseline finish date |  | 2028-12-31
Construction details:
Building No. A3 = Lower Gr + 1P to 2P + Gr/3P + 1st to 36th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 18 Slab, Brickwork upto 16 Floor, Internal Plaster upto 12 Floor, External Plaster upto 10.4 Floor Completed
|  |  |  | 1 | 1 | 2 | 36
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 18 Slab, Brickwork upto 16 Floor, Internal Plaster upto 12 Floor, External Plaster upto 10.4 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 9
Excavation |  | 0% |  | 36 | 100% | 38.24% |  | Excavation in process | 18
Plinth |  | 10% |  | 36 | 100% |  |  | Excavation Completed | 36
RCC (Including podiums) |  | 40% |  | 18 | 46.15% |  |  | Footing in Process | 9
Brickwork |  | 15% |  | 16 | 44.44% |  |  | Footing Completed | 18
Internal Plaster |  | 5% |  | 12 | 33.33% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 10.4 | 28.89% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 27
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 36
Building No. A4 = Lower Gr + 1P to 2P + Gr/3P + 1st to 36th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 19 Slab, Brickwork upto 17 Floor, Internal Plaster upto 12.75 Floor, External Plaster upto 11.05 Floor Completed
|  |  |  | 1 | 1 | 2 | 36
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 19 Slab, Brickwork upto 17 Floor, Internal Plaster upto 12.75 Floor, External Plaster upto 11.05 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 9
Excavation |  | 0% |  | 36 | 100% | 39.88% |  | Excavation in process | 18
Plinth |  | 10% |  | 36 | 100% |  |  | Excavation Completed | 36
RCC (Including podiums) |  | 40% |  | 19 | 48.72% |  |  | Footing in Process | 9
Brickwork |  | 15% |  | 17 | 47.22% |  |  | Footing Completed | 18
Internal Plaster |  | 5% |  | 12.75 | 35.42% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 11.05 | 30.69% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 27
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 36
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block/ Brick |  | Projected Parts Available |  | Yes/No | Yes
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A
Total |  | 0 |  | 0 |  | 0
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. A3 | Sale | 184 |  | 84819.7818 |  | 127229.6727
| Mhada | 31 |  | 10840.6397 |  | 16260.9595
Building No. A4 | Sale | 186 |  | 71446.3729 |  | 107169.5594
| Mhada | 29 |  | 9964.0195 |  | 14946.0293
Total |  | 430 |  | 177070.8139 |  | 265606.2209
Grand Total |  | 430 |  | 177070.8139 |  | 265606.2209
BUILDING / BLOCK - Configuration Details
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
45%
Building (Type A3)
Ground Floor
1 |  | Shop |  |  | 0 |  | 0
2 |  | Shop |  |  | 0 |  | 0
3 |  | Shop |  |  | 0 |  | 0
4 |  | Shop |  |  | 0 |  | 0
5 |  | Shop |  |  | 0 |  | 0
6 |  | Shop |  |  | 0 |  | 0
7 |  | Shop |  |  | 0 |  | 0
8 |  | Shop |  |  | 0 |  | 0
9 |  | Shop |  |  | 0 |  | 0
10 |  | Shop |  |  | 0 |  | 0
11 |  | Shop |  |  | 0 |  | 0
12 |  | Shop |  |  | 0 |  | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Balcony/AP Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
50%
Phase IV | [8 empty] | 10.764
Building No. A3 (Megah) | [7 empty] | Building Type A3 (Megah)
Lower Ground & 1st Podium Floor For Parking | [7 empty] | 215
2nd Podium Floor For Meter Room, Drivers Room, Society Office & Parking
3rd Podium, 1st to 3rd, 5th to 8th, 10th to 13th & 15th Floor For Residential
1 | Mhada | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803 | 27.021 | 2.3375
2 | Mhada | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803
3 | Sale | 1BHK | 320.0137 | 37.9969 | 358.0106 | 0 | 537.016
4 | Sale | 1.5BHK | 514.1963 | 29.7086 | 543.9049 | 0 | 815.8574
5 | Sale | 1.5BHK | 503.6476 | 29.3857 | 533.0333 | 0 | 799.5499 | 44.2255
6 | Sale | 1.5BHK | 498.5885 | 29.7086 | 528.2971 | 0 | 792.4457
4th, 9th, 14th Floor (Part Refuge Area)
1 | Mhada | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803
2 | - | Refuge Area
3 | Sale | 1BHK | 320.0137 | 37.9969 | 358.0106 | 0 | 537.016
4 | Sale | 1.5BHK | 514.1963 | 29.7086 | 543.9049 | 0 | 815.8574
5 | Sale | 1.5BHK | 503.6476 | 29.3857 | 533.0333 | 0 | 799.5499
6 | Sale | 1.5BHK | 498.5885 | 29.7086 | 528.2971 | 0 | 792.4457
16th Floor
1 | Sale | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803 | 9701.5734
2 | Mhada | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803
3 | Sale | 1BHK | 320.0137 | 37.9969 | 358.0106 | 0 | 537.016
4 | Sale | 1.5BHK | 514.1963 | 29.7086 | 543.9049 | 0 | 815.8574 | 8579.931
5 | Sale | 1.5BHK | 503.6476 | 29.3857 | 533.0333 | 0 | 799.5499
6 | Sale | 1.5BHK | 498.5885 | 29.7086 | 528.2971 | 0 | 792.4457
17th, 18th, 20th to 22nd, 25th to 28th, 30th to 33rd, 35th & 36th Floor
1 | Sale | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803
2 | Sale | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803
3 | Sale | 1BHK | 320.0137 | 37.9969 | 358.0106 | 0 | 537.016
4 | Sale | 1.5BHK | 514.1963 | 29.7086 | 543.9049 | 0 | 815.8574
5 | Sale | 1.5BHK | 503.6476 | 29.3857 | 533.0333 | 0 | 799.5499
6 | Sale | 1.5BHK | 498.5885 | 29.7086 | 528.2971 | 0 | 792.4457
19th, 24th, 29th & 34th Floor (Part Refuge Area)
1 | Sale | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803
2 | - | Refuge Area
3 | Sale | 1BHK | 320.0137 | 37.9969 | 358.0106 | 0 | 537.016
4 | Sale | 1.5BHK | 514.1963 | 29.7086 | 543.9049 | 0 | 815.8574
5 | Sale | 1.5BHK | 503.6476 | 29.3857 | 533.0333 | 0 | 799.5499
6 | Sale | 1.5BHK | 498.5885 | 29.7086 | 528.2971 | 0 | 792.4457
23rd Floor
1 | Sale | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803
2 | Sale | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803
3 | Sale | 1BHK | 320.0137 | 37.9969 | 358.0106 | 0 | 537.016
4 | Sale | 1.5BHK | 514.1963 | 29.7086 | 543.9049 | 0 | 815.8574
5 | Mhada | 1.5BHK | 503.6476 | 29.3857 | 533.0333 | 0 | 799.5499
6 | Sale | 1.5BHK | 498.5885 | 29.7086 | 528.2971 | 0 | 792.4457
Building No. A4 (Santai) | [8 empty] | 215
Lower Ground & 1st Podium Floor For Parking
2nd Podium Floor For Meter Room, Drivers Room, Society Office & Parking
3rd Podium, 1st to 3rd, 5th to 8th, 10th to 13th & 15th Floor For Residential
1 | Mhada | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803
2 | Mhada | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803
3 | Sale | 1.5BHK | 498.3732 | 29.7086 | 528.0818 | 0 | 792.1228 | 44.436
4 | Sale | 1BHK | 308.0657 | 35.6288 | 343.6945 | 0 | 515.5418
5 | Sale | 1BHK | 321.3054 | 35.6288 | 356.9342 | 0 | 535.4014
6 | Sale | 1BHK | 313.7706 | 35.6288 | 349.3994 | 0 | 524.0992
4th, 9th, 14th Floor (Part Refuge Area)
1 | - | Refuge Area
2 | Mhada | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803
3 | Sale | 1.5BHK | 498.3732 | 29.7086 | 528.0818 | 0 | 792.1228 | 44.436
4 | Sale | 1BHK | 308.0657 | 35.6288 | 343.6945 | 0 | 515.5418
5 | Sale | 1BHK | 321.3054 | 35.6288 | 356.9342 | 0 | 535.4014
6 | Sale | 1BHK | 313.7706 | 35.6288 | 349.3994 | 0 | 524.0992
16th to 18th, 20th to 23rd, 25th to 28th, 30th to 33rd, 35th & 36th Floor
1 | Sale | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803
2 | Sale | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803
3 | Sale | 1.5BHK | 498.3732 | 29.7086 | 528.0818 | 0 | 792.1228
4 | Sale | 1BHK | 308.0657 | 35.6288 | 343.6945 | 0 | 515.5418
5 | Sale | 1BHK | 321.3054 | 35.6288 | 356.9342 | 0 | 535.4014
6 | Sale | 1BHK | 313.7706 | 35.6288 | 349.3994 | 0 | 524.0992
19th, 24th, 29th & 34th Floor (Part Refuge Area)
1 | - | Refuge Area
2 | Sale | 1BHK | 307.958 | 35.6288 | 343.5869 | 0 | 515.3803
3 | Sale | 1.5BHK | 498.3732 | 29.7086 | 528.0818 | 0 | 792.1228
4 | Sale | 1BHK | 308.0657 | 35.6288 | 343.6945 | 0 | 515.5418
5 | Sale | 1BHK | 321.3054 | 35.6288 | 356.9342 | 0 | 535.4014
6 | Sale | 1BHK | 313.7706 | 35.6288 | 349.3994 | 0 | 524.0992
Ground Floor
1 |  | 1BHK |  |  | 0 |  | 0
2 |  | 1BHK |  |  | 0 |  | 0
3 |  | 1BHK |  |  | 0 |  | 0
4 |  | 1BHK |  |  | 0 |  | 0
5 |  | 1BHK |  |  | 0 |  | 0
6 |  | 1BHK |  |  | 0 |  | 0
7 |  | 1BHK |  |  | 0 |  | 0
8 |  | 1BHK |  |  | 0 |  | 0
9 |  | 1BHK |  |  | 0 |  | 0
10 |  | 1BHK |  |  | 0 |  | 0
11 |  | 1BHK |  |  | 0 |  | 0
12 |  | 1BHK |  |  | 0 |  | 0
1st Floor
1 |  | 1BHK |  |  | 0 |  | 0
2 |  | 1BHK |  |  | 0 |  | 0
3 |  | 1BHK |  |  | 0 |  | 0
4 |  | 1BHK |  |  | 0 |  | 0
5 |  | 1BHK |  |  | 0 |  | 0
6 |  | 1BHK |  |  | 0 |  | 0
7 |  | 1BHK |  |  | 0 |  | 0
8 |  | 1BHK |  |  | 0 |  | 0
9 |  | 1BHK |  |  | 0 |  | 0
10 |  | 1BHK |  |  | 0 |  | 0
11 |  | 1BHK |  |  | 0 |  | 0
12 |  | 1BHK |  |  | 0 |  | 0
2nd Floor
1 |  | 1BHK |  |  | 0 |  | 0
2 |  | 1BHK |  |  | 0 |  | 0
3 |  | 1BHK |  |  | 0 |  | 0
4 |  | 1BHK |  |  | 0 |  | 0
5 |  | 1BHK |  |  | 0 |  | 0
6 |  | 1BHK |  |  | 0 |  | 0
7 |  | 1BHK |  |  | 0 |  | 0
8 |  | 1BHK |  |  | 0 |  | 0
9 |  | 1BHK |  |  | 0 |  | 0
10 |  | 1BHK |  |  | 0 |  | 0
11 |  | 1BHK |  |  | 0 |  | 0
12 |  | 1BHK |  |  | 0 |  | 0
2nd Floor
1 |  | 1BHK |  |  | 0 |  | 0
2 |  | 1BHK |  |  | 0 |  | 0
3 |  | 1BHK |  |  | 0 |  | 0
4 |  | 1BHK |  |  | 0 |  | 0
5 |  | 1BHK |  |  | 0 |  | 0
6 |  | 1BHK |  |  | 0 |  | 0
7 |  | 1BHK |  |  | 0 |  | 0
8 |  | 1BHK |  |  | 0 |  | 0
9 |  | 1BHK |  |  | 0 |  | 0
10 |  | 1BHK |  |  | 0 |  | 0
11 |  | 1BHK |  |  | 0 |  | 0
12 |  | 1BHK |  |  | 0 |  | 0
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 9500
Recommended of Parking ( If Available) |  |  |  |  | 5,00,000/-
REMARKS ON RECOMMENDATION
1 | Construction work is in process at the time of Visit. Internal visit was not allowed.
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Labours found on site at the time of visit.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Enclose balcony + A.P Area.
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 50%
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Miss. Khushi
11 | We have updated Environmental Clearance certificate on 07/01/2025.
10 | Please check for Environmental Clearance Certificate.
Photographs Of Property : |  | Rumah Bali Phase 4
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Ajay Songare |  | Authorized Signatory Name & Seal of the agency
A3
A4
Phase 4
N
Phase 4
LG
3P
2P
1P
A4
A3
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C35: Take address from CC
Note on C47: height should also be mentioned
Note on C57: RERA Start date
Note on H89: if multiple buildings are in project and are connected internally
Note on C91: AAC Block or Brick
Note on H93: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3