## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 19/09/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-09-13
Name of the builder group |  |  |  |  | M/s. Adhiraj Constructions Pvt. Ltd.
Name of the builder company |  |  |  |  | M/s. Adhiraj Constructions Pvt. Ltd.
Name of the Project |  |  |  |  | Adhiraj Samyama-Tower 1C, 1D, Meraki, Oreka New Name - Adhiraj Capital City
Contect Details ( Name & Contact No.) |  |  |  |  | Mr. Sumit 8108755556
Site Person - Contact Details (Name & Contact No.) |  |  |  |  | NA |  |  |  | Mr. Sumit 8108755556
Name & No of Wings |  |  |  |  | (Tower 1C, 1D, Tower 1 - Meraki, Tower 3 - Oreka)
Docouments Provided |  |  |  |  | Refer Data
Name As per RERA & RERA No. |  | Adhiraj Samyama Tower 1C - P52000014859 Adhiraj Samyama Tower 1D - P52000014856 Adhiraj Capital City Tower 1 - Meraki - P52000022975 Adhiraj Capital City Tower 3 - Oreka - P52000022907
Project location details |  | Adhiraj Samyama & Adhiraj Capital City, Proposed Rental Housing Scheme On Plot Bearing S.No.- 64/2, 66/2, 67/1, 67/2/(1), 67/2/(2), 67/4, 68/1A, 68/1B, 68/2, 68/4, 69/0, 70/1, 70/2, 71/2, 71/3, 71/4, 72/1A, 72/1B, 72/3, 76/1, 76/2(1), 76/2(2), 77/1, 77/2, 79/3, 86/1, 86/2, 88/0, 89/1, 89/2, 90/0, 91/3, 99/2 Village - Rohinjan, Sector 36, Near CIDCO Project, Behind Rapid Action Force HQ, Kharghar, Navi Mumbai, Tal.- Panvel, Dist.- Raigad 410210.
S No. |  | 64/2, 66/2, 67/1, 67/2/(1), 67/2/(2), 67/4, 68/1A, 68/1B, 68/2, 68/4, 69/0, 70/1, 70/2, 71/2, 71/3, 71/4, 72/1A, 72/1B, 72/3, 76/1, 76/2(1), 76/2(2), 77/1, 77/2, 79/3, 86/1, 86/2, 88/0, 89/1, 89/2, 90/0, 91/3, 99/2 |  |  |  |  | Locality | Rohinjan
Road | Panvel Road |  |  |  | District | Raigad
City | Kharghar |  |  |  | Pin Code | 410210
Near by Landmark |  | Arihant Aalishan |  |  | Distance from city centre: |  | 1.7 Km from Taloja Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Swapnapurti Project |  | Open Plot |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.0842 |  | Longitude |  | 73.0782
Location Link |  | https://goo.gl/maps/5MaZvnJPt4EeNDoo8
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | Total plot area - 1,57,450.00 Sqmt. (As per 7/12)
Permissible FSI |  |  |  |  | 3 & 1
Permissible TDR/Paid FSI |  |  |  |  | NA
Total Fungible Area to Project |  |  |  |  | NA
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 3,78,633.39 Sqmt. & 1,38,703.25 Sqmt.
Total number of Buildings |  |  |  |  | 04 Towers
Approval Detail : Plan approval
Layout Approval No |  | PMC/TPD/1977 |  |  |  | Dated | 20/08/2019.
Approved Floor plan No. |  | PMC/TPD/1977 |  |  |  | Dated | 20/08/2019.
Commencement Certificate No. |  | PMC/TPD/1977 Valid Up to: CC upto approved floors as per ammended plan dated 20/08/2019 |  |  |  | Dated | 27/09/2019.
O. Certificate No.: |  | NA |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 27/09/2019. |  | Expected Completion |  | Tower 1C & 1D = 31/03/2027 Tower 1 & 3 (Meraki & Oreka) = 30/06/2025
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 3,78,633.39 Sqmt. & 1,38,703.25 Sqmt. |  | Approved no of units |  |  | NA
Approved no of Floors | Building 1C to 1D - Basement 2 + Basement 1 + Lower Ground + Upper Ground + Podium 1 + Podium 2 + R. G./1st to 45th floor & Tower 1 - Meraki & Tower 3 - Oreka - round/Stilt + Podium 1 to Podium 4 (part) Parking & (part) Resi. + 5th (part) Lobby & (part) Resi. + 6th to 47th Floor.
Proposed no of Floors | Building 1C to 1D - B.2 + B.1 + Lower G. + Upper G. + P.1 + P.2 + Podium R. G./1st to 45th floor & Tower 1 - Meraki & Tower 3 - Oreka - Ground/Stilt + Podium 1 to Podium 4 (part) Parking & (part) Resi. + 5th (part) Lobby & (part) Resi. + 6th to 47th Floor.
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Cement, sand, etc
Construction details: |  | Building 1C = B.2 + B.1 + Lower G. + Upper G. + P.1 + P.2 + Podium R. G./1st to 45th floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 11 Slab, Brickwork upto 9 Floor, Internal Plaster upto 7 Floor, External Plaster upto 6 Floor Completed
Basement | 2 | Ground | 2 | Podium |  | 2 | Floors | 45
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 11 Slab, Brickwork upto 9 Floor, Internal Plaster upto 7 Floor, External Plaster upto 6 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 11.25
Excavation |  | 45 | 100% |  | 22.98% |  | 54.18% |  | Excavation in process | 22.5
Plinth |  | 45 | 100% | [5 empty] | Excavation Completed | 45
RCC (Including podiums) |  | 11 | 22.45% | [5 empty] | Footing in Process | 11.25
Brickwork | Brickwork & Internal Plaster | 9 | 20% | [5 empty] | Footing Completed | 22.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 15.56% | [5 empty] | Basement 1 | 33.75
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 13.33% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 0
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 45
Construction details: |  | Building 1D = B.2 + B.1 + Lower G. + Upper G. + P.1 + P.2 + Podium R. G./1st to 45th floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 17 Slab, Brickwork upto 13 Floor, Internal Plaster upto 9.1 Floor, External Plaster upto 9.1 Floor Completed
Basement | 2 | Ground | 2 | Podium |  | 2 | Floors | 45
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 17 Slab, Brickwork upto 13 Floor, Internal Plaster upto 9.1 Floor, External Plaster upto 9.1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 11.25
Excavation |  | 45 | 100% |  | 29.58% |  | 58.87% |  | Excavation in process | 22.5
Plinth |  | 45 | 100% | [5 empty] | Excavation Completed | 45
RCC (Including podiums) |  | 17 | 34.69% | [5 empty] | Footing in Process | 11.25
Brickwork | Brickwork & Internal Plaster | 13 | 28.89% | [5 empty] | Footing Completed | 22.5
Internal Plaster | Brickwork & Internal Plaster | 9.1 | 20.22% | [5 empty] | Basement 1 | 33.75
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9.1 | 20.22% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 0
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 45
Construction details: |  | Tower 1 - Meraki = Ground/Stilt + Podium 1 to Podium 4 (part) Parking & (part) Resi. + 5th (part) Lobby & (part) Resi. + 6th to 47th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 47
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 11.75
Excavation |  | 47 | 100% |  | 11.67% |  | 46.25% |  | Excavation in process | 23.5
Plinth |  | 47 | 100% | [5 empty] | Excavation Completed | 47
RCC (Including podiums) |  | 2 | 4.167% | [5 empty] | Footing in Process | 11.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 23.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 35.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 47
Construction details: |  | Tower 3 - Oreka =Ground/Stilt + Podium 1 to Podium 4 (part) Parking & (part) Resi. + 5th (part) Lobby & (part) Resi. + 6th to 47th Floor. | [6 empty] | Excavation work Completed. Plinth work is process
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 47
Stage of construction: |  | Excavation work Completed. Plinth work is process | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 11.75
Excavation |  | 47 | 100% |  | 7.5% |  | 38.75% |  | Excavation in process | 23.5
Plinth |  | 35.25 | 75% | [5 empty] | Excavation Completed | 47
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 11.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 23.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 35.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 47
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | : 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Rate of Flats as quoted by builder |  |  |  |  | 9000
Floor rise |  |  |  |  | Rs. 30/- 2nd floor
Society Formation Charges |  |  |  |  | 5000 |  |  |  |  | 850 | 10835000
Club Membership Charges |  |  |  |  | 250000
Development charges |  |  |  |  | 250000
Corpus fund for common infrastructure & maintenance |  |  |  |  | 250000
Electric Meter & Installation |  |  |  |  | 70000
Legal charges |  |  |  |  | 10000
Maintenance for 2 years |  |  |  |  | 100000
Recommended Car Parking |  |  |  |  | 500000
Other Charges | Club Membership Charges Rs 2,00,000/- for 2BHK & Rs 2,50,000/- for 3BHK, Society Formation Rs 5,000/-, Development Cahrges Rs 1,69,500/- for 2BHK & Rs 2,51,250/- for 3BHK, Electrical, Water Connection Charges Rs 50,580/- for 2BHK & Rs 73,800/- for 3BHK, Maintenance Charges Rs 90,720/- for 2BHK & Rs 1,32,336/- for 3BHK, Commom Infra Charges Rs 1,81,440/- for 2BHK & Rs 2,64,672/- for 3BHK, Car Parking - Rs. 5,00,000/-
Remark : 1.Bldg 1D = Construction work was stopped. Work is same as last visit(19/10/2022). Internal visit was not allowed. Bldg 1C = Construction work was stopped. Work is same as last visit (06/11/2023). Tower 1 = Construction work is in the process at the time of visit (labour found) Tower 3= Construction work was stopped. Work is same as last visit (08/04/2023). 3. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 4. We have considered Other charges from cost sheet. 5. Car parking is subjected to authentic documentation. 6. Since the project has received first CC on 27/09/2019, But construction work of 1A, 1B, 1C, 1D, Tower 1, Tower 3 & 3B is not yet Completed. Please provide revised approved CC for 1A, 1B, 1C, 1D, Tower 1, Tower 3 & 3B. 7. As per RERA, completion period of project Adhiraj Capital City Tower 1 - Meraki & Tower 3 - Oreka is expired on 30/06/2025 but still project work is pending. 6. Details of project are collected from Mr. Sanjay kale - 8108755556
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Adhiraj Samyama-Tower 1C, 1D, Meraki, Oreka New Name - Adhiraj Capital City
Google Map :
1D
T3
1D
1D
1D

## Note
31/08/2020.

## 1C
Basement | Podium | Ground | Upper Floor
3 | 2 | 2 | 45
plinth | 10 | 10 | 100%
slab | 52 | 10 | 19.23% |  | Parking |  | Rate
Bricks | 45 | 2 | 4.444% |  | Palghar |  | 100000/-
plaster | 45 | 1 | 2.222% |  | Ulwe, karanjade |  | 200000/-
Flooring | 45 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 45 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 45 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
total | 18.58% | 36.66% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%
Particulars | total floor | 45
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 7.6923 | 0.66667 | 0.22222 | 0 | 0 | 0
RCC | 7.6923 | 5.7692 |  | Recommended |  | 30 | 5.7692 | 0.66667 | 0.22222 | 0 | 0 | 0
Bricks | 0.66667 | 0.66667
Plaster | 0.22222 | 0.22222
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0

## 1D
Basement | Podium | Ground | Upper Floor
3 | 2 | 2 | 45
plinth | 10 | 10 | 100%
slab | 52 | 12 | 23.08% |  | Parking |  | Rate
Bricks | 45 | 4 | 8.889% |  | Palghar |  | 100000/-
plaster | 45 | 2 | 4.444% |  | Ulwe, karanjade |  | 200000/-
Flooring | 45 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 45 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 45 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
total | 21.01% | 38.7% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%
Particulars | total floor | 45
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 9.2308 | 1.3333 | 0.44444 | 0 | 0 | 0
RCC | 9.2308 | 6.9231 |  | Recommended |  | 30 | 6.9231 | 1.3333 | 0.44444 | 0 | 0 | 0
Bricks | 1.3333 | 1.3333
Plaster | 0.44444 | 0.44444
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0

## 2
Particulars | totaL floor | 47
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 1.0417 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 48 | 0.5 | 0 | Progress |  |  | 10 | 0.41667 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 0.3125 | 0 | 0 | 0 | 0 | 0
| 47 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 47 | 0 | 0
Flooring | Total Floor | completed Floor
| 47 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 47 | 0 |  | RCC | 0.41667 | 0.3125
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 47 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 10.4167 | 30.3125

## 3
Particulars | totaL floor | 47
| total | completed
plinth | 10 | 2 | 20
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 48 | 0 | 0 | Progress |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 22 | 0 | 0 | 0 | 0 | 0 | 0
| 47 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 47 | 0 | 0
Flooring | Total Floor | completed Floor
| 47 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 2 | 22
| 47 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 47 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 2 | 22

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
99 Acres | Adhiraj Samyama | 4BHK | 2500 | 4000 | 8375 | 33500000
99 Acres | Adhiraj Samyama | 3BHK | 753.48 | 1205.568 | 10783.2988 | 13000000
99 Acres | Adhiraj Samyama | 2BHK | 1086 | 1737.6 | 6330.5709 | 11000000
99 Acres | Adhiraj Samyama | 1BHK | 527 | 843.2 | 8301.7078 | 7000000
99 Acres | Adhiraj Samyama | 3BHK | 900 | 1440 | 8333.3333 | 12000000
99 Acres | Adhiraj Samyama | 3BHK | 600 | 960 | 8333.3333 | 8000000
99 Acres | Adhiraj Samyama | 3BHK | 1020 | 1632 | 7659.3137 | 12500000
99 Acres | Adhiraj Samyama | 2BHK | 614 | 982.4 | 7939.7394 | 7800000
Average |  |  |  |  | 8257.0372
Valuation Adopted |  |  |  |  | 8300