## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 09/09/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-09-07
Name of the builder group |  |  |  |  | M/s. The Wadhwa Group
Name of the builder company |  |  |  |  | M/s. Wadhwa Construction & Infrastructure Pvt. Ltd.
Name of the Project |  |  |  |  | Tulip F3 - Wise City (Plot RZ8 : Building 4 Wing F3) |  |  |  | Wise City (Tulip F3)
Contact Details ( Name & Contact No.) |  |  |  |  | Miss.Preeti (08291920124)
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  |  | NA |  |  |  | Mr. Rohan 8108147059
Name/no. Of building |  |  |  |  | Building No.4 - Wing F3 (Type B)
Docouments Provided |  |  |  |  | 1. Copy of Plans. 2. Copy of CC.
Name of Wing & RERA Number |  | Building Name as per RERA |  |  | Name as per Builder |  | RERA Registration No.
|  | Wise City, South Block Phase I, Plot RZ8 : Building 4 Wing F3 |  |  | Tulip F3 |  | P52000016524
Project location details |  | Tulip F3-Wise City, South Block Phase I, Plot RZ8 : Building 4 Wing F3, Survey No.40 & Other, Village-Wardoli, Tal-Panvel, Dist-Raigad.
S No | 40 & Other |  |  | Plot No. | RZ8 | Locality | Wardoli
Road | Village-Wardoli Road |  |  |  | District | Raigad
City | Navi Mumbai |  |  |  | Pin Code | 410 206.
Near by Landmark |  | Village-Wardoli |  |  | Distance from city centre: |  | About 7.6 Km from Chikhale Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 2 to 3 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Land |  | Road |  | Open Land |  | Open Land
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 18.96542,73.1928313
Location Link |  | https://goo.gl/maps/PzcYfkb9cstqZAF18
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 556880.97
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0.7
Total FSI availaible for the project |  |  |  |  | 1.7
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 946697.649 |  | 41635.328
Total number of Buildings |  |  |  |  | 01 Building (01 Wing)
Approval Detail : Plan approval
Layout Approval No |  | CIDCO/NAINA/PANVEL/VARDOLI/TP/BP-236/AMENDED PERM/2019/585/SAP/162 |  |  |  | Dated | 20/05/2019.
Building plan approval No |  | CIDCO/NAINA/PANVEL/VARDOLI/TP/BP-236/AMENDED PERM/2019/585/SAP/162 |  |  |  | Dated | 20/05/2019.
C.certificate No |  | CIDCO/NAINA/PANVEL/VARDOLI/TP/BP-236/AMENDED PERM/2019/585/SAP/162 Validity : Building No.4 (Type B)-Wing F3 = LG + UG + 1st to 25th Floor |  |  |  | Dated | 20/05/2019. | Expiry date: One year from date of issue | (please see note).
O. Certificate No.: |  | NA |  |  | Date of approval: | Dated | NA | Expiry date: NA
Commencement date of construction |  |  | 20/05/2019. |  | Expected Completion |  | 31/12/2025.
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 946697.649 |  | Approved no of units |  |  | 205
Approved no of Floors |  |  | Building No.4 (Type B) - Wing F3 = LG + UG + 1st to 25th Floor
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Building No.4 (Type B) - Wing F3 = LG + UG + 1st to 25th Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 2 | Podium |  | 0 | Floors | 25
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% |  | 94.4% |  | 95% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% | [5 empty] | Excavation Completed | 25
RCC (Including podiums) |  | 27 | 100% | [5 empty] | Footing in Process | 6.25
Brickwork | Brickwork & Internal Plaster | 25 | 100% | [5 empty] | Footing Completed | 12.5
Internal Plaster | Brickwork & Internal Plaster | 25 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 25 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 25 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 25 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 22 | 88% | [5 empty] | Plinth in process | 18.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 25
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. (on Saleable area) | [5 empty] | 6900
Floor rise rate Per Sq. Ft. | [5 empty] | NA
Township Maintenance charges for 12 months, Cluster & Building Maintenance charges for 12 months & Development charges | [5 empty] | 2,50,000/-
MSEB/MJP/Electric Meter Charges | [5 empty] | 1,00,000/-
Club Membership Charges | [5 empty] | 50,000/-
Society formation charges | [5 empty] | 5000/-
Recommended Car Parking | [5 empty] | 3,00,000/-
Distress valuation of the property Per Sq. Ft. | [5 empty] | 5520
Building details floor wise
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Wing F3 (Type B) |  | 205 | 113131.3838 |  |  | 169697.0757
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Plot No.RZ-8
Building No.4 (Tulip F3)
Wing F3 (Type B)
Lower Ground Floor (Part area is under Earth Filling)
1 |  | Meter Room | [5 empty] | Lower Ground Floor
2
3 |  | 2 BHK | 524.9495 |  | 0 | 787.4243 | N
4 |  | 2 BHK | 588.1234 |  | 0 | 882.1851 | N
Upper Ground Floor
1 |  | 2 BHK | 588.1234 |  | 0 | 882.1851 | N | Upper Ground Floor
2 |  | 2 BHK | 524.9495 |  | 0 | 787.4243 | N
3 |  | 2 BHK | 524.9495 |  | 0 | 787.4243 | N
4 |  | 2 BHK | 588.1234 |  | 0 | 882.1851 | N
5 |  | 2 BHK | 588.1234 |  | 0 | 882.1851 | N
6 |  | 2 BHK | 524.9495 |  | 0 | 787.4243 | N
7 |  | Lobby
8 |  | 2 BHK | 588.1234 |  | 0 | 882.1851 | N
1st, 2nd, 4th to 6th, 7th, 9th, 10th, 11th, 12th, 14th to 17th, 19th to 22nd, 24th & 25th Floor
1 |  | 2 BHK | 602.5041 |  | 0 | 903.7562 | N | 1st, 2nd, 4th to 6th, 7th, 9th, 10th, 11th, 12th, 14th to 17th, 19th to 22nd, 24th & 25th Floor
2 |  | 2 BHK | 483.7126 |  | 0 | 725.5689 | N
3 |  | 2 BHK | 483.7126 |  | 0 | 725.5689 | N
4 |  | 2 BHK | 602.5041 |  | 0 | 903.7562 | N
5 |  | 2 BHK | 602.5041 |  | 0 | 903.7562 | N
6 |  | 2 BHK | 483.7126 |  | 0 | 725.5689 | N
7 |  | 2 BHK | 483.7126 |  | 0 | 725.5689 | N
8 |  | 2 BHK | 602.5041 |  | 0 | 903.7562 | N
3rd Floor
1 |  | 2 BHK | 602.5041 |  | 0 | 903.7562 | N | 3rd Floor
2 |  | 2 BHK | 571.4715 |  | 0 | 857.2073 | N
3 |  | 2 BHK | 571.4715 |  | 0 | 857.2073 | N
4 |  | 2 BHK | 602.5041 |  | 0 | 903.7562 | N
5 |  | 2 BHK | 602.5041 |  | 0 | 903.7562 | N
6 |  | 2 BHK | 571.4715 |  | 0 | 857.2073 | N
7 |  | 2 BHK | 571.4715 |  | 0 | 857.2073 | N
8 |  | 2 BHK | 602.5041 |  | 0 | 903.7562 | N
8th, 13th, 18th & 23rd Floor
1 |  | 2 BHK | 602.5041 |  | 0 | 903.7562 | N | 8th, 13th, 18th & 23rd Floor
2 |  | 2 BHK | 571.4715 |  | 0 | 857.2073 | N
3 |  | Refuge Area
4 |  | 2 BHK | 602.5041 |  | 0 | 903.7562 | N
5 |  | 2 BHK | 602.5041 |  | 0 | 903.7562 | N
6 |  | 2 BHK | 571.4715 |  | 0 | 857.2073 | N
7 |  | 2 BHK | 571.4715 |  | 0 | 857.2073 | N
8 |  | 2 BHK | 602.5041 |  | 0 | 903.7562 | N
Remarks: 1. Finishing work was in process at the time of visit. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area + F.B Area. 5. We have considered rate by verifying it from market inquire. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 7. We have considered Other charges from cost sheet. 8. The project has received first CC on 20/05/2019, But construction work of is not yet completed. 8. On site, we meet Mr.Shailesh - 9819688638.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nitesh Patil |  | Report Prepared By : |  |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY: |  |  | Tulip F3 - Wise City (Plot RZ8 : Building 4 Wing F3)
Google Map :

## C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 2 | 25
Particulars | total floor | 25
plinth | 10 | 7 | 70%
slab | 27 | 0 | 0% |  | Parking |  | Rate
Bricks | 27 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 27 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 27 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 27 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 27 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 7 | 27 |  | Progress |  | 7 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 27 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 7% | 27% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Note
Note
26/05/2020. | Pratiksha | 1
16/02/2021. | Dhanashree
As Bldg F2 is in Excavation process but Construction Stage was given upto footing Completed. (Since APF NEW)

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
99 Acres | Wise City | 1RK | 289 | 433.5 | 7843.1373 | 3400000
99 Acres | Wise City | 1BHK | 400 | 600 | 7666.6667 | 4600000
99 Acres | Wise City | 2BHK | 628 | 942 | 8174.0977 | 7700000
Average |  |  |  |  | 7894.6339
Valuation Adopted |  |  |  |  | 7900