## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-09-09
Project Name |  | Green Square phase II Tower 1 And 3 |  | Date & Time of Site Visit |  | 10/09/2025 @ 12:20PM
Name of the person met at site & Contact No. |  | Poornima 9892539779 Manish Tiwari 8382868528 |  | Date of Report Release |  | 11/09/2025
Data from APF Request Form
Branch Name/ID |  | Godrej One, Vikhroli East, Mumbai |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | Squarefeet Enterprises |  | Developer Name |  | Squarefeet Enterprises
Developer Office Address |  | Unit no 309-312, Centrum IT Park, Plot No C-3 Next to Satkar Grande Hotel, Wagle Estate Rd, opp. Raila Devi TMC Office, Thane West, Thane, Maharashtra 400604 | [5 empty] | Google
Project Address | As per ARF | Green Square phase II, Survey No.166/31, 168PT,169/4/D,170/4/A at Thane (M Corp.), Thane, Thane, 400607
| As per Legal Documents | Green Square phase II Tower 1 And 3, Proposed Building on Plot Bearing S. No 166/31, 168, 169/4/D, 170/4/A at Village - Kavesar, Tal Dist - Thane
| As per Actual at site | Green Square phase II Tower 1 And 3, S. No 166/31, 168, 169/4/D, 170/4/A, Near Saptgiri Chs, Sanghvi Hills, Ghodbunder Road, Kavesar, Thane, Thane 400607
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC & RERA certificate
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Thane Municipal Corporation (TMC)
RERA Registration No. | : | P51700077787 |  | RERA Registration Validity | : | 2030-12-31
Project Launch Date | : | 2024-10-30 |  | Construction Start Date | : | 2025-05-01
Proposed Date of Completion (As per RERA) | : | 2030-12-31 |  | Developer Bank Name (As per RERA) | : | AXIS BANK IFSC Code UTIB0001963
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  | Plot Area (In Sq.Mt) | : | 20952.13
FSI/FAR Permissible | : | 1.1 |  | Net Plot Area (In Sq.Mt) | : | 19904.52
Permissible Built up Area (In Sq.Mt) | : | 75039.29 |  | Proposed Built up Area (In Sq.Mt) | : | 75032.95
Total Number of Units Approved | : | Flats = 637 & Shop = 10 |  | Total Number of Units Planned | : | As per RERA = Not Mentioned
Latitude, Longitude | : | 19.257434, 72.963285 |  | Landmark | : | Saptgiri Chs, Sanghvi Hills
Location Link | : | https://maps.app.goo.gl/mvrPxxNiEe4yhNUJA
Extra Amenities available | : | Jogging Area, Banquet Hall, Seating Area, Kids’ Play Area, Chess Table, Pool Table, Swimming Pool, Gymnasium, Boxing Room, Library, Day Care Room, Party Area
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  | Width of the Road | : | 40M
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 1.10KM from Anand Nagar Bus Stop
Distance from the nearest School (Km) | : | About 1.10KM from DG International School |  | Distance from Hospital (Km) | : | About 0.90KM form Thane Noble Hospital
Distance from the Main Market (Km) | : | 1. Approx. 0.80KM from Dmart. 2. Approx. 7.20KM from High Street Mall. |  | Distance from Railway Station (Km) | : | 11.80KM from Thane Railway Station 12.90KM from Kalva Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North |  | South | East |  | West
East |  | 40.00 M. Wide Road |  |  | Internal Road
West |  | Other Plot |  |  | Green Square A&B
North |  | 40.00 M. Wide Road |  |  | Internal Road
South |  | Other Plot |  |  | Open Plot
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Tower 1 |  | Sale | Gr +1st to 22nd Floor |  |  | Gr +1st to 22nd Floor
Tower 3 |  | Sale | Gr +1st to 36th Floor |  |  | Gr +1st to 36th Floor
Tower 3 |  | Sale
Tower 4 |  | Sale
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | V.P. S06/0383/22 (2023/24) TMC/TD-DP/TPS/0080/24 |  |  |  | Date: | 2024-01-25
Approved Plan Details | : | V.P. S06/0383/22 (2023/24) TMC/TD-DP/TPS/0080/24 |  |  |  | Date: | 2024-01-25
CC Details Valid Up to: |  | V.P. No. S06/0383/22 (2003/24) TMC/TDD/0080/24 |  |  |  | Date: | 2024-01-25
Tower 1 = Ground (pt.)/Stilt(pt.) + 1st Floor Tower 3 = Ground (pt.)/Stilt(pt.) + 1st to 24th Floor & Club House
CC Details Valid Up to: |  | V.P. No. S06/0383/22 (2003/24) TMC/TDD/54 |  |  |  | Date: | 2024-11-25
Tower 1 = 2nd Floor to 22nd Floor Tower 3 = 25th to 35th Floor & 36th Floor(pt)
Environmental Clearance Details | : |  |  |  |  | Date:
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details | : |  |  |  |  | Date: | [6 empty] | 7 RCC 3Brick 2 plaster
Other NOC Details | : |  |  |  |  | Date:
Construction Status
Tower 1= Gr +1st to 22nd Floor. |  |  | Basement | Ground |  | Podium | Floors | Work not yet Started.
|  |  | 0 | 1 |  | 0 | 22 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 5.5
Excavation |  | 0 | 0% | 0% |  | Work not yet Started. |  | Excavation in process | 11
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 4.4
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 8.8
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 15.4
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Tower 3 = Gr +1st to 36th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Footing work Completed
|  |  | 0 | 1 |  | 0 | 36 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9
Excavation |  | 36 | 100% | 16% |  | Excavation work Completed. Footing work Completed |  | Excavation in process | 18
Plinth |  | 14.4 | 40% |  |  |  |  | Excavation Completed | 36
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 7.2
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 14.4
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 25.2
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 36
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0% | [7 empty] | 15000 | carpet
Construction Status
Tower 3 = . |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  | 0 | 1 |  | 0 | 3 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 1.5
Plinth |  | 3 | 100% |  |  |  |  | Excavation Completed | 3
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0.6
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 1.2
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 2.1
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 3
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 8%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area |  |  | Nearby | 99 | Builder | Index tap
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 14500 to 15500 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA |  |  | 13500 | 14000-15000 | 14500 | 12500
Car Parking Charges |  | 600000 |  | Other Charges | : | As applicable and documented. |  |  |  |  | Magic 14200
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 2192.4935
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 12662.579
Distress Value (Rs. Per sqft) |  |  |  |  | : | 1753.9948
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Shops |  | Sale |  | 10 |  | 2929.0997
Unit Details, Nomenclature and Area Details (Flats)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Tower 1 |  | Sale |  | 217 |  | 85127.3093
Tower 3 |  | Sale |  | 420 |  | 234069.2078
Total |  | - |  | 637 |  | 319196.5171 | 0
Grand Total |  | - |  | 647 |  | 322125.6168
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
Tower 1 | [8 empty] | 10.764
Ground Floor For Commercial, Entrance Lobby, Fitness Centre, Society Office, Meter Room, Drivers Room, Pump Room & Parking
1 |  | Sale | Shop | 289.9822 | 0 | 0 | 289.9822 |  | 26.5325
2 |  | Sale | Shop | 219.0474 | 0 | 0 | 219.0474
3 |  | Sale | Shop | 462.5291 | 0 | 0 | 462.5291 |  | 42.565
4 |  | Sale | Shop | 246.2803 | 0 | 0 | 246.2803
5 |  | Sale | Shop | 314.5241 | 0 | 0 | 314.5241
6 |  | Sale | Shop | 188.5853 | 0 | 0 | 188.5853
7 |  | Sale | Shop | 458.8693 | 0 | 0 | 458.8693
8 |  | Sale | Shop | 240.2525 | 0 | 0 | 240.2525
9 |  | Sale | Shop | 219.0474 | 0 | 0 | 219.0474
10 |  | Sale | Shop | 289.9822 | 0 | 0 | 289.9822
1st to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor For Residential | [7 empty] | 19
1 |  | Sale | 1BHK | 395.1464 | 26.5871 | 0 | 421.7335 | [7 empty] | 1701,..,2201 | 1701 | 2201
2 |  | Sale | 1BHK | 382.5526 | 26.5871 | 0 | 409.1396 | [7 empty] | 1702,..,2202 | 1702 | 2202
3 |  | Sale | 1BHK | 321.413 | 0 | 0 | 321.413 |  |  |  | 4545000 | 14140.6833 |  |  | 1703,..,2203 | 1703 | 2203
4 |  | Sale | 1BHK | 382.5526 | 26.5871 | 0 | 409.1396 | [7 empty] | 1704,..,2204 | 1704 | 2204
5 |  | Sale | 1BHK | 395.1464 | 26.5871 | 0 | 421.7335 | [7 empty] | 1705,..,2205 | 1705 | 2205
6 |  | Sale | 1BHK | 395.1464 | 28.094 | 0 | 423.2405 | [7 empty] | 1706,..,2206 | 1706 | 2206
7 |  | Sale | 1BHK | 322.5971 | 15.3925 | 0 | 337.9896 | [7 empty] | 1707,..,2207 | 1707 | 2207
8 |  | Sale | 1BHK | 322.5971 | 15.3925 | 0 | 337.9896 |  |  |  | 4899000 | 14494.5288 |  |  | 1708,..,2208 | 1708 | 2208
9 |  | Sale | 1BHK | 382.5526 | 26.5871 | 0 | 409.1396 | [7 empty] | 1709,..,2209 | 1709 | 2209
10 |  | Sale | 1BHK | 395.1464 | 26.5871 | 0 | 421.7335 | [7 empty] | 1710,..,2210 | 1710 | 2210
8th, 13th & 18th Floor (Part Refuge Area) | [7 empty] | 3
1 |  | Sale | 1BHK | 395.1464 | 26.5871 | 0 | 421.7335 | [7 empty] | 801,..,1801 | 801 | 1801
2 |  | Sale | 1BHK | 382.5526 | 26.5871 | 0 | 409.1396 | [7 empty] | 802,..,1802 | 802 | 1802
3 |  | - | Refuge Area | [11 empty] | 803,..,1803 | 803 | 1803
4 |  | Sale | 1BHK | 382.5526 | 26.5871 | 0 | 409.1396 | [7 empty] | 804,..,1804 | 804 | 1804
5 |  | Sale | 1BHK | 395.1464 | 26.5871 | 0 | 421.7335 | [7 empty] | 805,..,1805 | 805 | 1805
6 |  | Sale | 1BHK | 395.1464 | 28.094 | 0 | 423.2405 | [7 empty] | 806,..,1806 | 806 | 1806
7 |  | Sale | 1BHK | 322.5971 | 15.3925 | 0 | 337.9896 | [7 empty] | 807,..,1807 | 807 | 1807
8 |  | Sale | 1BHK | 322.5971 | 15.3925 | 0 | 337.9896 | [7 empty] | 808,..,1808 | 808 | 1808
9 |  | Sale | 1BHK | 382.5526 | 26.5871 | 0 | 409.1396 | [7 empty] | 809,..,1809 | 809 | 1809
10 |  | Sale | 1BHK | 395.1464 | 26.5871 | 0 | 421.7335 | [7 empty] | 810,..,1810 | 810 | 1810
Tower 3
Ground Floor For Entrance Lobby & Parking
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th & 35th Floor For Residential | [7 empty] | 29
1 |  | Sale | 2BHK | 528.5124 | 25.9412 | 0 | 554.4536 |  |  | 7999000 | 14426.8148 |  |  |  | 17901 to 3501 | 17901 | 3501
2 |  | Sale | 2BHK | 530.6652 | 25.9412 | 0 | 556.6064 | [7 empty] | 17902 to 3502 | 17902 | 3502
3 |  | Sale | 2BHK | 530.0194 | 31.0003 | 0 | 561.0197 | [7 empty] | 17903 to 3503 | 17903 | 3503
4 |  | Sale | 2BHK | 530.0194 | 31.0003 | 0 | 561.0197 | [7 empty] | 17904 to 3504 | 17904 | 3504
5 |  | Sale | 2BHK | 530.6652 | 25.9412 | 0 | 556.6064 |  |  | 8500000 | 15271.1133 |  |  |  | 17905 to 3505 | 17905 | 3505
6 |  | Sale | 2BHK | 528.5124 | 25.9412 | 0 | 554.4536 | [7 empty] | 17906 to 3506 | 17906 | 3506
7 |  | Sale | 2BHK | 528.5124 | 25.9412 | 0 | 554.4536 | [7 empty] | 17907 to 3507 | 17907 | 3507
8 |  | Sale | 2BHK | 530.6652 | 25.9412 | 0 | 556.6064 |  |  | 8130000 | 14606.3707 | 14763.7548 |  |  | 17908 to 3508 | 17908 | 3508
9 |  | Sale | 2BHK | 530.0194 | 31.0003 | 0 | 561.0197 | [7 empty] | 17909 to 3509 | 17909 | 3509
10 |  | Sale | 2BHK | 530.0194 | 31.0003 | 0 | 561.0197 | [7 empty] | 17910 to 3510 | 17910 | 3510
11 |  | Sale | 2BHK | 530.6652 | 25.9412 | 0 | 556.6064 | [7 empty] | 17911 to 3511 | 17911 | 3511
12 |  | Sale | 2BHK | 528.5124 | 25.9412 | 0 | 554.4536 | [7 empty] | 17912 to 3512 | 17912 | 3512
8th, 13th, 18th, 23rd, 28th & 33rd Floor (Part Refuge Area) | [7 empty] | 6
1 |  | Sale | 2BHK | 528.5124 | 25.9412 | 0 | 554.4536 | [7 empty] | 81301 to 3301 | 81301 | 3301
2 |  | Sale | 2BHK | 530.6652 | 25.9412 | 0 | 556.6064 | [7 empty] | 81302 to 3302 | 81302 | 3302
3 |  | - | Refuge Area | [11 empty] | 81303 to 3303 | 81303 | 3303
4 |  | Sale | 2BHK | 530.0194 | 31.0003 | 0 | 561.0197 | [7 empty] | 81304 to 3304 | 81304 | 3304
5 |  | Sale | 2BHK | 530.6652 | 25.9412 | 0 | 556.6064 | [7 empty] | 81305 to 3305 | 81305 | 3305
6 |  | Sale | 2BHK | 528.5124 | 25.9412 | 0 | 554.4536 | [7 empty] | 81306 to 3306 | 81306 | 3306
7 |  | Sale | 2BHK | 528.5124 | 25.9412 | 0 | 554.4536 | [7 empty] | 81307 to 3307 | 81307 | 3307
8 |  | Sale | 2BHK | 530.6652 | 25.9412 | 0 | 556.6064 |  |  | 7950000 | 14282.9824 |  |  |  | 81308 to 3308 | 81308 | 3308
9 |  | Sale | 2BHK | 530.0194 | 31.0003 | 0 | 561.0197 | [7 empty] | 81309 to 3309 | 81309 | 3309
10 |  | Sale | 2BHK | 530.0194 | 31.0003 | 0 | 561.0197 | [7 empty] | 81310 to 3310 | 81310 | 3310
11 |  | Sale | 2BHK | 530.6652 | 25.9412 | 0 | 556.6064 | [7 empty] | 81311 to 3311 | 81311 | 3311
12 |  | Sale | 2BHK | 528.5124 | 25.9412 | 0 | 554.4536 | [7 empty] | 81312 to 3312 | 81312 | 3312
36th Floor (Part Terrace Area) | [7 empty] | 1
1 |  | - | Terrace Area | [11 empty] | 301 to 3601 | 301 | 3601
2 |  | - | [12 empty] | 302 to 3602 | 302 | 3602
3 |  | - | [12 empty] | 303 to 3603 | 303 | 3603
4 |  | - | [12 empty] | 304 to 3604 | 304 | 3604
5 |  | - | [12 empty] | 305 to 3605 | 305 | 3605
6 |  | - | [12 empty] | 306 to 3606 | 306 | 3606
7 |  | Sale | 2BHK | 528.5124 | 25.9412 | 0 | 554.4536 | [7 empty] | 307 to 3607 | 307 | 3607
8 |  | Sale | 2BHK | 530.6652 | 25.9412 | 0 | 556.6064 | [7 empty] | 308 to 3608 | 308 | 3608
9 |  | Sale | 2BHK | 530.0194 | 31.0003 | 0 | 561.0197 | [7 empty] | 309 to 3609 | 309 | 3609
10 |  | Sale | 2BHK | 530.0194 | 31.0003 | 0 | 561.0197 | [7 empty] | 310 to 3610 | 310 | 3610
11 |  | Sale | 2BHK | 530.6652 | 25.9412 | 0 | 556.6064 | [7 empty] | 311 to 3611 | 311 | 3611
12 |  | Sale | 2BHK | 528.5124 | 25.9412 | 0 | 554.4536 | [7 empty] | 312 to 3612 | 312 | 3612
Project Specific Remarks & Observation
* | Construction work is in process at the time of Visit (labour found) Construction work was not active at the time of Visit. (labour Not found) All work completed. Wait for OC / OC received. Work not yet Started.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet +Balcony.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | Please check for Fire NOC.
Site & Building/Tower Photographs
Name of the Project |  |  | Green Square phase II Tower 1 And 3
Project Site Address |  |  | Green Square phase II Tower 1 And 3, S. No 166/31, 168, 169/4/D, 170/4/A, Near Saptgiri Chs, Sanghvi Hills, Ghodbunder Road, Kavesar, Thane, Thane 400607
Site Visit Date & Time |  |  | 10/09/2025 @ 12:20PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr.Ajay Sonagare |  | Authorized Signatory Name & Signature
Tower 1
Tower 3
T 1
T 3
Tower 3
Note on C9: SACHIN: As per initiation Mail
Note on C10: SACHIN: As per plans
Note on C11: SACHIN: As per plans
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G116: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0