## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-09-09
Branch Name/ID |  | Mahindra Rural Housing Finance - Kalyan |  |  | Date & Time of Site Visit | 10/09/2025 at 14:40
Name of the person met at site & Contact No |  | Mr. Shubham 9619081618 Mr. Islam 9930111077 |  |  | Date of Report Release | 11/09/2025 |  | Mr. Pravin 9619081618
Project Details
Name of the project |  | Dosti Greater Thane ­ Sector 3A ­ Cluster 1B ­ Phase 1, 2 & 3
Address |  | Dosti Greater Thane ­ Sector 3A ­ Cluster 1B ­ Phase 1, 2 & 3, Survey No.25/2, 25/3, 26/10, 26/13/7, 190, 23/1/B, 23/1/C of village Rahanal, S No.40/7 of village Kavani, S.No.151/2/A(pt), 152/1, 152/2, 152/3(pt), 152/4/A, 152/4/B, 152/4/C, 152/4/D, 152/5/A, 152/5/B, 153, 154/3/A, 154/3/B, 154/4, 154/7, 156/1, 156/2, 156/3, 156/4, 156/5, 157/1, 157/2, 157/3, 158, 159/1/A, 159/1/B, 159/1/C, 159/2, 160/1, 160/2, 161/1(pt), 161/3(pt), 161/4, 161/5, 162, 163/1(pt), 163/2(pt), 164/1(pt), 164/4, 164/4/5A, 164/6(pt), 165/1(pt), 165/2/A(pt), 165/2/B(pt), 165/3(pt), 174/5(pt) of village Purna, S No.14/3, 15/5, 16/1a, 16/2, 16/4, 16/5, 16/7, 16/9, 16/14, 16/15, 16/18, 16/21, 16/23, 16/23/A, 16/24, 16/25, 16/26, 16/27, 16/28, 16/29, 16/30, 16/31, 16/34, 16/35, 16/36, 16/39, 16/40, 17/1, 17/2, 17/3, 17/4, 17/5, 17/7, 17/8, 17/9, 17/10, 17/13, 17/14, 18/1, 18/2, 18/3, 18/5/A, 19/1/A, 19/2, 19/3, 19/5, 19/6A, 19/6C, 19/7, 19/8, 19/9, 19/10, 19/11, 19/12, 19/13 of Village Kopar, near Salwan Niwas 362, Internal Road, Rahanal, Kevani, Purna & Kopar, Bhiwandi, Bhiwandi, Thane - 421302. | [8 empty] | Thane | Palghar | Mumbai | Raigad | Pune
Survey No |  | 25/2, 25/3, 26/10, 26/13/7, 190, 23/1/B, 23/1/C of village Rahanal, S No.40/7 of village Kavani, S.No.151/2/A(pt), 152/1, 152/2, 152/3(pt), 152/4/A, 152/4/B, 152/4/C, 152/4/D, 152/5/A, 152/5/B, 153, 154/3/A, 154/3/B, 154/4, 154/7, 156/1, 156/2, 156/3, 156/4, 156/5, 157/1, 157/2, 157/3, 158, 159/1/A, 159/1/B, 159/1/C, 159/2, 160/1, 160/2, 161/1(pt), 161/3(pt), 161/4, 161/5, 162, 163/1(pt), 163/2(pt), 164/1(pt), 164/4, 164/4/5A, 164/6(pt), 165/1(pt), 165/2/A(pt), 165/2/B(pt), 165/3(pt), 174/5(pt) of village Purna, S No.14/3, 15/5, 16/1a, 16/2, 16/4, 16/5, 16/7, 16/9, 16/14, 16/15, 16/18, 16/21, 16/23, 16/23/A, 16/24, 16/25, 16/26, 16/27, 16/28, 16/29, 16/30, 16/31, 16/34, 16/35, 16/36, 16/39, 16/40, 17/1, 17/2, 17/3, 17/4, 17/5, 17/7, 17/8, 17/9, 17/10, 17/13, 17/14, 18/1, 18/2, 18/3, 18/5/A, 19/1/A, 19/2, 19/3, 19/5, 19/6A, 19/6C, 19/7, 19/8, 19/9, 19/10, 19/11, 19/12, 19/13 of Village Kopar | [8 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Rahanal, Kevani, Purna & Kopar | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Internal Road | [8 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Bhiwandi | [8 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Bhiwandi | [8 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Thane | [8 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 421302 | [8 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | Phase 1 - P51700053057 Phase 2 - P51700053096 Phase 3 - P51700053217 | [11 empty] | Mahad | Daund
Landmark |  | Salwan Niwas 362 | [11 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.258844,73.017936 | [8 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/R675kqUqcDEd41yS8 | [11 empty] | Poladpur | Purandhar
Name of the builder / developer |  | Adrika Developers Private Limited | [11 empty] | Mahasala | Bhor
Office address (agreement) |  | Dosti Group, 1st Floor, Lawrence and Mayo House, 276, Dr DN Road, Fort, Mumbai - 400001 | [11 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [11 empty] | Murud | Velhe
Builder Bank Details |  | HDFC Bank Ltd IFSC Code - HDFC0000060
Contact No. |  | Mrs. Rajni Shergill 7208963824
Location of the project Municipal Limit : |  | Mumbai Metropolitian Region Development Authority (MMRDA)
Project Type (Apartments/Plot/ Combined) |  | Apartments |  |  | Other HFC's Approval / Funding | None
No of Wings / Buildings |  | RERA |  | As Per Approved Plan |  | As Per Builder
|  | Phase 1 |  | Tower T3A-4 Tower T4-3 Tower T3A-5 |  | Dosti Serene Wing A Wing B Wing C
|  | Phase 2 |  | Tower T4-4 |  | Dosti Zion
|  | Phase 3 |  | Tower T3A-1 Tower T4-2 |  | Dosti Dazzle Wing A Wing B
No. of Tenements / Units in Project |  | Flats = 1952 |  |  | Exposure Limit (Proposed) | 292.8
Approved No. of Floor |  | Phase 1 T3A - 4 & 5 = G/ Stilt + 1st to 30th Floor T4 Type 3 = G + 1st to 30th Floor
Phase 2 T4 - 4 = G + 1st to 30th Floor
Phase 3 T3A - 1 = G/ Stilt + 1st to 30th Floor T4 - 2 = G/St + 1st to 22nd Floor
Proposed No. of Floor |  | Phase 1 T3A - 4 & 5 = G/ Stilt + 1st to 30th Floor T4 Type 3 = G + 1st to 30th Floor
Phase 2 T4 - 4 = G + 1st to 30th Floor
Phase 3 T3A - 1 = G/ Stilt + 1st to 30th Floor T4 - 2 = G/St + 1st to 30th Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | Boran | Kopar Boundary | Shri Raghunath Gana's Land | Kevni Boundary
|  | Approved Plan |  | Cluster 1A | Cluster 2 | Open Plot | 24M W Road
|  | Physical on site |  | Open Plot | Open Plot | Open Plot | Internal Road
Verification of survey No. (Title document) |  | Survey Nos 25/2, 26/10, 25/3, 190, 26/13/U, 26/13/7, 23/1/B, 23/1/C of Village Rahnal, Taluka Bhiwandi and District Thane, S No. 40/7 of Village Kevni, Taluka Bhiwandi and District Thane, 151/2/A, 152/1, 152/2, 152/3, 156/3, 156/4, 152/4/A (152/4/1/1), 161/5, 174/5, 152/4/B, 152/4/C (152/4/2), 152/4/D (152/4/3), 152/5/A (152/5pt), 154/3/A (154/3pt), 161/4, 162, 164/5/A(164/5), 165/2/A (162/2PT), 152/5/B (152/5PT), 154/3/B (154/3PT), 153, 154/4, 154/7, 156/1, 156/2, 157/1, 157/2, 157/3, 158, 159/1/A, 159/1/B, 159/1/C, 159/2, 160/1, 160/2, 161/1, 161/3, 164/1, 165/3, 163/1, 164/4, 165/1, 163/2, 164/6, 165/2/B (165/2PT) of Village Purna, 14/3, 16/23 (16/23PT), 15/5, 16/1/A, 16/25, 18/5/A, 16/2, 19/3, 16/4, 17/8, 16/5, 17/9, 16/7, 16/9, 16/24, 16/27, 16/34, 17/4, 17/10, 16/18, 16/21, 16/29, 19/5, 19/7, 16/23/A (16/23PT), 19/10, 16/26, 16/30, 16/39, 16/28, 16/31, 16/14, 16/35, 16/36, 16/40, 17/1, 19/12, 17/2, 17/5, 17/3, 17/7, 17/13, 17/14, 18/1, 18/2, 18/3, 19/1/A (19/1PT), 19/2, 19/6/A, 19/6/C, 19/8, 19/9, 19/11, 19/13 of Village Kopar, Taluka Bhiwandi and District Thane.
Plot area mentioned in the sale deed (As per 7/12) |  | 162866 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 136743.24
Approach road |  | Yes, Approx 9ft
Connectivity |  | 1. 2.3km from LB Joshi School. 2. 2km from Evershine English School 3. 2.3km from SS Hospital & Research Centre 4. 2.1km from Maruti Health Care 5. 1.7km from Shiv Mandir 6. 2.5km from Purneshwar Shiv Mandir 7. 2km from Vinayak Super Market 8. 2.6km from B mart 9. 1.5km from Kopar Bus stop 10. 5.3km from Bhiwandi Road Railway Station
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 136743.24
|  | Permissible FSI |  |  |  | 1.1
|  | Permissible TDR/Paid FSI |  |  |  | 1.1392
|  | Total FSI availaible for the project |  |  |  | 2.2392
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 305965.65
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 306191.88
Building plan approvals - Approval No : |  | SROT/BSNA/2501/BP/Rahnal-Kevani-Purna-Kopar-02/CC/1073/2023 Date - 02/08/2023
Building height / No. of Floors |  | Cluster 1B : Wing A - Tower T3A Bldg 4 = St + 1st to 30th Floor.(Height = 89.10m) Wing B - Tower T4 Bldg 3 = St + 1st to 30th Floor (Height = 89.10m) Wing C - Tower T3A Bldg 5 = St + 1st to 30th Floor (Height = 89.10m) Tower T4 Bldg 4 = St + 1st to 30th Floor (Height = 89.10m) Wing A - Tower T3A Bldg 1 = St + 1st to 30th Floor (Height = 89.10m) Wing B - Tower T4 Bldg 2 = St + 1st to 22nd Floor (Height = 66.30m)
Construction/Building Permission |  | SROT/BSNA/2501/BP/Rahnal-Kevani-Purna-Kopar-02/CC/1073/2023 Valid Upto - Cluster 1B - Tower T3A Bldg 1 = St + 1st to 30th Floor Tower T3A Bldg 4 & 5 = St + 1st to 30th Floor Tower T4 Bldg 3 & 4 = St + 1st to 30th Floor Tower T4 Bldg 2 = St + 1st to 22nd Floor
NA / Land conversion |  | Name of the authority : |  | Collector of Thane
|  | Reference No : |  | Mahsul/K-1/Te-8/Mou.Rahanal,Kevani,Purna,Kopar/Tal. Bhiwandi/SND/SR-05/2022
|  | Validity & area : mentioned |  | Date - 12/05/2022. Area - 157796.9 Sq.mt |  |  |  | 157796.9
Fire NOC |  | Not Provided
Environmental Clearance |  | SIA/MH/MIS/70385/2021 Date - 30/09/2022 Plot Area = 162866 Sq.mt Net Plot Area = 136743.24 Sq.mt B.U.A = 546870.95 Sq.mt
CONSTRUCTION PROGRESS
Baseline start date |  | Phase 1 - 12/10/2023, Phase 2 -16/10/2023, Phase 3 - 23/10/2023 |  | Baseline finish date | Phase 1, 2 & 3 - 31/10/2028
Construction details:
Phase 1 (Dosti Serene) Wing A = St + 1st + 30th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work in process
|  |  |  | 0 | 1 | 0 | 30
Stage of construction: |  | Excavation work in process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 7.5
Excavation |  | 0% |  | 15 | 50% | 0% |  | Excavation in process | 15
Plinth |  | 10% |  | 0 | 0% |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 40% |  | 0 | 0% |  |  | Footing in Process | 7.5
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 15
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 22.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 30
Phase 1 (Dosti Serene) Wing B = St + 1st + 30th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 0 | 1 | 0 | 30
Stage of construction: |  | Excavation work Completed. Plinth work completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 7.5
Excavation |  | 0% |  | 30 | 100% | 10% |  | Excavation in process | 15
Plinth |  | 10% |  | 30 | 100% |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 40% |  | 0 | 0% |  |  | Footing in Process | 7.5
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 15
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 22.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 30
Phase 1 (Dosti Serene) Wing C = St + 1st + 30th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Footing work is process
|  |  |  | 0 | 1 | 0 | 30 |  |  | Visit dtd 02/04/2025 Wing C work not started but piling in process gives in previous report common work given for all wings
Stage of construction: |  | Excavation work Completed. Footing work is process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 7.5
Excavation |  | 0% |  | 30 | 100% | 2.5% |  | Excavation in process | 15
Plinth |  | 10% |  | 7.5 | 25% |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 40% |  | 0 | 0% |  |  | Footing in Process | 7.5
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 15
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 22.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 30
Phase 2 (Dosti Zion) = St + 1st + 30th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Footing work is process
|  |  |  | 0 | 1 | 0 | 30
Stage of construction: |  | Excavation work Completed. Footing work is process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 7.5
Excavation |  | 0% |  | 30 | 100% | 2.5% |  | Excavation in process | 15
Plinth |  | 10% |  | 7.5 | 25% |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 40% |  | 0 | 0% |  |  | Footing in Process | 7.5
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 15
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 22.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 30
Phase 3 (Dosti Dazzle) = St + 1st + 30th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work in process
|  |  |  | 0 | 1 | 0 | 30
Stage of construction: |  | Excavation work in process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 7.5
Excavation |  | 0% |  | 15 | 50% | 0% |  | Excavation in process | 15
Plinth |  | 10% |  | 0 | 0% |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 40% |  | 0 | 0% |  |  | Footing in Process | 7.5
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 15
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 22.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 30
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | No
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block/ Brick |  | Projected Parts Available |  | Yes/No | No
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A
Total |  | 0 |  | 0 |  | 0
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Phase 1 Tower T3A(Type 4) |  | 343 |  | 128943.7859 |  | 193415.6788 |  |  | 686
Phase 1 Tower T4(Type 3) |  | 339 |  | 165305.439 |  | 247958.1585
Phase 1 Tower T3A(Type 5) |  | 343 |  | 128943.7859 |  | 193415.6788
Phase 2 Tower 4 (Type 4) |  | 339 |  | 165305.439 |  | 247958.1585
Phase 3 Tower 3A(Type 1) |  | 343 |  | 129124.6211 |  | 193686.9316
Phase 3 Tower 4(Type 2) |  | 245 |  | 119669.3082 |  | 179503.9623
Total |  | 1952 |  | 837292.379 |  | 1255938.5686 |  |  | 343
Grand Total |  | 1952 |  | 837292.379 |  | 1255938.5686
BUILDING / BLOCK - Configuration Details
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
45%
Building No.1
Ground Floor
1 |  | Shop |  |  | 0 |  | 0
2 |  | Shop |  |  | 0 |  | 0
3 |  | Shop |  |  | 0 |  | 0
4 |  | Shop |  |  | 0 |  | 0
5 |  | Shop |  |  | 0 |  | 0
6 |  | Shop |  |  | 0 |  | 0
7 |  | Shop |  |  | 0 |  | 0
8 |  | Shop |  |  | 0 |  | 0
9 |  | Shop |  |  | 0 |  | 0
10 |  | Shop |  |  | 0 |  | 0
11 |  | Shop |  |  | 0 |  | 0
12 |  | Shop |  |  | 0 |  | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | RERA Carpet area + CB Area | Balcony Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading: |  | 10.764
50%
Sector 3A - Cluster 1B
Phase 1 (Dosti Serene)
Wing A (Tower T3A Type 4)
Ground Floor For Entrance Lobby, Fitness Center, Creche, Meter Room, Society Office, Drivers Room & Parking
1st & 2nd Floor For Residential | [7 empty] | 2
1 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487 | 33.6123
2 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
3 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
4 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
5 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
6 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
3rd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor | [7 empty] | 23
1 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
2 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
3 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
4 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
5 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
6 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
7 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
8 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
9 |  | 1BHK | 319.3679 | 0 | 319.3679 | 0 | 479.0518
10 |  | 1BHK | 319.3679 | 0 | 319.3679 | 0 | 479.0518
11 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
12 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
1 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
2 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
3 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
4 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
5 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
6 |  | - | Refuge Area |  |  |  | -
7 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
8 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
9 |  | 1BHK | 319.3679 | 0 | 319.3679 | 0 | 479.0518
10 |  | 1BHK | 319.3679 | 0 | 319.3679 | 0 | 479.0518
11 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
12 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
Wing B (Tower T4 Type 3)
Ground Floor For Entrance Lobby, Fitness Center, Creche, Meter Room, Society Office, Drivers Room & Parking
1st & 2nd Floor For Residential | [7 empty] | 2
1 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
2 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
3 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
4 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
3rd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor | [7 empty] | 23
1 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
2 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
3 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
4 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
5 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
6 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
7 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
8 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
9 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
10 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
11 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
12 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
8th, 13th, 18th, 23rd, 28th Floor (Part Refuge Area)
1 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
2 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
3 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
4 |  | - | Refuge Area |  |  |  | -
5 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
6 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
7 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
8 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
9 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
10 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
11 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
12 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
Wing C (Tower T3A Type 5)
Ground Floor For Entrance Lobby, Fitness Center, Creche, Meter Room, Society Office, Drivers Room & Parking
1st & 2nd Floor For Residential | [7 empty] | 2
1 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487 | 33.6123
2 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
3 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
4 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
5 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
6 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
3rd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor | [7 empty] | 23
1 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
2 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
3 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
4 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
5 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
6 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
7 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
8 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
9 |  | 1BHK | 319.3679 | 0 | 319.3679 | 0 | 479.0518
10 |  | 1BHK | 319.3679 | 0 | 319.3679 | 0 | 479.0518
11 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
12 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
1 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
2 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
3 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
4 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
5 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
6 |  | - | Refuge Area |  |  |  | -
7 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
8 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
9 |  | 1BHK | 319.3679 | 0 | 319.3679 | 0 | 479.0518
10 |  | 1BHK | 319.3679 | 0 | 319.3679 | 0 | 479.0518
11 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
12 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
Phase 2 ( Dosti Zion)
Tower T4 (Type 4)
Ground Floor For Entrance Lobby, Fitness Center, Creche, Meter Room, Society Office, Drivers Room & Parking
1st & 2nd Floor For Residential | [7 empty] | 2
1 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472 | 44.8094 | 2.13
2 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
3 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
4 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
3rd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor | [7 empty] | 23
1 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
2 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
3 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
4 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
5 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
6 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
7 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
8 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
9 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
10 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
11 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
12 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
8th, 13th, 18th, 23rd, 28th Floor (Part Refuge Area) | [7 empty] | 5
1 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
2 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
3 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
4 |  | - | Refuge Area |  |  |  | -
5 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
6 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
7 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
8 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
9 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
10 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
11 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
12 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
Phase 3 (Dosti Dazzle)
Wing A (Tower T3A Type 1)
Ground Floor For Entrance Lobby, Fitness Center, Creche, Meter Room, Society Office, Drivers Room & Parking
1st & 2nd Floor For Residential | [7 empty] | 2
1 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487 | 33.6123
2 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
3 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
4 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
5 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
6 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
3rd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th & 30th Floor | [7 empty] | 23
1 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
2 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
3 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
4 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
5 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
6 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
7 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
8 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
9 |  | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956
10 |  | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956
11 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
12 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
1 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
2 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
3 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
4 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
5 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
6 |  | - | Refuge Area |  |  |  | -
7 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
8 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
9 |  | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956
10 |  | 1BHK | 322.5971 | 0 | 322.5971 | 0 | 483.8956
11 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487
12 |  | 1BHK | 370.8198 | 16.146 | 386.9658 | 0 | 580.4487 |  | 339 | 261
Wing B (Tower T4 Type 2)
Ground Floor For Entrance Lobby, Fitness Center, Creche, Meter Room, Society Office, Drivers Room & Parking
1st & 2nd Floor For Residential
1 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
2 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
3 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
4 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
3rd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd Floor
1 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
2 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
3 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
4 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
5 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
6 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
7 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
8 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
9 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
10 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
11 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
12 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
8th, 13th & 18th Floor (Part Refuge Area)
1 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
2 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
3 |  | 2BHK | 534.9708 | 22.9273 | 557.8981 | 0 | 836.8472
4 |  | - | Refuge Area |  |  |  | -
5 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
6 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
7 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
8 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
9 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
10 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
11 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
12 |  | 2BHK | 451.5498 | 0 | 451.5498 | 0 | 677.3247
2nd Floor
1 |  | 1BHK |  |  | 0 |  | 0
2 |  | 1BHK |  |  | 0 |  | 0
3 |  | 1BHK |  |  | 0 |  | 0
4 |  | 1BHK |  |  | 0 |  | 0
5 |  | 1BHK |  |  | 0 |  | 0
6 |  | 1BHK |  |  | 0 |  | 0
7 |  | 1BHK |  |  | 0 |  | 0
8 |  | 1BHK |  |  | 0 |  | 0
9 |  | 1BHK |  |  | 0 |  | 0
10 |  | 1BHK |  |  | 0 |  | 0
11 |  | 1BHK |  |  | 0 |  | 0
12 |  | 1BHK |  |  | 0 |  | 0
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 7000
Recommended of Parking ( If Available) |  |  |  |  | 3,00,000/-
REMARKS ON RECOMMENDATION
1 | Construction work is in process at the time of Visit. (Internal Visit not allowed)
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Labours found on site at the time of visit.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Balcony + CB Area.
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 50%
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Mr. Shubham 9619081618.
11 | Please check for Fire NOC.
Photographs Of Property : |  | Dosti Greater Thane ­ Sector 3A ­ Cluster 1B ­ Phase 1, 2 & 3
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Mangesh Laxman Bapardekar |  | Authorized Signatory Name & Seal of the agency
N
T4 Blgd4
T3A Bldg1
T4 Blgd2
T3A Bldg5
T4 Blgd3
T3A Bldg4
Phase 1
Phase 2
Phase 3
Cluster 1B
N
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G31: 15% of Total No of Flats
Note on E39: If Sale deed is provided
Note on F39: If Sale deed is provided
Note on G39: If Sale deed is provided
Note on H39: If Sale deed is provided
Note on C54: height should also be mentioned
Note on C62: RERA Start date
Note on F62: RERA completion date
Note on H136: if multiple buildings are in project and are connected internally
Note on C138: AAC Block or Brick
Note on H140: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3