## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-09-10
Branch Name/ID |  | Mahindra Rural Housing Finance - Kalyan |  |  | Date & Time of Site Visit | 10/09/2025 at 17:21
Name of the person met at site & Contact No |  | Mr. Raja Wadhawa 9594944955 |  |  | Date of Report Release | 16/09/2025
Project Details
Name of the project |  | Spectrum Residency
Address |  | Spectrum Residency, CTS No.4194, 4195, 4196 & 4206, Sheet No. 66, Redevelopment of " Kanta Villa, Block No. 586-A, Room No. 10, 11 & 12", near Kaushalya Kunj CHS, Pram Karia Marg, Ulhasnagar, Ulhasnagar East, Ulhasnagar, Thane - 421002. | [10 empty] | Thane | Palghar | Mumbai | Raigad | Pune
CTS No |  | 4194, 4195, 4196 & 4206, Sheet No. 66, Redevelopment of " Kanta Villa, Block No. 586-A, Room No. 10, 11 & 12" | [6 empty] | existing building name confirm with Anil Gera8655577915 |  |  |  | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Ulhasnagar | [10 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Pram Karia Marg | [10 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Ulhasnagar East | [10 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Ulhasnagar | [10 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Thane | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 421002 | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P51700051472 | [13 empty] | Mahad | Daund
Landmark |  | Kaushalya Kunj CHS | [13 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.2349374,73.1716746 | [10 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/VxQcS9aeq4DPnZtr7 | [13 empty] | Poladpur | Purandhar
Name of the builder / developer |  | Spectrum Developers | [13 empty] | Mahasala | Bhor
Office address (agreement) |  | Bk no. 110, Padma Niwas, 1st floor, Shani mandir road, behind Bus stand, Ulhasnagar, Thane, 421001 | [13 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [13 empty] | Murud | Velhe
Builder Bank Details |  | HDFC BANK IFSC Code : HDFC0000815
Contact No. |  | Mr. Sarjeet Yadav 7039490847 / Mr. Anil Gera 8655577915
Location of the project Municipal Limit : |  | Ulhasnagar Municipal Corporation
Project Type (Apartments/Plot/ Combined) |  | Apartments
No of Wings / Buildings |  | 01 Building |  |  | Other HFC's Approval / Funding | None
No. of Tenements / Units in Project |  | 21 |  |  | Exposure Limit (Proposed) | 3.15
Approved No. of Floor |  | Gr. + 1st to 7th Floor
Proposed No. of Floor |  | Gr. + 1st to 7th Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | Other Plot | Other Plot | Other Plot | 36 M W Road
|  | Physical on site |  | House | Shree Anandpur Satsang Bhawan | House | Pram Karia Marg
Verification of survey No. (Title document) |  | CTS No. 4194, 4195, 4196 & 4206
Plot area mentioned in the sale deed (As per 7/12) |  | 262.8 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 199.49
Approach road |  | Yes, Approx 117ft
Connectivity |  | 1. 0.35Km from (S.E.S) Sitaldas Khemani High School 2. 0.55Km from Chandrasekhar government school 3. 0.35Km from Global Hospital Ulhasnagar 4. 0.60Km from R.P Divine Care Hospital 5. 0.12Km from Ganesh Super Market 6. 0.29Km from Khemani Sabji Mandi 7. 0.50Km from Shree Shiv Mandir 8. 0.70Km from Vaishno Devi Mata Mandir 9. 2.30Km from Shivaji Chowk Bus stop 10. 3.10Km from Ulhasnagar Railway Station
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 199.49
|  | Permissible FSI |  |  |  | 1.1
|  | Permissible TDR/Paid FSI |  |  |  | 3.7978
|  | Total FSI availaible for the project |  |  |  | 4.8978
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 1270.9
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 977.06
Building plan approvals - Approval No : |  | UMP/NRV/BP/21/23/206 |  |  |  | Date | 2023-11-08
Building height / No. of Floors |  | Gr. + 1st to 7th Floor (Total Height = 21.70 M)
Construction/Building Permission Valid Upto |  | UMP/NRV/BP/21/23/206 Gr. + 1st to 7th Floor |  |  |  | Date | 2023-11-08
NA / Land conversion |  | Name of the authority : |  | NA
|  | Reference No : |  | NA |  | Date | NA |  | ``
|  | Validity & Area mentioned: |  | NA |  |  |  | Date - - Valid For one Year Area -
Other statutory permissions
Fire Noc No Valid Up to: | [5 empty] | Date
Environmental Clearance Certificate (EC) No Valid Up for: | [5 empty] | Date
Airport Noc No Valid Up for: | [5 empty] | Date
Valid upto Dated
Site Elevation (AMSL) = Permissible Top Elevation (AMSL) =
CONSTRUCTION PROGRESS
Baseline start date |  | 2023-06-23 |  | Baseline finish date |  | 2025-12-31 |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Construction details:
Gr + 1st + 7th Floor |  |  |  | Basement | Ground | Podium | Floors | All work Completed. OC Received.
|  |  |  | 0 | 1 | 0 | 7 | Piling Work in process | 1.75
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | Excavation in process | 3.5
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Excavation Completed | 7
Excavation |  | 0% |  | 7 | 100% | 92.14% |  | Footing in Process | 1.75
Plinth |  | 10% |  | 7 | 100% |  |  | Footing Completed | 3.5
RCC (Including podiums) |  | 40% |  | 8 | 100% |  |  | Basement 1 | 0
Brickwork |  | 15% |  | 7 | 100% |  |  | Basement 2 | 0
Internal Plaster |  | 5% |  | 7 | 100% |  |  | Basement 3 | 0
Ext. Plaster & Plumbing |  | 5% |  | 7 | 100% |  |  | Basement 4 | 0
Flooring & Fitting |  | 10% |  | 7 | 100% |  |  | Plinth in process | 5.25
Painting & Wooden |  | 5% |  | 7 | 100% |  |  | Plinth completed | 7
Building Common Amenities |  | 5% |  | 3 | 42.86%
Possession |  | 5% |  | 0 | 0%
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block/ Brick |  | Projected Parts Available |  | Yes/No | Yes
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A
Total |  | 0 |  | 0 |  | 0
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 21 |  | 8429.1808 |  | 12222.3121
Total |  | 21 |  | 8429.1808 |  | 12222.3121
Grand Total |  | 21 |  | 8429.1808 |  | 12222.3121
BUILDING / BLOCK - Configuration Details
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
50%
Building No.1
Ground Floor
1 |  | Shop |  |  | 0 | 0 | 0
2 |  | Shop |  |  | 0 | 0 | 0
3 |  | Shop |  |  | 0 | 0 | 0
4 |  | Shop |  |  | 0 | 0 | 0
5 |  | Shop |  |  | 0 | 0 | 0
6 |  | Shop |  |  | 0 | 0 | 0
7 |  | Shop |  |  | 0 | 0 | 0
8 |  | Shop |  |  | 0 | 0 | 0
9 |  | Shop |  |  | 0 | 0 | 0
10 |  | Shop |  |  | 0 | 0 | 0
11 |  | Shop |  |  | 0 | 0 | 0
12 |  | Shop |  |  | 0 | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
45%
Building No.1
Ground Floor For Meter/Pump Room & Parking
1st to 7th Floor For Residential | [9 empty] | 10.764
1 |  | 1BHK | 425.178 | 17.0071 | 442.1851 | 0 | 641.1684 |  |  | 6550.5409 | 3654660.0168 | 4725.7474
2 |  | 1BHK | 329.9166 | 15.7154 | 345.632 | 0 | 501.1665 | 29.0585 |  | 6983.7076 | 2856648.8106 | 6045.8954
3 |  | 1BHK | 366.9448 | 49.4068 | 416.3515 | 0 | 603.7097 | 32.0974 |  | 6446.8071 | 3441145.3128 | 5018.9685
Ground Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
1st Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
2nd Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
2nd Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5500
Recommended of Parking ( If Available) |  |  |  |  | 2,50,000/-
REMARKS ON RECOMMENDATION
1 | Construction work is in process at the time of Visit. Construction work was not active at the time of Visit. (labour Not found) All work completed. Wait for OC / OC received. Work not yet Started.
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Labours found on site at the time of visit.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Balcony + EP Area.
5 | We considered Saleable area as per our calculation. Loading |  |  |  | 45%
6 | We have considered rate by verifying it from market inquire.
7 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
8 | Car parking is subjected to authentic documentation.
9 | On Site, we meet Mr. Raja Wadhawa 9594944955
10 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
11 | As per approved plan dtd. 08/11/2023, Sheet No. 1 consist of latest approved structure plan (G + 1st to 7th floor) & sheet no. 2 consist of old building plan (G + 1st to 2nd floor). Old building has been demolished & new building has been constructed on same land parcel. Above details taken from Builder person (Mr. Anil Gera 8655577915). Please check from your end.
Photographs Of Property : |  | Spectrum Residency
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Mr. Sudhir Bhosale |  | Authorized Signatory Name & Seal of the agency
N
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C47: height should also be mentioned
Note on C60: RERA Start date
Note on H78: if multiple buildings are in project and are connected internally
Note on C80: AAC Block or Brick
Note on H82: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3