## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Sr.No. | Particulars |  |  |  | Details
1 | Name of the project |  |  |  | PG Vatika (C to F Wing)
2 | Address as per the site visit |  |  |  | PG Vatika, Gut No.45/1 & 45/2 Plot No. A, near Sarmilla Residency, Proposed Panvel Highway, MIDC Area, Mankivali, Badlapur East, Ambernath, Thane - 421503.
[5 empty] | Latitude, Longitude : |  | 19.148967,73.238225
| Location Link |  |  |  | https://maps.app.goo.gl/PTkwitTMk461GYC86
| RERA Name & No. |  |  |  | PG Vatika (C & D Wing) = P51700052819 PG Vatika (E & F Wing) = P51700080943
3 | Closest landmark |  |  |  | Sarmilla Residency
4 | Address as per the Sale brochure |  |  |  | Gut No. 45/1 & 45/2, PG - Vatika., Gadge Nagar, Near Panvelkar Estate, MIDC Road, Mankivali Village, Badlapur (E), Thahe - 421503
5 | Address as per the plans & permissions |  |  |  | Proposed Partly Commercial & Residential Building on Land Bearing Gut No. 45/1 & 45/2 (Plot A) At Villege Mankivali, Tal - Ambernath, Dist - Thane |  |  |  | Same
6 | Address as per the legal documentation |  |  |  | Proposed Partly Commercial & Residential Building on Land Bearing Gut No. 45/1 & 45/2 (Plot A) At Villege Mankivali, Tal - Ambernath, Dist - Thane
7 | Date of APF initiation from YBL |  |  |  | 2024-01-23
8 | Date of documents delivery / receipt |  |  |  | 2024-01-25
9 | List of documents provided |  |  |  | Area Statement & Approved Plans.
10 | Queries communicated to YBL regarding discrepancies in documentation, details etc |  |  |  | None
11 | Date of query resolution from YBL |  |  |  | None
12 | Any further documentation that needs to be complied prior to start of disbursement in the project? Provide complete details. |  |  |  | None
13 | Name of developer personnel for site visit coordination with contact details (Mobile, landline, email) |  |  |  | Mr. Nitesh Parsiya 9323713131
14 | Date of contacting concerned developer personnel for site visit |  |  |  | 2025-09-11
15 | Date, day & timing of Site visit |  |  |  | 11/09/2025 @ 2.14PM
16 | Name of the person conducting the site visit & contact details |  |  |  | Mr. Sudhir Bhosale
17 | Name of person met at site (Full Name, Designation, Mobile Number, Landline Number, email id) |  |  |  | 7058266641
18 | Details of Financial Institutions who's APF Approval Letters / Boards were displayed on site |  |  |  | None
19 | Details of sold v/s unsold units |  |  |  | NA
20 | Has the developer availed any kind of construction / project finance? If yes, details are required. |  |  |  | None
21 | Developer name |  |  |  | M/s. Gurukrupa Enterprises
22 | Developer group parent company |  |  |  | M/s. Gurukrupa Enterprises
23 | Developer office address along with contact details |  |  |  | A/1, Devina CHS, Ghanshyam Gupte Cross Road, Vishnunagar, Dombivali (West), Thane 421202
24 | Architect details ( Name, office address, mobile number, registration number ) |  |  |  | ER. R.K. Khambayat, M/s. Raj Associates, Office No. 102/103, 1st Floor, Vighnaharta Arcade, Near Spandan Hospital, New D.P. Road, Katrap, Badlapur East 421503
25 | Authority jurisdiction for the project location |  |  |  | Kulgoan Badlapur Municipal Council
26 | Zoning Approval for the project location as per the MDP |  |  |  | Kulgoan Badlapur Municipal Council
27 | Does the proposed development match with the Zoning Approval? Detailed feedback |  |  |  | Yes its comes under Residential zone
28 | Project type ( Residential / Mixed / Flats / Villas / Row Houses etc ) |  |  |  | Residential
29 | Plot area in sqmt |  |  |  | 8320
30 | Does the Plot Area match as per the legal documentation? |  |  |  | Yes
31 | Does the Plot Area match as per the Non Agriculture documentation? |  |  |  | Yes as per plan. But NA order not provided to verify.
32 | Does the ongoing construction match with the Approved Site Layout? If no, details expected. |  |  |  | Yes
33 | Net Plot Area |  |  |  | 7545
| Built Up Area |  |  |  | 18141.37 |  |  |  | 2.4044
| Built Up Area of Wing C to F |  |  |  | 11245.57 |  |  |  | 0.61989
34 | Basic FSI / FAR |  |  |  | 1.1
35 | Premium FSI / FAR |  |  |  | 0.33082
36 | Approved TDR |  |  |  | 0.070245
37 | Ancillary FSI |  |  |  | 0.90983
38 | Total FSI |  |  |  | 2.4109 |  |  |  | 2.4044
39 | Project launch date |  |  |  | Wing C & D = 05/10/2023 Wing E & F = 25/08/2025
40 | Average weighted stage of construction for the project with construction stages of individual wings
Construction details: |  | Wing C = Gr + 1st to 8th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 7 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 8
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 7 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 2
Excavation |  | 8 | 100% |  | 69.38% |  | 79.38% |  | Excavation in process | 4
Plinth |  | 8 | 100% | [5 empty] | Excavation Completed | 8
RCC (Including podiums) |  | 9 | 100% | [5 empty] | Footing in Process | 2
Brickwork | Brickwork & Internal Plaster | 8 | 100% | [5 empty] | Footing Completed | 4
Internal Plaster | Brickwork & Internal Plaster | 8 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 87.5% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 6
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 8
Construction details: |  | Wing D = Gr + 1st to 8th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 8
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 2
Excavation |  | 8 | 100% |  | 100% |  | 100% |  | Excavation in process | 4
Plinth |  | 8 | 100% | [5 empty] | Excavation Completed | 8
RCC (Including podiums) |  | 9 | 100% | [5 empty] | Footing in Process | 2
Brickwork | Brickwork & Internal Plaster | 8 | 100% | [5 empty] | Footing Completed | 4
Internal Plaster | Brickwork & Internal Plaster | 8 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 8 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 8 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 8 | 100% | [5 empty] | Plinth in process | 6
Possession |  | 8 | 100% | [5 empty] | Plinth completed | 8
Construction details: |  | Wing E = Gr + 1st to 8th Floor | [6 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 8
Stage of construction: |  | Excavation work Completed. Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 2
Excavation |  | 8 | 100% |  | 20% |  | 30% |  | Excavation in process | 4
Plinth |  | 8 | 100% | [5 empty] | Excavation Completed | 8
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 2
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 4
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 6
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 8
Construction details: |  | Wing F = Gr + 1st to 8th Floor | [6 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 8
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 2
Excavation |  | 0 | 0% |  | 0% |  | 0% |  | Excavation in process | 4
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 8
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 2
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 4
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 6
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 8
41 | Expected completion date for the project as projected by the developer |  |  |  | Wing C & D = 31/12/2026 Wing E & F = 31/12/2030
42 | Permissions applicable v/s available (Detailed analysis) |  |  |  | NA
43 | Physical & social infrastructure availability details ( Bus stop, railway station, public park, main road, airport, hospital, public transport, school, market etc ) |  |  |  | SCHOOL : Jijau School Of Excellence - 300m Holy Spirit High School - 1.10Km
SHOPPING : Reliance SMART Bazaar - 1.20Km Shreeji Centre Mall - 2.70Km
HOSPITALS : Gurudev Multi-Speciality Hospital - 1.40Km Central Hospital Badlapur - 2.20Km
PETROL PUMP : Bharat Petroleum, Petrol Pump - 2.10Km
44 | Internal & external amenities |  |  |  | Club House, Gymnasium, Childrens Play Area, Senior Citizen Sit-Out Area, Indoor Games, Multipurpose Hall, Landscaped Garden, etc.
45 | Boundary details ( Are they matching as per the legal & technical documentation ) |  |  |  | Yes
46 | Phase, building & wingwise structure details ( Approvals v/s proposed v/s constructed ( If 100 % complete ) ( Deviations to be pointed out ) |  |  |  | Approved Floor = |  | Wing C & D = Gr + 1st to 8th Floor Wing E & F = Gr + 1st to 8th Floor
[5 empty] | Proposed Floor = |  | Wing C & D = Gr + 1st to 8th Floor Wing E & F = Gr + 1st to 8th Floor
Approval Detail : Plan approval
Layout plan No. |  | 1106 |  |  |  | Dated | 2025-05-30
Approved Floor plan No (C & D Wing) |  | KBNP/NRV/BD/6139-101 |  |  |  | Dated | 2022-06-30
Commencement Certificate No. Valid upto: |  | KBNP/NRV/B.P./6139/2022-2023 Unique No. 101 Wing C to F = Stilt + 1st to 8th Floor |  |  |  | Dated | 30/06/2022
Approved Floor plan No (E & F Wing) |  | 1106 |  |  |  | Dated | 2025-05-30
CC Renewal No. Valid upto: |  | KBNP/NRV/0867/2025-2026 Wing C to F = Stilt + 1st to 8th Floor |  |  |  | Dated Valid Upto : | 25/04/2025 29/06/2026
Part O. Certificate No. Approved upto : |  | KBMC/TPD/2025-26/1106 Wing D = Gr + 1st to 8th Floor |  |  | Date of approval: | Dated | 2025-05-30 | NA
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  |  | Total Saleable Area
Wing C |  | 47 |  | 16860.3529 |  |  | 24447.5116
Wing D |  | 47 |  | 20821.6932 |  |  | 30191.4552
Wing E |  | 63 |  | 24168.1401 |  |  | 35043.8031
Wing F |  | 79 |  | 31617.2587 |  |  | 45845.0251
Grand Total |  | 236 |  | 93467.4448 |  |  | 135527.795
Building details Floor Wise
Details of Flats in Building
Flat No. (as per Approved Plan) | Description | Carpet area | Balcony/Otla | E.P Area | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
Wing C
Ground Floor For Entrance Lobby & Parking
1st to 7th Floor For Residential
1 | 1BHK | 316.1387 | 29.0628 | 39.154 | 384.3555 | 0 | 557.3155 | 1st to 7th Floor For Residential
2 | 1BHK | 309.465 | 29.0628 | 40.365 | 378.8928 | 0 | 549.3946
3 | 1RK | 237.8844 | 29.0628 | 20.1825 | 287.1297 | 0 | 416.3381
4 | 1BHK | 316.1387 | 29.0628 | 39.154 | 384.3555 | 0 | 557.3155
5 | 1BHK | 339.3889 | 29.0628 | 42.3832 | 410.835 | 0 | 595.7107
6 | 1RK | 250.1554 | 29.0628 | 20.1825 | 299.4007 | 0 | 434.131
8th Floor (Part Refuge Area)
1 | 1BHK | 316.1387 | 29.0628 | 39.154 | 384.3555 | 0 | 557.3155 | 8th Floor (Part Refuge Area)
2 | 1BHK | 309.465 | 29.0628 | 40.365 | 378.8928 | 0 | 549.3946 |  | 3804.1876
3 | 1RK | 237.8844 | 29.0628 | 20.1825 | 287.1297 | 0 | 416.3381
4 | 1BHK | 316.1387 | 29.0628 | 39.154 | 384.3555 | 0 | 557.3155
5 | 1BHK | 339.3889 | 29.0628 | 42.3832 | 410.835 | 0 | 595.7107
6 | Refuge Area
Wing D
Ground Floor For Entrance Lobby & Parking
1st to 7th Floor For Residential
1 | 1BHK | 313.5553 | 29.0628 | 39.154 | 381.7722 | 0 | 553.5696 | 1st to 7th Floor For Residential
2 | 1BHK | 313.5553 | 29.0628 | 39.154 | 381.7722 | 0 | 553.5696
3 | 1BHK | 318.1838 | 29.0628 | 39.154 | 386.4007 | 0 | 560.281
4 | 1.5BHK | 457.0394 | 29.0628 | 61.7585 | 547.8607 | 0 | 794.398
5 | 1.5BHK | 457.0394 | 29.0628 | 61.7585 | 547.8607 | 0 | 794.398
6 | 1BHK | 337.1285 | 29.0628 | 39.154 | 405.3453 | 0 | 587.7507
8th Floor (Part Refuge Area)
1 | 1BHK | 313.5553 | 29.0628 | 39.154 | 381.7722 | 0 | 553.5696 | 8th Floor (Part Refuge Area)
2 | 1BHK | 313.5553 | 29.0628 | 39.154 | 381.7722 | 0 | 553.5696
3 | Refuge Area
4 | 1.5BHK | 457.0394 | 29.0628 | 61.7585 | 547.8607 | 0 | 794.398
5 | 1.5BHK | 457.0394 | 29.0628 | 61.7585 | 547.8607 | 0 | 794.398
6 | 1BHK | 337.1285 | 29.0628 | 39.154 | 405.3453 | 0 | 587.7507
Wing E
Ground Floor For Entrance Lobby & Parking
1st to 7th Floor For Residential
1 | 1BHK | 322.0589 | 29.601 | 39.154 | 390.8139 | 0 | 566.6802 | 1st to 7th Floor For Residential | 28.54 | 2.75 | 4.325
2 | 1BHK | 313.5553 | 29.601 | 39.154 | 382.3104 | 0 | 554.35
3 | 1BHK | 313.5553 | 29.601 | 39.154 | 382.3104 | 0 | 554.35
4 | 1BHK | 322.0589 | 29.601 | 39.154 | 390.8139 | 0 | 566.6802
5 | 1BHK | 297.4093 | 29.601 | 37.9431 | 364.9534 | 0 | 529.1825
6 | 1BHK | 322.0589 | 29.601 | 39.154 | 390.8139 | 0 | 566.6802
7 | 1BHK | 313.5553 | 29.601 | 39.154 | 382.3104 | 0 | 554.35
8 | 1BHK | 313.5553 | 29.601 | 39.154 | 382.3104 | 0 | 554.35
8th Floor For Residential (Part Refuge Area)
1 | 1BHK | 322.0589 | 29.601 | 39.154 | 390.8139 | 0 | 566.6802 | 8th Floor For Residential (Part Refuge Area) | 28.54 | 2.75 | 4.325
2 | 1BHK | 313.5553 | 29.601 | 39.154 | 382.3104 | 0 | 554.35
3 | 1BHK | 313.5553 | 29.601 | 39.154 | 382.3104 | 0 | 554.35
4 | 1BHK | 322.0589 | 29.601 | 39.154 | 390.8139 | 0 | 566.6802
5 | - | Refuge Area
6 | 1BHK | 322.0589 | 29.601 | 39.154 | 390.8139 | 0 | 566.6802
7 | 1BHK | 313.5553 | 29.601 | 39.154 | 382.3104 | 0 | 554.35
8 | 1BHK | 313.5553 | 29.601 | 39.154 | 382.3104 | 0 | 554.35
Wing F
Ground Floor For Entrance Lobby & Parking
1st to 7th Floor For Residential
1 | 1BHK | 317.538 | 29.601 | 39.154 | 386.293 | 0 | 560.1249 | 1st to 7th Floor For Residential | 28.54 | 2.75 | 4.325
2 | 2BHK | 487.2863 | 29.601 | 61.3548 | 578.2421 | 0 | 838.451 |  | 4233.9981
3 | 1BHK | 322.0589 | 29.601 | 39.154 | 390.8139 | 0 | 566.6802 |  | 4499.8925
4 | 1RK | 237.8844 | 29.601 | 20.1825 | 287.6679 | 0 | 417.1185 |  | 4435.191 | 3859.8148
5 | 1BHK | 322.0589 | 29.601 | 39.154 | 390.8139 | 0 | 566.6802
6 | 1BHK | 313.5553 | 29.601 | 39.154 | 382.3104 | 0 | 554.35
7 | 1BHK | 313.5553 | 29.601 | 39.154 | 382.3104 | 0 | 554.35
8 | 1BHK | 322.0589 | 29.601 | 39.154 | 390.8139 | 0 | 566.6802
9 | 1BHK | 336.0521 | 29.601 | 42.3832 | 408.0363 | 0 | 591.6527
10 | 1BHK | 322.0589 | 29.601 | 39.154 | 390.8139 | 0 | 566.6802
8th Floor For Residential (Part Refuge Area)
1 | 1BHK | 317.538 | 29.601 | 39.154 | 386.293 | 0 | 560.1249 | 8th Floor For Residential (Part Refuge Area) | 28.54 | 2.75 | 4.325
2 | 2BHK | 487.2863 | 29.601 | 61.3548 | 578.2421 | 0 | 838.451
3 | 1BHK | 322.0589 | 29.601 | 39.154 | 390.8139 | 0 | 566.6802
4 | - | Refuge Area
5 | 1BHK | 322.0589 | 29.601 | 39.154 | 390.8139 | 0 | 566.6802
6 | 1BHK | 313.5553 | 29.601 | 39.154 | 382.3104 | 0 | 554.35
7 | 1BHK | 313.5553 | 29.601 | 39.154 | 382.3104 | 0 | 554.35
8 | 1BHK | 322.0589 | 29.601 | 39.154 | 390.8139 | 0 | 566.6802
9 | 1BHK | 336.0521 | 29.601 | 42.3832 | 408.0363 | 0 | 591.6527
10 | 1BHK | 322.0589 | 29.601 | 39.154 | 390.8139 | 0 | 566.6802
48 | Phase, building & wingwise naming & numbering details |  |  |  | Wing C & D = Gr + 1st to 8th Floor Wing E & F = Gr + 1st to 8th Floor
49 | Phase, building, wing, unit wise pricing details (Base pricing, floor rise, location / view specific, etc) |  |  |  | Flats = 236
50 | Are there any deviations between the ongoing construction & the available plans & permissions. If yes, details are expected. |  |  |  | No
51 | Pricing comparisons ( Builder pricing v/s Resale v/s Nearby Projects with Rationale & justification ) |  |  |  | As per Site Details :
[5 empty] | Recommended rate of the flat Per Sq. Ft. (on Saleable area) |  |  | 4300
Recommended rate of the Shop Per Sq. Ft. (on Saleable area)
52 | Transaction documentation details ( Black / White percentages etc ) |  |  |  | No
53 | All details payable |  |  |  | As per Market Inquiry :
[5 empty] | Recommended rate of the flat Per Sq. Ft. (on Saleable area) |  |  | 4300
Recommended rate of the Shop Per Sq. Ft. (on Saleable area)
[5 empty] | Recommended rate of Parking |  |  | 150000
54 | Different types of payment schemes offered such as CLPP, TLPP, C & TLPP, Interest Subvention Plans etc |  |  |  | NA
55 | Schedule of Payment as per the developer |  |  |  | At Booking |  |  | NA
[5 empty] | Commecement |  |  | 20%
[5 empty] | Plinth |  |  | 15%
[5 empty] | 1st Slab |  |  | 5%
[5 empty] | 2nd Slab |  |  | 5%
[5 empty] | 3rd Slab |  |  | 5%
[5 empty] | 4th Slab |  |  | 5%
[5 empty] | 5th Slab |  |  | 5%
[5 empty] | Completion of Brick work |  |  | 5%
[5 empty] | Completion of Plaster work |  |  | 5%
[5 empty] | Completion of Water Proofing |  |  | 5%
[5 empty] | Completion of Flooring, Doors & Windows |  |  | 5%
[5 empty] | Painting, Electrical & Sanitary Fittings |  |  | 5%
[5 empty] | On Possession |  |  | 5%
[5 empty] | Total |  |  | 90%
56 | Are there any discrepancies in the legal / technical documentation that may affect the business interests of YBL? If yes, please elaborate. |  |  |  | None
57 | Any evidences of social disturbances at the project site that may affect the business interests of YBL? If yes, please elaborate. |  |  |  | None
58 | Any notices or boards of litigation at project site / developer office that may affect the business interests of YBL? If yes, please elaborate. |  |  |  | None
59 | Any further documentation that needs to be tracked by the Financial Institution & obtained from the customer / developer post project completion? Provide complete details. |  |  |  | None
60 | Declarations :-
(a) | Have you done APF technical for this project for any other Financial Institution? |  |  |  | None
(b) | Have you done evaluation of this project for the Project / Construction Finance perspective for any Financial Insitution? |  |  |  | No
Remarks:
1 | Wing C & E = Construction work is in process at the time of Visit (labour found). Wing D = All Work Completed. OC Received. Wing F = Work is not yet started.
2 | We considered Saleable area as per our calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Balcony + E.P. Area.
5 | We have considered rate by verifying it from market inquire.
6 | Car parking is subjected to authentic documentation.
7 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
8 | We have refered approved plans and CC from RERA site on 25/01/2024.
9 | We have refered Part OC for wing D, from RERA site on 11/09/2025.
10 | Please provide OC plans for Wing D dtd.30/05/2025
11 | We have added Eing E & F on 11/09/2025.
PHOTOGRAPHS OF PROPERTY : |  |  | PG Vatika (C to F Wing)
Layout
Google Map :
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
Name of Engineer Visited the property |  | Mr. Sudhir Bhosale |  | Authorized Signatory Name & Seal of the agency
WING D
WING D
WING D
WING C
WING D
WING C
WING B
WING A
WING F
WING E
WING F
WING E
WING E
WING D
WING C
WING F
Note on F19: Sachin: Name mentioned in initiation mail
Note on F21: Visit Date
Note on F22: Visitor Name
Note on F23: Visitor Name
Note on F25: mention it if provided by builder or else NA
Note on F31: Sachin: Authority Name
Note on F105: Sachin: Take from RERA
Note on F107: 2 School 2 Shopping Centre or mall 2 Hospital
Note on F108: 2 School 2 Shopping Centre or mall 2 Hospital
Note on F109: 2 School 2 Shopping Centre or mall 2 Hospital
Note on F110: 2 School 2 Shopping Centre or mall 2 Hospital
Note on F210: Proposed Structure