## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/09/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-09-12
Name of the builder group |  |  |  | Shraddha Landmark Private Limited
Name of the builder company |  |  |  | Shraddha Landmark Private Limited
Name of the Project |  |  |  | Shraddha Presidency
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Nilesh 9833733555
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Vighnesh |  |  |  | AS per Legel title | Kannamwar Nagar Saket CHS Ltd.
Name / No of the Building |  |  |  | Wing A, B & C |  |  |  |  | Kannamwar Nagar Prerna CHS Ltd.
Name / No of the Existing Building |  |  |  | Building No 26, 27, 28 & 29 Known as Kannamwar Nagar Janhavi CHS Ltd. |  |  |  |  | Kannamwar Nagar Kalpavruksh CHS Ltd. |  | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plan |  |  |  |  | Kannamwar Nagar Janhavi CHS Ltd. |  | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800050356 |  |  |  | #N/A |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Shraddha Presidency, CTS No.356(pt.), S. No. 113(Pt.), Redevlopement of "Building No 26, 27, 28 & 29 Known as Kannamwar Nagar Janhavi CHS Ltd.", near Shushrusha Hospital, Aatmaram Surve Marg, Kannamwar Nagar, Hariyali, Vikhroli East, Kurla, Mumbai - 400083. | [8 empty] | Kalyan | Vasai | Kurla | Uran | Khed
CTS No |  | 356(pt.), S. No. 113(Pt.), Redevlopement of "Building No 26, 27, 28 & 29 Known as Kannamwar Nagar Janhavi CHS Ltd." | [8 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Kannamwar Nagar | [8 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Aatmaram Surve Marg |  | Locality/Village |  | Hariyali |  |  |  |  | Ambernath | Dahanu |  | Pen | Shirur
City |  | Vikhroli East |  | District |  | Mumbai |  |  |  |  | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Kurla |  | Pin Code |  | 400083 | [7 empty] | Mahad | Daund
Nearby Landmark |  | Shushrusha Hospital |  | Distance from city centre: |  | 1.00KM from Vikhroli Railway Station | [7 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [9 empty] | Mangaon | Ambegaon
[14 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [9 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [9 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [9 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | 18.30 M. Wide Road |  |  | Road Number 1
West | NA | 12.20 M. Wide Road |  |  | Aatmaram Surve Marg
North | NA | Building No 24 & 25 |  |  | Vrindavan CHS, Building 24
South | NA | 12.20 M. Wide Road |  |  | Road Number 1
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.112747,72.934752
Location Link |  | https://maps.app.goo.gl/T3hQJEJybn9S3Nbs8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2310.38
Permissible FSI |  |  |  | 3 |  |  |  | zero FSI Approval in C.C |  | 3
Permissible TDR/Paid FSI |  |  |  | 3.1222 |  |  |  | 3.1222
Total FSI availaible for the project |  |  |  | 6.1222 |  |  |  | 6.1222
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 14144.61
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority (MHADA)
Layout Approval No |  | Mhada-9/1242/2024 |  |  | Dated | 2024-01-18 |  | Plan & C.C From Rera
Approved Floor plan No. |  | Mhada-9/1242/2024 |  |  | Dated | 2024-01-18
Commencement-CC No Valid Up to: |  | MH/EE/(BP)/GM/MHADA-9/1242/2024/FCC/1/New |  |  | Dated | 2024-04-04
|  | This C.C. is further extended upto top of 7th floor of Wing A, B & C (i.e. Stilt (pt) for parking & 1st Part floor for Residential use + 2nd to 7th upper residential floors) as per approved amended plans dtd. 18.01.2024. |  |  | Valid Upto Date | 2025-03-02
|  | MH/EE/(BP)/GM/MHADA-9/1242/2024/FCC/1/Amend |  |  | Dated | 2024-12-04
|  | This C.C. is further extended upto top of 11th floor of Wing A, B & C (i.e. Stilt (pt) for parking + 1st Part floor for Residential use + 2nd to 11th upper residential floors) as per approved amended plans dtd. 18.01.2024. |  |  | Valid Upto Date | 2025-03-02
|  | MH/EE/(BP)/GM/MHADA-9/1242/2025/FCC/2/Amend |  |  | Dated | 2025-05-20
|  | This C.C. is further extended upto top of 19th floor of Wing A & B & upto top of 18th floor of Wing C as per approved amended plans dtd. 18.01.2024. |  |  | Valid Upto Date | 2026-03-02
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 14144.61 |  |  |  |  | 14144.61
Approved no of units |  |  | Flats - 303 |  |  |  |  | Flats -, Shops -, Offices -
Approved no of Floors |  |  | Wing A, B, & C = Gr + 1st to 21st Floor
Proposed no of Floors |  |  | Wing A, B, & C = Gr + 1st to 21st Floor
B Wing = 1B + G + 1st to 20th Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Jogging Track, Childrens Play Area, Indoor Games, Podium Garden, Gymnasium, Decorative Entrance, etc. |  |  |  |  | https://www.shraddhalandmark.com/shraddha-presidency.php
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A, B, & C = Gr + 1st to 21st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 17 Slab, Brickwork upto 16 Floor, Internal Plaster upto 12 Floor, External Plaster upto 10.4 Floor Completed | , RCC upto 17 Slab, Brickwork upto 16 Floor, Internal Plaster upto 12 Floor, External Plaster upto 10.4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 21 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 17 Slab, Brickwork upto 16 Floor, Internal Plaster upto 12 Floor, External Plaster upto 10.4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.25
Excavation |  | 21 | 100% | 55.86% |  | 77.32% |  | Excavation in process | 10.5
Plinth |  | 21 | 100% |  |  |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 17 | 77.27% |  |  |  |  | Footing in Process | 5.25
Brickwork | Brickwork & Internal Plaster | 16 | 76.19% |  |  |  |  | Footing Completed | 10.5
Internal Plaster | Brickwork & Internal Plaster | 12 | 57.14% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 10.4 | 49.52% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 21
Construction details: |  | B Wing = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 10% |  | 45% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | C Wing = 1B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 13000
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges
Club Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 600000
Distressed valuation of the Property |  |  |  |  | 10400
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 101 |  | 62642.282 |  | 93963.4231
Wing B |  | 100 |  | 37227.294 |  | 55840.941
Wing C |  | 102 |  | 38488.8348 |  | 57733.2522
Total |  | 303 |  | 138358.4108 |  | 207537.6163
Grand Total |  | 303 |  | 138358.4108 |  | 207537.6163
Building details Floor Wise
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Ground Floor
1 |  |  |  | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Dry Yard Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Wing A
Ground Floor for Parking & Entrance Lobby
1 |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
1st Floor for Residential, Fitness Center & Recreational Area
101 |  | Fitness Center
102 |  | 2BHK | 655.9582 | 24.7572 | 680.7154 | 0 | 1021.073 |  | 10.764
103 |  | 1BHK | 389.7644 | 0 | 389.7644 | 0 | 584.6467
104 |  | 2BHK | 655.9582 | 24.7572 | 680.7154 | 0 | 1021.073
105 |  | Fitness Center
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 0 | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 0 | 0
2nd to 6th, 8th to 13th, 15th to 21st Floor
201 to 2101 |  | 2BHK | 655.9582 | 24.7572 | 680.7154 | 0 | 1021.073
202 to 2102 |  | 2BHK | 655.9582 | 24.7572 | 680.7154 | 0 | 1021.073
203 to 2103 |  | 1BHK | 389.7644 | 0 | 389.7644 | 0 | 584.6467
204 to 2104 |  | 2BHK | 655.9582 | 24.7572 | 680.7154 | 0 | 1021.073
205 to 2105 |  | 2BHK | 655.9582 | 24.7572 | 680.7154 | 0 | 1021.073
7th Floor (Part Refuge Area)
701 |  | 2BHK | 655.9582 | 24.7572 | 680.7154 | 0 | 1021.073
702 |  | 2BHK | 655.9582 | 24.7572 | 680.7154 | 0 | 1021.073 |  | 10.764
703 |  | 1BHK | 389.7644 | 0 | 389.7644 | 0 | 584.6467
704 |  | Refuge Area
705 |  | 2BHK | 655.9582 | 24.7572 | 680.7154 | 0 | 1021.073
14th Floor (Part Refuge Area)
1401 |  | 2BHK | 655.9582 | 24.7572 | 680.7154 | 0 | 1021.073
1402 |  | 2BHK | 655.9582 | 24.7572 | 680.7154 | 0 | 1021.073 |  | 10.764
1403 |  | 1BHK | 389.7644 | 0 | 389.7644 | 0 | 584.6467
1404 |  | Refuge Area
1405 |  | 2BHK | 655.9582 | 24.7572 | 680.7154 | 0 | 1021.073
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0
202 & 502 |  |  |  | 0 | 0 | 0 | 0
203 & 503 |  |  |  | 0 | 0 | 0 | 0
204 & 504 |  |  |  | 0 | 0 | 0 | 0
205 & 505 |  |  |  | 0 | 0 | 0 | 0
Wing B
Ground Floor for Parking & Entrance Lobby
1st Floor for Residential, Fitness Center & Recreational Area
101 |  | 1BHK | 354.9967 | 0 | 354.9967 | 0 | 532.4951
102 |  | 1BHK | 380.938 | 0 | 380.938 | 0 | 571.4069
103 |  | 1BHK | 374.5872 | 0 | 374.5872 | 0 | 561.8808
104 |  | 1BHK | 374.4796 | 0 | 374.4796 | 0 | 561.7193
105 |  | Fitness Center
2nd to 6th, 8th to 13th, 15th to 21st Floor
201 to 2101 |  | 1BHK | 354.9967 | 0 | 354.9967 | 0 | 532.4951
202 to 2102 |  | 1BHK | 380.938 | 0 | 380.938 | 0 | 571.4069
203 to 2103 |  | 1BHK | 374.5872 | 0 | 374.5872 | 0 | 561.8808
204 to 2104 |  | 1BHK | 374.4796 | 0 | 374.4796 | 0 | 561.7193
205 to 2105 |  | 1BHK | 389.7644 | 0 | 389.7644 | 0 | 584.6467
7th Floor (Part Refuge Area)
701 |  | Refuge Area
702
703 |  | 1BHK | 374.5872 | 0 | 374.5872 | 0 | 561.8808
704 |  | 1RK | 233.9017 | 0 | 233.9017 | 0 | 350.8526
705 |  | 1BHK | 389.7644 | 0 | 389.7644 | 0 | 584.6467
14th Floor (Part Refuge Area)
1401 |  | Refuge Area
1402
1403 |  | 1BHK | 374.5872 | 0 | 374.5872 | 0 | 561.8808
1404 |  | 1RK | 233.9017 | 0 | 233.9017 | 0 | 350.8526
1405 |  | 1BHK | 389.7644 | 0 | 389.7644 | 0 | 584.6467
Wing C
Ground Floor for Parking & Entrance Lobby
1st Floor for Residential, Society Office & Recreational Area
101 |  | Society Office
102 |  | 1BHK | 374.5872 | 0 | 374.5872 | 0 | 561.8808
103 |  | 1BHK | 374.5872 | 0 | 374.5872 | 0 | 561.8808
104 |  | 1BHK | 374.049 | 0 | 374.049 | 0 | 561.0735
105 |  | 1BHK | 374.049 | 0 | 374.049 | 0 | 561.0735
2nd to 6th, 8th to 13th, 15th to 21st Floor
201 to 2101 |  | 1BHK | 389.7644 | 0 | 389.7644 | 0 | 584.6467
202 to 2102 |  | 1BHK | 374.5872 | 0 | 374.5872 | 0 | 561.8808
203 to 2103 |  | 1BHK | 374.5872 | 0 | 374.5872 | 0 | 561.8808
204 to 2104 |  | 1BHK | 374.049 | 0 | 374.049 | 0 | 561.0735
205 to 2105 |  | 1BHK | 374.049 | 0 | 374.049 | 0 | 561.0735
7th Floor (Part Refuge Area)
701 |  | 1BHK | 389.7644 | 0 | 389.7644 | 0 | 584.6467
702 |  | Refuge Area
703 |  | 1BHK | 374.5872 | 0 | 374.5872 | 0 | 561.8808
704 |  | 1BHK | 374.049 | 0 | 374.049 | 0 | 561.0735
705 |  | 1BHK | 374.049 | 0 | 374.049 | 0 | 561.0735
14th Floor (Part Refuge Area)
1401 |  | 1BHK | 389.7644 | 0 | 389.7644 | 0 | 584.6467
1402 |  | Refuge Area
1403 |  | 1BHK | 374.5872 | 0 | 374.5872 | 0 | 561.8808
1404 |  | 1BHK | 374.049 | 0 | 374.049 | 0 | 561.0735
1405 |  | 1BHK | 374.049 | 0 | 374.049 | 0 | 561.0735
Remarks:
* | Construction work is in process at the time of Visit. Internal Visit was not allowed. (Slow Speed)
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Dry Yard Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | We have updated Approved Plans from Mhada Site (on 29/03/2024)
* | We have Refered Approved C.C. & Layout Plan from Mhada Site (on 29/03/2024)
* | We have updated latest CC from Mhada site (On 12/06/2024 & 19/03/2025).
* | We have updated latest CC from Mhada site (On 06/06/2025).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sagar Naresh Katale |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Shraddha Presidency
Layout :
Google Map :
Formulas:
Hariyali = [Hariyali, row above]
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D59: Sachin: If multiple building in project or complex just mention builtup of required building
Wing A
Wing B
Wing A
Wing C
Wing B

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC