## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 16/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Goregaon | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-09-15 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | A.M Enterprises | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | A.M Enterprises | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Aim Horizon | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | 8692902585 / 9702103699
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Rohan
Name / No of the Building |  |  |  | Sale Wing A & Rehab Wing B
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800047046 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Aim Horizon, CTS No.280, 280/1 to 13, 281, 281/1 to 20, near Anant Nandadeep Co Op Hsg Society, Internal Road, , Mogra, Jogeshwari (East), Andheri, Mumbai - 400060. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
CTS No |  | 280, 280/1 to 13, 281, 281/1 to 20 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | NA | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Road |  | Locality/Village |  | Mogra | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Jogeshwari (East) |  | District |  | Mumbai | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Andheri |  | Pin Code |  | 400060 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Anant Nandadeep Co Op Hsg Society |  | Distance from city centre: |  | 1KM from Jogeshwari Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Other Plot |  |  | Trimurti Society
West | NA | Other Plot |  |  | Laxmi Narayan Apartment
North | NA | 9.15 M Wide Road |  |  | Road
South | NA | Other Plot |  |  | Anant Nandadeep Co Op Hsg Society
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.130327,72.853136
Location Link |  | https://maps.app.goo.gl/FWWDg6LfkoCrVzjV7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 916.8
Permissible FSI |  |  |  | 4
Permissible TDR/Paid FSI |  |  |  | 1.3688
Total FSI availaible for the project |  |  |  | 5.3688
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 4922.09 |  |  |  | 0.18626
Total number of Buildings |  |  |  | 02 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Slum Rehabilitation Authority (SRA) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | KE/PVT/0252/20201103/AP/C |  |  | Dated | 2023-10-09 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | KE/PVT/0252/20201103/AP/C |  |  | Dated | 2023-10-09 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | KE/PVT/0252/20201103/AP/C |  |  | Dated | 2023-06-07 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | This CC is further extended for Rehab wing B from 1st floor to 18th floor & 19 th (Pt) Floor including O.H.W.T & L.M.R and for sale wing A from 1st floor to 9th Floor & R.C.C frame work from 10th Floor to 12th Floor & 13th (Pt) Floor as per approved plan dated 25/07/2022 |  |  | Valid Upto Date | [11 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  |  |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 4922.09
Approved no of units |  |  | Flats - 90, Shops - 6
Approved no of Floors |  |  | Sale Wing A = Gr + 1st to 13th Floor Rehab Wing B = Gr + 1st to 19th Floor
Proposed no of Floors |  |  | Sale Wing A = Gr + 1st to 19th Floor
Rehab Wing B = Gr + 1st to 19th Floor
C Wing = 1B + G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 31/12/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Rain Water Harvesting, Sewage treatment plant, Aesthetically designed landscape garden, Fire Fighting Equipment
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Sale Wing A = Gr + 1st to 19th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 17 Floor, Painting upto 17 Floor, Finishing upto 3 Floor Completed | , Flooring upto 17 Floor, Painting upto 17 Floor, Finishing upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 17 Floor, Painting upto 17 Floor, Finishing upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% | 89.21% |  | 94.47% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% |  |  |  |  | Excavation Completed | 19
RCC (Including podiums) |  | 20 | 100% |  |  |  |  | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 19 | 100% |  |  |  |  | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 19 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 19 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 17 | 89.47% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 17 | 89.47% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 15.79% |  |  |  |  | Plinth in process | 14.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 19
Construction details: |  | Rehab Wing B = Gr + 1st to 19th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 17 Floor, Painting upto 17 Floor, Finishing upto 3 Floor Completed | , Flooring upto 17 Floor, Painting upto 17 Floor, Finishing upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 19 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 17 Floor, Painting upto 17 Floor, Finishing upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4.75
Excavation |  | 19 | 100% | 89.21% |  | 94.47% |  | Excavation in process | 9.5
Plinth |  | 19 | 100% |  |  |  |  | Excavation Completed | 19
RCC (Including podiums) |  | 20 | 100% |  |  |  |  | Footing in Process | 4.75
Brickwork | Brickwork & Internal Plaster | 19 | 100% |  |  |  |  | Footing Completed | 9.5
Internal Plaster | Brickwork & Internal Plaster | 19 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 19 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 17 | 89.47% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 17 | 89.47% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 15.79% |  |  |  |  | Plinth in process | 14.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 19
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 18000 | [11 empty] | 800000 | 300000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 35000 | [11 empty] | 900000 | 350000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 400000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 500000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 600000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 700000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 800000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 900000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 1000000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000
Recommended rate of Parking |  |  |  |  | 600000 | [11 empty] | 1800000
Distressed valuation of the Property |  |  |  |  | 14400
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | Builder sheet | Sheet | Housing | Magic Brick
Sale Wing A |  | 3 |  | 408.4938 |  | 633.1654 |  | 18000 to 20000 | 250000 | 16077.8942 | 18076.4572
Rehab Wing B |  | 3 |  | 538.6306 |  | 834.8774 |  |  |  | 16008.0043 | 18175.0108
Total |  | 6 |  | 947.1244 |  | 1468.0428 |  |  |  | 16042.9492 | 15883.9112
Residential Area Details : | [10 empty] | 17378.4598
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Sale Wing A |  | 55 |  | 23898.0175 |  | 35847.0263
Rehab Wing B |  | 35 |  | 10503.5112 |  | 15755.2668 |  | Sale Plan
Total |  | 90 |  | 34401.5287 |  | 51602.2931 |  | https://jannathomes.com/uploads/projects/floor_plan////28619c596bb7d21f8c048deb7f744ec7.pdf
Grand Total |  | 96 |  | 35348.6531 |  | 53070.3358 |  | https://www.99acres.com/aim-horizon-jogeshwari-east-mumbai-andheri-dahisar-npxid-r399437
Building details Floor Wise | [7 empty] | https://www.magicbricks.com/aim-horizon-jogeshwari-east-mumbai-pdpid-4d4235333337303237
Details of Residential & Commercials in Building | [7 empty] | https://housing.com/in/buy/projects/page/285887-aim-horizon-by-aim-realtors-in-jogeshwari-east
Shop No. (Approved Plan) | Sale / Rehab | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
55%
Sale Wing A
Ground Floor for Commercial
1 |  | Shop | 166.3038 | 0 | 166.3038 | 0 | 257.7709
2 | Sale | Shop | 107.8553 | 0 | 107.8553 | 0 | 167.1757
3 | Sale | Shop | 134.3347 | 0 | 134.3347 | 0 | 208.2188 | 10.764
Rehab Wing B
Ground Floor for Commercial
1 | Rehab | Shop | 113.022 | 0 | 113.022 | 0 | 175.1841
2 | Rehab | Shop | 212.4814 | 0 | 212.4814 | 0 | 329.3461
3 | Rehab | Shop | 213.1272 | 0 | 213.1272 | 0 | 330.3472 | 10.764
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Sale Wing A
1st Floor for Residential
1 |  | Fitness Center
2 |  | Society Office |  | 0 | 0 | 0 | 0
3 |  | 2BHK | 537.2312 | 0 | 537.2312 | 0 | 805.8469
4 |  | 2BHK | 544.4431 | 0 | 544.4431 | 0 | 816.6647 | 63.6421
5 |  | Society Office |  | 0 | 0 | 0 | 0
2nd & 3rd Floor
1 |  | 1BHK | 435.1885 | 0 | 435.1885 | 0 | 652.7828
2 |  | 1BHK | 396.2228 | 0 | 396.2228 | 0 | 594.3343
3 |  | 2BHK | 537.2312 | 0 | 537.2312 | 0 | 805.8469
4 |  | 1BHK | 447.3518 | 0 | 447.3518 | 0 | 671.0278
5 |  | Other Amenity
4th to 7th, 9th to 12th Floor
1 |  | 1BHK | 435.1885 | 0 | 435.1885 | 0 | 652.7828
2 |  | 1BHK | 396.2228 | 0 | 396.2228 | 0 | 594.3343
3 |  | 2BHK | 537.2312 | 0 | 537.2312 | 0 | 805.8469
4 |  | 1BHK | 381.4762 | 0 | 381.4762 | 0 | 572.2142
5 |  | 1BHK | 381.4762 | 0 | 381.4762 | 0 | 572.2142
8th Floor for part Refuge Area
1 |  | 1BHK | 435.1885 | 0 | 435.1885 | 0 | 652.7828
2 |  | 1BHK | 396.2228 | 0 | 396.2228 | 0 | 594.3343
3 |  | 2BHK | 537.2312 | 0 | 537.2312 | 0 | 805.8469
4 |  | Refuge Area
5
13th Floor (Part Terrace)
1 |  | Terrace Area
2
3
4 |  | 1BHK | 381.4762 | 0 | 381.4762 | 0 | 572.2142
5 |  | 1BHK | 381.4762 | 0 | 381.4762 | 0 | 572.2142
Rehab Wing B
1st Floor for Residential
1 |  | Balwadi
2 |  | Welfare Center
2nd & 3rd Floor
1 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505 | 10.764
2 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505
4th to 7th, 9th to 12th Floor
1 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505
2 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505
8th Floor for (Part Refuge Area)
1 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505
2 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505
13th Floor
1 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505
2 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505
14th Floor
1 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505
2 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505
15th Floor for (Part Refuge Area)
1 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505
2 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505
16th to 18th Floor
1 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505
2 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505
19th Floor (Part Terrace Area)
1 |  | Terrace Area
2 |  | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 450.1505
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Environment Clearance Certificate.
* | Please provide revised CC & approved floor plans.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Pratik Niwate |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Aim Horizon
Layout :
Google Map :
Formulas:
Mogra = [Mogra, row above]
Sale Wing A
Rehab Wing B
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F108: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H143: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14
15
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate