## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 17/09/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-09-15
Name of the builder group |  |  |  | M/s. Jay Ganesh Developers
Name of the builder company |  |  |  | M/s. Jay Ganesh Developers
Name of the Project |  |  |  | Kalas Darshan
Contact Details ( Name & Contact No.) |  |  |  | Mr. Samir Lohi 9225220555
Name / No of the Building |  |  |  | Tower 1 To 8
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet.
RERA No. |  |  |  | P51700034000
Project location details |  | Kalash Darshan, Proposed affordable housing under pradhan mantri awas yojna on private land bearing Gut No.7/1, 7/2, 7/3, 73/2/A, 73/4/A, 73/4/B, 73/4/C, 73/5/A at Titwala East, Mumbai, Maharashtra.
Gut No |  | 7/1, 7/2, 7/3, 73/2/A, 73/4/A, 73/4/B, 73/4/C, 73/5/A
Locality |  | Titwala
Road |  | Internal Rd |  | Village |  | Titwala
City |  | Kalyan |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 621605
Nearby Landmark |  | MTDC Titwala East |  | Distance from city centre: |  | 2.7KM from Titwala Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | MTDC titwala
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.2992 |  | Longitude |  | 73.226
Location Link |  | https://goo.gl/maps/y1gcZ3bGDV2buCSM7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 38974.16
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.6
Total FSI availaible for the project |  |  |  | 1.6
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 62358.66
Total number of Buildings |  |  |  | 08 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | MHADA
Layout Approval No |  | EE/BP/PMAY/A/MHADA/117/2022 |  |  | Dated | 2022-03-23
Approved Floor plan No. |  | EE/BP/PMAY/A/MHADA/117/2022 |  |  | Dated | 2022-03-23
Commencement-CC No |  | EE/BP/PMAY/A/MHADA/602/2023 |  |  | Dated | 2023-07-25
Building No.2 & 3 = Gr + 1st to 8th Floor Building No.4, 5 & 6 = Gr + 1st to 9th Floor Building No.7 = Gr + 1st to 7th Floor
Commencement-CC No (For Building No. 1 & 8) Valid Upto: |  | AMVBPK/PMAY/207/2022 |  |  | Dated | 2022-04-28
Plinth Level
Commencement-CC No |  | EE/BP/PMAY/A/MHADA/830/2023 |  |  | Dated | 2023-10-30
Building No. 1 = Gr + 1st to 8th Floor
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 62358.66
Approved no of units |  |  | Flats -1381
Approved no of Floors |  |  | Tower 1, 2, 3 - Gr + 1st to 8th Floor Tower 4, 5, 6 & 8 - Gr + 1st to 9th Floor Tower 7 - Gr + 1st to 7th Floor
Proposed no of Floors |  |  | Tower 1 = Gr + 1st to 8th Floor
Tower 2 = Gr + 1st to 8th Floor
Tower 3 = Gr + 1st to 8th Floor
Tower 4 = Gr + 1st to 9th Floor
Tower 5 = Gr + 1st to 9th Floor
Tower 6 = Gr + 1st to 9th Floor
Tower 7 = Gr + 1st to 7th Floor
Tower 8 = Gr + 1st to 9th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Tower 1 = Gr + 1st to 8th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 7 Floor, Painting upto 4.5 Floor Completed | , Flooring upto 7 Floor, Painting upto 4.5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 8 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 7 Floor, Painting upto 4.5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2
Excavation |  | 8 | 100% | 86.56% |  | 94.38% |  | Excavation in process | 4
Plinth |  | 8 | 100% |  |  |  |  | Excavation Completed | 8
RCC (Including podiums) |  | 9 | 100% |  |  |  |  | Footing in Process | 2
Brickwork | Brickwork & Internal Plaster | 8 | 100% |  |  |  |  | Footing Completed | 4
Internal Plaster | Brickwork & Internal Plaster | 8 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 87.5% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4.5 | 56.25% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 6
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 8
Construction details: |  | Tower 2 & 3 = Gr + 1st to 8th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 7 Floor, Painting upto 7 Floor, Finishing upto 2 Floor Completed | , Flooring upto 7 Floor, Painting upto 7 Floor, Finishing upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 8 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 7 Floor, Painting upto 7 Floor, Finishing upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2
Excavation |  | 8 | 100% | 89.38% |  | 94.38% |  | Excavation in process | 4
Plinth |  | 8 | 100% |  |  |  |  | Excavation Completed | 8
RCC (Including podiums) |  | 9 | 100% |  |  |  |  | Footing in Process | 2
Brickwork | Brickwork & Internal Plaster | 8 | 100% |  |  |  |  | Footing Completed | 4
Internal Plaster | Brickwork & Internal Plaster | 8 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 87.5% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 87.5% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 25% |  |  |  |  | Plinth in process | 6
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 8
Construction details: |  | Tower 3 = Gr + 1st to 8th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 7 Floor, Flooring upto 7 Floor, Painting upto 6 Floor, Finishing upto 2 Floor Completed | , External Plaster upto 7 Floor, Flooring upto 7 Floor, Painting upto 6 Floor, Finishing upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 8 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 7 Floor, Flooring upto 7 Floor, Painting upto 6 Floor, Finishing upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2
Excavation |  | 8 | 100% | 87.5% |  | 93.75% |  | Excavation in process | 4
Plinth |  | 8 | 100% |  |  |  |  | Excavation Completed | 8
RCC (Including podiums) |  | 9 | 100% |  |  |  |  | Footing in Process | 2
Brickwork | Brickwork & Internal Plaster | 8 | 100% |  |  |  |  | Footing Completed | 4
Internal Plaster | Brickwork & Internal Plaster | 8 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 87.5% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 87.5% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 6 | 75% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 25% |  |  |  |  | Plinth in process | 6
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 8
Construction details: |  | Tower 4 = Gr + 1st to 9th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 8 Floor, Flooring upto 5 Floor, Painting upto 3 Floor Completed | , External Plaster upto 8 Floor, Flooring upto 5 Floor, Painting upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 9 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 8 Floor, Flooring upto 5 Floor, Painting upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.25
Excavation |  | 9 | 100% | 81.11% |  | 92.22% |  | Excavation in process | 4.5
Plinth |  | 9 | 100% |  |  |  |  | Excavation Completed | 9
RCC (Including podiums) |  | 10 | 100% |  |  |  |  | Footing in Process | 2.25
Brickwork | Brickwork & Internal Plaster | 9 | 100% |  |  |  |  | Footing Completed | 4.5
Internal Plaster | Brickwork & Internal Plaster | 9 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 8 | 88.89% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 55.56% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 33.33% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 6.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 9
Construction details: |  | Tower 5 = Gr + 1st to 9th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 7 Floor, Painting upto 5 Floor Completed | , Flooring upto 7 Floor, Painting upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 9 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 7 Floor, Painting upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.25 | T5 DISBURSEMENT 93 % by AKASH MOTE on 31/07/2025
Excavation |  | 9 | 100% | 85.56% |  | 93.89% |  | Excavation in process | 4.5
Plinth |  | 9 | 100% |  |  |  |  | Excavation Completed | 9
RCC (Including podiums) |  | 10 | 100% |  |  |  |  | Footing in Process | 2.25
Brickwork | Brickwork & Internal Plaster | 9 | 100% |  |  |  |  | Footing Completed | 4.5
Internal Plaster | Brickwork & Internal Plaster | 9 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 77.78% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 55.56% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 6.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 9
Construction details: |  | Part II = Tower 5 = Gr + 1st to 9th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 3 Floor, External Plaster upto 1 Floor Completed | , Internal Plaster upto 3 Floor, External Plaster upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 9 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 3 Floor, External Plaster upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.25
Excavation |  | 9 | 100% | 61.11% |  | 82.22% |  | Excavation in process | 4.5
Plinth |  | 9 | 100% |  |  |  |  | Excavation Completed | 9
RCC (Including podiums) |  | 10 | 100% |  |  |  |  | Footing in Process | 2.25
Brickwork | Brickwork & Internal Plaster | 9 | 100% |  |  |  |  | Footing Completed | 4.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 33.33% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 1 | 11.11% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 6.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 9
Average Progress % |  | 73.33% |  | Average Disbursement % |  | 88.06%
Construction details: |  | Tower 6 = Gr + 1st to 9th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 7 Floor, Flooring upto 4 Floor, Painting upto 3 Floor Completed | , External Plaster upto 7 Floor, Flooring upto 4 Floor, Painting upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 9 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 7 Floor, Flooring upto 4 Floor, Painting upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.25
Excavation |  | 9 | 100% | 78.89% |  | 91.11% |  | Excavation in process | 4.5
Plinth |  | 9 | 100% |  |  |  |  | Excavation Completed | 9
RCC (Including podiums) |  | 10 | 100% |  |  |  |  | Footing in Process | 2.25
Brickwork | Brickwork & Internal Plaster | 9 | 100% |  |  |  |  | Footing Completed | 4.5
Internal Plaster | Brickwork & Internal Plaster | 9 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 77.78% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 44.44% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 33.33% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 6.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 9
Construction details: |  | Tower 7 = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 6 Floor, Finishing upto 2 Floor Completed | , Painting upto 6 Floor, Finishing upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 6 Floor, Finishing upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 90.71% |  | 95% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 6 | 85.71% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 28.57% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Tower 8 = Gr + 1st to 9th Floor | [5 empty] | Excavation Completed, Footing work is process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 9 | Excavation | , Footing work is process
Stage of construction: |  | Excavation Completed, Footing work is process | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.25
Excavation |  | 9 | 100% | 2.5% |  | 26.25% |  | Excavation in process | 4.5
Plinth |  | 2.25 | 25% |  |  |  |  | Excavation Completed | 9
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 2.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 4.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 6.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 9
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3600 |  |  | 3400 to 3600 | OC Charges | Rushikesh | 2023-10-13
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges |  |  |  |  | 10000
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection & Development Charges |  |  |  |  | 150000
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking
Distressed valuation of the Property |  |  |  |  | 2880
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower 1, 2 & 3 |  | 321 |  | 120595.4331 |  | 174863.378
Tower 4 |  | 198 |  | 74364.827 |  | 107828.9992
Tower 5, 6 |  | 536 |  | 201163.5737 |  | 291687.1819
Tower 7 |  | 88 |  | 33041.7772 |  | 47910.5769
Tower 8 |  | 238 |  | 89311.233 |  | 129501.2879
Total |  | 1381 |  | 518476.844 |  | 751791.4238
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
5 |  |  |  | 0 | 0 | Ground Floor
6 |  |  |  | 0 | 0 | Ground Floor
7 |  |  |  | 0 | 0 | Ground Floor
8 |  |  |  | 0 | 0 | Ground Floor
9 |  |  |  | 0 | 0 | Ground Floor
10 |  |  |  | 0 | 0 | Ground Floor
11 |  |  |  | 0 | 0 | Ground Floor
12 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
Tower 1, 2 & 3
Ground Floor For Residential
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | Ground Floor For Residential
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | 1BHK | 374.4699 | 0 | 542.9813
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 377.9994 | 0 | 548.0991
7 |  | 1BHK | 377.9994 | 0 | 548.0991
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 374.4699 | 0 | 542.9813
10 |  | 1BHK | 374.528 | 0 | 543.0656
11 |  | 1BHK | 374.528 | 0 | 543.0656
12 |  | 1BHK | 377.9994 | 0 | 548.0991
1st to 6th & 8th Floor
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | 1st to 6th & 8th Floor
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | 1BHK | 374.4699 | 0 | 542.9813
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 377.9994 | 0 | 548.0991
7 |  | 1BHK | 377.9994 | 0 | 548.0991
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 374.4699 | 0 | 542.9813
10 |  | 1BHK | 374.528 | 0 | 543.0656
11 |  | 1BHK | 374.528 | 0 | 543.0656
12 |  | 1BHK | 377.9994 | 0 | 548.0991
7th Floor (Part Refuge Area)
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | 7th Floor (Part Refuge Area)
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | Refuge Area
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 377.9994 | 0 | 548.0991
7 |  | 1BHK | 377.9994 | 0 | 548.0991
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 374.4699 | 0 | 542.9813
10 |  | 1BHK | 374.528 | 0 | 543.0656
11 |  | 1BHK | 374.528 | 0 | 543.0656
12 |  | 1BHK | 377.9994 | 0 | 548.0991
Tower 4
Ground Floor For Residential
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | Ground Floor For Residential
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | 1BHK | 374.528 | 0 | 543.0656
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 374.528 | 0 | 543.0656
7 |  | 1BHK | 374.528 | 0 | 543.0656
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 377.9994 | 0 | 548.0991
10 |  | 1BHK | 377.9994 | 0 | 548.0991
11 |  | 1BHK | 374.528 | 0 | 543.0656
12 |  | 1BHK | 374.528 | 0 | 543.0656
13 |  | 1BHK | 374.528 | 0 | 543.0656
14 |  | 1BHK | 377.9994 | 0 | 548.0991
15 |  | 1BHK | 377.9994 | 0 | 548.0991
16 |  | 1BHK | 374.528 | 0 | 543.0656
17 |  | 1BHK | 374.528 | 0 | 543.0656
18 |  | 1BHK | 374.528 | 0 | 543.0656
19 |  | 1BHK | 374.528 | 0 | 543.0656
20 |  | 1BHK | 377.9994 | 0 | 548.0991
1st to 7th & 9th Floor
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | 1st to 7th & 9th Floor
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | 1BHK | 374.528 | 0 | 543.0656
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 374.528 | 0 | 543.0656
7 |  | 1BHK | 374.528 | 0 | 543.0656
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 377.9994 | 0 | 548.0991
10 |  | 1BHK | 377.9994 | 0 | 548.0991
11 |  | 1BHK | 374.528 | 0 | 543.0656
12 |  | 1BHK | 374.528 | 0 | 543.0656
13 |  | 1BHK | 374.528 | 0 | 543.0656
14 |  | 1BHK | 377.9994 | 0 | 548.0991
15 |  | 1BHK | 377.9994 | 0 | 548.0991
16 |  | 1BHK | 374.528 | 0 | 543.0656
17 |  | 1BHK | 374.528 | 0 | 543.0656
18 |  | 1BHK | 374.528 | 0 | 543.0656
19 |  | 1BHK | 374.528 | 0 | 543.0656
20 |  | 1BHK | 377.9994 | 0 | 548.0991
8th Floor (Part Refuge Area)
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | 1BHK | 374.528 | 0 | 543.0656
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 374.528 | 0 | 543.0656
7 |  | 1BHK | 374.528 | 0 | 543.0656
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 377.9994 | 0 | 548.0991
10 |  | 1BHK | 377.9994 | 0 | 548.0991
11 |  | 1BHK | 374.528 | 0 | 543.0656
12 |  | 1BHK | 374.528 | 0 | 543.0656
13 |  | 1BHK | 374.528 | 0 | 543.0656
14 |  | 1BHK | 377.9994 | 0 | 548.0991
15 |  | 1BHK | 377.9994 | 0 | 548.0991
16 |  | Refuge Area
17
18 |  | 1BHK | 374.528 | 0 | 543.0656
19 |  | 1BHK | 374.528 | 0 | 543.0656
20 |  | 1BHK | 377.9994 | 0 | 548.0991
Tower 5 & 6
Ground Floor For Residential
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | Ground Floor For Residential
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | 1BHK | 377.9994 | 0 | 548.0991
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 374.528 | 0 | 543.0656
7 |  | 1BHK | 374.528 | 0 | 543.0656
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 374.528 | 0 | 543.0656
10 |  | 1BHK | 374.528 | 0 | 543.0656
11 |  | 1BHK | 374.528 | 0 | 543.0656
12 |  | 1BHK | 374.528 | 0 | 543.0656
13 |  | 1BHK | 377.9994 | 0 | 548.0991
14 |  | 1BHK | 377.9994 | 0 | 548.0991
15 |  | 1BHK | 374.528 | 0 | 543.0656
16 |  | 1BHK | 374.528 | 0 | 543.0656
17 |  | 1BHK | 374.528 | 0 | 543.0656
18 |  | 1BHK | 374.528 | 0 | 543.0656
19 |  | 1BHK | 374.528 | 0 | 543.0656
20 |  | 1BHK | 377.9994 | 0 | 548.0991
21 |  | 1BHK | 374.528 | 0 | 543.0656
22 |  | 1BHK | 374.528 | 0 | 543.0656
23 |  | 1BHK | 374.528 | 0 | 543.0656
24 |  | 1BHK | 374.528 | 0 | 543.0656
25 |  | 1BHK | 374.528 | 0 | 543.0656
26 |  | 1BHK | 374.528 | 0 | 543.0656
27 |  | 1BHK | 377.9994 | 0 | 548.0991
1st to 7th & 9th Floor
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | 1st to 7th & 9th Floor
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | 1BHK | 377.9994 | 0 | 548.0991
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 374.528 | 0 | 543.0656
7 |  | 1BHK | 374.528 | 0 | 543.0656
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 374.528 | 0 | 543.0656
10 |  | 1BHK | 374.528 | 0 | 543.0656
11 |  | 1BHK | 374.528 | 0 | 543.0656
12 |  | 1BHK | 374.528 | 0 | 543.0656
13 |  | 1BHK | 377.9994 | 0 | 548.0991
14 |  | 1BHK | 377.9994 | 0 | 548.0991
15 |  | 1BHK | 374.528 | 0 | 543.0656
16 |  | 1BHK | 374.528 | 0 | 543.0656
17 |  | 1BHK | 374.528 | 0 | 543.0656
18 |  | 1BHK | 374.528 | 0 | 543.0656
19 |  | 1BHK | 374.528 | 0 | 543.0656
20 |  | 1BHK | 377.9994 | 0 | 548.0991
21 |  | 1BHK | 374.528 | 0 | 543.0656
22 |  | 1BHK | 374.528 | 0 | 543.0656
23 |  | 1BHK | 374.528 | 0 | 543.0656
24 |  | 1BHK | 374.528 | 0 | 543.0656
25 |  | 1BHK | 374.528 | 0 | 543.0656
26 |  | 1BHK | 374.528 | 0 | 543.0656
27 |  | 1BHK | 377.9994 | 0 | 548.0991
8th Floor (Part Refuge Area)
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | 1BHK | 377.9994 | 0 | 548.0991
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 374.528 | 0 | 543.0656
7 |  | 1BHK | 374.528 | 0 | 543.0656
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 374.528 | 0 | 543.0656
10 |  | 1BHK | 374.528 | 0 | 543.0656
11 |  | 1BHK | 374.528 | 0 | 543.0656
12 |  | 1BHK | 374.528 | 0 | 543.0656
13 |  | 1BHK | 377.9994 | 0 | 548.0991
14 |  | 1BHK | 377.9994 | 0 | 548.0991
15 |  | 1BHK | 374.528 | 0 | 543.0656
16 |  | 1BHK | 374.528 | 0 | 543.0656
17 |  | 1BHK | 374.528 | 0 | 543.0656
18 |  | 1BHK | 374.528 | 0 | 543.0656
19 |  | 1BHK | 374.528 | 0 | 543.0656
20 |  | 1BHK | 377.9994 | 0 | 548.0991
21 |  | 1BHK | 374.528 | 0 | 543.0656
22 |  | 1BHK | 374.528 | 0 | 543.0656
23 |  | Refuge Area
24
25 |  | 1BHK | 374.528 | 0 | 543.0656
26 |  | 1BHK | 374.528 | 0 | 543.0656
27 |  | 1BHK | 377.9994 | 0 | 548.0991
Tower 7
Ground Floor For Residential
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | Ground Floor For Residential
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | 1BHK | 374.528 | 0 | 543.0656
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 377.9994 | 0 | 548.0991
7 |  | 1BHK | 377.9994 | 0 | 548.0991
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 374.528 | 0 | 543.0656
10 |  | 1BHK | 374.528 | 0 | 543.0656
11 |  | 1BHK | 374.528 | 0 | 543.0656
1st Floor (Part Terrace Area)
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | 1st Floor (Part Terrace Area)
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | 1BHK | 374.528 | 0 | 543.0656
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 377.9994 | 0 | 548.0991
7 |  | 1BHK | 377.9994 | 0 | 548.0991
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 374.528 | 0 | 543.0656
10 |  | 1BHK | 374.528 | 0 | 543.0656
11 |  | 1BHK | 374.528 | 0 | 543.0656
2nd to 7th Floor
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | 2nd to 7th Floor
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | 1BHK | 374.528 | 0 | 543.0656
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 377.9994 | 0 | 548.0991
7 |  | 1BHK | 377.9994 | 0 | 548.0991
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 374.528 | 0 | 543.0656
10 |  | 1BHK | 374.528 | 0 | 543.0656
11 |  | 1BHK | 374.528 | 0 | 543.0656
Tower 8
Ground Floor For Residential
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | Ground Floor For Residential
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | 1BHK | 374.528 | 0 | 543.0656
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 374.528 | 0 | 543.0656
7 |  | 1BHK | 374.528 | 0 | 543.0656
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 374.528 | 0 | 543.0656
10 |  | 1BHK | 374.528 | 0 | 543.0656
11 |  | 1BHK | 377.9994 | 0 | 548.0991
12 |  | 1BHK | 377.9994 | 0 | 548.0991
13 |  | 1BHK | 374.528 | 0 | 543.0656
14 |  | 1BHK | 374.528 | 0 | 543.0656
15 |  | 1BHK | 377.9994 | 0 | 548.0991
16 |  | 1BHK | 374.528 | 0 | 543.0656
17 |  | 1BHK | 374.528 | 0 | 543.0656
18 |  | 1BHK | 374.528 | 0 | 543.0656
19 |  | 1BHK | 374.528 | 0 | 543.0656
20 |  | 1BHK | 374.528 | 0 | 543.0656
21 |  | 1BHK | 374.528 | 0 | 543.0656
22 |  | 1BHK | 374.528 | 0 | 543.0656
23 |  | 1BHK | 374.528 | 0 | 543.0656
24 |  | 1BHK | 377.9994 | 0 | 548.0991
1st to 7th & 9th Floor
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | 1st to 7th & 9th Floor
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | 1BHK | 374.528 | 0 | 543.0656
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 374.528 | 0 | 543.0656
7 |  | 1BHK | 374.528 | 0 | 543.0656
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 374.528 | 0 | 543.0656
10 |  | 1BHK | 374.528 | 0 | 543.0656
11 |  | 1BHK | 377.9994 | 0 | 548.0991
12 |  | 1BHK | 377.9994 | 0 | 548.0991
13 |  | 1BHK | 374.528 | 0 | 543.0656
14 |  | 1BHK | 374.528 | 0 | 543.0656
15 |  | 1BHK | 377.9994 | 0 | 548.0991
16 |  | 1BHK | 374.528 | 0 | 543.0656
17 |  | 1BHK | 374.528 | 0 | 543.0656
18 |  | 1BHK | 374.528 | 0 | 543.0656
19 |  | 1BHK | 374.528 | 0 | 543.0656
20 |  | 1BHK | 374.528 | 0 | 543.0656
21 |  | 1BHK | 374.528 | 0 | 543.0656
22 |  | 1BHK | 374.528 | 0 | 543.0656
23 |  | 1BHK | 374.528 | 0 | 543.0656
24 |  | 1BHK | 377.9994 | 0 | 548.0991
8th Floor (Part Refuge Area)
1 |  | 1BHK | 377.9994 | 0 | 548.0991 | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 374.528 | 0 | 543.0656
3 |  | 1BHK | 374.528 | 0 | 543.0656
4 |  | 1BHK | 374.528 | 0 | 543.0656
5 |  | 1BHK | 374.528 | 0 | 543.0656
6 |  | 1BHK | 374.528 | 0 | 543.0656
7 |  | 1BHK | 374.528 | 0 | 543.0656
8 |  | 1BHK | 374.528 | 0 | 543.0656
9 |  | 1BHK | 374.528 | 0 | 543.0656
10 |  | 1BHK | 374.528 | 0 | 543.0656
11 |  | 1BHK | 377.9994 | 0 | 548.0991
12 |  | 1BHK | 377.9994 | 0 | 548.0991
13 |  | 1BHK | 374.528 | 0 | 543.0656
14 |  | 1BHK | 374.528 | 0 | 543.0656
15 |  | 1BHK | 377.9994 | 0 | 548.0991
16 |  | 1BHK | 374.528 | 0 | 543.0656
17 |  | 1BHK | 374.528 | 0 | 543.0656
18 |  | 1BHK | 374.528 | 0 | 543.0656
19 |  | Refuge Area
20
21 |  | 1BHK | 374.528 | 0 | 543.0656
22 |  | 1BHK | 374.528 | 0 | 543.0656
23 |  | 1BHK | 374.528 | 0 | 543.0656
24 |  | 1BHK | 377.9994 | 0 | 548.0991
Remarks:
* | Tower 1 to 8 = Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Please provide latest CC for Tower 1.
* | On Site, we meet Mr. Avinash : 9136396678
* | Validity of CC is expired on 08/06/2023. Please provide latest CC.
* | Since Tower 8 have received CC on 28/04/2022, but as of construction work is not started.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Kalas Darshan
Google Map :
T1
T2
T3
T5
T5
T6
T6
T7
Bldg No.2
Bldg No.2
Bldg No.7
Bldg No.8
Bldg No.8

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted