## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-09-12
Branch Name/ID |  | Mahindra Rural Housing Finance - Thane |  |  | Date & Time of Site Visit | 12/09/2025 at 15:30
Name of the person met at site & Contact No |  | NA |  |  | Date of Report Release | 26/09/2025
Project Details
Name of the project |  | Puraniks Unicorn Phase I & II
Address |  | Puraniks Unicorn Phase I & II, Survey No.55/1/C & 55/1/G, near Puranik City Reserva, Ghodbunder Road, Mogharpada, Thane West, Thane, Thane - 400615. | [8 empty] | Thane | Palghar | Mumbai | Raigad | Pune
Survey No |  | 55/1/C & 55/1/G | [8 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Mogharpada | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Ghodbunder Road | [8 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Thane West | [8 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Thane | [8 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Thane | [8 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 400615 | [8 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | Phase I = P51700032292 Phase II = P51700047561 | [11 empty] | Mahad | Daund
Landmark |  | Puranik City Reserva | [11 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.2785976,72.9662376 | [8 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/e7tjfmHNEGAZC7bz6 | [11 empty] | Poladpur | Purandhar
Name of the builder / developer |  | M/s.Puranik Builders Limited | [11 empty] | Mahasala | Bhor
Office address (agreement) |  | Puraniks One, Ghodbunder Road, Near Kanchan Pushpa, Opp. Suraj Water Par, Thane, 400615 | [11 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [11 empty] | Murud | Velhe
Builder Bank Details |  | HDFC BANK IFSC Code : HDFC0001440
Contact No. |  | Mr. Pankaj Mhatre 8169147639
Location of the project Municipal Limit : |  | Thane Municipal Corporation (TMC)
Project Type (Apartments/Plot/ Combined) |  | Apartments + Shop
No of Wings / Buildings |  | Phase I - Celestia T6A Phase II - Asta T6B |  |  | Other HFC's Approval / Funding | None
No. of Tenements / Units in Project |  | Flats = 502, Shop = 15 |  |  | Exposure Limit (Proposed) | 75.3
Approved No. of Floor |  | Phase I - T6A = LG + UG + 1st to 32nd Floor Phase II - T6B = LG + UG + 1st to 32nd Floor
Proposed No. of Floor |  | Phase I - T6A = LG + UG + 1st to 32nd Floor Phase II - T6B = LG + UG + 1st to 33rd Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | Other Plot/ Nala | Other Plot | Nala | 20 M W DP Raod
|  | Physical on site |  | Nala | Open Plot | Nala | Raod
Verification of survey No. (Title document) |  | Survey No. 55, Hissa No. 1C & Survey No. 55, Hissa No. 1G
Plot area mentioned in the sale deed (As per 7/12) |  | 8350 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 7054.51
Approach road |  | Yes, Approx 65ft
Connectivity |  | 1. 2.1Km from Arunodaya Public School 2. 2.7Km from Ryan International School, Thane 3. 1.0Km from Brahmand Multispeciality Hospital 4. 1.6Km from Oscar Hospital 5. 1.2Km from Mahalaxmi Super Market 6. 2.4Km from Eden Super Market 7. 0.95Km from Ratneshwar Shiv Temple 8. 1.6Km from Om Vitthal Rakhumai Mandir 9. 1.7Km from Poushmata Mandir Bus Stop 10. 13.9Km from Thane Railway Station
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 7054.51
|  | Permissible FSI |  |  |  | 1.1
|  | Permissible TDR/Paid FSI |  |  |  | 2.9091
|  | Total FSI availaible for the project |  |  |  | 4.0091
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 28283.31
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 28282.49
Building plan approvals - Approval No : |  | S06/0367/21 TMC/TD-DP/TPS/4309/23 |  |  |  | Date | 2023-02-27
Building height / No. of Floors |  | Phase I - T6A = LG + UG + 1st to 32nd Floor (Total Height = 96.60 Mtrs) Phase II - T6B = LG + UG + 1st to 32nd Floor (Total Height = 96.60 Mtrs)
Construction/Building Permission Valid Upto |  | S06/0367/21 TMC/TDD/TPS/4309/23 Phase I - T6A =LG + UG + 1st to 32nd Floor Phase II - T6B = LG + UG + 1st to 31st Floor |  |  |  | Date | 2023-02-27
NA / Land conversion |  | Name of the authority : |  | NA
|  | Reference No : |  | NA |  | Date | NA |  | ``
|  | Validity & Area mentioned: |  | NA |  |  |  | Date - - Valid For one Year Area -
Other statutory permissions
Fire Noc No Valid Up to: |  | TMC/CFO/M/HR/141/110 Valid Upto : T6B = LG + UG + 1st to 33rd Floor (Total Height = 103.85 Mtrs) |  |  |  | Date | 2022-07-20
|  | TMC/CFO/M/HR/97/112 Valid Upto : T6A = LG + G + 1P + 1st to 32nd Floor (Total Height = 101 Mtrs) |  |  |  | Date | 2022-07-21
Environmental Clearance Certificate (EC) No Valid Up for: |  | SIA/MH/MIS/243404/2021 |  |  |  | Date | 2025-08-29
Survey No. 55/1/C & 55/1/G Total Builtup Area = 40146.83 Sq.m.
Airport Noc No Valid Up for: | [5 empty] | Date
Valid upto Dated
Site Elevation (AMSL) = Permissible Top Elevation (AMSL) =
CONSTRUCTION PROGRESS
Baseline start date |  | Phase I - 22/12/2021 Phase II - 09/11/2022 |  | Baseline finish date |  | Phase I - 31/12/2028 Phase II - 31/12/2029
Construction details: | [7 empty] | Excavation work Completed. Plinth work completed, RCC upto 21 Slab, Brickwork upto 20 Floor, Internal Plaster upto 15 Floor, External Plaster upto 13 Floor Completed
Phase I - T6A = LG + UG + 1st to 32nd Floor |  |  |  | Basement | Ground | Podium | Floors | All work Completed. OC Received.
|  |  |  | 1 | 1 | 0 | 32 | Piling Work in process | 8
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 21 Slab, Brickwork upto 20 Floor, Internal Plaster upto 15 Floor, External Plaster upto 13 Floor Completed | [5 empty] | Excavation in process | 16
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Excavation Completed | 32
Excavation |  | 0% |  | 32 | 100% | 49.2% |  | Footing in Process | 8
Plinth |  | 10% |  | 32 | 100% |  |  | Footing Completed | 16
RCC (Including podiums) |  | 40% |  | 21 | 63.64% |  |  | Basement 1 | 0
Brickwork |  | 15% |  | 20 | 62.5% |  |  | Basement 2 | 0
Internal Plaster |  | 5% |  | 15 | 46.88% |  |  | Basement 3 | 0
Ext. Plaster & Plumbing |  | 5% |  | 13 | 40.62% |  |  | Basement 4 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Plinth in process | 24
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Plinth completed | 32
Building Common Amenities |  | 5% |  | 0 | 0%
Possession |  | 5% |  | 0 | 0%
Construction details: | [7 empty] | Excavation work Completed. Plinth work completed, RCC upto 15 Slab, Brickwork upto 14 Floor, Internal Plaster upto 10.5 Floor, External Plaster upto 9.1 Floor Completed
Phase II - T6B = LG + UG + 1st to 32nd Floor |  |  |  | Basement | Ground | Podium | Floors | All work Completed. OC Received.
|  |  |  | 1 | 1 | 0 | 32 | Piling Work in process | 8
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 15 Slab, Brickwork upto 14 Floor, Internal Plaster upto 10.5 Floor, External Plaster upto 9.1 Floor Completed | [5 empty] | Excavation in process | 16
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Excavation Completed | 32
Excavation |  | 0% |  | 32 | 100% | 37.81% |  | Footing in Process | 8
Plinth |  | 10% |  | 32 | 100% |  |  | Footing Completed | 16
RCC (Including podiums) |  | 40% |  | 15 | 45.45% |  |  | Basement 1 | 0
Brickwork |  | 15% |  | 14 | 43.75% |  |  | Basement 2 | 0
Internal Plaster |  | 5% |  | 10.5 | 32.81% |  |  | Basement 3 | 0
Ext. Plaster & Plumbing |  | 5% |  | 9.1 | 28.44% |  |  | Basement 4 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Plinth in process | 24
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Plinth completed | 32
Building Common Amenities |  | 5% |  | 0 | 0%
Possession |  | 5% |  | 0 | 0%
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block/ Brick |  | Projected Parts Available |  | Yes/No | Yes
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building T6B |  | 15 |  | 8239.8366 |  | 12771.7468
Total |  | 15 |  | 8239.8366 |  | 12771.7468
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building T6A |  | 252 |  | 96442.8566 |  | 144664.285
Building T6B |  | 250 |  | 96159.01 |  | 144238.5149
Total |  | 502 |  | 192601.8666 |  | 288902.7999
Grand Total |  | 517 |  | 200841.7032 |  | 301674.5467
BUILDING / BLOCK - Configuration Details
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
55%
Phase II
Building T6B
Lower Ground Floor For Society Office/Letter Box Room, Meter Room, Drivers Room, Fire Control Room, Entrance Lobby & Parking
Upper Ground Floor For Commercial, Residential, Creche/Fit Center, LV Room & Parking
1 |  | Shop | 388.9033 | 188.5207 | 577.424 | 0 | 895.0072 | 36.1209
2 |  | Shop | 379.6463 | 183.9998 | 563.6461 | 0 | 873.6514 |  |  | 10.764
3 |  | Shop | 368.5594 | 176.3143 | 544.8737 | 0 | 844.5542
4 |  | Shop | 363.5003 | 176.3143 | 539.8146 | 0 | 836.7126
5 |  | Shop | 521.5158 | 249.5526 | 646.2921 | 0 | 1001.7527 | 48.0156
6 |  | Shop | 408.8167 | 195.7541 | 604.5708 | 0 | 937.0848
7 |  | Shop | 419.2578 | 205.7 | 522.1078 | 0 | 809.2671
8 |  | Shop | 367.8059 | 179.4789 | 547.2848 | 0 | 848.2915
9 |  | Shop | 422.487 | 203.4396 | 524.2068 | 0 | 812.5205
10 |  | Shop | 292.135 | 161.3793 | 453.5142 | 0 | 702.9471
11 |  | Shop | 254.5686 | 106.1599 | 360.7285 | 0 | 559.1293
12 |  | Shop | 278.68 | 136.5306 | 415.2105 | 0 | 643.5763
13 |  | Shop | 306.5587 | 165.4804 | 472.0391 | 0 | 731.6606
14 |  | Shop | 451.1192 | 197.3041 | 648.4234 | 0 | 1005.0562
15 |  | Shop | 705.4726 | 342.6827 | 819.7001 | 0 | 1270.5352
Ground Floor
1 |  | Shop |  |  | 0 | 0 | 0
2 |  | Shop |  |  | 0 | 0 | 0
3 |  | Shop |  |  | 0 | 0 | 0
4 |  | Shop |  |  | 0 | 0 | 0
5 |  | Shop |  |  | 0 | 0 | 0
6 |  | Shop |  |  | 0 | 0 | 0
7 |  | Shop |  |  | 0 | 0 | 0
8 |  | Shop |  |  | 0 | 0 | 0
9 |  | Shop |  |  | 0 | 0 | 0
10 |  | Shop |  |  | 0 | 0 | 0
11 |  | Shop |  |  | 0 | 0 | 0
12 |  | Shop |  |  | 0 | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
50%
Phase I
Building T6A
Lower Ground Floor For Meter Room, Letter Room, Fire Control Room & Parking
Upper Ground Floor For Residential, Driver Room, Society Office, Creche/Fit Center, Electric Room, LV Room & Parking
1 |  | - | Electric Room/ LV Room/Parking
2 |  | -
3 |  | - | Society Office/Parking
4 |  | - | Driver Room/Parking
5 |  | - | Parking
6 |  | - | Creche/Fit Center
7 |  | 1BHK | 384.7054 | 0 | 384.7054 | 0 | 577.058 | 33.1585
8 |  | 2BHK | 488.0398 | 0 | 488.0398 | 0 | 732.0596 | 42.4534
1st to 5th, 7th to 10th, 12th to 15th, 17th to 20th, 22nd to 25th, 27th to 30th & 32nd Floor For Residential
1 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797 |  |  | 4533796.8
2 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797 |  |  | 4533796.8
3 |  | 2BHK | 488.4703 | 0 | 488.4703 | 0 | 732.7055 |  |  | 7327054.8
4 |  | 2BHK | 488.4703 | 0 | 488.4703 | 0 | 732.7055 | 43.0021 |  | 7327054.8
5 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797 |  |  | 4533796.8
6 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797 |  |  | 4533796.8
7 |  | 1BHK | 384.7054 | 0 | 384.7054 | 0 | 577.058 |  |  | 5770580.4
8 |  | 2BHK | 488.0398 | 0 | 488.0398 | 0 | 732.0596 |  |  | 7320596.4
6th, 11th, 16th, 21st, 26th & 31st Floor (Part Refuge Area)
1 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797
2 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797
3 |  | 2BHK | 488.4703 | 0 | 488.4703 | 0 | 732.7055
4 |  | 2BHK | 488.4703 | 0 | 488.4703 | 0 | 732.7055
5 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797
6 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797
7 |  | - | Refuge Area
8 |  | 2BHK | 488.0398 | 0 | 488.0398 | 0 | 732.0596
Phase II
Building T6B
Upper Ground Floor For Residential, Commercial, Creche/Fit Center, Electrical Room, LV Room & Parking
1 |  | - | Electrical Room/LV Room/Parking
2 |  | - | Creche/Fit Center
3 |  | - | Commercial
4 |  | -
5 |  | - | Parking
6 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797
7 |  | 1BHK | 386.7505 | 0 | 386.7505 | 0 | 580.1258
8 |  | 2BHK | 490.0849 | 0 | 490.0849 | 0 | 735.1274
1st Floor For Residential
1 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797
2 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797
3 |  | 2BHK | 494.4982 | 0 | 494.4982 | 0 | 741.7472 |  | 1398.9756
4 |  | 2BHK | 494.4982 | 0 | 494.4982 | 0 | 741.7472 |  | 145.9598
5 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797 |  |  | 10.764
6 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797
7 |  | 1BHK | 386.7505 | 0 | 386.7505 | 0 | 580.1258
8 |  | 2BHK | 490.0849 | 0 | 490.0849 | 0 | 735.1274
2nd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th & 29th to 31st Floor For Residential
1 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797 |  |  | 4533796.8
2 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797 |  |  | 4533796.8
3 |  | 2BHK | 494.4982 | 0 | 494.4982 | 0 | 741.7472 | 43.03 |  | 7417472.4
4 |  | 2BHK | 494.4982 | 0 | 494.4982 | 0 | 741.7472 |  |  | 7417472.4
5 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797 |  |  | 4533796.8
6 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797 |  |  | 4533796.8
7 |  | 1BHK | 386.7505 | 0 | 386.7505 | 0 | 580.1258 | 33.6085 |  | 5801257.8
8 |  | 2BHK | 490.0849 | 0 | 490.0849 | 0 | 735.1274 |  |  | 7351273.8
8th, 13th, 18th, 23rd & 28th Floor (Part Refuge Area)
1 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797
2 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797
3 |  | 2BHK | 494.4982 | 0 | 494.4982 | 0 | 741.7472
4 |  | 2BHK | 494.4982 | 0 | 494.4982 | 0 | 741.7472
5 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797
6 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797
7 |  | - | Refuge Area
8 |  | 2BHK | 490.0849 | 0 | 490.0849 | 0 | 735.1274
32nd Floor (Part Terrace Area)
1 |  | - | Terrace Area
2 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797
3 |  | 2BHK | 494.4982 | 0 | 494.4982 | 0 | 741.7472 | 43.03
4 |  | 2BHK | 494.4982 | 0 | 494.4982 | 0 | 741.7472
5 |  | 1BHK | 302.2531 | 0 | 302.2531 | 0 | 453.3797
6 |  | - | Terrace Area
7 |  | - | [5 empty] | 33.6085
8 |  | -
Ground Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
1st Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
2nd Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
2nd Floor
1 |  | 1BHK |  |  | 0 | 0 | 0
2 |  | 1BHK |  |  | 0 | 0 | 0
3 |  | 1BHK |  |  | 0 | 0 | 0
4 |  | 1BHK |  |  | 0 | 0 | 0
5 |  | 1BHK |  |  | 0 | 0 | 0
6 |  | 1BHK |  |  | 0 | 0 | 0
7 |  | 1BHK |  |  | 0 | 0 | 0
8 |  | 1BHK |  |  | 0 | 0 | 0
9 |  | 1BHK |  |  | 0 | 0 | 0
10 |  | 1BHK |  |  | 0 | 0 | 0
11 |  | 1BHK |  |  | 0 | 0 | 0
12 |  | 1BHK |  |  | 0 | 0 | 0
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 10000
Recommended of Parking ( If Available) |  |  |  |  | 3,00,000/-
REMARKS ON RECOMMENDATION
1 | Construction work is in process at the time of Visit. Construction work was not active at the time of Visit. (labour Not found) All work completed. Wait for OC / OC received. Work not yet Started.
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Labours found on site at the time of visit.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet .
5 | We considered Saleable area as per our calculation. Loading |  |  |  | 50%
6 | We have considered rate by verifying it from market inquire.
7 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
8 | Car parking is subjected to authentic documentation.
9 | Nala is located at north & east side of the project.
10 | We have not drafted Terrace Area of Building T6B, Flat no. 103 & 104 due to improper dimentions.
11 | We have referred Environmental Clearance Certificate from Official Parivesh site.
12 | Please provide Fire NOC for Building T6A.
13 | On Site, we meet Mr. .....
Photographs Of Property : |  | Puraniks Unicorn Phase I & II
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Mr. Ajay Songare |  | Authorized Signatory Name & Seal of the agency
T6A
T6B
T6A
T6B
T6A
T6B
Nala
Nala
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C47: height should also be mentioned
Note on C61: RERA Start date
Note on H94: if multiple buildings are in project and are connected internally
Note on C96: AAC Block or Brick
Note on H98: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3