## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-09-15
Branch Name/ID |  | Mahindra Rural Housing Finance - Thane |  |  | Date & Time of Site Visit | 16/09/2025 at 14:53
Name of the person met at site & Contact No |  | Mr. Anurag Tiwari 8356892131/9320016817 |  |  | Date of Report Release | 19/09/2025
Project Details
Name of the project |  | Anandam - II
Address |  | Anandam - II, Survey No.112/1, 113/2, 114/1A, 114/9A, 114/10/11/B & 115/6, near Today Global Codename Cloud City, Mumbra Panvel Highway, Rohinjan, Taloja Panchanand West, Panvel, Raigad - 410210. | [8 empty] | Thane | Palghar | Mumbai | Raigad | Pune
Survey No |  | 112/1, 113/2, 114/1A, 114/9A, 114/10/11/B & 115/6 | [8 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Rohinjan | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Mumbra Panvel Highway | [8 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Taloja Panchanand West | [8 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Panvel | [8 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Raigad | [8 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 410210 | [8 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P52000048037 | [11 empty] | Mahad | Daund
Landmark |  | Today Global Codename Cloud City | [11 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.087971,73.074390 | [8 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/k395aXDdTbavVRtNA | [11 empty] | Poladpur | Purandhar
Name of the builder / developer |  | M/s. Today Global Homes | [11 empty] | Mahasala | Bhor
Office address (agreement) |  | Office No.-1601 & 1602, 16th Floor, Kesar Solitaire, Plot No.-05, Sector No.-19, Palm Beach Road, Sanpada, Navi Mumbai, Tal. Thane, Dist. Thane 400705. | [11 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [11 empty] | Murud | Velhe
Builder Bank Details |  | A/c No. 095605001504 Bank Name - ICICI Bank LTD IFSC Code - ICIC0000956
Contact No. |  | Mr. Anurag Tiwari 8356892131
Location of the project Municipal Limit : |  | Panvel Municipal Corporation
Project Type (Apartments/Plot/ Combined) |  | Apartments
No of Wings / Buildings |  | Building No.1 Building No.2 (Wing A & B) Building No.3 (Wing A & B) |  |  | Other HFC's Approval / Funding | None |  |  |  | 807
No. of Tenements / Units in Project |  | Flats = 807 |  |  | Exposure Limit (Proposed) | 121.05 |  | 121.05
Approved No. of Floor |  | Building No.1 = G + P(1A) + P(1B) + 2nd to 22nd Floor Building No.2 (Wing A & B) = G + P(1A) + P(1B) + 2nd to 22nd Floor Building No.3 (Wing A & B) = G + 2P + 3rd to 28th Floor
Proposed No. of Floor |  | Building No.1 = G + P(1A) + P(1B) + 2nd to 22nd Floor Building No.2 (Wing A & B) = G + P(1A) + P(1B) + 2nd to 22nd Floor Building No.3 (Wing A & B) = G + 2P + 3rd to 28th Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | Other Plot | Other Plot | Other Plot | Other Plot
|  | Physical on site |  | House | Open Plot | Today Global Codename Cloud City | Open Plot
Verification of survey No. (Title document) |  | Survey No. 112/1, 113/2, 114/1A, 114/9A, 114/10/11/B & 115/6
Plot area mentioned in the sale deed (As per 7/12) |  | 16010 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 15228.221
Approach road |  | Yes, Approx 26ft
Connectivity |  | 1. 0.70km from Shree Chatrapati Shivaji Maharaj High School 2. 2.0km from Harmony School 3. 4.0km from Dolphin Hospital 4. 4.5km from Kharghar Medcity Hospital Sector -34 5. 1.8km from Foodmall Super Market 6. 7.5km from DMart Kharghar 7. 7.5km from Owe Dam 8. 0.85km from Jagruteshwar Shiv Mandir Rohinjan 9. 2.1km from Kharghar Valley Shilp Sec 36 Bus stop 10. 2.8km from Taloja Panchanand Railway Station
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 15228.221
|  | Permissible FSI |  |  |  | 1.1
|  | Permissible TDR/Paid FSI |  |  |  | 2.5641
|  | Total FSI availaible for the project |  |  |  | 3.6641
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 55832.963
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 55797.878
Building plan approvals - Approval No : |  | PMP/NRV/16278/2558/2024 |  |  |  | Date | 2024-10-22
Building height / No. of Floors |  | Building No.1 = G + P(1A) + P(1B) + 2nd to 22nd Floor (Height = 80.051 Mtrs) Building No.2 (Wing A & B) = G + P(1A) + P(1B) + 2nd to 22nd Floor Height = 80.051 Mtrs) Building No.3 (Wing A & B) = G + 2P + 3rd to 28th Floor Height = 94.45 Mtrs)
Construction/Building Permission Valid Upto |  | PMC/TP/Rohinjan/112/1 & others/21-24/16278/2558/2024 Building No.1 = G + Podium 1A + Podium 1B + 2nd to 22nd Floor Building No.2 = G + Podium 1A + Podium 1B + 2nd to 22nd Floor Building No.3 = G + 2P + 3rd to 28th Floor No. of Residential Units = 807 Nos. |  |  |  | Date | 2024-10-22
NA / Land conversion |  | Name of the authority : |  | NA
|  | Reference No : |  | NA |  | Date | NA |  | ``
|  | Validity & Area mentioned: |  | NA |  |  |  | Date - - Valid For one Year Area -
Other statutory permissions
Fire Noc No. Valid Up to: |  | Pmc/Fire/2121/ Ref No.904/3202 |  |  |  | Date | 2022-11-11
Building No.1 (Wing A) = G + Podium 1 & 2 + 3rd to 21st Floor (Height = 67.65 Mtrs) Building No.2 (Wing A) = G + Podium 1 & 2 + 3rd to 22nd Floor (Height = 70.65 Mtrs) Building No.2 (Wing B) = G + Podium 1 & 2 + 3rd to 18th Floor (Height = 58.65 Mtrs) Building No.3 (Wing A) = G + Podium 1 & 2 + 3rd to 28th Floor (Height = 88.65Mtrs) Building No.3 (Wing B) = G + Podium 1 & 2 + 3rd to 24th Floor (Height = 76.65Mtrs)
Environmental Clearance Certificate (EC) No Valid Up for: |  | SIA/MH/MIS/281965/2022 |  |  |  | Date | 2023-04-11
S No. 112/1, 113/2, 114/1A, 114/9A, 114/10/11/B & 115/6 Proposed BUA =103266 Sq.Mt Building No. 1 = G + 1st to 33rd Floor Building No. 2 (Wing A) = G + 1st to 34th Floor Building No. 2 (Wing B) = G + 1st to 29th Floor Building No. 3 (Wing A) = G + 1st to 32nd Floor Building No. 3 (Wing B) = G + 1st to 35th Floor
Airport Noc No Valid Up for: |  | NAVI/WEST/B/012122/649755 |  |  |  | Date | 2023-01-02
[6 empty] | Valid upto Dated | 2031-01-01
|  | Site Elevation (AMSL) = 24.05 M Permissible Top Elevation (AMSL) = 157.05 M | [5 empty] | 133
CONSTRUCTION PROGRESS
Baseline start date |  | 2022-12-07 |  | Baseline finish date |  | 2027-12-31
Construction details:
Building No.1 = G + P(1A) + P(1B) + 2nd to 22nd Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 15 Slab, Brickwork upto 10 Floor, Internal Plaster upto 4 Floor Completed
|  |  |  | 0 | 1 | 1 | 22
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 15 Slab, Brickwork upto 10 Floor, Internal Plaster upto 4 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 5.5
Excavation |  | 0% |  | 22 | 100% | 42.73% |  | Excavation in process | 11
Plinth |  | 10% |  | 22 | 100% |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 40% |  | 15 | 62.5% |  |  | Footing in Process | 5.5
Brickwork |  | 15% |  | 10 | 45.45% |  |  | Footing Completed | 11
Internal Plaster |  | 5% |  | 4 | 18.18% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 16.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 22
Building No.2 (Wing A) = G + P(1A) + P(1B) + 2nd to 22nd Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 18 Slab, Brickwork upto 12 Floor, Internal Plaster upto 4 Floor Completed
|  |  |  | 0 | 1 | 1 | 22
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 18 Slab, Brickwork upto 12 Floor, Internal Plaster upto 4 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 5.5
Excavation |  | 0% |  | 22 | 100% | 49.09% |  | Excavation in process | 11
Plinth |  | 10% |  | 22 | 100% |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 40% |  | 18 | 75% |  |  | Footing in Process | 5.5
Brickwork |  | 15% |  | 12 | 54.55% |  |  | Footing Completed | 11
Internal Plaster |  | 5% |  | 4 | 18.18% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 16.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 22
Building No.2 (Wing B) = G + P(1A) + P(1B) + 2nd to 22nd Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 18 Slab, Brickwork upto 11 Floor, Internal Plaster upto 4 Floor Completed
|  |  |  | 0 | 1 | 1 | 22
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 18 Slab, Brickwork upto 11 Floor, Internal Plaster upto 4 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 5.5
Excavation |  | 0% |  | 22 | 100% | 48.41% |  | Excavation in process | 11
Plinth |  | 10% |  | 22 | 100% |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 40% |  | 18 | 75% |  |  | Footing in Process | 5.5
Brickwork |  | 15% |  | 11 | 50% |  |  | Footing Completed | 11
Internal Plaster |  | 5% |  | 4 | 18.18% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 16.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 22
Building No.3 (Wing A) = G + 2P + 3rd to 28th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed
|  |  |  | 0 | 1 | 0 | 28
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 7
Excavation |  | 0% |  | 28 | 100% | 18.28% |  | Excavation in process | 14
Plinth |  | 10% |  | 28 | 100% |  |  | Excavation Completed | 28
RCC (Including podiums) |  | 40% |  | 6 | 20.69% |  |  | Footing in Process | 7
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 14
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 21
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 28
Building No.3 (Wing B) = G + 2P + 3rd to 28th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 7 Slab Completed
|  |  |  | 0 | 1 | 0 | 28
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 7 Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 7
Excavation |  | 0% |  | 28 | 100% | 19.66% |  | Excavation in process | 14
Plinth |  | 10% |  | 28 | 100% |  |  | Excavation Completed | 28
RCC (Including podiums) |  | 40% |  | 7 | 24.14% |  |  | Footing in Process | 7
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 14
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 21
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 28
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block |  | Projected Parts Available |  | Yes/No | No
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. 1 |  | 141 |  | 76626.8009 |  | 114940.2013
Building No. 2 | Wing A | 141 |  | 78321.5604 |  | 117482.3406
| Wing B | 180 |  | 96700.5091 |  | 145050.7637
Building No. 3 | Wing A | 197 |  | 110638.7966 |  | 165958.1949
| Wing B | 148 |  | 89175.7842 |  | 133763.6763
Total |  | 807 |  | 451463.4512 |  | 677195.1768
BUILDING / BLOCK - Configuration Details
Details of Residential in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet + Enclosed Balcony Area | Balcony + Chajja Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
50%
Building No. 1
Ground Floor For Parking, Entrance Lobby, Meter Room, Drivers Room, LV Room, Panel Room & Fire Control Room
Podium 1A & 1B Floor For Parking
2nd Floor For Residential, Society Office & Stilt Parking | [7 empty] | 1
1 |  | - | Society Office
2 |  | - | Stilt Parking |  | #VALUE! | 0 | #VALUE!
3 |  | 2BHK | 518.6095 | 67.0059 | 585.6154 | 0 | 878.4231
4 |  | 2BHK | 518.6095 | 67.0059 | 585.6154 | 0 | 878.4231
5 |  | 2BHK | 518.6095 | 67.0059 | 585.6154 | 0 | 878.4231
6 |  | 2BHK | 518.6095 | 67.0059 | 585.6154 | 0 | 878.4231
7 |  | - | Stilt Parking |  | #VALUE! | 0 | #VALUE!
3rd to 7th, 9th to 12th, 14th to 17th, 19th to 22nd Floor For Residential | [7 empty] | 17
1 |  | 1BHK | 368.6993 | 69.0242 | 437.7234 | 0 | 656.5852 | 34.118
2 |  | 1BHK | 368.6993 | 69.6781 | 438.3774 | 0 | 657.566
3 |  | 2BHK | 518.6095 | 97.7398 | 616.3493 | 0 | 924.524 | 48.405
4 |  | 2BHK | 518.6095 | 97.7398 | 616.3493 | 0 | 924.524
5 |  | 2BHK | 518.6095 | 97.7398 | 616.3493 | 0 | 924.524
6 |  | 2BHK | 518.6095 | 97.7398 | 616.3493 | 0 | 924.524
7 |  | 1BHK | 368.6993 | 69.6781 | 438.3774 | 0 | 657.566
8th, 13th & 18th Floor For Residential (Part Refuge Area) | [7 empty] | 3
1 |  | Refuge Area
2 |  | 1BHK | 368.6993 | 69.6781 | 438.3774 | 0 | 657.566
3 |  | 2BHK | 518.6095 | 97.7398 | 616.3493 | 0 | 924.524
4 |  | 2BHK | 518.6095 | 97.7398 | 616.3493 | 0 | 924.524
5 |  | 2BHK | 518.6095 | 97.7398 | 616.3493 | 0 | 924.524
6 |  | 2BHK | 518.6095 | 97.7398 | 616.3493 | 0 | 924.524
7 |  | 1BHK | 368.6993 | 69.6781 | 438.3774 | 0 | 657.566
Building No. 2 (Wing A)
Ground Floor For Parking, Entrance Lobby, Telecommunication Room, Meter Room, Drivers Room, LV Room, Panel Room & Fire Control Room
Podium 1A & 1B Floor For Parking
2nd Floor For Residential & Stilt Parking | [7 empty] | 1
- |  | - | Stilt Parking |  | #VALUE! | 0 | #VALUE!
2 |  | 1BHK | 383.1338 | 73.1172 | 456.251 | 0 | 684.3765
3 |  | 1BHK | 362.5584 | 68.5156 | 431.074 | 0 | 646.611
4 |  | 2BHK | 538.4422 | 109.5264 | 647.9686 | 0 | 971.9529
5 |  | 2BHK | 538.4422 | 112.3842 | 650.8264 | 0 | 976.2396
- |  | - | Stilt Parking |  | #VALUE! | 0 | #VALUE!
- |  | - | Stilt Parking |  | #VALUE! | 0 | #VALUE!
3rd Floor For Residential | [7 empty] | 1
1 |  | 1BHK | 362.5584 | 71.9304 | 434.4889 | 0 | 651.7333 | 33.3275
2 |  | 2BHK | 527.9473 | 97.7398 | 625.6871 | 0 | 938.5307
3 |  | 1BHK | 362.5584 | 68.5156 | 431.074 | 0 | 646.611
4 |  | 2BHK | 538.4422 | 109.5264 | 647.9686 | 0 | 971.9529 | 50.1775
5 |  | 2BHK | 538.4422 | 112.3842 | 650.8264 | 0 | 976.2396
6 |  | 2BHK | 538.4422 | 112.3842 | 650.8264 | 0 | 976.2396 |  | 660000
7 |  | 1BHK | 362.5584 | 68.5156 | 431.074 | 0 | 646.611
4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor | [7 empty] | 16 | 9000
1 |  | 1BHK | 362.5584 | 71.9304 | 434.4889 | 0 | 651.7333 |  | 5865599.61
2 |  | 2BHK | 527.9473 | 97.7398 | 625.6871 | 0 | 938.5307 | 10207.0647 | 8446775.8635
3 |  | 1BHK | 362.5584 | 68.5156 | 431.074 | 0 | 646.611 | 9279.1497 | 5819498.7435
4 |  | 2BHK | 538.4422 | 109.5264 | 647.9686 | 0 | 971.9529 |  | 8747575.8435
5 |  | 2BHK | 538.4422 | 112.3842 | 650.8264 | 0 | 976.2396 |  | 8786156.7105
6 |  | 2BHK | 538.4422 | 112.3842 | 650.8264 | 0 | 976.2396 |  | 8786156.7105
7 |  | 1BHK | 362.5584 | 68.5156 | 431.074 | 0 | 646.611 |  | 5819498.7435
8th, 13th & 18th Floor For Residential (Part Refuge Area) | [7 empty] | 1
1 |  | Refuge Area
2 |  | 2BHK | 527.9473 | 97.7398 | 625.6871 | 0 | 938.5307
3 |  | 1BHK | 362.5584 | 68.5156 | 431.074 | 0 | 646.611
4 |  | 2BHK | 538.4422 | 109.5264 | 647.9686 | 0 | 971.9529
5 |  | 2BHK | 538.4422 | 112.3842 | 650.8264 | 0 | 976.2396
6 |  | 2BHK | 538.4422 | 112.3842 | 650.8264 | 0 | 976.2396
7 |  | 1BHK | 362.5584 | 68.5156 | 431.074 | 0 | 646.611
Building No. 2 (Wing B)
Ground Floor For Parking, Entrance Lobby, Telecommunication Room, Meter Room, Drivers Room, LV Room, Panel Room & Fire Control Room
Podium 1A & 1B Floor For Parking | [7 empty] | 1
2nd Floor For Residential, Society Office & Stilt Parking | [7 empty] | 1
- |  | Society Office
2 |  | 2BHK | 519.5783 | 97.7398 | 617.3181 | 0 | 925.9771
3 |  | 2BHK | 519.5783 | 97.7398 | 617.3181 | 0 | 925.9771
4 |  | 1BHK | 362.5584 | 70.7679 | 433.3263 | 0 | 649.9895
- |  | Stilt Parking
-
-
-
-
3rd Floor For Residential | [7 empty] | 1
1 |  | 2BHK | 519.5783 | 98.8297 | 618.4079 | 0 | 927.6119
2 |  | 2BHK | 519.5783 | 97.7398 | 617.3181 | 0 | 925.9771
3 |  | 2BHK | 519.5783 | 97.7398 | 617.3181 | 0 | 925.9771
4 |  | 1BHK | 362.5584 | 70.7679 | 433.3263 | 0 | 649.9895
5 |  | 2BHK | 519.5783 | 96.65 | 616.2282 | 0 | 924.3424
6 |  | 1BHK | 362.5584 | 67.4984 | 430.0568 | 0 | 645.0852
7 |  | 1BHK | 362.5584 | 71.8578 | 434.4162 | 0 | 651.6243
8 |  | 2BHK | 519.5783 | 97.7398 | 617.3181 | 0 | 925.9771
9 |  | 1BHK | 362.5584 | 69.6781 | 432.2365 | 0 | 648.3547
4th to 7th, 9th to 12th, 14th to 17th & 19th to 22nd Floor | [7 empty] | 16
1 |  | 2BHK | 519.5783 | 98.8297 | 618.4079 | 0 | 927.6119
2 |  | 2BHK | 519.5783 | 97.7398 | 617.3181 | 0 | 925.9771
3 |  | 2BHK | 519.5783 | 97.7398 | 617.3181 | 0 | 925.9771
4 |  | 1BHK | 362.5584 | 70.7679 | 433.3263 | 0 | 649.9895
5 |  | 2BHK | 519.5783 | 96.65 | 616.2282 | 0 | 924.3424
6 |  | 1BHK | 362.5584 | 67.4984 | 430.0568 | 0 | 645.0852
7 |  | 1BHK | 362.5584 | 71.8578 | 434.4162 | 0 | 651.6243
8 |  | 2BHK | 519.5783 | 97.7398 | 617.3181 | 0 | 925.9771
9 |  | 1BHK | 362.5584 | 69.6781 | 432.2365 | 0 | 648.3547
8th, 13th & 18th Floor For Residential (Part Refuge Area) | [7 empty] | 3
1 |  | 2BHK | 519.5783 | 98.8297 | 618.4079 | 0 | 927.6119
2 |  | 2BHK | 519.5783 | 97.7398 | 617.3181 | 0 | 925.9771
3 |  | 2BHK | 519.5783 | 97.7398 | 617.3181 | 0 | 925.9771
4 |  | 1BHK | 362.5584 | 70.7679 | 433.3263 | 0 | 649.9895
5 |  | 2BHK | 519.5783 | 96.65 | 616.2282 | 0 | 924.3424
6 |  | 1BHK | 362.5584 | 68.5882 | 431.1466 | 0 | 646.72
7 |  | Refuge Area
8 |  | 2BHK | 519.5783 | 97.7398 | 617.3181 | 0 | 925.9771
9 |  | 1BHK | 362.5584 | 69.6781 | 432.2365 | 0 | 648.3547
Building No. 3 (Wing A)
Ground Floor For Parking, Entrance Lobby, Telecommunication Room, Meter Room, Drivers Room, LV Room, Panel Room & Fire Control Room
1st & 2nd Podium Floor For Parking | [7 empty] | 2
3rd Floor For Residential, Utility Area & Society Office | [7 empty] | 1
- |  | Utility Area
2 |  | 2BHK | 519.5783 | 67.0059 | 586.5842 | 0 | 879.8763
3 |  | 1BHK | 361.482 | 39.9614 | 401.4434 | 0 | 602.1651
4 |  | 2BHK | 519.5783 | 67.0059 | 586.5842 | 0 | 879.8763
- |  | Utility Area & Society Office
-
-
-
4th to 6th, 8th to 11th, 13th to 16th, 18th to 21st & 23rd to 26th Floor as Residential | [7 empty] | 19
1 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
2 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
3 |  | 1BHK | 361.482 | 68.2976 | 429.7796 | 0 | 644.6694
4 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
5 |  | 1BHK | 361.482 | 68.2976 | 429.7796 | 0 | 644.6694
6 |  | 1BHK | 361.482 | 68.2976 | 429.7796 | 0 | 644.6694
7 |  | 2BHK | 541.779 | 111.0037 | 652.7828 | 0 | 979.1742
8 |  | 2BHK | 541.779 | 111.0037 | 652.7828 | 0 | 979.1742
7th, 12th, 17th, 22nd & 27th Floor For Residential (Part Refuge Area) | [7 empty] | 5
1 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
2 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
3 |  | 1BHK | 361.482 | 68.2976 | 429.7796 | 0 | 644.6694
4 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
5 |  | Refuge Area
6 |  | 1BHK | 361.482 | 68.2976 | 429.7796 | 0 | 644.6694
7 |  | 2BHK | 541.779 | 111.0037 | 652.7828 | 0 | 979.1742
8 |  | 2BHK | 541.779 | 111.0037 | 652.7828 | 0 | 979.1742
28th Floor For Residential (Part Terrace Area) | [7 empty] | 1
1 |  | Terrace Area
2 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
3 |  | 1BHK | 361.482 | 68.2976 | 429.7796 | 0 | 644.6694
4 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
5 |  | 1BHK | 361.482 | 68.2976 | 429.7796 | 0 | 644.6694
6 |  | 1BHK | 361.482 | 68.2976 | 429.7796 | 0 | 644.6694
7 |  | 2BHK | 541.779 | 111.0037 | 652.7828 | 0 | 979.1742
8 |  | 2BHK | 541.779 | 111.0037 | 652.7828 | 0 | 979.1742
Building No. 3 (Wing B)
Ground Floor For Parking, Entrance Lobby, Telecommunication Room, Meter Room, Drivers Room, LV Room, Panel Room & Fire Control Room
1st & 2nd Podium Floor For Parking | [7 empty] | 2
3rd Floor For Residential & Utility Area | [7 empty] | 1
1 |  | Utility Area
2 |  | 2BHK | 541.779 | 82.5868 | 624.3658 | 0 | 936.5487
3 |  | 1BHK | 370.174 | 39.9614 | 410.1353 | 0 | 615.203
4 |  | 2BHK | 519.5783 | 67.0059 | 586.5842 | 0 | 879.8763
5 |  | 2BHK | 519.5783 | 67.0059 | 586.5842 | 0 | 879.8763
6 |  | Utility Area
4th to 6th, 8th to 11th, 13th to 16th, 18th to 21st & 23rd to 26th Floor as Residential | [7 empty] | 19
1 |  | 2BHK | 541.779 | 117.4622 | 659.2412 | 0 | 988.8618
2 |  | 2BHK | 541.779 | 117.4622 | 659.2412 | 0 | 988.8618
3 |  | 1BHK | 370.174 | 68.2976 | 438.4715 | 0 | 657.7073
4 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
5 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
6 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
7th, 12th, 17th, 22nd & 27th Floor For Residential (Part Refuge Area) | [7 empty] | 5
1 |  | Refuge Area
2 |  | 2BHK | 541.779 | 117.4622 | 659.2412 | 0 | 988.8618
3 |  | 1BHK | 370.174 | 68.2976 | 438.4715 | 0 | 657.7073
4 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
5 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
6 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
28th Floor For Part Terrace Area | [7 empty] | 1
1 |  | 2BHK | 541.779 | 117.4622 | 659.2412 | 0 | 988.8618
2 |  | 2BHK | 541.779 | 117.4622 | 659.2412 | 0 | 988.8618
3 |  | 1BHK | 370.174 | 68.2976 | 438.4715 | 0 | 657.7073
4 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
5 |  | 2BHK | 519.5783 | 106.6443 | 626.2226 | 0 | 939.3339
6 |  | Terrace Area
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 9500
Recommended of Parking ( If Available) |  |  |  |  | 4,00,000/-
REMARKS ON RECOMMENDATION
1 | Construction work is in process at the time of Visit (labour found) Construction work was not active at the time of Visit. (labour Not found) All work completed. Wait for OC / OC received. Work not yet Started.
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | 3 to 4 Labours found on site at the time of visit.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Enclose balcony + Balcony + Chajja Area.
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 50%
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Mr. Anurag Tiwari 9320016817
11 | We have updated fire Noc on 26/07/2025
Photographs Of Property : |  | Anandam - II
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Mr. Sunil Peravi |  | Authorized Signatory Name & Seal of the agency
Building No. 3
Building No. 2
Building No. 1
A
B
A
B
Anandam ­ II
Bldg No. 1
Bldg No. 2B
Bldg No. 2B
Bldg No. 2A
Bldg No. 1
Bldg No. 3A
Bldg No. 3B
3B
Bldg No. 1
2A
2B
3A
3B
3A
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C47: height should also be mentioned
Note on C61: RERA Start date
Note on H135: if multiple buildings are in project and are connected internally
Note on C137: AAC Block or Brick
Note on H139: If present on slopy area

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3