## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 19/09/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-09-16
Name of the builder group |  |  |  | Paranjape Spaces And Services Pvt Ltd
Name of the builder company |  |  |  | Paranjape Spaces And Services Pvt Ltd
Name of the Project |  |  |  | Paranjape Athena
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Rahul Varma 8600991763
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Rahul Varma 8600991763
Name / No of the Building |  |  |  | Wing A to E
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet.
RERA No. |  |  |  | P51800049529
Project location details |  | Paranjape Athena, C.T.S No.609, Redevlopement of "Building No 1 & 2 Teachers Colony Co Op- Hsg. Society Ltd. S. No. 379", near UPL House, Sharda Devi Road, Teachers Colony, Bandra, Bandra East, Andheri, Mumbai - 400051.
C.T.S No |  | 609, Redevlopement of "Building No 1 & 2 Teachers Colony Co Op- Hsg. Society Ltd. S. No. 379"
Locality |  | Teachers Colony
Road |  | Sharda Devi Road |  | Locality/Village |  | Bandra
City |  | Bandra East |  | District |  | Mumbai
Taluka |  | Andheri |  | Pin Code |  | 400051
Nearby Landmark |  | UPL House |  | Distance from city centre: |  | 1.2KM from Khar Road Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | UPL House
West | NA | NA |  |  | Service Rd/Western Express Hwy
North | NA | NA |  |  | Sharda Devi Rd/New Link Rd
South | NA | NA |  |  | Indraprasad Co-operative HS
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.070334, 72.847296
Location Link |  | https://goo.gl/maps/aZirEwFxeTzbzZNo9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3209.31
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 1.4268
Total FSI availaible for the project |  |  |  | 4.4268
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 14206.99
Total number of Buildings |  |  |  | 05 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority (MHADA)
Layout Approval No |  | Mhada-92/941/2024 |  |  | Dated | 2024-08-29
Approved Floor plan No. |  | Mhada-92/941/2024 |  |  | Dated | 2024-08-29
Commencement-CC No Valid Up to: |  | MH/EE/(BP)/GM/MHADA-92/941/2025/FCC/3/Amend |  |  | Dated Valid Upto Date | 15/01/2025 08/01/2026
This C.C. is now Further extended for Wing ‘C’ 12th to 13th upper floor for residential user i.e. for Building comprising of five wings designated as wing ‘A’, ‘B’, ‘C’, ‘D’, & ‘E’ having common Ground floor for Parking + Wing ‘A’, and ‘B’ 1st to 14th upper floors, Wing ‘C’ 1st to 13th upper floor & Wing ‘D’ and ‘E’ 1st to 11th upper residential floors with total Max height of 45.70 mtrs. AGL as per approved plan u/no. MH/EE/BP Cell/GM/MHADA - 92/941/2024 dated: 29.08.2024.” Note:- That the guidelines for reduction of Air Pollution issued by Chief Engineer (D.P.) BMC dt. 15/09/2023, Hon’ble Municipal Commissioner (BMC) dt. 25/10/2023 and MHADA circular vide No. ET-321, dtd. 25.10.2023 shall be strictly followed on site.
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 14206.99
Approved no of units |  |  | Flats - 215
Approved no of Floors |  |  | Wing A to E = B + P + Gr + 1st to 14th Floor
Proposed no of Floors |  |  | Wing A to D = Gr + 1st to 14th Floor
Wing E = Gr + 1st to 14th Floor
Wing E = B + P + Gr + 1st to 8th Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Swimming Pool, Gym, Club House, Lounge, Spa, Kids Play Area, Laundry Service, Resereved Parking.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction |  |  | changed on 21/08/2025 as per mr. vimlesh
Construction details: |  | Wing A to D = Gr + 1st to 14th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 12 Floor, Flooring upto 8 Floor Completed | , External Plaster upto 12 Floor, Flooring upto 8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 12 Floor, Flooring upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 79.29% |  | 92.14% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 85.71% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 8 | 57.14% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Wing D = B + P + Gr + 1st to 14th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 1 Slab Completed | , RCC upto 1 Slab
Basement | 1 | Ground | 1 | Podium | 1 | Floors | 14 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 1 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 12.5% |  | 46.88% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 1 | 6.25% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Wing E = Gr + 1st to 14th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 12 Floor, External Plaster upto 6 Floor Completed | , Internal Plaster upto 12 Floor, External Plaster upto 6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 12 Floor, External Plaster upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 68.21% |  | 86.43% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 12 | 85.71% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 42.86% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 28000 |  |  | 23000 to 28000 aakash mote on 26/11/2024.
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 1200000
Distressed valuation of the Property |  |  |  |  | 22400
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 41 |  | 26274.1705 |  | 40724.9643 |  |  |  | 42 | 41
Wing B |  | 41 |  | 26416.5782 |  | 40945.6963 |  |  |  | 42 | 41
Wing C |  | 53 |  | 31902.3432 |  | 49448.632 |  |  |  | 36 | 34
Wing D |  | 39 |  | 23131.2763 |  | 35853.4782 |  |  |  | 23 | 23
Wing E |  | 41 |  | 32429.6716 |  | 50265.9909 |  |  |  | 24 | 23
Total |  | 215 |  | 140154.0398 |  | 217238.7617
Grand Total |  | 215 |  | 140154.0398 |  | 217238.7617
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Wing A
Basement Floor For Parking
Ground Floor For Parking & Entrance Lobby
Podium Floor For Parking | [9 empty] | 10.764
1st Floor For Residential
1 |  | 2BHK | 641.642 | 0 | 994.5452 | 1st Floor For Residential |  | 56.482 | 59.9575 |  | 22623.407
2 |  | 2BHK | 641.8573 | 0 | 994.8788 | 1st Floor For Residential |  | 55.615 |  | 22120.6646
3 |  | 2BHK | 639.0587 | 0 | 990.541 | 1st Floor For Residential |  | 55.615 | 59.9575 |  | 25806.4516
2nd to 6th & 8th to 14th Floor
1 |  | 2BHK | 641.642 | 0 | 994.5452 | 2nd to 6th & 8th to 14th Floor |  |  | 26846.443
2 |  | 2BHK | 641.8573 | 0 | 994.8788 | 2nd to 6th & 8th to 14th Floor
3 |  | 2BHK | 639.0587 | 0 | 990.541 | 2nd to 6th & 8th to 14th Floor
7th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 7th Floor (Part Refuge Area)
2 |  | 2BHK | 641.8573 | 0 | 994.8788 | 7th Floor (Part Refuge Area)
3 |  | 2BHK | 639.0587 | 0 | 990.541 | 7th Floor (Part Refuge Area)
Wing B
Ground Floor For Parking & Entrance Lobby
1st Floor For Residential
1 |  | 2BHK | 645.4094 | 0 | 1000.3846 | 1st Floor For Residential
2 |  | 2BHK | 645.4094 | 0 | 1000.3846 | 1st Floor For Residential
3 |  | 2BHK | 642.1802 | 0 | 995.3794 | 1st Floor For Residential
2nd to 6th & 8th to 14th Floor
1 |  | 2BHK | 645.4094 | 0 | 1000.3846 | 2nd to 6th & 8th to 14th Floor
2 |  | 2BHK | 645.4094 | 0 | 1000.3846 | 2nd to 6th & 8th to 14th Floor
3 |  | 2BHK | 642.1802 | 0 | 995.3794 | 2nd to 6th & 8th to 14th Floor
7th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 7th Floor (Part Refuge Area)
2 |  | 2BHK | 645.4094 | 0 | 1000.3846 | 7th Floor (Part Refuge Area)
3 |  | 2BHK | 642.1802 | 0 | 995.3794 | 7th Floor (Part Refuge Area)
Wing C
Ground Floor For Parking & Entrance Lobby
1st Floor For Residential & Amenities
1 |  | 2BHK | 616.5619 | 0 | 955.671 | 1st Floor For Residential & Amenities
2 |  | 2BHK | 627.5412 | 0 | 972.6889 | 1st Floor For Residential & Amenities
3 |  | Society Office |  |  |  | 1st Floor For Residential & Amenities
4 |  | Fitness Center |  |  |  | 1st Floor For Residential & Amenities
2nd to 6th & 8th to 14th Floor
1 |  | 2BHK | 616.5619 | 0 | 955.671 | 2nd to 6th & 8th to 14th Floor
2 |  | 2BHK | 627.5412 | 0 | 972.6889 | 2nd to 6th & 8th to 14th Floor
3 |  | 2BHK | 687.6043 | 0 | 1065.7867 | 2nd to 6th & 8th to 14th Floor |  | 25051.9171
4 |  | 1BHK | 474.0466 | 0 | 734.7722 | 2nd to 6th & 8th to 14th Floor
7th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 7th Floor (Part Refuge Area)
2 |  | 2BHK | 627.5412 | 0 | 972.6889 | 7th Floor (Part Refuge Area)
3 |  | 2BHK | 687.6043 | 0 | 1065.7867 | 7th Floor (Part Refuge Area)
4 |  | 1BHK | 474.0466 | 0 | 734.7722 | 7th Floor (Part Refuge Area)
Wing D
Ground Floor For Parking
1st Floor For Residential & Amenities
1 |  | Fitness Center |  |  |  | 1st Floor For Residential & Amenities
2 |  | 3BHK | 897.7176 | 0 | 1391.4623 | 1st Floor For Residential & Amenities
3 |  | Fitness Center |  |  |  | 1st Floor For Residential & Amenities
2nd to 6th & 8th to 14th Floor
1 |  | 2BHK | 666.9374 | 0 | 1033.753 | 2nd to 6th & 8th to 14th Floor
2 |  | 2BHK | 630.9749 | 0 | 978.0111 | 2nd to 6th & 8th to 14th Floor
3 |  | 1BHK | 446.5984 | 0 | 692.2275 | 2nd to 6th & 8th to 14th Floor |  |  | 23113.7899
7th Floor (Part Refuge Area)
1 |  | 3BHK | 852.8317 | 0 | 1321.8892 | 7th Floor (Part Refuge Area)
2 |  | Refuge Area |  |  |  | 7th Floor (Part Refuge Area)
3 |  | 1BHK | 446.5984 | 0 | 692.2275 | 7th Floor (Part Refuge Area)
Wing E
Ground Floor For Parking & Entrance Lobby
1st Floor For Residential
1 |  | 3BHK | 887.7071 | 0 | 1375.946 | 1st Floor For Residential |  | 26672.5589
2 |  | 3BHK | 853.2623 | 0 | 1322.5565 | 1st Floor For Residential |  | 27749.2864
3 |  | 2BHK | 638.8434 | 0 | 990.2073 | 1st Floor For Residential |  | 26964.0517
2nd to 6th & 8th to 14th Floor
1 |  | 3BHK | 887.7071 | 0 | 1375.946 | 2nd to 6th & 8th to 14th Floor
2 |  | 3BHK | 853.2623 | 0 | 1322.5565 | 2nd to 6th & 8th to 14th Floor
3 |  | 2BHK | 638.8434 | 0 | 990.2073 | 2nd to 6th & 8th to 14th Floor
7th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 7th Floor (Part Refuge Area)
2 |  | 3BHK | 853.2623 | 0 | 1322.5565 | 7th Floor (Part Refuge Area)
3 |  | 2BHK | 638.8434 | 0 | 990.2073 | 7th Floor (Part Refuge Area)
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated revised approved Plans & CC on 17/09/2025.
* | Recommended Rates/Other Charges of the Property have been revised on 26/11/2024
* | Construction work goes beyond the approved plan & CC permission for Wing C, D & E. Please provide revised approved plan & CC.
* | Validity of CC is expired on 08/01/2025. Please provide revised CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Tushar Bhuwad |  | Report By : |  | Sachin
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Paranjape Athena
Layout :
Google Map :

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted